## CHAF Project List
Active CHAF Projects |  |  |  |  | 2019-03-15 | [24 empty] | SHIFT 2018
[5 empty] | SYP info |  | If an item # is associated with a CHAF the Highway Plan Description, Type of Work and Cost Estimates are shown.
SHIFT? | Dist | ADD / MPO | CHAF ID | Item # (s) | Letting Date | Active Project | Project Description | Type of Work | County | Primary Route | Primary BMP | Primary EMP | Length | Improvement Assumption | SBF | NHS | P | P Sched Yr | D | D Sched Yr | R | R Sched Yr | U | U Sched yr | C | C Sched Yr | Estimate Date | Purpose | Need | Sponsor | Score Type | SHIFT Score (Max 100) | Congestion | Benefit / Cost | Crash History | Road Characteristics | Economic | Freight | Asset Mgmt | Quantitative Score | District Boost | Local Boost
Y; Potential Committed | 3 | Bowling Green MPO | IP20060201 | 3-8857 |  | A | IMPROVE US-31W FROM CAMPBELL LANE (US-231) TO UNIVERSITY BOULEVARD (US-231X). (14CCN)(16CCR)(18CCR) | MAJOR WIDENING(O) | Warren | 114-US-0031W -000 | 10.561 | 11.688 | 1.127 | Major Widening-Urban Streets | 25 |  |  |  | 0 |  | 1750000 | 2019 | 5800000 | 2019 | 4550000 | 2022 | 2019-03-01 08:56 | Reduce congestion and increase mobility. | US 31W between US 231 (Campbell Lane) and US 231X (University Blvd.) is a two lane facility with 12' lanes and 4' shoulders. There is a mixture of land use which includes residential, commercial, churches, schools,and Western Kentucky University's souther | 3 | West | 71.0662 | 8.8454 | 12.6804 | 14.3686 | 0 | 9.5533 | 2.921 | 7.6976 | 56 | 15
Y; Potential Committed | 4 | Lincoln Trail ADD | IP20050036 | 4-8502.20 |  | A | IMPROVE US 62 FROM JUST EAST OF BEEHIVE CURVE TO KY 224. CONSTRUCTION SEGMENT 2. | MINOR WIDENING(O) | Grayson | 043-US-0062 -000 | 24.5 | 25.5 | 1 | Modernize Roadway-Urban | 16 | [9 empty] | 5000000 | 2024 |  | IMPROVE US 62 FROM JUST EAST OF BEEHIVE CURVE TO KY 224 IN CLARKSON | US 62 is a 2 lane route with a lot of traffic connecting Leitchfield and Clarkson. Many trucks use this corridor and there have been numerous accidents.
Y; Potential Committed | 4 | Elizabethtown-Radcliff MPO | IP20150340 | 4-154 | 401769 | A | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-31WB TO CS-2255 (WILSON ROAD). (10CCR)(12CCR) | CONGESTION MITIGTN(O) | Hardin | 047-US-0031W -000 | 18.818 | 28.4 | 9.582 | Auxiliary Lanes or Operation Improvements | 11 | Y |  |  | 500000 | 2021 | 1000000 | 2024 | 1000000 | 2024 | 9000000 | 2024 | 2018-07-10 08:18 | Address congestion, safety, and mobility along US 31W in Elizabethtown and Radcliff | US 31W is the main corridor that runs through Hardin County. This section of US 31W has numerous accidents along congestion through Elizabethtown and Radcliff. | Radcliff/Elizabethtown MPO | South | 82.6126 | 9.0995 | 14.9289 | 14.9822 | 0 | 0 | 4.3602 | 9.2417 | 53 | 15 | 15
Y; Potential Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150266 | 5-48.10 |  | A | ADDITION OF NB AND SB AUXILIARY LANES ON I-71 NEAR KENNEDY, INCLUDING OPERATIONAL IMPROVEMENTS TO THE ZORN INTERCHANGE. (2004BOPC) | RECONSTRUCTION(O) | Jefferson | 056-I -0071 -000 | 0 | 2.5 | 2.5 | Add Lane to Full Control Facility | 25 | Y |  |  | 0 | 2019 | 3000000 | 2020 | 2000000 | 2020 | 38260000 | 2022 | 2019-03-07 15:10 | Improve safety and reduce congestion on I-71 from I-64 near the Kennedy interchange to Zorn Ave. | This project is needed because of a higher than average crash rate, inadequate current and future capacity, and roadway deficiencies on I-71 from I-64 near the Kennedy interchange to Zorn Avenue. The critical crash rate factor (CCRF) in this 2 mile secti | 5 | Statewide | 76.1712 | 17.9031 | 16.652 | 11.9108 | 4.4053 | 8.6344 | 5.6388 | 11.027
Y; Potential Committed | 5 | KIPDA ADD | IP20150281 | 5-8713 |  | A | CONSTRUCT A THIRD LANE ON US-60 FROM THE MASONIC HOME TO ROCKET LANE. (12CCN)(14CCR) | RECONSTRUCTION(O) | Shelby | 106-US-0060 -000 | 11.5 | 12.878 | 1.378 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 0 |  | 0 |  | 2170000 | 2021 | 2018-07-10 08:18 | Improve safety and mobility for all modes including freight. | Schools, commercial and residential developments exist along the route. The employment annual growth rate of the area just west of the project is 2.9%. The truck percentage in 2015 was 6.721%. This route connects Louisville, Shelbyville, and Frankfort. | 5 | North | 75.09 | 8.2092 | 12.6 | 8.1115 | 1.5231 | 8.3692 | 0 | 6.2769 | 45 | 15 | 15
Y; Potential Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150316 | 5-8509 |  | A | WIDEN KY-245 FROM BERNHEIM FOREST TO THE COMMUNITY COLLEGE. (08CCN)(10CCR)(14CCR)(16CCR) | MINOR WIDENING(O) | Bullitt | 015-KY-0245 -000 | 4.425 | 6.415 | 1.99 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 0 |  | 0 |  | 0 |  | 13140000 | 2022 | 2019-03-01 13:52 | The purpose of the KY 245 Widening Project is to provide an improved transportation facility to meet the additional traffic demand forecasted to occur and accommodate any existing or future developments, and/or tourist destinations along the corridor. K | The area has significant institutions and tourist destinations near the interchange that attracts local traffic, visitors and travelers along 1-65. Among the most important attractions are the Bernheim Arboretum, Jim Beam Distillery, The Boy Scout Camp, B | 5 | North | 78.7869 | 7.6062 | 12.5077 | 8.0423 | 0 | 8.9231 | 4.3231 | 7.3846 | 49 | 15 | 15
Y; Potential Committed | 5 | KIPDA ADD | IP20150447 | 5-65.40 |  | A | WIDEN I-64 TO 6-LANES FROM 0.458 MILE EAST OF THE KY-55 INTERCHANGE TO THE KY-1790 UNDERPASS. (2006BOPC) | MAJOR WIDENING(O) | Shelby | 106-I -0064 -000 | 32.3 | 35.9 | 3.6 | Add Lane to Full Control Facility | 25 | Y |  |  | 6000000 | 2019 | 0 |  | 3600000 | 2020 | 133680000 | 2022 | 2019-03-08 10:32 | WIDEN I-64 TO 6-LANES FROM 0.458 MILE EAST OF THE KY-55 INTERCHANGE TO 0.737 MILE EAST OF THE KY-53 INTERCHANGE AT SHELBYVILLE. (2006BOPC)(NH PORTION) | This route serves as a major connector linking Louisville, Frankfort, and Lexington. The V/SF rating indicates and increasing capacity problems. The truck percentage shows the importance of this east and west interstate to freight movement. Address cur | 5 | Statewide | 72.4343 | 17.0396 | 12.9515 | 9.2841 | 1.8062 | 9.8458 | 7.0925 | 14.4145
Y; Potential Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160174 | 5-537 |  | A | SIX LANE PRIORITY SECTION OF I-265 BETWEEN TAYLORSVILLE ROAD AND I-71. | MAJOR WIDENING(O) | Jefferson | 056-I -0265 -000 | 23.409 | 34.727 | 11.318 | Add Lane to Full Control Facility | 25 | Y |  |  | 0 | 2018 | 4980000 | 2020 | 6510000 | 2020 | 278400000 | 2022 | 2019-03-07 15:15 | The purpose of the proposed project is to decrease existing congestion on the mainline of I-265 Gene Snyder Freeway between KY 155 Taylorsville Road and I-71. | Carrying 65,000 to 88,000 vehicles per day today, the existing I-165 corridor does not provide adequate capacity to serve current peak period traffic volumes. It exhibits poor Level of Service (LOS), inflated travel times, and ramp queue lengths that bac | 5 | Statewide | 81.7992 | 18.5374 | 14.2731 | 14.7687 | 4.4053 | 9.0749 | 6.2555 | 14.4842
Y; Potential Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160176 | 5-8952 |  | A | WIDEN US-60 TO THREE LANES FROM EASTWOOD CUTOFF (MP 14.7) TO ROCKCREST WAY (MP 15.1). (LOCALS WILL DO DESIGN FOR $330,000). (16CCN)(18CCR) | MINOR WIDENING(O) | Jefferson | 056-US-0060 -000 | 14.718 | 15.114 | 0.396 | Install Two-way Left Turn Lane | 28 |  |  |  | 330000 |  | 410000 | 2019 | 460000 | 2020 | 1000000 | 2021 | 2019-03-08 10:50 | Improve safety and mobility. | The Critical Rate Factor (CRF) along this segment of US 60 is 0.53. The KY State Data Center Report shows an employment annual growth rate in this area ranging from 1.6% to 2.9% and a population annual growth rate ranging from 0.4% to 2.6%. | 5 | North | 55.8038 | 5.6923 | 12.7385 | 5.1577 | 1.5231 | 8.0923 | 3.0154 | 4.5846 | 41 | 15
Y; Potential Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160185 | 5-8203 | 2024-03-15 | A | RECONSTRUCT BILLTOWN ROAD FROM NORTH OF COLONNADES PLACE TO SOUTH OF EASUM ROAD. (04CCN)(06CCN)(08CCR)(10CCR)(12CCR) | RECONSTRUCTION(O) | Jefferson | 056-KY-1819 -000 | 6.9 | 8.1 | 1.2 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 3280000 | 2024 | 2019-03-07 14:44 | The purpose of this project is to bring geometric deficiencies up to modern roadway standards and improve corridor wide capacity and operations. | Limited right-of-way and narrow shoulders (three feet or less) exists along the length of the corridor. Historic traffic volumes have shown strong growth along Billtown Road with traffic volumes expected to increase by 7.5% per year along the length of Bi | 5 | North | 77.3315 | 5.5815 | 11.1231 | 9.3808 | 3.6 | 8.7385 | 2.9692 | 5.9385 | 47 | 15 | 15
Y; Potential Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160218 | 5-391.30 |  | A | IMPROVE OPERATIONAL PERFORMANCE OF THE I-65/KY-480 INTERCHANGE INCLUDING RAMP IMPROVEMENTS AND TURNING LANES. (12CCR)(14CCR)(2014BOP)(16CCR) | RECONSTRUCTION(O) | Bullitt | 015-I -0065 -000 | 115.147 | 115.938 | 0.791 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 |  | 0 |  | 9490000 | 2023 | 2018-07-10 08:18 | The purpose of this project is to reduce future traffic congestion at the I-65/KY 480 (Cedar Grove Road) interchange to acceptable levels of service (i.e., A, B, C, or D) and to improve access to existing and committed businesses in the Cedar Grove Busine | The I-65/KY 480 southbound ramps' signalized intersection west of I-65 operates at LOS C during the AM peal travel period and LOS D during the peak PM travel period. In the 2040 design year, it is projected to operate at LOS D during the AM peak and LOS | 5 | North | 63.8462 | 2.3692 | 10.2462 | 12.0462 | 0 | 0 | 2.7846 | 6.4 | 34 | 15 | 15
Y; Potential Committed | 7 | Lexington MPO | IP20150307 | 7-252 | 2010-05-03 | I | IMPROVE NEWTOWN PIKE FROM KY-4 TO I-75. (16CCR)(18CCR)(SEE 7-252.01 FOR BREAKOUT SECTION LET TO CONSTRUCTION IN MAY 2010) | MAJOR WIDENING(O) | Fayette | 034-KY-0922 -000 | 1.65 | 3.4 | 1.75 | Arterial to Partial Control | 23 | Y |  |  |  |  | 9320000 | 2019 | 11860000 | 2019 | 0 | 2021 | 2019-01-23 07:45 | Address congestion, improve safety and mobility on Newtown Pike from KY-4 to I-75. | The following needs have been identified on this project: 1) Address Congestion, 2) Improve Safety, 3) Improve Mobility. | 7 | Statewide | 68.3376 | 14.1145 | 17.4449 | 12.7037 | 0 | 5.1101 | 5.3304 | 13.6338
Y; Potential Committed | 7 | Lexington MPO | IP20150346 | 7-87.20 |  | A | EAST NICHOLASVILLE BYPASS SECTION IA: IMPROVE CONNECTIVITY AND MOBILITY EAST AROUND NICHOLASVILLE FROM SOUTH OF KY-39 TO NORTH OF KY-169. | NEW ROUTE(O) | Jessamine | 057-US-0027X -000 | 0 | 2.4 | 2.4 | Construct Road in New Location | 0 | [9 empty] | 15630000 | 2024 |  | Improve mobility and safety on E. Nicholasville Bypass Section IA from approximately 50 ft. S. of KY 39 to 125 ft. N. of KY 169. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Safety. | 7 | North | 67.0331 | 6.7754 | 3.6 | 13.6731 | 0 | 8.5846 | 4.4 | 0 | 37 | 15 | 15
Y; Potential Committed | 7 | Bluegrass ADD | IP20150393 | 7-196.30 |  | A | IMPROVE US-27 FROM WEST LANCASTER BYPASS TO KY-34. (2006BOPC) (16CCN)(18CCR) | RELOCATION(O) | Garrard | 040-US-0027 -000 | 5.199 | 10.331 | 5.132 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 0 | 2019 | 9000000 | 2020 | 8270000 | 2021 | 35440000 | 2022 | 2019-03-04 08:06 | Reconstruction of US-27 from W Lancaster Bypass to KY 34. | The following needs have been identified on this project: 1) Improve Mobility. | 7 | North | 79.3938 | 7.5015 | 8.2615 | 8.3538 | 2.1385 | 9.8769 | 3.9077 | 9.3538 | 49 | 15 | 15
Y; Potential Committed | 7 | Bluegrass ADD | IP20150407 | 7-8705 |  | A | IMPROVE US-460 FROM RUSSELL CAVE ROAD TO US-27 BYPASS IN PARIS.(12CCN)(14CCR)(16CCR) | RECONSTRUCTION(O) | Bourbon | 009-US-0460 -000 | 1.394 | 7.696 | 6.302 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2019 | 14000000 | 2019 | 22320000 | 2021 | 2019-01-07 15:36 | Improve mobility on US 460 between Russell Cave Rd. (MP 1.394) to US 27 bypass (MP 7.696) in Paris. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Access. | 7 | North | 73.5646 | 2.9723 | 9 | 8.1923 | 3.0615 | 7.8154 | 2.6154 | 9.9077 | 44 | 15 | 15
Y; Potential Committed | 8 | Cumberland Valley ADD | IP20150056 | 8-8952 |  | A | IMPROVE KY-461 FROM US-150 TO THE EXISTING FOUR LANE APPROACH AT US-25.(16CCN)(18CCR) | RECONSTRUCTION(O) | Rockcastle | 102-KY-0461 -000 | 7 | 9.404 | 2.404 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 100000 |  | 0 | 2019 | 5800000 | 2020 | 6700000 | 2021 | 36000000 | 2025 | 2018-07-10 08:18 | The purpose of this project The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on US 461. | With The New Developed US-150, Access From The Industrial Park, As Well As Lincoln County Has Provided Travelers Easier Access To I-75. A Lot Of Tourists Visit The Area In The Summertime For Access To Go To Lake Cumberland, As Well As Renfro Valley Enter | CUMBERLAND VALLEY ADD | South | 80.3874 | 4.1611 | 13.8626 | 11.3922 | 0.90047 | 9.4787 | 4.6209 | 5.9716 | 50 | 15 | 15
Y; Potential Committed | 9 | FIVCO ADD | IP20080523 | 9-8311 |  | A | IMPROVE SAFETY AT THE EAST CARTER HIGH SCHOOL. (06CCN)(08CCR)(12CCR) | SAFETY(P) | Carter | 022-KY-0001 -000 | 10 | 10.2 | 0.2 | Improve Intersection | 26 | [5 empty] | 720000 | 2020 | 490000 | 2021 | 2000000 | 2022 | 2018-07-10 08:18 |  | A vertical curve exists in this segment of KY-1 that makes visibility a major problem for vehicles turning off KY-1 onto 1.a county road that serves several residences, 2.a new apartment complex directly across from East Carter High School, 3.an entrance | FIVCO ADD | East | 66.6437 | 9.4132 | 11.2275 | 11.1826 | 1.6467 | 0 | 0 | 3.1737 | 37 | 15 | 15
Y; Potential Committed | 11 | Cumberland Valley ADD | IP20150207 | 11-147 / 11-147.01 |  | A | REDUCE CONGESTION ON US-25 FROM KY-1006 TO KY-2069; IMPROVE CONNECTIVITY FROM US-25 NEAR KY-2069 TO KY-229; IMPROVE KY-229 FROM THE NEW CONNECTOR NORTH TO KY-192; AND IMPROVE ACCESS TO THE SCHOOL FROM KY-192 BYPASS. (06CCR)(10CCR)(12CCR)(14CCR) | MAJOR WIDENING(O) | Laurel | 063-US-0025 -000 | 9 | 10.505 | 1.505 | Arterial to Partial Control | 23 |  |  |  | 0 |  | 0 |  | 0 |  | 54760000 | 2022 | 2018-07-10 08:18 | The purpose of this project is to reduce congestion on US 25 from KY 1006 to KY 2069; improve connectivity from US 25 near KY 2069 to KY 229; improve KY 229 from the new connector north to KY 192; and improve access to the school from KY 192 bypass. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 89.8578 | 9.6209 | 12.9384 | 13.5782 | 1.327 | 9.6682 | 4.9052 | 7.8199 | 60 | 15 | 15
Y | 1 | Purchase ADD | IP19970001 |  |  |  | New Interstate facility from Missouri State Line to I-24 at Paducah. See Interstate design option from Alternate B in May 1997 Southern KY Corridor Stuy - see I-24 in McCracken County for continuation of I-66 routing. | New Route | Ballard | 004-US-0060 -000 | 0 | 16.937 | 16.937 | Construct Road in New Location | 0 | Y | 1650000 |  | 30800000 |  | 34100000 |  | 16500000 |  | 502150000 |  | 2010-09-28 10:08 | New Interstate facility from Missouri State Line to I-24 at Paducah. | ISTEA of 1991 spelled out a proposal for a new interstate highway named I-66 from Virginia to California. KYTC then conducted a feasibility study that determined that I-66 was economically feasible across the southern tier of KY. That study prioritized se
Y | 1 | Purchase ADD | IP19970002 |  |  |  | Address future service, condition and safety issues from Paducah U.S. 68 at Exit 16 to Wendel H. Ford West KY Parkway at Eddyville Exit 42 to accommodate future I-66 / I-69 concurrent routing. | Major Widening | McCracken | 073-I -0024 -000 | 15.833 | 17.32 | 1.487 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 15000000 |  | 5000000 |  | 2000000 |  | 250000000 |  | 2013-02-04 11:39 | Address future service, condition and safety issues accommodate future I-66 / I-69 / I-24 concurrent routing. | ISTEA of 1991 spelled out a proposal for a new interstate highway named I-66 from Virginia to California. KYTC then conducted a feasibility study that determined that I-66 was economically feasible across the southern tier of KY. That study prioritized se
Y | 1 | Purchase ADD | IP19990001 |  |  |  | Paducah Outer Loop (Massac Creek Parkway) New Construction from US 60 to I-24 / KY 305 Interchange. Includes new interchange at US 60. See Alternate 1 Section 4 in November 1999 Scoping Study. See also March 2002 Urban Transportation Study. | Bypass | McCracken | 073-KY-0305 -000 | 4.035 | 8.491 | 4.456 | Construct Road in New Location | 0 |  | 0 |  | 2000000 |  | 6500000 |  | 4500000 |  | 28800000 |  | 2010-09-28 11:36 | Provide new system connectivity to relieve congestion and improve mobility. | An outer loop has been identified as a need in Paducah since the 1950s. A version of the loop was listed as a No. 1 priority for the Paducah area in 1991, where it was described in the Highway and Thoroughfare Needs for the Greater Paducah Area report. Ma
Y | 1 | Purchase ADD | IP19990002 |  |  |  | Address future congestion, provide connectivity, economic development, and improved mobility from KY994 to US45 in McCracken County. | Bypass | McCracken | 073-KY-0999 -000 | 0 | 2.952 | 2.952 | Construct Road in New Location | 0 |  | 0 |  | 2000000 |  | 7500000 |  | 4200000 |  | 18000000 |  | 2018-11-02 10:28 | Provide new system connectivity to relieve congestion and improve mobility. | An outer loop has been an identified need since 1950s. A version of the loop was listed as a No. 1 priority for Paducah area in 1991 and it was described in the Highway and Thoroughfare Needs for the Greater Paducah Area report. Development occurring in w
Y | 1 | Purchase ADD | IP19990003 |  |  |  | Address future congestion, access, and economic development issues from the I-24/KY 1954 interchange to KY 994. | Bypass | McCracken | 073-KY-0999 -000 | 2.952 | 4.206 | 1.254 | Construct Road in New Location | 0 |  | 0 |  | 1050000 |  | 4200000 |  | 2100000 |  | 16800000 |  | 2010-09-28 11:50 | Provide new system connectivity to relieve congestion and improve mobility. | An outer loop has been id as a need in Paducah since 1950s. A version of the loop was listed as a No. 1 priority for Paducah in 1991 and it was described in the Highway and Thoroughfare Needs for the Greater Paducah Area report. Development occurring in
Y | 1 | Purchase ADD | IP20000085 |  |  |  | Address safety issues with truck access to the Calvert City Industrial Complex and the Marshall County-Calvert City Riverport from I-24 to US 62/KY1523 intersection. | New Interchange | Marshall | 079-I -0024 -000 | 22.595 | 22.695 | 0.1 | Construct Road in New Location | 0 | Y | 0 |  | 2500000 |  | 3000000 |  | 3000000 |  | 30000000 |  | 2015-04-01 12:18 | This project is proposed due to problems and concerns with truck traffic exiting I-24 & I-69 traveling north toward the industrial area. | These trucks sometimes contain hazardous materials and are traveling directly through residential areas. The trucks need to be re-routed to the west side of the city to a new I-24 interchange, then turn north along a new extension of KY 1523 to the exist
Y | 1 | Purchase ADD | IP20000086 |  |  |  | Address congestion, freight movement, access issues and need for eastern bypass around Murray from US 641 South to US 641 North. | Bypass | Calloway | 018-US-0641 -000 | 4.957 | 10.217 | 5.26 | Construct Road in New Location | 0 | Y | 1000000 |  | 5000000 |  | 8000000 |  | 5000000 |  | 40000000 |  | 2010-09-28 10:41 | Address congestion, freight movement, access issues and need for eastern bypass around Murray from US 641 South to US 641 North. | Murray is the county seat and largest urban center in Calloway County and is home to Murray State University. A bypass study is needed for the City of Murray to determine if it is warranted and decide priority segments for construction. US 641, the main
Y | 1 | Purchase ADD | IP20000087 |  |  |  | Address congestion, freight movement, access issues and need for western bypass around Murray from US 641 South to US 641 North. | Bypass | Calloway | 018-US-0641 -000 | 4.957 | 10.217 | 5.26 | Construct Road in New Location | 0 | Y | 500000 |  | 4000000 |  | 5000000 |  | 2500000 |  | 18000000 |  | 2015-04-01 14:24 | Address congestion, freight movement, access issues and need for western bypass around Murray from US 641 South to US 641 North. | Murray is the county seat and largest urban center in Calloway County and is home to Murray State University. A bypass study is needed for the city of Murray to determine if it is warranted and decide priority segments for construction. US 641, the main
Y | 1 | Purchase ADD | IP20020001 |  |  |  | Improve Intermodal Access and Economic Development on KY 1523 connecting Marshall County - Calvert City Riverport. | New Route | Marshall | 079-KY-1523 -000 | 0.234 | 2.864 | 2.63 | Construct Road in New Location | 0 |  | 0 |  | 1500000 |  | 2000000 |  | 2200000 |  | 12000000 |  | 2014-12-12 15:21 | This project is needed to aid in the development of the Marshall County - Calvert City Riverport by providing a more direct route to the Parkway and I-24 for truck access. | To provide better connectivity with the riverport and the Calvert City Industrial Complex. The riverport is currently being developed on the Tennessee River (on the north west side of Calvert City) along a local road (Sharpe-Calvert RD) that is accessed
Y | 1 | Purchase ADD | IP20020002 |  |  |  | Address economic development issues for Fulton County Industrial Park and access issues for high clearance vehicles between KY 307 and US 51 due to the low clearance railroad bridges located on KY 307 & KY 94. | New Route | Fulton | 038-PF-9999 - |  |  |  | Local Roadway Improvements | 3 |  | 0 |  | 350000 |  | 400000 |  | 400000 |  | 1000000 |  | 2015-04-01 14:30 | The purpose of this project is to provide a new connector route between KY 307 & US 51 that would provide alternate access to the Fulton County Industrial Park and open a corridor for farm implements to utilize and avoid the city. | The need driving this project is low clearance railroad bridges on KY 307 and KY 94. There are access issues with truck traffic and agriculture traffic moving through the city of Fulton accessing the industrial park and farm lands in the area. The concer
Y | 1 | Pennyrile ADD | IP20040001 |  |  |  | RECONSTRUCT SECTION OF KY 91 WITH TRUCK PASSING LANE FROM FRAZER RD TO CROOKED CREEK BRIDGE from MP 5.705 to MP 6.143 | Reconstruction | Crittenden | 028-KY-0091 -000 | 5.705 | 6.143 | 0.438 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 500000 |  | 250000 |  | 2000000 |  | 2017-04-11 10:40 | Improve safety and traffic flow. | This section of KY 91 has a steep grade with poor geometrics and 2/9 lanes. Truck traffic on the route slows traffic flow while ascending steep grades. KY 91 from Marion to the Ohio River has only 31 percent passing distances with most of these in the n | PENNYRILE ADD | West | 19.2758 | 0.50859 | 7.6289 | 2.7191 | 3.5052 | 0 | 0 | 4.9141 | 19
Y | 1 | Pennyrile ADD | IP20040002 |  |  |  | MAJOR WIDENING TO 4 LANES FROM APPROX. 0.8 MI E OF TENNESSEE RIVER BRIDGE TO APPROX. 0.5 MI E OF RUDD-SPEES RD NEAR OHIO VALLEY BAPTIST CHURCH AT LEDBETTER from MP 0.80 to MP 4.06 SEE SEGMENT 2 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Reconstruction | Livingston | 070-US-0060 -000 | 0.8 | 4.063 | 3.263 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 15500000 |  | 2010-02-25 16:51 |  | Livingston county has a large commuter work force that travels to the Paducah area and this is the main highway to that city. Also, Livingston County does not currently have any routes that are on the National Truck Network.
Y | 1 | Pennyrile ADD | IP20040003 |  |  |  | MAJOR WIDENING TO 4 LANES FROM PROPOSED SMITHLAND BYPASS TO DYER MINE RD. from MP 14.7 to MP 17.16. SEE SEGMENT 7 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Livingston | 070-US-0060 -000 | 14.7 | 17.16 | 2.46 | Other Improvement Types | 0 |  | 200000 |  | 1500000 |  | 1000000 |  | 2000000 |  | 17000000 |  | 2010-02-25 16:51 | Improve safety and geometrics | Livingston county has a large commuter work force that travels to the Paducah area and this is the main highway to that city. Also, Livingston County does not currently have any routes that are on the National Truck Network.
Y | 1 | Pennyrile ADD | IP20040004 |  |  |  | RECONSTRUCT KY 453 FROM I-24 NORTH TO 0.1 MI S OF GUM CREEK CULVERT from MP 4.19 to MP 8.11. | Reconstruction | Livingston | 070-KY-0453 -000 | 4.198 | 8.119 | 3.921 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 3000000 |  | 4000000 |  | 11700000 |  | 2010-02-25 16:51 | Improve safety and geometrics | This is a narrow 2 lane road with poor geometrics
Y | 1 | Pennyrile ADD | IP20040005 |  |  |  | RECONSTRUCTION FROM 0.1 MI S OF GUM CREEK CULVERT TO 0.3 MI N OF Dry Bridge RD from MP 8.1 to MP 12.4. | Reconstruction | Livingston | 070-KY-0453 -000 | 8.119 | 12.412 | 4.293 | Modernize Roadway-Rural | 26 |  | 0 |  | 1750000 |  | 3500000 |  | 1750000 |  | 13000000 |  | 2017-04-11 11:33 |  | Livingston County does not have any routes that are on the National truck network. This project will upgrade an existing system to allow for better truck access and improve safety. | PENNYRILE ADD | West | 35.3411 | 3.7732 | 5.6701 | 7.8737 | 3.2131 | 6.0481 | 0 | 8.7629 | 35
Y | 1 | Pennyrile ADD | IP20040006 |  |  |  | RECONSTRUCTION OF KY 453 along "S" Curves from BMP 13.100 to EMP 13.600. | Safety-Haz-Elm | Livingston | 070-KY-0453 -000 | 13.1 | 13.6 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 2000000 |  | 750000 |  | 5400000 |  | 2017-04-11 11:41 | Improve safety, geometrics and truck access | Improve safety | PENNYRILE ADD | West | 32.3162 | 3.7595 | 5.4639 | 6.2371 | 4.1065 | 5.945 | 0 | 6.8041 | 32
Y | 1 | Pennyrile ADD | IP20040007 |  |  |  | RECONSTRUCTION FROM ECHO SPRING BRANCH BRIDGE TO US 60 AT SMITHLAND from MP 14.1 to MP 15.6 | Reconstruction | Livingston | 070-KY-0453 -000 | 14.176 | 15.641 | 1.465 | Other Improvement Types | 0 |  | 300000 |  | 1000000 |  | 2000000 |  | 2500000 |  | 7200000 |  | 2010-02-25 16:51 | Improve safety and Geometrics | Livingston County does not have any routes that are on the National truck network. This project will upgrade an existing system to allow for better truck access and improve safety.
Y | 1 | Pennyrile ADD | IP20040008 |  |  |  | WIDEN KY 1489 FROM US 68 TO LAKE BARKLEY STATE PARK ENTRANCE from MP 1.884 to MP 5.195. | Minor Widening | Trigg | 111-KY-1489 -000 | 1.884 | 5.195 | 3.311 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2000000 |  | 5000000 |  | 15000000 |  | 2017-04-10 11:13 | Improve safety. | This section of KY 1489 has 2/9 lanes with 3 foot shoulders. This route is too narrow to suppport all the boat and RV traffic that currentlt travels on it. This route provides direct assess to Lake Barkley and the Lake Barkkley State Park so in the summ | PENNYRILE ADD | West | 21.8067 | 1.622 | 4.8969 | 6.4046 | 3.6254 | 5.2577 | 0 | 0 | 22
Y | 1 | Purchase ADD | IP20040038 |  |  |  | Address condition, safety, congestion and future capacity issues on US 60 through City of LaCenter | Bypass | Ballard | 004-US-0060 -000 | 9.634 | 11.271 | 1.637 | Construct Road in New Location | 0 | Y | 0 |  | 1500000 |  | 2600000 |  | 1500000 |  | 12600000 |  | 2010-09-28 10:22 | Improve regional connectivity, mobility, and access along US 60 corridor. | This project is part of an overall plan to widen US 60 west of Paducah. Capacity is expected to become an issue in the near future as traffic growth continues to increase. This project will serve to upgrade the existing system. US 60 serves as a regional
Y | 1 | Purchase ADD | IP20040039 |  |  |  | Address condition, safety and congestion issues on US 60 through the City of Barlow. | Bypass | Ballard | 004-US-0060 -000 | 5.851 | 7.372 | 1.521 | Construct Road in New Location | 0 | Y | 250000 |  | 1000000 |  | 2000000 |  | 1050000 |  | 8400000 |  | 2010-09-28 10:35 | Improve regional connectivity, mobility, and access along US 60 corridor. | This project is part of an overall plan to widen US 60 west of Padacah. Capacity is expected to become an issue in the near future as traffic growth continues to increase. This project will serve to upgrade the existing system. US 60 serves as a regional
Y | 1 | Purchase ADD | IP20060001 |  |  |  | Increase the intersection turning radius at US 51 & KY 121 in Wickliffe to improve truck access. | Spot Improvement | Ballard | 004-US-0051 -000 | 3.338 | 3.4 | 0.062 | Improve Intersection | 26 |  | 0 |  | 400000 |  | 1250000 |  | 750000 |  | 1000000 |  | 2017-04-10 09:56 | The purpose of this project is to improve intersection geometric to provide better accessibility for truck traffic. | This intersection with KY 121 joins two truck routes and truck traffic is very heavy. Truck traffic accounts for alomst 40% of the traffic (including counts for KY 121) using this intersection. The intersection is signal controlled having only 2 lanes of | PURCHASE ADD | West | 22.5876 | 1.7457 | 4.0722 | 6.4433 | 2.3024 | 0 | 4.2784 | 3.7457 | 23
Y | 1 | Purchase ADD | IP20060002 |  |  |  | Address safety, tourism, and access issues to the entrance of Fort Jefferson Park in Wickliffe. | Spot Improvement | Ballard | 004-US-0051 -000 | 2.667 | 2.719 | 0.052 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 100000 |  | 100000 |  | 250000 |  | 2017-04-10 11:43 | Improve access to Fort Jefferson Park in Wickliffe | This will improve access to Fort Jefferson Park in Wickliffe. Currently there are horizontal and vertical aligment issues at the current entrance and the lack of turning lanes create sight distance and speed issues. Passenger vehicles also must negoiate | 1 | West | 19.0653 | 1.7457 | 4.2784 | 1.5464 | 3.9519 | 0 | 4.2784 | 3.2646 | 19
Y | 1 | Purchase ADD | IP20060003 |  |  |  | Improve truck access issues to the Wickliffe-Ballard County Riverport and industrial park in Wickliffe. | Spot Improvement | Ballard | 004-US-0051 -000 | 3.94 | 4.04 | 0.1 | Construct Road in New Location | 0 | Y | 0 |  | 110000 |  | 150000 |  | 450000 |  | 350000 |  | 2015-04-01 14:15 | Improve access to Wickliffe-Ballard County Riverport. | The city of Wickliffe owns approximatley 25 acres that make-up the Wickliffe Industrial Park and joins with the Wickliffe-Ballard County Riverport. The industrial park is not fully developed but has 2 tenants Economy Boat and Galaxy Cable. It also has a | PURCHASE ADD | West | 23.9983 | 5.622 | 0 | 2.2423 | 3.4708 | 7.9038 | 4.7595 | 0 | 24
Y | 1 | Purchase ADD | IP20060004 |  |  |  | Address condition, safety, congestion and future capacity issues from proposed Barlow eastern bypass to proposed LaCenter southern bypass. (See Segment 4 in April 1998 Advance Planning Study) | Major Widening | Ballard | 004-US-0060 -000 | 7.14 | 9.73 | 2.59 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 2000000 |  | 2000000 |  | 3250000 |  | 14300000 |  | 2015-04-02 11:26 | Improve regional connectivity, mobility, and access along US 60 corridor. | This project is part of an overall plan to widen US 60 west of Padacah. Capacity is expected to become an issue in the near future as traffic growth continues to increase. This project will serve to upgrade the existing system. US 60 serves as a regional
Y | 1 | Purchase ADD | IP20060005 |  |  |  | Address condition, safety and congestion issues from US 51 to KY 1280. See Segment 1 in April 1998 Advance Planning Study. | Major Widening | Ballard | 004-US-0060 -000 | 0 | 3.93 | 3.93 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 2250000 |  | 4000000 |  | 2700000 |  | 24000000 |  | 2015-04-01 14:19 | Improve regional connectivity, mobility, and access along US 60 corridor. | This project is part of an overall plan to widen US 60 west of Padacah. US 60 is a major corridor through Ballard County and provides accessiblity to the region between Missouri and Illinois via the US 51 Ohio River Bridge near Wickliffe. The KYTC Safet
Y | 1 | Purchase ADD | IP20060006 |  |  |  | Address condition, safety and congestion issues from KY 1280 to the proposed Barlow eastern bypass. See Segment 2 in April 1998 Advance Planning Study. | Major Widening | Ballard | 004-US-0060 -000 | 3.93 | 5.74 | 1.81 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 1500000 |  | 2250000 |  | 1000000 |  | 10000000 |  | 2014-12-11 10:44 | Improve regional connectivity, mobility, and access along US 60 corridor. | This project is part of an overall plan to widen US 60 west of Padacah. US 60 serves as a regional access route to Paducah from the western part of the region as well as parts of southeast Missouri and southern Illinois via the the Ohio River Bridge near
Y | 1 | Purchase ADD | IP20060007 |  |  |  | Improve geometric deficiencies and truck mobility at the intersection with KY286 in Wickliffe. | Reconstruction | Ballard | 004-KY-0121 -000 | 8.262 | 8.369 | 0.107 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 750000 |  | 750000 |  | 2000000 |  | 2015-04-03 10:32 | Improve intersection to address sight distance issue and truck access. | Geometric deficiencies created with a Y-intersection. KY 286 is also on a steep grade as it approaches junction with KY 121. This is an issue for the high number of trucks that use this intesection. The intersection has a control stop for KY 121 north bo | PURCHASE ADD | West | 16.1718 | 2.323 | 2.4227 | 1.9072 | 2.3024 | 0 | 3.677 | 3.5395 | 16
Y | 1 | Purchase ADD | IP20060008 |  |  |  | Correct intersection geometrics and improve safety on KY 286 at the intersection with Hershel Jones Road/N. Ballard Church Road near Wickliffe. | Safety-Haz-Elm | Ballard | 004-KY-0286 -000 | 4 | 4.53 | 0.53 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 400000 |  | 500000 |  | 1200000 |  | 2017-04-10 10:37 | Improve intersection alignment to address sight distance issues. | Ky 286 & Herschel Jones Road and N. Ballard Church Road. Intersection has sight distance issues due to vertical & horizontal alignments on KY 286. Intersection is a school bus entrance and also has truck activity related to Pilgrams Pride (poultry farmi | PURCHASE ADD | West | 29.5206 | 2.8454 | 10.3093 | 4.768 | 3.2646 | 0 | 3.488 | 4.8454 | 30
Y | 1 | Purchase ADD | IP20060009 |  |  |  | Correct intersection alignment and address safety issues at KY 893 near TN State Line in Hazel. | Safety-Haz-Elm | Calloway | 018-US-0641 -000 | 0 | 0.069 | 0.069 | Improve Intersection | 26 | Y | 0 |  | 350000 |  | 300000 |  | 500000 |  | 1000000 |  | 2017-04-10 10:01 | Correct intersection alignment and address safety issues at KY 893 near TN State Line in Hazel. | This project is located at the KY/TN State Line in Hazel and is in a congested area. KY 893 intersects US 641 in a curve which creates somewhat of a sight distance issue. There are also clear zone obstacles adding to sight line issues from the US 641 SB a | PURCHASE ADD | West | 38.6323 | 5.8144 | 11.4948 | 9.1753 | 4.9656 | 0 | 3.7113 | 3.4708 | 39
Y | 1 | Purchase ADD | IP20060010 |  |  |  | Correct intersection geometrics, and address turning movements, safety and capacity issues at the intersection of Sycamore Street and US 641X in Murray | Reconstruction | Calloway | 018-US-0641X -000 | 1.115 | 1.235 | 0.12 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 200000 |  | 500000 |  | 1000000 |  | 2010-02-25 16:51 | Improve intersection design, and address turning movements, safety and capacity issues at the intersection of Sycamore Street and US 641X in Murray | The intersection has substandard design issues given it is a Y intersection with one leg of the Y allowing traffic to travel in both directions while the other leg allows only US 641X south bound traffic to turn onto Sycamore Street. This merging traffic
Y | 1 | Purchase ADD | IP20060011 |  |  |  | Correct substandard roadway geometrics and address safety, service and access issues on KY 822 (16th St.) between KY 1550 (Glendale Road) and KY 821 (Sycamore Street) | Reconstruction | Calloway | 018-KY-0822 -000 | 0 | 0.73 | 0.73 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 1750000 |  | 3000000 |  | 2010-02-25 16:51 | Correct substandard roadway geometrics and address safety, service and access issues on KY 822 (16th St.) between KY 1550 (Glendale Road) and KY 821 (Sycamore Street) | This segment can be highly congested during peak traffic periods. Narrow lanes and inadequate shoulders add to safety, congestion and access issues. Safety is a concern with low shoulder edges that have approximately a 4' drop off. The intersection with K
Y | 1 | Purchase ADD | IP20060012 |  |  |  | Correct substandard roadway geometrics, to improve traffic flow, safety and access management issues from KY 1377 to Truman Creek Bridge in Bardwell | Reconstruction | Carlisle | 020-US-0051 -000 | 6.134 | 8.259 | 2.125 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 3000000 |  | 7000000 |  | 2014-12-11 11:09 | Improve US 51 to provide better regional connectivity, improve mobility and improve travel time reliability between Fulton and Wickliffe. | There are several geometric issues w/ US 51 in Bardwell. There is no curb and gutter and there are existing drainage problems. A curve on the south end of town has limited sight distance, poor horizontal alignment, and a steep grade that can cause issues
Y | 1 | Purchase ADD | IP20060013 |  |  |  | Correct roadway geometrics on US 62 from KY 1372 to County Road 1318 (Polivick Road) to address safety, access and regional connectivity issues. | Reconstruction | Carlisle | 020-US-0062 -000 | 1.062 | 2.105 | 1.043 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 750000 |  | 500000 |  | 3000000 |  | 2017-04-13 09:42 | Improve US 62 to provide better regional connectivity, improve mobility and improve travel time reliability between Bardwell and Paducah. | US 62 is the main route from Bardwell and portions of Carlisle County to Paducah and I-24. Improvements to the road are needed to provide better access to the interstate, medical facilities and services, shopping and dining facilities in Paducah. Narrow | 1 | West | 24.1357 | 2.9072 | 2.5258 | 1.7784 | 3.7629 | 7.1134 | 0 | 6.0481 | 24
Y | 1 | Purchase ADD | IP20060014 |  |  |  | Correct substandard roadway geometrics on US 62 from KY 1181 to KY 408 to address access issues, safety concerns, flood prone area and regional connectivity. | Reconstruction | Carlisle | 020-US-0062 -000 | 2.868 | 5.048 | 2.18 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 1500000 |  | 7000000 |  | 2017-04-13 09:25 | Improve US 62 to provide better regional connectivity, improve mobility and improve travel time reliability between Bardwell and Paducah. The section between KY 1181 to KY 408 has safety concerns related to roadway and structure geometrics and is in a fl | US 62 the main route from Bardwell and portions of Carlisle County to Paducah and I-24. Improvements are needed to provide better access to the interstate, medical facilities and services, shopping and dining facilities in Paducah. Narrow lanes and inadeq | 1 | West | 32.0954 | 2.9072 | 6.2371 | 5.9407 | 2.3024 | 7.1134 | 0 | 7.5945 | 32
Y | 1 | Purchase ADD | IP20060015 |  |  |  | Improve safety, mobility and connectivity, and address geometric deficiencies along US 62 between Hobbs Rd / Boswell Rd to KY 307. | Reconstruction | Carlisle | 020-US-0062 -000 | 8.09 | 8.932 | 0.842 | Modernize Roadway-Rural | 26 |  | 30000 |  | 300000 |  | 600000 |  | 300000 |  | 2700000 |  | 2018-10-11 15:47 | Improve US 62 to provide better regional connectivity, improve mobility and improve travel time reliability between Bardwell and Paducah. The section between Hobbs Rd / Boswell Rd and KY 307 has bridge structures that are narrow, creating safety concerns | US 62 is the main route from Bardwell and portions of Carlisle County to Paducah and I-24. Improvements are needed to provide better access to the interstate, medical facilities and services, shopping and dining facilities in Paducah. Narrow lanes and in | PURCHASE ADD | West | 24.8729 | 3.9794 | 2.7835 | 2.268 | 3.2646 | 7.0447 | 0 | 5.5326 | 25
Y | 1 | Purchase ADD | IP20060016 |  |  |  | Improve roadway geometrics at Y-intersection of US 62 & KY 307 to provide adequate sight distance and address safety concerns. | Reconstruction | Carlisle | 020-US-0062 -000 | 8.932 | 9.127 | 0.195 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 1000000 |  | 500000 |  | 2500000 |  | 2017-04-10 10:35 | Remove "Y" alignment and improve sight distances and safety. | US 62 is the main route from Bardwell and portions of Carlisle County to Paducah and I-24. Improvements are needed to provide better access to the interstate, medical facilities and services, shopping and dining facilities in Paducah. The intersection at | PURCHASE ADD | West | 19.4158 | 4.1924 | 3.299 | 4.7423 | 3.2646 | 0 | 0 | 3.9175 | 19
Y | 1 | Purchase ADD | IP20060017 |  |  |  | Correct substandard roadway geometrics on US 62 from .173 miles east of Shelby Rd / Hayes Rd to KY 1820 to address access safety, and regional connectivity issues. | Reconstruction | Carlisle | 020-US-0062 -000 | 9.3 | 12.6 | 3.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1500000 |  | 10000000 |  | 2018-10-11 15:53 | This project is part of an overall plan to improve the regional connectivity between Carlisle County and the Paducah. | US 62 is the main route from Bardwell and portions of Carlisle County to Paducah and I-24. Improvements are needed to provide better access to the interstate, medical facilities and services, shopping and dining facilities, etc. in Paducah. Narrow lanes a | PURCHASE ADD | West | 70.4777 | 4.2062 | 8.9175 | 7.6804 | 3.6598 | 7.5945 | 0 | 8.4192 | 40 | 15 | 15
Y | 1 | Purchase ADD | IP20060017 |  |  |  | Correct substandard roadway geometrics on US 62 from .173 miles east of Shelby Rd / Hayes Rd to KY 1820 to address access safety, and regional connectivity issues. | Reconstruction | Carlisle | 020-US-0062 -000 | 9.3 | 12.6 | 3.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1500000 |  | 10000000 |  | 2018-10-11 15:53 | This project is part of an overall plan to improve the regional connectivity between Carlisle County and the Paducah. | US 62 is the main route from Bardwell and portions of Carlisle County to Paducah and I-24. Improvements are needed to provide better access to the interstate, medical facilities and services, shopping and dining facilities, etc. in Paducah. Narrow lanes a | 1 | West | 15.2749 | 4.1924 | 2.8351 | 1.0309 | 3.2646 | 0 | 0 | 3.9519 | 15
Y | 1 | Purchase ADD | IP20060018 |  |  |  | Geometric configuration improvements to the intersection of KY 121 and KY 408. See Segment 8 / Priority 8 in February 2000 KY 121 Corridor Planning Study. | Reconstruction | Carlisle | 020-KY-0121 -000 | 1.5 | 1.7 | 0.2 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 650000 |  | 500000 |  | 1700000 |  | 2015-04-01 14:25 | Improve intersection alignment with KY 408 to KY 121. | This project is priority # 8 of the 2000 Corridor Planning Study for KY 121, which is an overall plan for upgrading KY 121 from Mayfield to Wickliffe. The KY 408 approaches to KY 121 are slightly offset, creating an excess of access points along this sect
Y | 1 | Purchase ADD | IP20060019 |  |  |  | Correct substandard roadway geometrics and address safety issues from KY 80 to KY 1371. | Reconstruction | Carlisle | 020-KY-1377 -000 | 0 | 3.638 | 3.638 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1500000 |  | 1875000 |  | 9000000 |  | 2010-02-25 16:51 | Improve KY 1377 between two major routes in the county (US 51 & KY 80) that also provide access to the county school system. | KY 1377 is a main access to the Carlisle County Schools, which is located near the intersection with KY 1371. Due to traffic generated by the schools, safety is a major concern with this route. The narrow lanes, lack of shoulders, and issues with vertical
Y | 1 | Purchase ADD | IP20060020 |  |  |  | Correct substandard roadway geometrics and address safety issues from KY 1371 to US 51. | Reconstruction | Carlisle | 020-KY-1377 -000 | 3.638 | 8.459 | 4.821 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2000000 |  | 2500000 |  | 12000000 |  | 2010-02-25 16:51 | Improve KY 1377 between two major routes in the county (US 51 & KY 80) that also provide access to the county school system. | KY 1377 is a main access to the Carlisle County Schools, which is located near the intersection with KY 1371. Due to traffic generated by the schools, safety is a major concern with this route. The narrow lanes, lack of shoulders, and issues with vertical
Y | 1 | Pennyrile ADD | IP20060021 |  |  |  | MAJOR WIDENING OF US 60 TO 4 LANES FROM PROPOSED SALEM BYPASS TO KY 297 from MP 0.0 to MP 4.9. SEE SEGMENT 12 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Crittenden | 028-US-0060 -000 | 0 | 4.9 | 4.9 | Other Improvement Types | 0 |  | 200000 |  | 2000000 |  | 2500000 |  | 3500000 |  | 27000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | This project is needed to provide better traffic flow and improve substandard curves and geometrics along the route. This project is one phase of a multi-phase plan to upgrage US 60 from Henderson to Paducha. The existing route does not allow 102" wide
Y | 1 | Pennyrile ADD | IP20060022 |  |  |  | MAJOR WIDENING TO 4 LANES FROM KY 297 TO PROPOSED MARION BYPASS from MP 4.9 to MP 7.9. SEE SEGMENT 13 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Crittenden | 028-US-0060 -000 | 4.9 | 7.9 | 3 | Other Improvement Types | 0 |  | 200000 |  | 1500000 |  | 1500000 |  | 2000000 |  | 18000000 |  | 2010-02-25 16:51 | Improve Safety and traffic flow | The project is needed to provide better traffic flow and improve substandard curves and geometrics along the route. This project is one phase of a multi-phase plan to upgrade US 60 from Henderson to Paducah. The project is also needed to provide a bett
Y | 1 | Pennyrile ADD | IP20060023 |  |  |  | MAJOR WIDENING TO 4 LANES FROM PROPOSED MARION BYPASS TO REPTON RD from MP 11.3 to MP 14.72 SEE SEGMENT 15 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Crittenden | 028-US-0060 -000 | 11.3 | 14.72 | 3.42 | Other Improvement Types | 0 |  | 200000 |  | 1500000 |  | 2000000 |  | 2500000 |  | 20000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | The project is needed to provide better traffic flow and improve substandard curves and geometrics along the route. This project is one phase of a multi-phase plan to upgrade US 60 from Henderson to Paducah. The project is also needed to provide a bett
Y | 1 | Pennyrile ADD | IP20060024 |  |  |  | MAJOR WIDENING TO 4 LANES FROM REPTON RD TO KY 365 from MP 14.7 to MP 17.25 SEE SEGMENT 16 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Crittenden | 028-US-0060 -000 | 14.72 | 17.25 | 2.53 | Other Improvement Types | 0 |  | 200000 |  | 1500000 |  | 1500000 |  | 1750000 |  | 16000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | The project is needed to provide better traffic flow and improve substandard curves and geometrics along the route. This project is one phase of a multi-phase plan to upgrade US 60 from Henderson to Paducah. The project is also needed to provide a bett
Y | 1 | Pennyrile ADD | IP20060025 |  |  |  | MAJOR WIDENING ON US 60 TO 4 LANES FROM 0.4 MI SW OF BLACKFORD RD TO PROPOSED SULLIVAN BYPASS from MP 20.9 to MP 23.01. SEE SEGMENT 18 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Crittenden | 028-US-0060 -000 | 20.95 | 23.018 | 2.068 | Other Improvement Types | 0 |  | 200000 |  | 2000000 |  | 1500000 |  | 1500000 |  | 25000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | The project is needed to provide better traffic flow and improve substandard curves and geometrics along the route. This project is one phase of a multi-phase plan to upgrade US 60 from Henderson to Paducah. The project is also needed to provide a bett
Y | 1 | Pennyrile ADD | IP20060026 |  |  |  | Improve safety and mobility, and reduce congestion for motor vehicles on a section of US 60 near Hospital in Marion. | Major Widening | Crittenden | 028-US-0060 -000 | 8.49 | 8.76 | 0.27 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 200000 |  | 500000 |  | 1050000 |  | 2015-04-02 11:36 | Improve safety and traffic flow. | There is a high CRF along this section. The project is needed to releive congestion and improve traffic flow and safety caused by left turning vehicles blocking traffic. There are two high traffic generators on theis section: the high school and the hosp
Y | 1 | Pennyrile ADD | IP20060027 |  |  |  | RECONSTRUCT SECTION OF KY 91 WITH TRUCK PASSING LANE FROM 0.5 MI N OF FOREST GROVE SCHOOL RD TO 0.4 MI S OF HEATH HOLLOW RD (EASELY'S HILL)(MP 6.0 t MP 6.4) | Safety-Haz-Elm | Crittenden | 028-KY-0091 -000 | 10.507 | 10.907 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 300000 |  | 500000 |  | 1000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | The route has horizontal and vertical substandard geometrics in the form of a 90 degree curve at the bottom of a steep hill commonly know as Easley's Curve. There have been several fatalities on this curve over the years and the CRF does not adequately r
Y | 1 | Pennyrile ADD | IP20060028 |  |  |  | RECONSTRUCT WITH TRUCK PASSING LANE FROM HEATH HOLLOW RD TO 0.5 MI S OF OLD FORDS FERRY RD from MP 6.7 to MP 7.5 | Safety-Haz-Elm | Crittenden | 028-KY-0091 -000 | 11.265 | 12.007 | 0.742 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 350000 |  | 750000 |  | 3000000 |  | 2010-02-25 16:51 | Improve safety and geometrics | The route has horizontal and vertical substandard geometrics in the form of a 90 degree curve at the bottom of a steep hill commonly know as Easley's Curve. There have been several crashes on these "S" curves over the years and the CRF does not adequatel
Y | 1 | Pennyrile ADD | IP20060029 |  |  |  | RECONSTRUCT KY 1668 FROM US 60 TO THE ENTRANCE OF THE ROCK QUARRY from MP 0.0 to MP 1.3 | Minor Widening | Crittenden | 028-KY-1668 -000 | 0 | 1.88 | 1.88 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 750000 |  | 750000 |  | 3000000 |  | 2017-04-13 11:17 | Truck access and safety | This is an economic development project. The existing 2/9 lane road does not provide adequate width and weight standards needed for truck traffic generated by the rock quarry that is located on this road. The 9 foot lanes create safety hazards for vehic | PENNYRILE ADD | West | 15.5954 | 0.59107 | 8.1959 | 2.8737 | 3.9347 | 0 | 0 | 0 | 16
Y | 1 | Purchase ADD | IP20060030 |  |  |  | Address geometric alignment issues, access issues and future capacity issues at the US 45 / KY 307 intersection in Fulton. | Reconstruction | Fulton | 038-US-0045 -000 | 1.696 | 1.868 | 0.172 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 500000 |  | 750000 |  | 2000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve the geometric alignment of the intersection to better facilitate the traffic flow and mobility through the intersection. | This is one of the main intersections in the city of Fulton. Vehicles travel through this intersection to access the Purchase Parkway, the Industrial Park, downtown business district and several residential areas. The intersection has issues with the al
Y | 1 | Purchase ADD | IP20060031 |  |  |  | Correct geometric deficiencies to address inadequate passing zones, improved operating speeds to minimize delays and improved connectivity from Purchase Parkway (Future I-69) to Hickman County Line. | Major Widening | Fulton | 038-US-0051 -000 | 0 | 4.682 | 4.682 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3500000 |  | 3000000 |  | 15000000 |  | 2014-12-11 11:14 | The purpose of this project is to improve system connectivity of a regional corridor. | US 51 the primary north-south corridor connecting the four river counties and cities of Fulton, Clinton, Bardwell & Wickliffe in the Purchase and links KY with TN & IL. According to the 1995 study the alignment geometrics of US 51 are somewhat restricted
Y | 1 | Purchase ADD | IP20060032 |  |  |  | Address sight distance issues with the approaches of US 51 & KY 94 intersection at the railroad overpass. | Reconstruction | Fulton | 038-US-0051 -000 | 2.45 | 2.55 | 0.1 | Improve Intersection | 26 |  | 0 |  | 750000 |  | 250000 |  | 300000 |  | 3500000 |  | 2010-02-25 16:51 | Improve sight distance at intersection with KY 94. | There are sight distance issues at this intersection. This segment of US 51 is a railroad bridge overpass with the KY 94 approaches located at the south end of the bridge along the overpass. KY 94 traffic has limited sight of vehicles traveling south on
Y | 1 | Purchase ADD | IP20060033 |  |  |  | Correct geometric deficiencies and address economic development, safety, intermodal and truck access issues to the Hickman-Fulton County Riverport facilities from TN State line to KY 1282. | Reconstruction | Fulton | 038-KY-0094 -000 | 0 | 1.436 | 1.436 | Modernize Roadway-Rural | 26 |  | 100000 |  | 750000 |  | 1000000 |  | 750000 |  | 5400000 |  | 2010-02-25 16:51 | This project is needed for improved intermodal access for trucks to the Hickman-Fulton County Riverport, Cargill Grain and Bunge Corportation (grain elevator). | There are significant lengths of highway with less than “preferred” lane widths and shoulders, in places where culverts exist the “heads” are even with roadway and deep drop-offs are present in those areas. A majority of the truck traffic is generated by
Y | 1 | Purchase ADD | IP20060034 |  |  |  | Address safety and geometric alignment issues at KY 1282 and railroad crossing. | Safety-Haz-Elm | Fulton | 038-KY-0094 -000 | 1.41 | 1.46 | 0.05 | Improve Railroad Crossing | 55 |  | 0 |  | 250000 |  | 250000 |  | 450000 |  | 1000000 |  | 2010-02-25 16:51 | Improve alignment of KY 94 where it crosses the railroad tracks at a skewed angle near the intersection with KY 1282. | This intersection is T-intersection in a S-curve with a rail line crossing KY 94 at an angle to the T-intersection. There are no warning signs, lights or gates at the railroad. The rail crossing is also very rough. Although there seems to be sufficient si
Y | 1 | Purchase ADD | IP20060035 |  |  |  | Correct geometric deficiencies and address economic development, safety, intermodal and truck access issues to the Hickman-Fulton County Riverport facilities from railroad crossing near KY 1282 to Sycamore Road. | Reconstruction | Fulton | 038-KY-0094 -000 | 1.536 | 6.273 | 4.737 | Modernize Roadway-Rural | 26 |  | 100000 |  | 2000000 |  | 2000000 |  | 1500000 |  | 18000000 |  | 2010-02-25 16:51 | This project is needed for improved intermodal access for trucks to the Hickman-Fulton County Riverport, Cargill Grain and Bunge Corportation. | There are significant lengths of highway with less than “preferred” lane widths and shoulders, in places where culverts exist the “heads” are even with roadway and deep drop-offs are present in those areas. There are areas where minor off-tracking occurs
Y | 1 | Purchase ADD | IP20060036 |  |  |  | Address Hickman Riverport access from Sycamore Road to railroad crossing due to substandard highway design and geometric deficiencies. | Reconstruction | Fulton | 038-KY-0094 -000 | 6.273 | 11.89 | 5.617 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1250000 |  | 2300000 |  | 1500000 |  | 19000000 |  | 2010-02-25 16:51 | Project is needed for improved truck access to Hickman Riverport. | Problems identified are minor off-tracking and horizontal curve safe speed problems, significant lengths of highway with less than preferred lane and shoulder widths, rough railroad crossings, and truck traffic backups and minor truck crashes during harve
Y | 1 | Purchase ADD | IP20060037 |  |  |  | Correct substandard geometrics to the Y-intersection at KY 166 & KY 125 to address safety and access issues. | Reconstruction | Fulton | 038-KY-0166 -000 | 0 | 0.05 | 0.05 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 300000 |  | 200000 |  | 1500000 |  | 2017-04-10 10:34 | Correct substandard geometrics to the Y-intersection at KY 166 & KY 125 to address safety and access issues. | KY 166 / KY 125 is a Y-intersection that has issues with sight distance and horizontal alignments. KY 166 intersects with KY 125. KY 166 west has a control stop with KY 125 having right-of-way. KY 166 west traffic must look back over the left to view t | PURCHASE ADD | West | 24.5 | 0.52234 | 9.9485 | 6.8299 | 1.323 | 0 | 2.646 | 3.2302 | 24
Y | 1 | Purchase ADD | IP20060038 |  |  |  | Address economic development, and truck access issues to the Fulton Industrial Park from the Purchase Parkway to Holland Lane in Fulton. | Reconstruction | Fulton | 038-KY-0307 -000 | 1.232 | 2.096 | 0.864 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 350000 |  | 400000 |  | 1500000 |  | 2017-04-10 10:27 | Provide improved truck access from the Purchase Parkway to the Fulton Industrial Park. | This project is needed to provide improved truck access from the Purchase Parkway to the Fulton Industrial Park. Narrow lanes and shoulders exist along the route. Trucks must pull into on-coming lanes when leaving the industrial park and travel along th | PURCHASE ADD | West | 24.3093 | 2.3849 | 3.6598 | 3.0928 | 0.94502 | 6.5636 | 0 | 7.6632 | 24
Y | 1 | Purchase ADD | IP20060039 |  |  |  | Correct substandard intersection geometrics and address access issues at KY 309 & KY 1099 in Hickman to improve the less than adequate truck turning radius. | Reconstruction | Fulton | 038-KY-1099 -000 | 1.016 | 1.116 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 250000 |  | 1000000 |  | 750000 |  | 2014-12-11 11:21 |  | This project is needed to improve intermodal accessiblity. The turning radius at KY 309 and KY 1099 is less than adequate for trucks traveling this route. Most trucks are accessing the Hickman- Fulton County Riverport and other local industry. Trucks
Y | 1 | Purchase ADD | IP20060040 |  |  |  | Address access, economic development and freight movement issues to US 51 / Purchase Parkway interchange in Fulton for future I-69 accommodations. | Reconstruction | Fulton | 038-JC-9003 -000 | 1.191 | 1.524 | 0.333 | Innovative Interchange | 40 | Y | 0 |  | 2000000 |  | 1500000 |  | 1500000 |  | 20000000 |  | 2010-02-25 16:51 |  | A national study completed in 1993 concluded that construction of I-69 from Canada to Mexico was feasible. The corridor will enter KY from the IN state line near Henderson and exit KY into TN at the state line near Fulton. The KY General Assembly has outl
Y | 1 | Purchase ADD | IP20060041 |  |  |  | Address access, economic development and freight movement issues to KY 307 / Purchase Parkway interchange in Fulton for future I-69 accommodations. | Reconstruction | Fulton | 038-JC-9003 -000 | 2.174 | 2.692 | 0.518 | Innovative Interchange | 40 | Y | 0 |  | 2000000 |  | 1500000 |  | 1500000 |  | 20000000 |  | 2010-02-25 16:51 |  | A national study completed in 1993 concluded that construction of I-69 from Canada to Mexico was feasible. The corridor will enter KY from the IN state line near Henderson and exit KY into TN at the state line near Fulton. The KY General Assembly has outl
Y | 1 | Purchase ADD | IP20060042 |  |  |  | Address safety, access, and congestion issues on Broadway from .5 mi west of the Purchase Parkway to the eastern city limits of Mayfield (KY 121 Bypass). | Reconstruction | Graves | 042-KY-0058 -000 | 5.53 | 6.116 | 0.586 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 7500000 |  | 3000000 |  | 4500000 |  | 2017-04-11 10:55 | Address roadway geometrics, safety, access, and congestion issues along Broadway. | This is the main east west connection in city of Mayfield traveling from the Purchase Parkway to the KY 121 Bypass. Peak traffic periods are very congested. There is a lack of turn lanes over the length of the corridor. Between 6th & 9th streets there ar | PURCHASE ADD | West | 36.8548 | 6.7904 | 6.1856 | 8.518 | 1.2715 | 8.7285 | 0 | 5.3608 | 37
Y | 1 | Purchase ADD | IP20060043 |  |  |  | Address access, congestion, and geometric alignment issues from the eastern city limits of Mayfield to KY 131. | Reconstruction | Graves | 042-KY-0058 -000 | 6.401 | 8.156 | 1.755 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 1500000 |  | 8500000 |  | 2010-02-25 16:51 | The purpose of this project is to improve mobility through a congested area providing improved system linkage, access and reduced hazards. | A congested area exists along the route between MP 7.2 and 7.9. There are food and commercial businesses located in this area including two restaurants, a carpet outlet and a church. Two concrete mixing plants located in this area generate truck traffic
Y | 1 | Purchase ADD | IP20060044 |  |  |  | Address access and service issues along KY 121 business route from East College Street to KY 58 in Mayfield. | Minor Widening | Graves | 042-KY-0121X -000 | 1.5 | 1.87 | 0.37 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 1750000 |  | 1000000 |  | 4000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve system linkage, mobility and access along the corridor a major east - west connection in the City of Mayfield. | This is the major north-south business route through the city of Mayfield. There are access issues during periods of heavy traffic. Less than adeuate turn lane storage is an issue at the traffic signals (4 traffic signals in this section) during peak per
Y | 1 | Purchase ADD | IP20060045 |  |  |  | Address safety, congestion and access issues from East Farthing Street to Charles Drive in Mayfield. | Minor Widening | Graves | 042-KY-0303 -000 | 16.034 | 16.807 | 0.773 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 3000000 |  | 2500000 |  | 3000000 |  | 2018-11-01 10:07 | The purpose of this project is to improve system linkage, mobility, access and pedestrian safety. | Narrow lanes, narrow shoulders, no turn lanes and multiple entry / exit points create access, congestion and safety issues. This urban arterial serves as a collector route for several residential areas accessing the business area of Mayfield which creates | PURCHASE ADD | West | 67.7998 | 9.2646 | 9.0722 | 11.7655 | 2.3024 | 0 | 0 | 5.3952 | 38 | 15 | 15
Y | 1 | Purchase ADD | IP20060046 |  |  |  | Correct geometric deficiencies and improve safety, access, and regional connectivity from KY-703 in Clinton to .160 miles south of Obion Creek Bridge. | Reconstruction | Hickman | 053-US-0051 -000 | 8.275 | 13.685 | 5.41 | Modernize Roadway-Rural | 26 |  | 0 |  | 1700000 |  | 5500000 |  | 4000000 |  | 33000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve system connectivity of a regional corridor. | US 51 is a primary north south corridor connecting the four river counties in the Purchase and links KY w/ TN,IL & MO. Based on the 1995 study - alignment geometrics are somewhat restricted with 23% of the route having adequate passing sight distance, app
Y | 1 | Purchase ADD | IP20060047 |  |  |  | Correct geometric deficiencies to address safety, tourism & economic development issues from Columbus to KY 1772. | Reconstruction | Hickman | 053-KY-0058 -000 | 0.573 | 4.375 | 3.802 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 2000000 |  | 13300000 |  | 2010-02-25 16:51 | This project is needed to improve system connectivity and provide improved corridor to Columbus-Belmont State Park. | Narrow lanes with little or no shoulders in most locations and narrow bridges are a concern, especially for tourists unfamiliar to the area and for the larger RVs accessing the park. This segment of KY 58 has vertical & horizontal geometric issues giving
Y | 1 | Purchase ADD | IP20060048 |  |  |  | Improve geometric deficiencies and address condition, safety tourism, and economic development issues from KY 123 in Columbus to Carlisle County Line. | Reconstruction | Hickman | 053-KY-0080 -000 | 1.53 | 3.44 | 1.91 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1000000 |  | 9000000 |  | 2010-02-25 16:51 | This project is to improve system connectivity for tourism. | Columbus-Belmont State Park is accessed by KY 80. Narrow lanes and little or no shoulder in most locations create concern, especially for tourists unfamiliar to the area & for the larger RVs accessing the park. Based on information from Ky's Parks Dept, 8
Y | 1 | Purchase ADD | IP20060049 |  |  |  | Address safety, tourism & economic development issues from KY 80 in Columbus to Carlisle County Line. | Reconstruction | Hickman | 053-KY-0123 -000 | 21.79 | 22.958 | 1.168 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 750000 |  | 500000 |  | 5000000 |  | 2010-02-25 16:51 | This project is to improve system connectivity for tourism. | KY 123 is part of the national trail, Great River Road, and is also part of the bike route, Mississippi River Trail. Columbus-Belmont State Park is accessed by KY 123. Narrow lanes and little or no shoulder in most locations create concern, especially for
Y | 1 | Pennyrile ADD | IP20060050 |  |  |  | SECTION 2 OF PROPOSED SMITHLAND BYPASS FROM JOE GRIMMETT RD TO US 60 AT MP 14.7. SEE SEGMENT 6 IN APRIL, 1998 ADVANCE PLANNING STUDY from MP 13.08 to MP 14.7. | Major Widening | Livingston | 070-US-0060 -000 | 13.082 | 14.7 | 1.618 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 750000 |  | 750000 |  | 12000000 |  | 2010-02-25 16:51 |  | This project is bneeded to provide for better traffic flow and improve substandard curves and geometrics along the route. The project is also needed to provide a better truck route from Crittenden County to Paducah. the existing route does not allow 102
Y | 1 | Pennyrile ADD | IP20060051 |  |  |  | Major widening of US 60 to 4 lanes from approx. 0.5 MI east of Rudd-Spees Rd to KY937. (See Segment 3 in April 1998 Advance Planning Study) | Major Widening | Livingston | 070-US-0060 -000 | 4.063 | 7.83 | 3.767 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 4100000 |  | 2500000 |  | 22200000 |  | 2018-11-16 17:29 | Improve safety and traffic flow | Livingston county has a large commuter work force that travels to the Paducah area and this is the main highway to that city. Also, Livingston County does not currently have any routes that are on the National Truck Network.
Y | 1 | Pennyrile ADD | IP20060052 |  |  |  | MAJOR WIDENING OF US 60 TO 4 LANES FROM KY 937 TO PROPOSED SMITHLAND BYPASS. SEE SEGMENT 4 IN APRIL, 1998 ADVANCE PLANNING STUDY from MP 7.8 to MP 10.0 | Major Widening | Livingston | 070-US-0060 -000 | 7.83 | 10 | 2.17 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 4000000 |  | 2500000 |  | 15000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | Livingston county has a large commuter work force that travels to the Paducah area and this is the main highway to that city. Also, Livingston County does not currently have any routes that are on the National Truck Network.
Y | 1 | Pennyrile ADD | IP20060054 |  |  |  | CONSTRUCT EAST BOUND TURN LANE ON US 62 AT LYON CO INDUSTRIAL PARK | Minor Widening | Lyon | 072-US-0062 -000 | 12.9 | 13.066 | 0.166 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 750000 |  | 1000000 |  | 1000000 |  | 4500000 |  | 2017-04-10 10:45 | truck access and economic development | Truck access | PENNYRILE ADD | West | 36.128 | 4.4055 | 9.6907 | 5.8634 | 0 | 7.4914 | 3.0412 | 5.6357 | 36
Y | 1 | Purchase ADD | IP20060055 |  |  |  | Address safety, congestion, and future capacity issues from US 60 to US 68 in Paducah. See March, 2002 Paducah-McCracken County Transportation Study | Major Widening | McCracken | 073-I -0024 -000 | 4.328 | 16.27 | 11.942 | Add Lane to Full Control Facility | 25 | Y | 500000 |  | 6000000 |  | 1000000 |  | 4000000 |  | 100000000 |  | 2010-02-25 16:51 | The purpose of this project is to reduce interstate congestion and improve mobility. | The 2002 Urban Study demonstrated that additional through lanes are needed from US 60 to US 68. Presently this 4-lane interstate would require expansion to 6-lanes. Even at 6-lanes the road will be at/near capacity (67,000-87,000 vpd); however a 6-lane fu
Y | 1 | Purchase ADD | IP20060056 |  |  |  | Address safety, traffic movement and congestion at signalized intersections of US 45 and US 62 along the I-24 interchange in Paducah. See March, 2002 Paducah - McCracken County Transportation Study | New Interchange | McCracken | 073-I -0024 -000 | 6.405 | 6.875 | 0.47 | Other Improvement Types | 0 | Y | 0 |  | 2500000 |  | 500000 |  | 750000 |  | 8000000 |  | 2010-02-25 16:51 | The purpose of this project is to reduce congestion and provide system connectivity. | The existing interchange of US 45/US62/I-24 is a split diamond with the east bound service road providing a direct connection into and out of the Whitehaven Rest Area. The ramps are signalized at both US 45 & US 62 and the ramp termini are consistently hi
Y | 1 | Purchase ADD | IP20060058 |  |  |  | Correct geometric deficiencies and address safety issues at intersection of 21st & Jackson Street in Paducah. | Reconstruction | McCracken | 073-US-0060 -000 | 13.945 | 14.005 | 0.06 | Improve Intersection | 26 | Y | 0 |  | 500000 |  | 1000000 |  | 2000000 |  | 4500000 |  | 2010-02-25 16:51 | The purpose of this project is to address design deficiency and improve mobility. | This is a signalized intersection that intersects in a sharp curve. The curve in US 60 creates issues with the intersection alignment at South 21st Street and an entrance/exit location for a nearby church, which also uses the signal. Off-tracking of sem
Y | 1 | Purchase ADD | IP20060059 |  |  |  | Address issues with service, congestion and safety from US 45 to I-24 in Paducah. See March, 2002 Paducah-McCracken County Transportation Study. | Minor Widening | McCracken | 073-US-0062 -000 | 11.837 | 12.881 | 1.044 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 6000000 |  | 5000000 |  | 7200000 |  | 2017-04-11 09:34 | The purpose of this project is to improve mobility, service and access to the existing system. | The need to widen this segment was identified more than 30 years ago. With the large population and employment growth expected to occur in the southwest part of the county, it is expected that widening US 62 will become a necessity by the year 2025. This | 1 | West | 43.9553 | 9.5395 | 10.6701 | 13.4021 | 0.94502 | 0 | 3.9691 | 5.4296 | 44
Y | 1 | Purchase ADD | IP20060061 |  |  |  | Address future congestion, access, continuity of the outer loop project , and economic development issues for western McCracken County from I-24 to US 45. See Alt. 1, Sect. 5 in Nov. 1999 Study. See also March 2002 study. | Reconstruction | McCracken | 073-KY-0305 -000 | 7.8 | 11.427 | 3.627 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 10000000 |  | 9000000 |  | 20000000 |  | 2010-02-25 16:51 | Provide new system connectivity to relieve congestion and improve mobility. | An outer loop has been identified as a need in Paducah since the 1950s. A version of the loop was listed as a No. 1 priority for the Paducah area in 1991, where it was described in the Highway and Thoroughfare Needs for the Greater Paducah Area report. Ma
Y | 1 | Purchase ADD | IP20060062 |  |  |  | Correct geometric deficiencies and address safety issues on Clinton Road (KY 339) from 0.11 miles south of Old Farm Road (CR-1001F5)to US 45. | Reconstruction | McCracken | 073-KY-0339 -000 | 6.13 | 7.152 | 1.022 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1500000 |  | 1500000 |  | 4000000 |  | 2017-04-13 10:55 | Correct geometric deficiencies, improve mobility and reduce hazards. | Narrow lanes, narrow shoulders and horizontal alignment issues exist on this route which create safety concerns. There are several curves rated uncomfortable or unsafe when traveled at prevailing speed limit. Substandard intersection alignments with 2 rou | PURCHASE ADD | West | 37.6899 | 8.433 | 9.7938 | 7.4356 | 4.7079 | 7.3196 | 0 | 0 | 38
Y | 1 | Purchase ADD | IP20060063 |  |  |  | Correct geometric deficiencies and address safety issues from Graves County Line to KY 1954 in Paducah. | Reconstruction | McCracken | 073-KY-0450 -000 | 0 | 7.772 | 7.772 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 3000000 |  | 6000000 |  | 27600000 |  | 2010-02-25 16:51 | The purpose of this project is to address design deficiencies that impact road departure crashes. | Narrow lanes and shoulders exist in most areas. Most roadway departure areas are unrecoverable and several locations have fixed objects such as large trees and utility poles within a few feet of the road edge. Past Critical Rate Factor numbers have indica
Y | 1 | Purchase ADD | IP20060064 |  |  |  | Correct geometric deficiencies and address safety and access issues at the I-24 & Purchase Parkway interchange near Calvert City as part of improvements for future I-69 corridor. (Six Year Plan Item No. 800.00) | Reconstruction | Marshall | 079-I -0024 -000 | 24.891 | 24.991 | 0.1 | Innovative Interchange | 40 | Y | 200000 |  | 1500000 |  | 3000000 |  | 2000000 |  | 28000000 |  | 2015-03-16 14:36 | This project has been completed. | This interchange is located on the future I-69 corridor. Improvements are needed to address safety and access issues at the current location and to improve the traffic flow for what will be an interchange for 2 interstates (I-69 & I-24). The I-24 / Purc
Y | 1 | Purchase ADD | IP20060065 |  |  |  | Correct geometric alignment deficiencies and address access and traffic flow issues at US 62 / US 641 / KY 282 interchange. | Reconstruction | Marshall | 079-US-0062 -000 | 10.65 | 11.15 | 0.5 | Innovative Interchange | 40 |  | 0 |  | 750000 |  | 250000 |  | 750000 |  | 12000000 |  | 2010-02-25 16:51 | Improve mobility and system connectivity by correcting alignment of existing intersection. | This project is needed to improve access to US 62, US 641 and KY 282 where the routes intersect. The design of this intersection is a 1/2 clover leaf ramp layout for the intersection of KY 282 with US 62 and US 641 South bound traffic. The remaining porti
Y | 1 | Purchase ADD | IP20060066 |  |  |  | Correct geometric deficiencies and address safety issues with intersection at KY 408. | Reconstruction | Marshall | 079-US-0068 -000 | 16.665 | 16.805 | 0.14 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 400000 |  | 400000 |  | 600000 |  | 2017-04-11 09:57 | The purpose of this project is to address design deficiency with intersection alignment. | The intersection with KY 408 is a Y-intersection with a turn lane and a cross-over connection. KY 408 eastbound traffic traveling to US 68 eastbound has a one-way ramp for access. KY 408 eastbound turning to US 68 westbound uses the cross-over to access | 1 | West | 19.0584 | 6.0687 | 3.5567 | 1.1856 | 0.94502 | 0 | 3.5223 | 3.7801 | 19
Y | 1 | Purchase ADD | IP20060067 |  |  |  | Improve safety and address geometric deficiencies at the Y-intersection with KY95. | Reconstruction | Marshall | 079-US-0068 -000 | 7.745 | 7.845 | 0.1 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 400000 |  | 400000 |  | 750000 |  | 2017-04-13 10:35 | The purpose of this project is to correct design deficiencies and reduce safety issues. | This intersection is at a skewed angle where KY 95 intersects with US 68, the angle can create sight line issues for KY 95 traffic entering US 68. KY 95 from US 68 is the northbound access to North Marshall County Middle School. Historically this location | PURCHASE ADD | West | 29.3849 | 7.3058 | 5.6186 | 8.2474 | 1.5808 | 0 | 3.0241 | 3.6082 | 29
Y | 1 | Purchase ADD | IP20060068 |  |  |  | Correct geometric alignment and address design and safety issues at intersection with US 641 in Draffenville. | Reconstruction | Marshall | 079-US-0068 -000 | 10 | 10.1 | 0.1 | Realign Intersection | 26 |  | 0 |  | 600000 |  | 1500000 |  | 750000 |  | 2500000 |  | 2010-02-25 16:51 | The purpose of this project is to address design deficiencies and reduce hazards to improve system connectivity and mobility. | The intersection with US 641 S is a signalized intersection with US 641 intersecting at a slight angle to US 68. The intersection has been aligned with US 641 intersecting as a "3-legged Y-intersection. One lane is for US 68 east bound to US 641 southbou
Y | 1 | Purchase ADD | IP20060069 |  |  |  | Improve safety and address geometric deficiencies with one-way couplet from 17th St to KY348 in Benton. | Safety-Haz-Elm | Marshall | 079-US-0641 -000 | 7.8 | 8.815 | 1.015 | Modernize Roadway-Rural | 26 | Y | 0 |  | 500000 |  | 1000000 |  | 2000000 |  | 3000000 |  | 2018-10-02 11:11 | This project is needed to address safety issues along the one-way couplet of US641 in Benton (Main Street). | Lane widths range from 10'-16' with curb and gutter. On-street parking is located along the route. According to local law enforcement one problem along this route is vehicles making left hand turns from the right hand lane resulting in collisions. There | 1 | West | 76.5773 | 7.5189 | 13.866 | 12.0876 | 4.6048 | 0 | 0 | 8.5 | 47 | 15 | 15
Y | 1 | Purchase ADD | IP20060070 |  |  |  | Address access issues for truck traffic at KY 95 intersection with KY 1523 in Calvert City. | Reconstruction | Marshall | 079-KY-0095 -000 | 7.22 | 7.32 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 250000 |  | 500000 |  | 500000 |  | 2017-04-11 11:23 | The purpose of this project is to improve design deficiencies in order to provide better freight access for truck traffic. | Access issues exist at this intersection for truck traffic into and out of the Calvert City Industrial Area. There is inadequate turning radius for truck traffic. Trucks must cross over into the opposing lanes to complete turns or drop tires off along t | PURCHASE ADD | West | 15.8488 | 5.8144 | 2.0103 | 0 | 0.75601 | 0 | 2.9038 | 4.3643 | 16
Y | 1 | Purchase ADD | IP20060071 |  |  |  | Improve US 68 & I-69 interchange in Marshall County (Draffenville) to meet interstate standards. | Reconstruction | Marshall | 079-I -0069 -000 | 46.694 | 47.232 | 0.538 | Innovative Interchange | 40 | Y | 0 |  | 3000000 |  | 3000000 |  | 1500000 |  | 25000000 |  | 2010-02-25 16:51 | Improve/complete I-69 system connectivity. | Improvements to will be necessary to accommodate interstate travel including improvements to current interchanges to add acceleration / deceleration lanes. ADT on US 68 is 9367 with 6.9% trucks. The impact of I-69 will help economic development and prov
Y | 1 | Pennyrile ADD | IP20060072 |  |  |  | CADIZ BYPASS - MAJOR WIDENING TO 4 LANES (2 LANE INITIAL CONSTRUCTION)from MP 15.9 to MP 20.7. Per email correspondence with D2 and PEADD on 1-16-15 this PIF is currently under construction. | Major Widening | Trigg | 111-US-0068 -000 | 15.977 | 20.73 | 4.753 | Other Improvement Types | 0 | Y | 0 |  | 500000 |  | 200000 |  | 500000 |  | 15000000 |  | 2015-03-16 14:43 |  | This project is needed to complete the 4-laning of the US 68/80 corridor from the City of Bowling Green to Mayfield. This section of US 68/80 is one of the few remaining sections of US 68/80 that has not been upgraded to a 4-lane route.
Y | 1 | Purchase ADD | IP20070001 |  |  |  | Address congestion, safety and intersection alignment issues from US 45/US 62 to Broadway/Buckner Ln/32nd Street intersection. | Reconstruction | McCracken | 073-KY-0731 -000 | 0 | 0.447 | 0.447 | Modernize Roadway-Rural | 26 |  | 200000 |  | 1000000 |  | 3000000 |  | 2500000 |  | 6000000 |  | 2010-02-25 16:51 | The purpose of this project is to relief congestion, improve mobility and improve system connectivity. | KY 731 is a local street connecting US45/US 62 to US60X. There are 3 schools located near the ends of this segment. The RT also serves as a connecting rt to access the downtown Paducah area. Safety and congestion issues are a The intersection with Broadw | PURCHASE ADD | West | 28.3849 | 8.7285 | 5.3093 | 7.3196 | 3.9691 | 0 | 0 | 3.0584 | 28
Y | 1 | Pennyrile ADD | IP20070002 |  |  |  | Address safety concerns on Glenwood Rd (CR-1005) from KY 272 to US 68/80 from MP 0.0 to MP 2.1 | Reconstruction | Trigg | 111-CR-1005 -000 | 0 | 2.1 | 2.1 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 1000000 |  | 750000 |  | 10000000 |  | 2015-01-15 13:25 | Improve safety and geometrics | Glenwood Road (CR-1005) is currently being used as a major connector route between US 68/80 and KY 272. This north/south county road has subtandard verticle and horizontal curves, as well as narrow 9 foot lanes and one foot shoulders. There is also a br
Y | 1 | Pennyrile ADD | IP20070003 |  |  |  | Address safety concerns on Kings Chapel Rd (CR-1004) from KY 272 to US 68/80 from MP 0.0 to MP 3.7 | Reconstruction | Trigg | 111-CR-1014 -000 | 0 | 3.7 | 3.7 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2000000 |  | 3000000 |  | 18000000 |  | 2015-01-15 13:25 | Improve safety and Geometrics | kings Chapel Road (CR-1004) is currently being used as a major connector route between US 68/80 and KY 272. This north/south county road has subtandard verticle and horizontal curves, as well as narrow 9 foot lanes and one foot shoulders. This is a requ
Y | 1 | Purchase ADD | IP20070256 |  |  |  | Address congestion, geometric deficiencies, and access issues from KY121 to Utterback Road in Murray. | Minor Widening | Calloway | 018-CS-1047 -000 | 0 | 1.079 | 1.079 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 3500000 |  | 3000000 |  | 4000000 |  | 2018-08-06 15:05 | Address congestion, geometric deficiencies, and access issues from KY121 to Utterback Road in Murray. | According to KYTC the ADT on 16th St ranges from 4300 to 5300 vehicles per day. A 2007 study conducted by the city looked at the level of service for 16th St. Expected growth in traffic volume would take the LOS from a C to D by 2030 if no improvements | PURCHASE ADD | West | 28.6358 | 8.3505 | 5.7216 | 9.1753 | 2.3024 | 0 | 0 | 3.086 | 29
Y | 1 | Purchase ADD | IP20080002 |  |  |  | Correct roadway geometrics, inadequate passing zones, improve operating speeds and improve connectivity from Carlisle County Line to railroad overpass in Wickliffe. | Reconstruction | Ballard | 004-US-0051 -000 | 0 | 3.233 | 3.233 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18500000 |  | 2010-02-25 16:51 | Improve regional connectivity, mobility and access along US 51 corridor between Tennessee and Illinois. | US 51 the primary north/south corridor connecting the river counties and cities of Fulton, Clinton, Bardwell & Wickliffe in the Purchase and links KY to TN & IL. The alignment geometrics of US 51 are somewhat restricted. Only 23% of the route has adequate
Y | 1 | Purchase ADD | IP20080003 |  |  |  | Improve roadway geometrics, safety, mobility and travel time reliability to US 62 near Lovelaceville, from Carlisle County Line to McCracken County Line. | Reconstruction | Ballard | 004-US-0062 -000 | 0 | 1.754 | 1.754 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 1250000 |  | 1500000 |  | 6500000 |  | 2018-08-06 12:22 | Improve regional connectivity, mobility along US 62 corridor between Paducah and Bardwell. | US 62 is the main route for city of Bardwell, and parts of Carlisle and Ballard counties to Paducah and I-24. Improvements to the road are needed to give better access to the interstate, regional medical facilities and services, shopping and dining facili | 1 | West | 35.3651 | 5.2921 | 6.2887 | 5.5026 | 4.433 | 7.0103 | 0 | 6.8385 | 35
Y | 1 | Purchase ADD | IP20080004 |  |  |  | Address sidewalk needs on US 641 (12th St) between Sycamore and Glendale Streets in Murray to improve access and pedestrian safety. | Spot Improvement | Calloway | 018-US-0641 -000 | 6.67 | 7.17 | 0.5 | Other Improvement Types | 0 | Y | 0 |  | 100000 |  | 500000 |  | 200000 |  | 750000 |  | 2010-02-25 16:51 | Address sidewalk needs on US 641 (12th St) between Sycamore and Glendale Streets in Murray to improve access and pedestrian safety. | The Murray Urban Study identified a need for sidewalks along US 641 between Sycamore (KY 821) and Glendale Streets (US 641X). Sidewalks exist along this main north-south corridor for most of the 5-lane section in Murray. When the section of US 641 from
Y | 1 | Purchase ADD | IP20080005 |  |  |  | Address safety and congestion issues at US 641 and KY 94 in Murray | Reconstruction | Calloway | 018-US-0641 -000 | 7.66 | 7.75 | 0.09 | Improve Intersection | 26 | Y | 0 |  | 150000 |  | 250000 |  | 750000 |  | 500000 |  | 2017-04-10 10:20 | Address safety and congestion issues at US 641 and KY 94 in Murray | The Murray Urban Study identifed the need to improve the US 641 and KY 94 intersection in Murray. In an on-site visit to the location it was observed that larger vehicles (semi-trucks) have trouble negotiating turn movements without off-tracking into on- | PURCHASE ADD | West | 44.1821 | 9.2165 | 13.5567 | 12.8866 | 0 | 0 | 4.9485 | 3.5739 | 44
Y | 1 | Purchase ADD | IP20080006 |  |  |  | Improve roadway geometrics and address safety, tourism and access issues from KY 121 in New Concord to Primrose Drive near KY Lake. | Minor Widening | Calloway | 018-KY-0444 -000 | 0 | 6.437 | 6.437 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 2000000 |  | 15000000 |  | 2010-02-25 16:51 | Improve roadway geometrics and address safety, tourism and access issues from KY 121 in New Concord to Primrose Drive near KY Lake. | This project is needed to provide better access to KY Lake recreation and campground areas and help promote tourism for the lake. This area also serves several lakeside subdivisions. There are safety concerns with the narrow lanes and lack of shoulders f
Y | 1 | Purchase ADD | IP20080007 |  |  |  | Address geometric deficiencies and improve safety and sight distance issues from Bridle Path to Beane Road. | Spot Improvement | Calloway | 018-KY-0732 -000 | 2.46 | 3.05 | 0.59 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 750000 |  | 350000 |  | 1500000 |  | 2018-08-06 15:19 | Address geometric deficiencies and improve safety and sight distance issues from Bridle Path to Beane Road. | Narrow lanes with inadequate shoulders create potential safety concerns and access issues. Vehicles pulling boat trailers and campers use this route to access recreational areas of KY Lake and this segment of KY 732 is a .5 mile stretch of S curves with | 1 | West | 14.7706 | 0.48797 | 4.3814 | 5.0387 | 4.8625 | 0 | 0 | 0 | 15
Y | 1 | Purchase ADD | IP20080008 |  |  |  | Improve roadway geometrics and address access issues to the Murray-Calloway County Airport from KY 121 to KY 1509. | Minor Widening | Calloway | 018-KY-0783 -000 | 8.1 | 10.44 | 2.34 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 2000000 |  | 4000000 |  | 2017-04-10 11:48 | Improve roadway geometrics and address access issues to the Murray-Calloway County Airport from KY 121 to KY 1509. | The purpose of this project is to improve access to the airport. Kyle-Oakley Airport is mainly used for people distribution (small aircraft) and very little if any freight distribution takes place. However, with the construction of a four-lane highway f | 1 | West | 17.7869 | 1.1203 | 5.7732 | 7.2165 | 3.677 | 0 | 0 | 0 | 18
Y | 1 | Purchase ADD | IP20080009 |  |  |  | Improve safety, geometric deficiencies, and reduce congestion at the intersection with KY 821 in Murray. | Reconstruction | Calloway | 018-KY-0822 -000 | 0.68 | 0.78 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 250000 |  | 750000 |  | 700000 |  | 2015-03-27 16:24 | Improve safety, geometric deficiencies, and reduce congestion at the intersection with KY 821 in Murray. | The 2008 Urban Study found that congestion and safety are issues at this signalized intersection. The lack of turn lanes and turning radii also contribute to the congestion and safety issues. This intersection provides a main access point to Murray High
Y | 1 | Purchase ADD | IP20080010 |  |  |  | Correct roadway geometrics and address congestion and safety issues at KY 1550 (Wisewell Road) and Johnny Robertson Road near Murray. | Reconstruction | Calloway | 018-KY-1550 -000 | 4.5 | 4.6 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 150000 |  | 500000 |  | 800000 |  | 2017-04-10 11:50 | Correct roadway geometrics and address congestion and safety issues at KY 1550 (Wisewell Road) and Johnny Robertson Road near Murray. | The Murray Urban Study indicates the need for this project to be congestion and safety. In the past several years the residential growth in this area of Calloway County, just south west of the city limits of Murray, has seen substantial increases. This ar | 1 | West | 20.0069 | 4.8179 | 4.0206 | 3.9691 | 3.8316 | 0 | 0 | 3.3677 | 20
Y | 1 | Purchase ADD | IP20080011 |  |  |  | Correct roadway geometrics and improve safety, access and regional connectivity from Hickman County Line to KY 1377 south of Bardwell. | Reconstruction | Carlisle | 020-US-0051 -000 | 0 | 6.134 | 6.134 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2500000 |  | 4000000 |  | 24000000 |  | 2010-02-25 16:51 | Improve US 51 to provide better regional connectivity, improve mobility and improve travel time reliability between Fulton and Wickliffe. | US 51 is the primary north / south corridor connecting the four river counties in the Purchase and links KY w/ TN,IL & MO. Based on the 1995 study - alignment geometrics are somewhat restricted with 23% of the route having adequate passing sight distance,
Y | 1 | Purchase ADD | IP20080012 |  |  |  | Correct roadway geometrics, inadequate passing zones and improved operating speeds to minimize delay and improve connectivity from Truman Creek Bridge in Bardwell to Ballard County Line. | Reconstruction | Carlisle | 020-US-0051 -000 | 8.259 | 12.655 | 4.396 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1000000 |  | 2500000 |  | 10000000 |  | 2015-04-01 14:27 | Improve US 51 to provide better regional connectivity, improve mobility and improve travel time reliability between Fulton and Wickliffe. | US51 the primary north/south corridor connecting the river counties and cities of Fulton, Clinton, Bardwell & Wickliffe in the Purchase and links KY to TN & IL. The alignment geometrics of US 51 are somewhat restricted. Only 23% of the route has adequate
Y | 1 | Purchase ADD | IP20080013 | 1-333 | 767011 | A | CORRECT GEOMETRIC DEFICIENCIES AT INTERSECTION OF US-51/US-62/FRONT ST/ELM ST IN BARDWELL TO ADDRESS FLOW, SAFETY, AND ACCESS ISSUES.(12CCR)(18CCN) | SAFETY(P) | Carlisle | 020-US-0051 -000 | 7.839 | 8.047 | 0.208 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 340000 | 2020 | 2018-07-10 08:18 | Correct geometric deficiencies at intersection of US 51 / US 62 / Front Street / Elm Street in Bardwell to address traffic flow, safety and access issues. | The geometrics of the interesection with US 51 / US 62 / Front Street / and a nearby somewhat "5th" leg - Elm Street create access issues, limit truck turning movements and truck operations. Trucks turning from US 62 to north bound US 51 also impede traf | 1 | West | 29.799 | 4 | 9.8969 | 5.799 | 1.5808 | 0 | 3.8832 | 4.6392 | 30
Y | 1 | Purchase ADD | IP20080014 |  |  |  | Correct intersection geometric deficiencies at US 45 and KY 1718 at the ICR railroad overpass in Fulton and address safety and sight distance issues. | Reconstruction | Fulton | 038-US-0045 -000 | 1.315 | 1.415 | 0.1 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 150000 |  | 300000 |  | 750000 |  | 2010-02-25 16:51 | This project is needed to improve safety and access along US 45 at the intersection with KY 1718. | At this intersection US 45 intersects with KY 1718 and the entrances to the city cemetery and city park. KY 1718 also serves as the truck access to the business district in Fulton. The geometrics of the intersection create sight distance issues. KY 171
Y | 1 | Purchase ADD | IP20080015 |  |  |  | Correct geometric deficiencies and address safety issues and freight access from Tennessee State Line to KY 166. | Reconstruction | Fulton | 038-KY-0125 -000 | 0 | 1.659 | 1.659 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 500000 |  | 750000 |  | 3000000 |  | 2017-04-10 10:25 | Correct geometric deficiencies and address safety issues and freight access. | The KY 125 corridor links city of Hickman with Union City, TN and Fulton (via KY 166). This route provides access to medical facilities, shopping and restaraunts in Union City for residents of Fulton County. It provides access to the ferry crossing and ri | PURCHASE ADD | West | 33.1108 | 2.1443 | 12.7835 | 6.8428 | 2.3024 | 6.1512 | 2.8866 | 0 | 33
Y | 1 | Purchase ADD | IP20080016 |  |  |  | Correct geometric deficiencies and address safety and freight access issues from KY 166 to KY 1099 in Hickman. | Reconstruction | Fulton | 038-KY-0125 -000 | 1.659 | 5.386 | 3.727 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1500000 |  | 3000000 |  | 10000000 |  | 2018-09-24 14:05 | Correct geometric deficiencies and address safety and freight access issues. | The KY 125 corridor links city of Hickman with Union City, TN and Fulton (via KY 166). This route provides access to medical facilities, shopping and restaurants in Union City for residents of Fulton County. It provides access to the ferry crossing and ri | PURCHASE ADD | West | 39.9708 | 2.6254 | 7.8351 | 7.5515 | 2.3024 | 7.4227 | 3.299 | 8.9347 | 40
Y | 1 | Purchase ADD | IP20080017 |  |  |  | Address geometric deficiencies on KY 166 from KY 125 to KY 1127 to allow preferred truck travel and better access to the Purchase Parkway (Future I-69) and the Hickman - Fulton County Riverport. | Reconstruction | Fulton | 038-KY-0166 -000 | 0 | 3.039 | 3.039 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1500000 |  | 9000000 |  | 2017-04-13 09:47 | Address geometric deficiencies on KY 166 to allow preferred truck travel and better access to the Purchase Parkway (Future I-69) and the Hickman - Fulton County Riverport. | This project is needed for freight movement and intermodal access. KY166 is a major east-west corridor in Fulton County connecting the cities of Hickman and Fulton providing access to the Purchase Parkway (future I-69) and is a vital corridor to the Hickm | 1 | West | 30.488 | 0.52234 | 6.4948 | 5.2062 | 1.323 | 5.6357 | 2.646 | 8.6598 | 30
Y | 1 | Purchase ADD | IP20080018 |  |  |  | Address geometric deficiencies on KY 166 from KY 117 to KY 239 to allow preferred truck travel and better access to the Purchase Parkway (Future I-69) and the Hickman - Fulton County Riverport. | Reconstruction | Fulton | 038-KY-0166 -000 | 3.039 | 5.106 | 2.067 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 1500000 |  | 8000000 |  | 2014-12-11 11:18 |  | This project is needed for freight movement and intermodal access. KY166 is a major east-west corridor in Fulton County connecting the cities of Hickman and Fulton providing access to the Purchase Parkway (future I-69) and is a vital corridor to the Hickm
Y | 1 | Purchase ADD | IP20080019 |  |  |  | Address geometric deficiencies on KY 166 from KY 239 to KY 1125 to allow preferred truck travel and better access to the Purchase Parkway (Future I-69) and the Hickman - Fulton County Riverport. | Reconstruction | Fulton | 038-KY-0166 -000 | 5.106 | 8.978 | 3.872 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3000000 |  | 1500000 |  | 16000000 |  | 2014-12-11 11:19 |  | This project is needed for freight movement and intermodal access. KY166 is a major east-west corridor in Fulton County connecting the cities of Hickman and Fulton providing access to the Purchase Parkway (future I-69) and is a vital corridor to the Hickm
Y | 1 | Purchase ADD | IP20080020 |  |  |  | Address geometric deficiencies on KY 166 from KY 1125 to Myatt Road in Fulton to allow preferred truck travel and better access to the Purchase Parkway (Future I-69) and the Hickman - Fulton County Riverport. | Reconstruction | Fulton | 038-KY-0166 -000 | 8.978 | 12.594 | 3.616 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1500000 |  | 11000000 |  | 2017-04-13 09:52 | Address geometric deficiencies on KY 166 to allow preferred truck travel and better access to the Purchase Parkway (Future I-69) and the Hickman - Fulton County Riverport. | This project is needed for freight movement and intermodal access. KY166 is a major east-west corridor in Fulton County connecting the cities of Hickman and Fulton providing access to the Purchase Parkway (future I-69) and is a vital corridor to the Hickm | 1 | West | 36.4966 | 3.1546 | 5.567 | 6.6753 | 1.323 | 7.5601 | 3.3162 | 8.9003 | 36
Y | 1 | Purchase ADD | IP20080021 |  |  |  | Address geometric deficiencies and drainage issues along KY58 between Tice Road to KY121 Bypass. | Drainage Improvement | Graves | 042-KY-0058 -000 | 6.116 | 6.444 | 0.328 | Maintenance Improvement | 10 |  | 0 |  | 350000 |  | 250000 |  | 350000 |  | 500000 |  | 2017-04-10 10:29 | The purpose of this project is to address flooding issues due to poor water drainage from the street during periods of heavy rainfall. | There are drainage issues along KY 58 (East Broadway) near the KY 121 Bypass in Mayfield. During periods of heavy rain fall, run-off water is slow to drain from KY 58 with water ponding occuring along the street. This creates a hazardous driving condit | PURCHASE ADD | West | 12.6065 | 6.756 | 0 | 5.8505 | 0 | 0 | 0 | 0 | 13
Y | 1 | Purchase ADD | IP20080022 |  |  |  | Improve geometric deficiencies and address school access and safety issues from KY 339 / KY 381 in Sedalia to KY 121 Bypass in Mayfield. | Reconstruction | Graves | 042-KY-0097 -000 | 12.676 | 18.262 | 5.586 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 5000000 |  | 3500000 |  | 25000000 |  | 2010-02-25 16:51 | This project is needed to improve roadway geometrics and reduce hazards created by less than preferred lane and shoulder widths and horizontal alignments. | Inadequate lane and shoulder widths, horizontal alignment issues, narrow bridges, flood prone areas, and raised culvert heads directly next to the roadside edge create safety and access issues for this corridor. KY 97 is a main north-south access route to
Y | 1 | Purchase ADD | IP20080024 |  |  |  | Address safety, congestion and future capacity issues to accommodate increase truck traffic from .041 miles south of Harris Lane to KY 945. | Reconstruction | Graves | 042-KY-0121 -000 | 11 | 14.024 | 3.024 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 2000000 |  | 9000000 |  | 2017-04-13 10:04 | Address safety, congestion and future capacity issues to accommodate increase truck traffic. | This segment of KY 121 corridor is rural 2 lane road near the urban limits of Mayfield. KY 121 is on the National Truck Route. The goal of this project is to improve safety, relieve congestion, improve capacity, accommodate increased truck use and promote | PURCHASE ADD | West | 40.4476 | 4.5498 | 6.134 | 8.0284 | 1.5808 | 7.3883 | 3.7973 | 8.9691 | 40
Y | 1 | Purchase ADD | IP20080025 |  |  |  | Improve intersection geometric deficiencies at KY 121 and KY 1213. | Reconstruction | Graves | 042-KY-0121 -000 | 17 | 18 | 1 | Improve Intersection | 26 |  | 0 |  | 400000 |  | 400000 |  | 250000 |  | 2250000 |  | 2010-02-25 16:51 | Improve intersection geometrics to reduce hazards and improve system mobility. | This project is priority # 7 of the 2000 Corridor Planning Study for KY 121, which is an overall plan for upgrading KY 121 from Mayfield to Wickliffe. KY 121 is recognized on the state truck network and is heavily traveled by logging trucks coming from t
Y | 1 | Purchase ADD | IP20080027 |  |  |  | Correct geometric deficiencies and address safety and truck access issues from KY 58 to KY 483. | Reconstruction | Graves | 042-KY-0131 -000 | 0 | 4.555 | 4.555 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2000000 |  | 2500000 |  | 16000000 |  | 2017-04-13 10:12 | Correct geometric deficiencies and address safety and truck access issues to improve regional connectivity. | This project is needed to improve system linkage along the KY 131 corridor from 1.09 miles south of the Purchase Parkway to KY 284 in Reidland. Narrow lanes and inadequate shoulders are issues for traffic using this route, in particular freight traffic. | PURCHASE ADD | West | 40.2646 | 2.9966 | 7.268 | 10.3093 | 3.5395 | 6.5979 | 0 | 9.5533 | 40
Y | 1 | Purchase ADD | IP20080028 |  |  |  | Correct geometric deficiencies and address safety and truck access issues from KY 483 to KY 849. | Reconstruction | Graves | 042-KY-0131 -000 | 4.555 | 9.445 | 4.89 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 2500000 |  | 20000000 |  | 2014-12-12 16:00 | Correct geometric deficiencies and address safety and truck access issues to improve regional connectivity. | This project is needed to improve system linkage along the KY 131 corridor from 1.09 miles south of the Purchase Parkway to KY 284 in Reidland. Narrow lanes and inadequate shoulders are issues for traffic using this route, in particular freight traffic.
Y | 1 | Purchase ADD | IP20080029 |  |  |  | Correct geometric deficiencies and address safety and truck access issues from KY 849 to KY 348 in Symsonia. | Reconstruction | Graves | 042-KY-0131 -000 | 9.445 | 12.887 | 3.442 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 3500000 |  | 2000000 |  | 14000000 |  | 2014-12-12 16:01 | Correct geometric deficiencies and address safety and truck access issues to improve regional connectivity. | This project is needed to improve system linkage along the KY 131 corridor from 1.09 miles south of the Purchase Parkway to KY 284 in Reidland. Narrow lanes and inadequate shoulders are issues for traffic using this route, in particular freight traffic.
Y | 1 | Purchase ADD | IP20080030 |  |  |  | Correct geometric deficiencies and address safety and truck access issues from KY 348 in Symsonia to McCracken County Line. | Reconstruction | Graves | 042-KY-0131 -000 | 12.887 | 14.44 | 1.553 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1000000 |  | 5000000 |  | 2017-04-13 10:01 | Correct geometric deficiencies and address safety and truck access issues to improve regional connectivity. | This project is needed to improve system linkage along the KY 131 corridor from 1.09 miles south of the Purchase Parkway to KY 284 in Reidland. Narrow lanes and inadequate shoulders are issues for traffic using this route, in particular freight traffic. | 1 | West | 33.7311 | 3.0309 | 8.2474 | 5.9923 | 3.5395 | 6.4261 | 0 | 6.4948 | 34
Y | 1 | Purchase ADD | IP20080031 |  |  |  | Improve safety, access, and regional connectivity, and address geometric deficiencies from Hickman C/L to Cane Creek Bridge. | Reconstruction | Hickman | 053-US-0051 -000 | 0 | 2.4 | 2.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1000000 |  | 2000000 |  | 8500000 |  | 2017-04-13 10:23 | Improve geometric deficiencies and address safety, access, and regional connectivity. | The purpose of this project is to improve system connectivity of a regional corridor. US 51 is a primary north south corridor connecting the four river counties in the Purchase and links KY w/ TN,IL & MO. Based on the 1995 study - alignment geometrics are | PURCHASE ADD | West | 31.5292 | 3.8488 | 2.6289 | 3.9175 | 2.3024 | 6.9759 | 3.5739 | 8.2818 | 32
Y | 1 | Purchase ADD | IP20080032 |  |  |  | Correct geometric deficiencies, and improve safety, access and regional connectivity from Bayou De Chein Bridge to Martin Road. | Reconstruction | Hickman | 053-US-0051 -000 | 4.508 | 6.65 | 2.142 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 1500000 |  | 6500000 |  | 2018-09-24 14:56 | Correct geometric deficiencies, and improve safety, access and regional connectivity. | The purpose of this project is to improve system connectivity of a regional corridor. US 51 is a primary north south corridor connecting the four river counties in the Purchase and links KY w/ TN,IL & MO. Based on the 1995 study - alignment geometrics are | PURCHASE ADD | West | 35.3746 | 4.8935 | 3.6082 | 5.1031 | 2.3024 | 7.6289 | 3.9003 | 7.9381 | 35
Y | 1 | Purchase ADD | IP20080033 |  |  |  | Correct geometric deficiencies and improve safety, access, and regional connectivity from Clayton Street to KY-703 in Clinton. | Reconstruction | Hickman | 053-US-0051 -000 | 7.264 | 8.275 | 1.011 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 3000000 |  | 9000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve system connectivity of a regional corridor. | US 51 is a primary north south corridor connecting the four river counties in the Purchase and links KY w/ TN,IL & MO. Based on the 1995 study - alignment geometrics are somewhat restricted with 23% of the route having adequate passing sight distance, app
Y | 1 | Purchase ADD | IP20080034 |  |  |  | Replace functionally obsolete bridges and improve geometric deficiencies to address safety, tourism and economic development issues from KY 1772 to KY 1540. | Reconstruction | Hickman | 053-KY-0058 -000 | 4.375 | 6.273 | 1.898 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1000000 |  | 1500000 |  | 7000000 |  | 2017-04-13 10:17 | This project is needed to improve system connectivity and provide improved corridor to Columbus-Belmont State Park. | Narrow lanes with little or no shoulders in most locations and narrow bridges are a concern, especially for tourists unfamiliar to the area and for the larger RVs accessing the park. This segment of KY 58 has 5 bridges that are narrow and 4 are identified | 1 | West | 20.7869 | 0.80412 | 2.268 | 3.0928 | 1.9759 | 5.4983 | 0 | 7.1478 | 21
Y | 1 | Purchase ADD | IP20080035 |  |  |  | Improve geometric deficiencies and address safety, tourism and economic development issues from KY 1540 to Cane Creek. | Reconstruction | Hickman | 053-KY-0058 -000 | 6.273 | 7.654 | 1.381 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 1200000 |  | 5000000 |  | 2015-04-01 14:34 | This project is needed to improve system connectivity and provide improved corridor to Columbus-Belmont State Park. | Narrow lanes with little or no shoulders in most locations and narrow bridges are a concern, especially for tourists unfamiliar to the area and for the larger RVs accessing the park. Based on information from Ky's Parks Dept, 85,107 visited the park from
Y | 1 | Purchase ADD | IP20080036 |  |  |  | Improve geometric deficiencies and replace functionally obsolete bridges to address safety, tourism, and economic development issues from Cane Creek to western city limits of Clinton (KY 123). | Reconstruction | Hickman | 053-KY-0058 -000 | 7.654 | 9.49 | 1.836 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1000000 |  | 1500000 |  | 7000000 |  | 2015-04-01 14:34 | This project is needed to improve system connectivity and provide improved corridor to Columbus-Belmont State Park. | Narrow lanes with little or no shoulders in most locations and narrow bridges are a concern, especially for tourists unfamiliar to the area and for the larger RVs accessing the park. Based on information from Ky's Parks Dept, 85,107 visited the park from
Y | 1 | Purchase ADD | IP20080037 |  |  |  | Improve safety, truck mobility, and geometric deficiencies at the ICR Railroad Overpass. | Reconstruction | Hickman | 053-KY-0307 -000 | 0.85 | 1.05 | 0.2 | Improve Railroad Crossing | 55 |  | 0 |  | 400000 |  | 250000 |  | 200000 |  | 4000000 |  | 2017-04-10 10:41 | This project is needed to address concerns with the roadway geometrics related to the low clearance railroad underpass. | The low clearance (12'-6") creates access issues for truck traffic; and because the area is heavily agriculture, it presents problems for farm implements. Trucks have to find alternate routes to get around the low clearance of the railroad. Sight distanc | PURCHASE ADD | West | 12.012 | 0.4055 | 3.7113 | 3.1701 | 4.7251 | 0 | 0 | 0 | 12
Y | 1 | Purchase ADD | IP20080038 |  |  |  | Improve safety and geometric deficiencies at the intersection with KY 1529. | Safety-Haz-Elm | Hickman | 053-KY-0307 -000 | 3.1 | 3.2 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 200000 |  | 200000 |  | 800000 |  | 2017-04-10 10:42 | Improve geometric deficiencies and reduce hazards. | KY 307 is a main north/south corridor connecting the river counties in the Purchase. It provides access to the Fulton Industrial Park, Obion Creek Wildlife Management Area, and the Purchase Parkway (future I-69). This project is needed to address concer | PURCHASE ADD | West | 6.677 | 0.33677 | 0 | 0 | 1.9759 | 0 | 0 | 4.3643 | 7
Y | 1 | Purchase ADD | IP20080039 |  |  |  | Improve geometric deficiencies at intersection of KY 307 and Rose Road (CR-1114) to address safety and sight distance issues. | Safety-Haz-Elm | Hickman | 053-KY-0307 -000 | 3.81 | 3.83 | 0.02 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 200000 |  | 200000 |  | 800000 |  | 2017-04-10 10:43 | Improve geometric deficiencies and reduce hazards. | KY 307 is a main north/south corridor connecting the river counties in the Purchase. It provides access to the Fulton Industrial Park, Obion Creek Wildlife Management Area, and the Purchase Parkway (future I-69). This project is needed to address concer | PURCHASE ADD | West | 5.4742 | 0.33677 | 0 | 0 | 1.9759 | 0 | 0 | 3.1615 | 6
Y | 1 | Purchase ADD | IP20080040 |  |  |  | Improve geometric deficiencies and address safety issues on US 62 from the Ballard County Line to the Paducah Commerce Park in order to provide improved regional system linkage between Bardwell and Paducah. | Reconstruction | McCracken | 073-US-0062 -000 | 0 | 7.851 | 7.851 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3500000 |  | 5000000 |  | 48000000 |  | 2015-04-01 12:21 | The purpose of this project is to improve the system linkage from Bardwell to Paducah. | US 62 is the main route for city of Bardwell & Carlise Co and some Ballard Co residents to Paducah and I-24. Improvements to the road are needed to give better access to the interstate, regional medical facilities and services, shopping and dining facilit
Y | 1 | Purchase ADD | IP20080041 |  |  |  | Improve safety, truck mobility, and access and address geometric deficiencies from Graves C/L to KY284 in Reidland. | Reconstruction | McCracken | 073-KY-0131 -000 | 0 | 3.603 | 3.603 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2000000 |  | 2000000 |  | 13000000 |  | 2018-10-02 12:24 | Improve safety, truck mobility, and access and address geometric deficiencies. | This project is needed to improve system linkage along the KY 131 corridor from 1.09 miles south of the Purchase Parkway to KY 284 in Reidland. Narrow lanes and inadequate shoulders are issues for traffic using this route, in particular freight traffic. | PURCHASE ADD | West | 74.3428 | 4.7079 | 10.5155 | 9.8582 | 4.0722 | 6.6323 | 0 | 8.5567 | 44 | 15 | 15
Y | 1 | Purchase ADD | IP20080042 |  |  |  | Correct geometric deficiencies and address safety, mobility and access issues from US 45 (Lone Oak Road) to KY 994 (Old Mayfield Road) in Paducah. | Reconstruction | McCracken | 073-KY-1310 -000 | 0 | 1.055 | 1.055 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 3000000 |  | 5500000 |  | 2017-04-11 10:07 | Correct geometric deficiencies and address safety, mobility and access issues. | There are design deficiancy concerns due to narrow lanes and less than adequate shoulder widths along the length of this route. Vertical alignments create sight distance issues near the intersection of KY 1310 and the entrance to a large residential area. | 1 | West | 37.9588 | 7.7182 | 5.2577 | 7.5258 | 2.3024 | 6.9072 | 0 | 8.2474 | 38
Y | 1 | Purchase ADD | IP20080043 |  |  |  | Correct geometric deficiencies and address safety and sight distance issues at the intersection of US 68 and Barge Island Road/KY 962. | Reconstruction | Marshall | 079-US-0068 -000 | 17.9 | 18.16 | 0.26 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 150000 |  | 350000 |  | 1500000 |  | 2010-02-25 16:51 | The purpose of this project is to address design deficiency of the intersection and provide transportation infrastructure to facilitate tourism and economic development. | RV traffic & trucks pulling boat trailers are heavy in this area because of the access to several lake resort/campground areas, Land Between the Lakes & Ken Lake State Park. The intersection with KY 962 & Barge Island Rd has horizontal & vertical alignmen
Y | 1 | Purchase ADD | IP20080044 |  |  |  | Correct geometric deficiencies and address safety, service and congestion issues from the Clarks River Bridge in Benton to Benton Baptist Temple Road / Happy Hollow Road. | Reconstruction | Marshall | 079-US-0641 -000 | 10.002 | 11.147 | 1.145 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 3000000 |  | 1500000 |  | 8000000 |  | 2014-12-12 15:28 | The purpose of this project is to improve connectivity between Benton and Draffenville. | This is the main connection between the two cities for local traffic. This section is very congested during peak periods. The route is in a congested area that creates a heavy commercial/residential mix of traffic. It also provides access to Marshall Cou
Y | 1 | Purchase ADD | IP20080045 |  |  |  | Correct geometric deficiencies and address safety, service, and congestion issues from Benton Baptist Temple Road / Happy Hollow Rd to US 68 in Draffenville. | Reconstruction | Marshall | 079-US-0641 -000 | 11.147 | 12.862 | 1.715 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2500000 |  | 2000000 |  | 9000000 |  | 2014-12-12 15:29 | The purpose of this project is to improve connectivity between Benton and Draffenville. | This is the main connection between the two cities for local traffic. This section is very congested during peak periods. The route is in a congested area that creates a heavy commercial/residential mix of traffic. It also provides access to Marshall Cou
Y | 1 | Purchase ADD | IP20080046 |  |  |  | Address safety, access, and condition issues between KY 1824 and Cope Road. | Reconstruction | Marshall | 079-US-0641 -000 | 5.368 | 6.695 | 1.327 | Modernize Roadway-Rural | 26 | Y | 0 |  | 750000 |  | 3000000 |  | 2500000 |  | 7000000 |  | 2014-12-12 15:24 | The purpose of this project is to improve access to business areas south of Benton and access to the city of Benton from US 641 Bypass. | This portion of US 641 is the main access route to Benton from the south. Horizontal alignments and narrow shoulders, and lack of turning lanes contribute to the access and safety issues. This project will serve to better operate the existing system.
Y | 1 | Purchase ADD | IP20080047 |  |  |  | Address safety, access and condition issues between Cope Road to 17th Street in Benton. | Reconstruction | Marshall | 079-US-0641 -000 | 6.695 | 7.815 | 1.12 | Modernize Roadway-Rural | 26 | Y | 0 |  | 750000 |  | 3500000 |  | 2500000 |  | 6500000 |  | 2014-12-12 15:26 | The purpose of this project is to improve access to business areas south of Benton and access to the city of Benton from US 641 Bypass. | This portion of US 641 is the main access route to Benton from the south. Horizontal alignments and narrow shoulders, and lack of turning lanes contribute to the access and safety issues. This project will serve to better operate the existing system.
Y | 1 | Purchase ADD | IP20080048 |  |  |  | Correct intersection geometric deficiencies and address safety and sight distance issues at KY 402 and KY 58. | Reconstruction | Marshall | 079-KY-0402 -000 | 0 | 0.175 | 0.175 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 200000 |  | 200000 |  | 1000000 |  | 2017-04-11 09:54 | The purpose of this project is to improve design deficiencies of a Y intersection. | KY 58 intersects at a Y- with KY 402 at ths location. KY 402 has the ROW with the KY 58 traffic having yield signs and stop signs depending on the direction of travel. The geometric configuration of this intersection creates safety issues with sight dis | 1 | West | 7.8213 | 0.67354 | 1.7526 | 0 | 1.5808 | 0 | 0 | 3.8144 | 8
Y | 1 | Pennyrile ADD | IP20100025 |  |  |  | New Northeast Connector from US 68 approx 2.5 Mi W of I-24 to KY 778 N. of Cadiz. | New Route | Trigg | 111-US-0068X -000 | 1.926 | 4.519 | 2.593 | Other Improvement Types | 0 |  | 250000 |  | 1000000 |  | 2000000 |  | 1000000 |  | 12000000 |  | 2015-01-15 13:24 | Improve truck access and traffic flow. | There is traffic congestion in downtown Cadiz and intersection with poor truning radius for trucks. This proposed connector would reduce congestion downtown and provide better truck access to northern Trigg County.
Y | 1 | Pennyrile ADD | IP20100040 |  |  |  | This project is needed to improve traffic flow and relieve congestion on US 60 inside the City of Marion. In downtown Marion, US 60 has a high ADT with 2/10 lanes. Due to strip commercial development and on-street parking, traffic flow is a problem in t | New Route | Crittenden | 028-US-0060 -000 | 9.24 | 11.3 | 2.06 | Other Improvement Types | 0 |  | 400000 |  | 1000000 |  | 1500000 |  | 1500000 |  | 20000000 |  | 2011-10-27 14:56 | Improve congestion on US 60 in Downtown Marion | There is traffic congestion in downtown Marion and poor truck access. This project will bypass downtown and provide better truck access around Marion.
Y | 1 | Pennyrile ADD | IP20100041 |  |  |  | Construct new Southwestern Marion Bypass from US 60 west to US 641. | New Route | Crittenden | 028-US-0060 -000 | 7.223 | 9.204 | 1.981 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2500000 |  | 2000000 |  | 15000000 |  | 2011-01-19 16:00 | Improve traffic flow and truck access. | This will provide better truck access around marion and decress traffic congestion downtown.
Y | 1 | Purchase ADD | IP20110174 |  |  |  | Address safety, service, and access issues from Purchase Parkway to US 641 south in Draffenville. | Spot Improvement | Marshall | 079-US-0068 -000 | 9.415 | 10.032 | 0.617 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 250000 |  | 250000 |  | 3000000 |  | 2018-11-01 12:33 | The purpose of this project is to implement access management strategies to improve overall traffic flow and service of the corridor. | During peak periods this segment is very congested and multiple entry points create potential safety issues with vehicles turning, vehicles crossing traffic lanes, rear-end collisions, etc. The raised mountable median can be used for left turn movements b | PURCHASE ADD | West | 77.3273 | 9.3677 | 14.5361 | 12.049 | 0.75601 | 0 | 4.433 | 6.1856 | 47 | 15 | 15
Y | 1 | Pennyrile ADD | IP20110195 |  |  |  | On KY 139 south of US 68 Bypass address narrow lanes that creates a safety problems for over size vehicles and farm equipment. | Minor Widening | Trigg | 111-KY-0139 -000 | 13.48 | 15.29 | 1.81 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2500000 |  | 2600000 |  | 6000000 |  | 2015-01-15 13:26 | Improve safety and geometrics | Narrow lanes and a narrow bridge create a safety problem for over size vehicles.
Y | 1 | Purchase ADD | IP20120005 |  |  |  | Improve intersection geometric deficiencies (lack of turning radius) to address truck access issues at Clayton Street and US 51 in Clinton. | Spot Improvement | Hickman | 053-US-0051 -000 | 7.2 | 7.3 | 0.1 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 100000 |  | 200000 |  | 375000 |  | 2015-04-01 14:31 | Address inadequate geometrics for truck turning and improve access. | This project is needed to improve freight access for trucks by addressing the lack of turning radius at the intersection of US51 & Clayton Street in Clinton. US 51 is part of the state designated national truck network. Trucks leaving facilities in Clint
Y | 1 | Purchase ADD | IP20120006 |  |  |  | Improve intersection gemetrics and address sight distance issues with access to US 51 from KY 1301 and the entrance of Harpers Country Hams near Clinton. | Reconstruction | Hickman | 053-US-0051 -000 | 11.1 | 11.4 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 175000 |  | 150000 |  | 350000 |  | 750000 |  | 2015-04-01 14:32 | The purpose of this project is to address safety and freight access issues for trucks and other traffic exiting Harpers Country Hams and KY 1301. | Due to the geometrics of US 51 a hillcrest is present near this intersection. As vehilces travel south on US 51 this crest can "blind" any truck traffic or other cars waiting to leave the industry or exit from KY 1301. Likewise the crest prevents the t
Y | 1 | Purchase ADD | IP20120007 |  |  |  | The purpose of this project is to address improvements in Bardwell from US 51 to KY 1372 by upgrading to an urban section with sidewalks and turn lanes. | Reconstruction | Carlisle | 020-US-0062 -000 | 0 | 1.062 | 1.062 | Modernize Roadway-Rural | 26 |  | 0 |  | 450000 |  | 250000 |  | 400000 |  | 3500000 |  | 2017-04-10 11:15 | Make improvements to US 62 to provide better access to courthouse and county fairgrounds, including adding curb and gutter and sidewalks. Improve US 62 to provide better regional connectivity, improve mobility and improve travel time reliability between B | This project is needed to provide turning lanes to the new county courthouse and the entrance to the county fairgrounds. The addition of sidewalks will improve pedestrian access from within the city to the courthouse and county fairgrounds which also has | PURCHASE ADD | West | 28.2474 | 2.8179 | 4.5876 | 5.3093 | 2.3024 | 7.079 | 0 | 6.1512 | 28
Y | 1 | Purchase ADD | IP20120008 |  |  |  | Improve the safety and mobility and address geometric deficiencies and congestion at the intersection with Buckner Lane, Broadway, and LaBelle Avenue in Paducah. | Reconstruction | McCracken | 073-KY-0731 -000 | 0.415 | 0.447 | 0.032 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 3000000 |  | 300000 |  | 2000000 |  | 2017-04-10 11:17 | Address geometric deficiencies and improve mobility, reduce travel time and system connectivity. | City officials have looked at the possibility of constructing a roundabout at this intersection to help with safety, traffic flow and peak period congestion at this 5 leg intersection. Improvements would also help the geometrics of the dis-junction / junc
Y | 1 | Purchase ADD | IP20120010 |  |  |  | PROJECT INACTIVE. DUPLICATE OF ACTIVE PROJECT IP20180005. Improve safety and address geometric deficiencies at the intersection with KY 1628 / Palestine Rd (CR 1024). | Reconstruction | Carlisle | 020-US-0062 -000 | 11 | 11.2 | 0.2 | Improve Intersection | 26 |  | 0 |  | 125000 |  | 500000 |  | 135000 |  | 900000 |  | 2017-04-10 11:54 |  | This project is needed to address safety concerns with the geometrics of the intersection creating sight distance issues. The roads intersecting with US 62 are at skewed angles and a slight crest in the US 62 roadway just west of the intersection raise c
Y | 1 | Purchase ADD | IP20120011 |  |  |  | Widen from KY 1286 to Village Square Drive to improve level of service and safety. See 2013 Planning Study (Priority 6). | Minor Widening | McCracken | 073-KY-0998 -000 | 1.718 | 2.17 | 0.452 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 750000 |  | 500000 |  | 3000000 |  | 2017-04-10 11:18 | To improve level of service and safety. See 2013 Planning Study (Priority 6). | Substandard lane width and shoulders exist along KY 998. The KY 998 southern approach to US 60 was recently improved to Village Square Drive, providing 12 ft lanes and left turn lane. The current plan study recommends widening this segment to 11 ft lanes | PURCHASE ADD | West | 25.2036 | 7.622 | 4.1753 | 5.3995 | 2.3024 | 0 | 0 | 5.7045 | 25
Y | 1 | Purchase ADD | IP20120012 |  |  |  | Widen from New Holt Road to KY 998 to improve level of service and safety. See 2013 Planning Study (Priority 5). | Minor Widening | McCracken | 073-KY-1286 -000 | 6.423 | 6.916 | 0.493 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 750000 |  | 450000 |  | 3000000 |  | 2017-04-10 11:25 | To improve level of service and safety. See 2013 Planning Study (Priority 5) | KY 1286 is existing 2 10-11 ft lanes with 3 ft shoulders and a 45 MPH limit. This location exhibits more frequent crashes at the New Holt intersection than can be attributed to random occurances. The current plan study recommends widening to include bike | PURCHASE ADD | West | 27.5473 | 8.488 | 7.0103 | 4.9356 | 2.3024 | 0 | 0 | 4.811 | 28
Y | 1 | Purchase ADD | IP20120013 |  |  |  | A planning study to review McCracken Blvd (CS1067) in Paducah and determine upgrades needed from increase in traffic since the opening of the new McCracken County High School. | Minor Widening | McCracken | 073-CS-1067 -000 | 0 | 2.024 | 2.024 | Transportation Studies | 0 |  | 150000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-10-02 12:44 | This project is needed to provide an improved alternate access or back entrance for the newly consolidated McCracken County High School. A planning study is needed to review McCracken Blvd (CS1067) in Paducah. | The opening of the high school is expected to increase traffic in this area. This route will be used to provide access to the rear entrance of the high school from the southern and eastern portions of the county and by those looking to avoid the congesti | 1 | West | 7.9983 | 0 | 0 | 6.4175 | 1.5808 | 0 | 0 | 0 | 8
Y | 1 | Pennyrile ADD | IP20120016 |  |  |  | Improve line-of-sight on curve near KY 1199 intersection from MP. 0.500 to MP 0.700. | Safety-Haz-Elm | Lyon | 072-KY-3171 -000 | 0.5 | 0.7 | 0.2 | Realign Intersection | 26 |  | 0 |  | 135000 |  | 55000 |  | 85000 |  | 495000 |  | 2017-04-10 11:27 | Improve safety and geometric of curve and intersection | Vehicles traveling south bound on KY 3171 and turning onto KY 1199 have poor line-of-sight for north bound KY 3171 traffic due to curve and bank that obstruct the line of sight to on-coming traffic. | PENNYRILE ADD | West | 5.2371 | 0.46048 | 0 | 0 | 4.7766 | 0 | 0 | 0 | 5
Y | 1 | Pennyrile ADD | IP20120052 |  |  |  | Improve the geometric deficiencies and truck mobility at the US641/US60 intersection in Marion. | Spot Improvement | Crittenden | 028-US-0060 -000 | 9.155 | 9.24 | 0.085 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 200000 |  | 250000 |  | 800000 |  | 2018-08-29 11:16 | Improve truck access, traffic flow and safety. | Trucks cannot make the turning radius needed on this intersection going from south bound US 60 to west bound US 60. There are also problems with trucks turning from east bound on US 60 turning north toward downtown. This causses traffic congestion as tru | PENNYRILE ADD | West | 35.9416 | 6.8522 | 9.3299 | 10.2062 | 1.5808 | 0 | 3.8144 | 4.1581 | 36
Y | 1 | Purchase ADD | IP20120059 |  |  |  | Access management along US 60 from New Holt Road to James-Sanders Blvd in Paducah. (Per September 2012 Scoping Study) | Congestion Management | McCracken | 073-US-0060 -000 | 10.13 | 10.484 | 0.354 | Arterial to Partial Control | 23 | Y | 0 |  | 200000 |  | 50000 |  | 50000 |  | 1700000 |  | 2015-04-01 15:49 | The purpose of this project is to reduce congestion, improve mobility, improve access and reduce hazards. | This section is one of the most congested routes in the region. The congestion, along with multiple stop lights and the numerous entrance / exit locations contribute to a high number of crashes through this corridor. Access control measures could improv
Y | 1 | Purchase ADD | IP20120084 |  |  |  | Improve mobility, address geometric deficiencies, and reduce congestion along Brinn Rd (CR1401) between KY 80 and Utterback Road (CR1552) in Murray. | Minor Widening | Calloway | 018-CR-1401 -000 | 0.811 | 1.132 | 0.321 | Modernize Roadway-Rural | 26 |  | 0 |  | 700000 |  | 2000000 |  | 2400000 |  | 4000000 |  | 2018-09-21 16:13 | Improve mobility, address geometric deficiencies, and reduce congestion along Brinn Rd (CR1401) between KY 80 and Utterback Road (CR1552) in Murray. | According to KYTC the ADT on 16th St ranges from 4300 to 5300 vehicles per day. A 2007 study conducted by the city looked at the level of service for 16th St. Expected growth in traffic volume would take the LOS from a C to D by 2030 if no improvements | PURCHASE ADD | West | 14.1692 | 2.4124 | 5.1031 | 3.3892 | 3.2646 | 0 | 0 | 0 | 14
Y | 1 | Purchase ADD | IP20130140 |  |  |  | Alignment and intersection improvements new New Holt Road to improve safety and traffic flow. See 2013 Planning Study (Priority 2). | Minor Widening | McCracken | 073-KY-1286 -000 | 6.35 | 6.65 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 1500000 |  | 600000 |  | 2100000 |  | 2013-11-05 15:21 | Address roadway geometrics and improve mobility and system connectivity. See 2013 Planning Study (Priority 2). | The existing intersection is signalized with left turn bays on New Holt Rd. KY 1286 is 2 10 ft travel lanes with 45 MPH. Currently this location exhibits more frequent crashes than can be attributed to random occurrences. Two improvements are recommended
Y | 1 | Purchase ADD | IP20130141 |  |  |  | Widen from US 62 to New Holt Road to improve level of service and safety. See 2013 Planning Study (Priority 4). | Minor Widening | McCracken | 073-KY-1286 -000 | 5 | 6.423 | 1.423 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 5700000 |  | 1900000 |  | 8400000 |  | 2013-11-05 15:17 | Improve level of service and safety. See 2013 Planning Study (Priority 4). | KY 1286 is 2 10-11 ft lanes with 3 ft shoulders and 45 MPH limit. This location exhibits more frequent crashes at the curve south of Buckner Ln than can be attributed to random occurrences. Traffic volumes are anticipated to approach capacity by the desi
Y | 1 | Purchase ADD | IP20130142 |  |  |  | Add turn lanes at KY 1286 and KY 998 intersection to improve traffic flow and safety. See 2013 Planning Study (Priority 7). | Spot Improvement | McCracken | 073-KY-1286 -000 | 6.8 | 6.916 | 0.116 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 500000 |  | 500000 |  | 750000 |  | 2015-04-01 12:27 | To improve traffic flow and safety. See 2013 Planning Study (Priority 7). | KY 1286 ends with a stop sign at KY 998. North-south movements on KY 998 do not stop. According to the 2013 plan study existing traffic and safety data do not justify adding turn lanes at this time and this improvement should be considered at traffic vol
Y | 1 | Pennyrile ADD | IP20140028 |  |  |  | Reconstruct and elevate a 0.12 mile section of KY 295 above the floodplain from M.P. 1.038 to M.P. 1.605 just south of Dycusburg | Safety-Haz-Elm | Crittenden | 028-KY-0295 -000 | 1.038 | 1.605 | 0.567 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 100000 |  | 75000 |  | 500000 |  | 2015-01-15 13:31 | Improve safety and provide access to local residents in large floods. | This section of KY 295 is in the 100 year floodplain and flood waters will occasionally block the road stranding approx. 40 people from access into or out of the homes.
Y | 1 | Purchase ADD | IP20140030 |  |  |  | Address geometric alignment and potential safety issues to KY 497 from KY 94 to the barge terminal entrance on KY Lake to improve access for truck traffic. | Minor Widening | Calloway | 018-KY-0497 -000 | 0 | 2.635 | 2.635 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 3500000 |  | 1000000 |  | 8000000 |  | 2018-08-06 16:08 | Address geometric alignment and potential safety issues to KY 497 from KY 94 to the barge terminal entrance on KY Lake to improve access for truck traffic. | There are horizontal and vertical alignment issues / concerns along this route for truck traffic accessing the grain handling facility and port on KY Lake. The narrow lanes and lack of shoulders also are a concern for recreational vehicles and trucks wit
Y | 1 | Purchase ADD | IP20140031 | 1-398 |  | A | IMPROVE ACCESS AND REDUCE CONGESTION ON US-62 FROM KY-95 TO THE EXISTING FOUR-LANE HIGHWAY AT LONE VALLEY RD NEAR I-24 INTERCHANGE AND FUTURE I-69 CONNECTION. | MAJOR WIDENING(O) | Marshall | 079-US-0062 -000 | 7.2 | 8.497 | 1.297 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 750000 | 2021 | 250000 | 2023 | 500000 | 2023 | 3500000 | 2024 | 2018-07-10 08:17 | Address access and future capacity on US 62 from KY 95 to the existing four-lane highway at Lone Valley Rd near I-24 interchange and future I-69 connection for economic/tourism development. | The purpose of this project is to provide transportation infrastructure to facilitate tourism and economic development from I-24 and the state park to Calvert City. It will also continue the existing four lane from the interstate to KY 95 and help accommo | PURCHASE ADD | West | 80.7302 | 5.8076 | 14.8454 | 10.5928 | 0 | 7.7663 | 4.2612 | 7.457 | 51 | 15 | 15
Y | 1 | Purchase ADD | IP20150134 | 1-8853 |  | A | SAFETY IMPROVEMENT AT INTERSECTION OF KY-1099 AND KY-125. (14CCN)(18CCN) | SAFETY(P) | Fulton | 038-KY-1099 -000 | 2.25 | 2.288 | 0.038 | Improve Intersection | 26 |  |  |  | 0 |  | 550000 | 2021 | 840000 | 2021 | 1560000 | 2023 | 2018-07-10 08:18 | Improve intersection to allow more adequate truck turning movements. | This project is needed to improve intermodal accessibility. The turning radius at KY 125&KY 1099 is less than adequate for trucks traveling this route. Most trucks are accessing the Hickman-Fulton County Riverport and other local industry. Trucks are | 1 | West | 45.8179 | 3.7732 | 2.0619 | 0 | 4.0378 | 0 | 2.8522 | 3.0928 | 16 | 15 | 15
Y | 1 | Pennyrile ADD | IP20150350 |  |  |  | NEW CONNECTOR ROUTE BETWEEN CHESTNUT OAK CEMETERY ROAD/KY 1271/US 62. (14CCN) | New Route | Lyon | 072-KY-0810 -000 | 2.884 | 3.756 | 0.872 | Construct Road in New Location | 0 |  | 0 |  | 1000000 |  | 3000000 |  | 2000000 |  | 4000000 |  | 2015-07-08 14:56 | Unknown | Unknown
Y | 1 | Purchase ADD | IP20150351 | 1-8702 |  | A | NEW ACCESS ROAD FROM KY-305 NEAR KY-998, EXTENDING WEST TO THE OHIO RIVER MEGAPARK. (2-LANE INITIAL, 4-LANE ULTIMATE)(12CCN)(14CCR)(18CCN) | NEW ROUTE(O) | McCracken | 073-KY-0305 -000 | 6.53 | 8.348 | 1.818 | Construct Road in New Location | 0 |  | 0 |  | 2000000 |  | 4310000 | 2021 | 3630000 | 2023 | 16990000 | 2024 | 2018-07-10 08:18 | Provide access to the proposed Ohio River Megapark. | The Greater Paducah Economic Development Council has planned a unique site opportunity entitled Riverport West Industrial Complex for recruiting major industrial companies. The property encompasses 1,540 rail-served acres on the Ohio River in western McC | 1 | West | 29.5799 | 6.268 | 0 | 10.3737 | 0.91065 | 7.9725 | 4.055 | 0 | 30
Y | 1 | Pennyrile ADD | IP20150440 | 1-330 | 767011 | A | PADUCAH-HENDERSON; RELOCATE US-60 FROM EAST OF THE TENNESSEE RIVER BRIDGE TO EAST OF RUDD-SPEES ROAD (00CCR)(12CCR)(14CCR) | RELOCATION(O) | Livingston | 070-US-0060 -000 | 0.875 | 4.2 | 3.325 | 2 Lane to 4 Lane Divided - Rural | 36 | [5 empty] | 1580000 | 2021 | 1560000 | 2021 | 17310000 | 2025 | 2018-07-10 08:18 | This is part of a larger corridor project to reconstruct US 60 from Paducah to Henderson KY. This is one phase of a multi-phase corridor project. | Improve traffic flow, safety and truck access | 1 | West | 85.9914 | 7.0653 | 14.0722 | 12.3454 | 1.9759 | 8.6942 | 3.3849 | 8.4536 | 56 | 15 | 15
Y | 1 | Purchase ADD | IP20160033 |  |  |  | RECONSTRUCT JULIAN CARROLL PKWY INTERSECTION W/THE MAYFIELD BYPASS TO PROVIDE SUPERIOR THROUGH MOVEMENT TO THE PARKWAY. (I-69 CORRIDOR IMPROVEMENT)(SEE 1-234.20 FOR R,U,C)(12CCR) | Reconstruction | Graves | 042-I -0069 -000 | 21.285 | 21.89 | 0.605 | Innovative Interchange | 40 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-06 10:39 | PROJECT COMPLETED IN 2018 | PROJECT COMPLETED IN 2018
Y | 1 | Pennyrile ADD | IP20160141 |  |  |  | Improve truck access and safety | New Route | Crittenden | 028-KY-0091 -000 | 0 | 2.88 | 2.88 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-11-02 14:24 |  | MARION TO FREDONIA; SURFACING AND INCIDENTAL GRADE AND DRAIN.(12CCR)(14CCR)
Y | 1 | Pennyrile ADD | IP20160149 | 1-8951 |  | A | REALIGN KY 124 APPROACH TO KY 139 TO IMPROVE INTERSECTION ANGLE AND SIGHT DISTANCE. (16CCN)(18CCN) | AIR QUALITY(P) | Trigg | 111-KY-0139 -000 | 17.8 | 17.95 | 0.15 | Improve Intersection | 26 |  |  |  | 210000 | 2019 | 170000 | 2020 | 170000 | 2020 | 680000 | 2020 | 2018-07-10 08:18 | Improve Safety | REALIGN KY 124 APPROACH TO KY 139 TO IMPROVE INTERSECTION ANGLE AND SIGHT DISTANCE. | 1 | West | 13.7131 | 4.1168 | 3.1443 | 1.4175 | 1.323 | 0 | 0 | 3.7113 | 14
Y | 1 | Purchase ADD | IP20170013 |  |  |  | Correct substandard geometric design of Y-intersection and address safety concerns with US 62 and KY 286. | Safety-Haz-Elm | McCracken | 073-US-0062 -000 | 3.171 | 3.369 | 0.198 | Realign Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 300000 |  | 750000 |  | 2017-04-11 10:27 | The purpose of this project is to improve the safety of a major intersection between US 62 and KY 286 in southwestern McCracken County. | Improvements to this intersection will improve a major regional corridor that provides access for residents of Ballard and Carlisle Counties to the regional services offered in Paducah, i.e. hospitals, major retail and dining establishments, the community
Y | 1 | Pennyrile ADD | IP20170023 |  |  |  | Widen KY 139 from the intersection of KY 124 north of Cadiz to the I-24 Interchange in Caldwell Co (EMP 0.348) | Minor Widening | Trigg | 111-KY-0139 -000 | 17.905 | 24.62 | 6.715 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 1500000 |  | 10000000 |  | 2017-03-31 11:07 | Improve safety and geometrics | Narrow lanes and substandard geometrics along this route create poor access for trucks and safety issues for vehicles in general. This is intended to be the first phase of a KY 139 reconstruction/widening project that would eventually cover the entire KY | PENNYRILE ADD | West | 48.1761 | 2.3643 | 9.3814 | 10.2448 | 1.9759 | 0 | 0 | 9.2096 | 33 |  | 15
Y | 1 | Pennyrile ADD | IP20170024 |  |  |  | On US 62 where the P&L Rail overpass meets the two (2) KY 810 intersections, reconstruct US 62/KY 810 (North and South) intersections with turn lanes or other measure to improve line of sight and safety issues. | Safety-Haz-Elm | Lyon | 072-US-0062 -000 | 3.57 | 3.836 | 0.266 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 250000 |  | 500000 |  | 1500000 |  | 2017-03-31 11:02 | Improve safety | There is a line-of-sight issues on US 62 with east and west bound vehicles approaching both north and south bound intersections of KY 810. The line-of-sight issues are largely due to poor geometrics on US 62 as it curves to go under the P&L Railroad unde | PENNYRILE ADD | West | 66.8943 | 6.1512 | 13.9691 | 7.4613 | 0.68729 | 0 | 4.3986 | 4.2268 | 37 | 15 | 15
Y | 1 | Pennyrile ADD | IP20170025 |  |  |  | Construct new Interchange on I-24 at the overpass of KY 124 | New Interchange | Trigg | 111-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 0 |  | 2000000 |  | 500000 |  | 500000 |  | 25000000 |  | 2017-03-31 11:16 | Improve access to I-24 for Northern Trigg County and the west side of Caldwell County. | A new interchange on I-24 at the KY 124 overpass would improve vehicle access to the north side of Trigg County and the west side of Caldwell County. | PENNYRILE ADD | West | 42.8814 | 7.8557 | 0 | 5.0258 | 0.54983 | 9.5533 | 4.8969 | 0 | 28 |  | 15
Y | 1 | Purchase ADD | IP20170075 |  |  |  | Address condition, access and future congestion issues from approx 1 mile north of Wickliffe to Ohio River Bridge.(Section L - 1993 Scoping Study) | Relocation | Ballard | 004-US-0051 -000 | 4.644 | 7.327 | 2.683 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 2500000 |  | 750000 |  | 250000 |  | 25000000 |  | 2018-08-06 12:46 | Address condition, access and future congestion issues from approx 1 mile north of Wickliffe to Ohio River Bridge.(Section L - 1993 Scoping Study) | This project is part of an overall plan to widen US 60 west of Paducah continuing with US 51 to the Ohio River. This section travels through the Willow Slough area into the Ohio River bottoms. There is limited shoulders resulting in minimal opportunity f | 1 | West | 46.4768 | 5.622 | 9.6392 | 6.3015 | 3.7285 | 7.9038 | 4.7595 | 8.5223 | 46
Y | 1 | Purchase ADD | IP20180005 |  |  |  | Improve intersection with US 62 and KY 1628 / Palestine Rd (CR 1024). | Reconstruction | Carlisle | 020-US-0062 -000 | 11 | 11.2 | 0.2 | Improve Intersection | 26 |  | 0 |  | 125000 |  | 500000 |  | 135000 |  | 900000 |  | 2018-10-11 15:55 | This project is needed to address safety concerns related to sight distance issues with the intersection geometrics. | The roads intersecting with US 62 are at skewed angles and a slight crest in the US 62 roadway just west of the intersection create sight limitations for vehicles turning onto US 62.
Y | 1 | Purchase ADD | IP20180012 |  |  |  | Improve geometric alignments and address access issues and safety concerns from KY 2206 to the entrance of Marshall County Hospital in Benton. | Reconstruction | Marshall | 079-KY-0348 -000 | 5.78 | 7.207 | 1.427 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 1500000 |  | 6000000 |  | 2018-10-02 10:44 | Improve geometric alignments and address access issues and safety concerns | There are concerns with the vertical and horizontal alignments along this segment. Also contributing to concerns are the lack of shoulders and some sight distance issues. Since the hospital was relocated along this segment there has been an increase in t
Y | 1 | Purchase ADD | IP20180013 |  |  |  | Add turn lanes at entrances to Reidland Elementary School. | Spot Improvement | McCracken | 073-KY-0131 -000 | 4.833 | 5.815 | 0.982 | [14 empty] | Improve access to Reidland Elementary School. | During peak traffic periods, just before school and right after, this section of KY 131 can be very congested and with the many vehicles / buses stopping to turn into school entrance increases the concern for rear end collisions. The addition of turn lan
Y | 1 | Purchase ADD | IP20180073 |  |  |  | Upgrade/Widen KY 121 bypass in Mayfield to four lanes. | Major Widening | Graves | 042-KY-0121 -000 | 5.499 | 8.938 | 3.439 |  |  | Y | [11 empty] | This project is needed because the capacity of KY 121 between the intersections with KY 80 / KY 97 and US 45 is becoming inadequate to meet future traffic volumes, resulting in congestion and reduced mobility on this stretch of highway. | This project is needed to address future traffic volumes and level of service along the KY 121 Bypass. The bypass opened in the late 1990's. When it was constructed in it's current form (two lane highway), the anticipated growth of this corridor was rec
Y | 1 | Purchase ADD | IP20190022 |  |  |  | Planning Study of US 45 from intersection at KY 1241/KY 6042 at 5.785 MP to intersection at US 62/KY 731 at 9.224 MP. | Transportation Study | McCracken | 073-US-0045 -000 | 5.785 | 9.224 | 3.439
Y | 1 | Purchase ADD | IP20190023 |  |  |  | Reconstruct intersection of US 641 S and KY 58. | Spot Improvement | Marshall | 079-KY-0058 -000 | 8.136 | 8.236 | 0.1
Y | 1 | Purchase ADD | IP20190049 |  |  |  | Increase the directional capacity of the roadway during the daily peak travel periods. | Transportation Study | McCracken | 073-US-0045 -000 | 6.338 | 9.203 | 2.865
Y | 1 | Purchase ADD | IP20190050 |  |  |  | Widen from KY 1286 (Friendship Road) to US 62 to improve mobility, safety and address geometric deficiencies. | Reconstruction | McCracken | 073-KY-0998 -000 | 0 | 1.718 | 1.718
Y | 1 | Purchase ADD | IP20190051 |  |  |  | Correct geometric deficiencies and address safety, service and congestion issues from KY 782 (Griggstown Road) to western I-69 ramps. | Reconstruction | Marshall | 079-US-0068 -000 | 8.736 | 9.384 | 0.648
Y | 1 | Purchase ADD | IP20190054 |  |  |  | Improve safety, access, geometric deficiencies and economic development issues from Ezell Lane to Clayton Street | Reconstruction | Hickman | 053-US-0051 -000 | 6.866 | 7.264 | 0.398
Y | 1 | Purchase ADD | IP20190056 |  |  |  | Improve safety and roadway geometrics at intersection with E Tucker/W Tucker Road. | Reconstruction | Graves | 042-KY-0303 -000 | 14.7 | 14.9 | 0.2
Y | 1 | Purchase ADD | IP20190057 |  |  |  | Correct roadway geometrics and address congestion and safety issues at KY 94 and KY 1660 (Johnny Robertson Road) near Murray. | Spot Improvement | Calloway | 018-KY-0094 -000 | 7.598 | 7.798 | 0.2
Y | 1 | Pennyrile ADD | IP20190114 |  |  |  | Stabilization of the western bank on KY 137 due to Ohio River Erosion | Reconstruction | Livingston | 070-KY-0137 -000 | 3.4 | 4.4 | 1 | [14 empty] | Stabilization of bank erosion due to Ohio River undercutting Road | Safety and Maintenance
Y | 1 | Pennyrile ADD | IP20190133 |  |  |  | On KY 120 reconstruct substandard curve between Herman Travis Rd Intersection and Piney Creek | Reconstruction | Crittenden | 028-KY-0120 -000 | 8.9 | 9.1 | 0.2 | [14 empty] | Reconstruct substandard curve to improve safety | Improve safety
Y | 1 | Pennyrile ADD | IP20190152 |  |  |  | Turn Lane on westbound US 62 at Kuttawa Springs Rd Intersection | Safety-Haz-Elm | Lyon | 072-US-0062 -000 | 8.7 | 8.67 | -0.03 | [14 empty] | Improve safety with a turn lane for west bound traffic on US 62 at the Kuttawa Springs Intersection | Improve traffic flow and safety
Y | 2 | Green River ADD | IP20000002 |  |  |  | Address safety and service concerns of US 60 from the Daviess/Hancock county line to Lewisport. SEE SEGMENT 5 IN JULY, 1998 ADVANCE PLANNING STUDY. | Major Widening | Hancock | 046-US-0060 -000 | 0 | 1.993 | 1.993 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 5400000 |  | 3000000 |  | 25000000 |  | 2010-02-25 16:51 |  | US 60 from Maceo in Daviess County to Lewisport in Hancock County is a two lane route that is bordered by four lane routes on the east and west presenting safety concerns resulting from the reduction of traffic lanes from four to two. Numerous fatalitie
Y | 2 | Evansville-Henderson MPO | IP20000003 |  |  |  | Reduce congestion and improve the safety and mobility of the interchange of US 41 and US 60 in Henderson. | New Interchange | Henderson | 051-US-0041 -000 | 15.883 | 16.083 | 0.2 | Other Improvement Types | 0 | Y | 250000 |  | 2000000 |  | 3000000 |  | 1200000 |  | 25000000 |  | 2015-08-05 13:59 | Reduce congestion and eliminate bottleneck. | The US 41 corridor is highly traveled as it provides access to significant commercial and service and industry land uses. Congestion is prominent along the majority of the corridor and is most heavily concentrated in the vicinity of US 60/Green Street.
Y | 2 | Pennyrile ADD | IP20000005 |  |  |  | SPOT IMPROVEMENTS FROM KY 189 TO KY 181 AT GREENVILLE. SEE FEBRUARY 2003 INTERMEDIATE PLANNING STUDY. | Minor Widening | Muhlenberg | 089-US-0062 -000 | 8.78 | 10.398 | 1.618 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2605000 |  | 2014-07-09 10:45 |  | The high CRF and ADT indicate safety issues along the route as well as congestion. Left turning vehicles block traffic while waiting on-coming traffic to clear.
Y | 2 | Pennyrile ADD | IP20000006 |  |  |  | RECONSTRUCTION FROM KY 277 TO US 431 IN CENTRAL CITY | Reconstruction | Muhlenberg | 089-KY-0304 -000 | 0.402 | 0.713 | 0.311 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 250000 |  | 400000 |  | 1000000 |  | 2010-02-25 16:51 |  | There is a high CRF along this section.
Y | 2 | Green River ADD | IP20000007 |  |  |  | MAJOR WIDENING FROM PROPOSED WAVERLY BYPASS TO PROPOSED CORYDON BYPASS. SEE SEGMENT 28 IN APRIL, 1998 ADVANCE PLANNING STUDY. | Major Widening | Union | 113-US-0060 -000 | 23.86 | 26.069 | 2.209 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 0 |  | 0 |  | 0 |  | 17000000 |  | 2015-03-19 09:26 |  | US 60 is a two-lane AAA rated truck route that provides regional connection to the Henderson, KY-Evansville, IN area as well provides access to Illinois via KY 109 or KY 56 in Morganfield.
Y | 2 | Evansville-Henderson MPO | IP20040009 |  |  |  | Improve safety and level of service on the eastern approach of the intersection. | Reconstruction | Henderson | 051-US-0041 -000 | 17.323 | 17.353 | 0.03 | Improve Intersection | 26 | Y | 0 |  | 700000 |  | 2000000 |  | 1000000 |  | 7000000 |  | 2015-08-05 12:54 | Improve level of service. | Reconstruct the east approach of Watson Ln at US 41 to improve level of service.
Y | 2 | Evansville-Henderson MPO | IP20040010 |  |  |  | Widen Green Street to improve safety and level of service throughout the corridor. | Major Widening | Henderson | 051-US-0041A -000 | 13.235 | 17.397 | 4.162 | Major Widening-Urban Streets | 25 | Y | 0 |  | 2200000 |  | 3500000 |  | 3000000 |  | 25100000 |  | 2018-12-11 14:11 | Improve safety and relieve congestion on a busy urban thoroughfare. | A planning study was completed for the US 41A/Green St corridor and was finalized in January, 2010. The study recommended major widening to 5 lanes for most of the corridor.
Y | 2 | Evansville-Henderson MPO | IP20040011 |  |  |  | Widen Atkinson St to improve level of service and reduce congestion. | Major Widening | Henderson | 051-CS-1014 -000 | 0.248 | 0.856 | 0.608 | Modernize Roadway-Urban | 16 |  | 0 |  | 1000000 |  | 1500000 |  | 2500000 |  | 5500000 |  | 2019-01-14 15:08 | Relieve congestion and improve safety. | Atkinson Street is congested from Madison Street to Washington Steet. Major widening would help reduce the congestion and provide a safer more efficient route. | Evansville/Henderson MPO | West | 37.4931 | 9.3058 | 7.9381 | 9.6134 | 2.2852 | 8.3505 | 0 | 0 | 38
Y | 2 | Pennyrile ADD | IP20040012 |  |  |  | Address congestion from North Drive to Hospital Drive in Madisonville, by majoring widening and replacing the super elevated bridge over the CSX railroad from MP 16.63 to MP 16.98 | Minor Widening | Hopkins | 054-US-0041 -000 | 16.634 | 16.989 | 0.355 | Other Improvement Types | 0 |  | 0 |  | 900000 |  | 1900000 |  | 2000000 |  | 6500000 |  | 2010-02-25 16:51 | Improve safety and congestion | This section of road has a high CRF and ADT. Madisonville has severe congestion problems on all its north/south corridors and this section of US 41 is the City's major north/south route with the most congestion problems. This project includes, and is fu
Y | 2 | Owensboro MPO | IP20040036 |  |  |  | US 431 - Reconstruct to provide better traffic flow, provide better access, and improve safety. Project begins at the McLean/ Daviess County Line and ends at KY 140 East. | Reconstruction | Daviess | 030-US-0431 -000 | 0 | 2.599 | 2.599 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2500000 |  | 3000000 |  | 13000000 |  | 2010-07-15 16:19 | The purpose of this project is to improve safety, reliability and mobility along US 431, better control access and reduce congestion. | This section of US 431 does not provide sufficient safety that make drivers feel safe. There are high banks, since the road is in the floodplain, and guard rails. The guard rails force drivers to hug the center line. Residents of the counties south of O
Y | 2 | Owensboro MPO | IP20040037 |  |  |  | Pleasant Valley Rd - Reconstruct from KY 144 to the hospital main entrance, to better accommodate future traffic loads accessing the commercial area along KY 54 and Pleasant Valley Road. *The scope of this project has been reduced because improvements | Reconstruction | Daviess | 030-CR-1013 -000 | 0 | 0.655 | 0.655 | Local Roadway Improvements | 3 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4000000 |  | 2010-08-23 05:15 | The purpose of this project is to improve safety, reliability and mobility along US 60, better control access and reduce congestion. | This project is to improve access from the new US 60 Bypass Extension to the commercial areas along US 60 East in Daviess County. Also, the east industrial part is adjancent to Pleasant Valley Road, this would enhance access to US 60 East and the US 60 B
Y | 2 | Owensboro MPO | IP20050002 |  |  |  | US 60 - Address safety issues and provide an access to the west industrial park. Project is at the intersection of US 60 and KY 1554. | Reconstruction | Daviess | 030-US-0060 -000 | 4.213 | 4.313 | 0.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 350000 |  | 300000 |  | 1100000 |  | 2010-06-11 15:59 | The purpose of this project is to improve safety, reliability and mobility at the US 60-Ky 1554 intersection, better control access and reduce congestion | KY 1554 intersects with US 60 at an angle (roughly 60 degree angle). There is frequent truck traffic on this route as it serves as a connector from US 60 to the Audubon Parkway. There is a large industry nearby that generates truck traffic.
Y | 2 | Pennyrile ADD | IP20050003 |  |  |  | Reconstruct the KY 70/KY 1337 Intersection and improve sight distance on KY 70 | Safety-Haz-Elm | Hopkins | 054-KY-0070 -000 | 12.331 | 12.431 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 200000 |  | 200000 |  | 800000 |  | 2015-08-05 13:51 | Improve safety | There is limited sight distance and poor geometrics at this intersection which creates a safety hazard.
Y | 2 | Owensboro MPO | IP20050032 |  |  |  | KY 144 - Reconstruct to provide 12 foot driving lanes and turn lanes where needed. Project begins near US 60 interchange at Reid Rd (KY 1456) and ends at Jones Rd (KY 1389). | Reconstruction | Daviess | 030-KY-0144 -000 | 2.09 | 4.966 | 2.876 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 3500000 |  | 3500000 |  | 6500000 |  | 2014-12-11 08:59 | The purpose of this project is to improve safety, reliability and mobility along KY 144, better control access and reduce congestion. | Coal mines are going to reopen in Knottsville. During the time that the mines were open, there was many accidents along KY 144 involving coal trucks. The road is narrow, 10 - 12 foot lanes, and has problems with horizontal alignments.
Y | 2 | Owensboro MPO | IP20050033 |  |  |  | Fairview Drive - Extend from existing section to Pleasant Valley Road near Hayden Road. Project begins at Calumet Trace (CR 1507A) and ends at Pleasant Valley Road (CR 1013). | New Route | Daviess | 030-CR-1507L -000 | 0.506 | 0.582 | 0.076 | Local Roadway Improvements | 3 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4000000 |  | 2014-12-11 09:53 | The purpose of this project is to improve safety, reliability and mobility along KY 3143, better control access and reduce congestion. | To extend Fairview from Calumet Trace* to Pleasant Valley Road, to provide a direct access for traffic along KY 54 to the new US 60 Bypass Extension. Residents on the eastern side of Daviess County do not have easy access to the growing commercial distric
Y | 2 | Pennyrile ADD | IP20050043 |  |  |  | Address congestion issues with new connector east of the Illinois Central Railroad from KY 400 to KY 911. | New Route | Christian | 024-US-0041A -000 | 0 | 1.738 | 1.738 | Other Improvement Types | 0 | Y | 0 |  | 400000 |  | 900000 |  | 300000 |  | 4800000 |  | 2012-03-15 08:47 |  | This project will relieve congestion from US 41A
Y | 2 | Pennyrile ADD | IP20060073 |  |  |  | North Jefferson St. - Reconstruct the intersection at east Green Street in Princeton. | Reconstruction | Caldwell | 017-US-0062 -000 | 7.245 | 7.345 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 300000 |  | 600000 |  | 1200000 |  | 2015-01-29 08:37 |  | The intersection of US 62 (N. Jefferson St) and Green St. has a substandard turning radius for truck traffic. Truck traffic is diverted onto Green St. as part of the designated truck route through the City. Trucks have difficulty making the turn and som
Y | 2 | Pennyrile ADD | IP20060074 |  |  |  | RECONSTRUCT INTERSECTION AT KY 293 IN PRINCETON from MP 11.3 to MP 11.4. | Minor Widening | Caldwell | 017-KY-0139 -000 | 11.347 | 11.447 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 500000 |  | 600000 |  | 1000000 |  | 2010-02-25 16:51 |  | The intersection of KY 293 and KY 139 is congested and has poor traffic flow mainly due to the lack of left turn lanes at the intersection. This intersection has a high ADT and a widening of this intersection will improve traffic flow.
Y | 2 | Pennyrile ADD | IP20060075 |  |  |  | GROOMS LANE - RECONSTRUCTION AND EXTENSION FROM KY KY 293 TO US 62 AT NEW PARKWAY CONNECTOR W OF PRINCETON | New Route | Caldwell | 017-KY-1495 -000 | 2.517 | 5.517 | 3 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 800000 |  | 900000 |  | 10500000 |  | 2010-02-25 16:51 | Improve truck access and traffic flow. | This is part of a larger project that comprise a series of connector routes around the City of Princeton to relieve traffic congestion in downtown Princeton improve truck access The existing truck route is routed through residential neighborhoods with su
Y | 2 | Pennyrile ADD | IP20060077 |  |  |  | Improve safety on US 41 at Old Madisonville Road. | Reconstruction | Christian | 024-US-0041 -000 | 15.26 | 15.46 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 300000 |  | 500000 |  | 1000000 |  | 2010-02-25 16:51 |  | Construct turn lanes. There is a safety problem at this intersection.
Y | 2 | Pennyrile ADD | IP20060079 |  |  |  | MAJOR WIDENING OF US 68/80 FROM KY 1007 TO THE US 68 BYPASS IN HOPKINSVILLE | Major Widening | Christian | 024-US-0068 -000 | 7.137 | 10.137 | 3 | Other Improvement Types | 0 | Y | 0 |  | 2200000 |  | 2500000 |  | 2250000 |  | 13900000 |  | 2019-03-11 11:41 | to address congestion issues on US 68/80. | This section of road has traffic congestion problems
Y | 2 | Pennyrile ADD | IP20060080 | 2-899 |  | A | ADDRESS CONGESTION AND MOBILITY OF US 68 FROM KY 91 TO KY 1007 IN HOPKINSVILLE. (18CCN) | RECONSTRUCTION(O) | Christian | 024-US-0068 -000 | 9.221 | 10.137 | 0.916 | Modernize Roadway-Rural | 26 | Y |  |  | 0 | 2021 | 1930000 | 2023 | 3900000 | 2023 | 5630000 | 2024 | 2019-03-11 09:00 |  | A high CRF indicates safety issues along this route. The route has a large amount of strip commercial development along it. Left turning vehicles block traffic waiting for on-coming traffic to clear. Need to widen roadway. | PENNYRILE ADD | West | 88.1924 | 8.1581 | 13.2474 | 13.6082 | 3.1615 | 9.6564 | 4.3814 | 5.9794 | 58 | 15 | 15
Y | 2 | Pennyrile ADD | IP20060081 |  |  |  | RECONSTRUCTION FROM I-24 TO US 68 (HOPKINSVILLE BYPASS) | Reconstruction | Christian | 024-KY-0107 -000 | 10.797 | 15.681 | 4.884 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2500000 |  | 2000000 |  | 16700000 |  | 2010-02-25 16:51 |  | poor geometrics
Y | 2 | Pennyrile ADD | IP20060082 |  |  |  | CONSTRUCT TURN LANES AT 21 ST STREET IN HOPKINSVILLE | Spot Improvement | Christian | 024-KY-0107 -000 | 18 | 18.2 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 500000 |  | 600000 |  | 900000 |  | 2015-08-05 13:40 |  | There is a high CFR and congestion at this intersection. Turn lanes are needed to help traffic flow.
Y | 2 | Pennyrile ADD | IP20060083 |  |  |  | Improve safety and reduce congestion on KY 109 from US 68 to KY 1682 in Hopkinsville. | Major Widening | Christian | 024-KY-0109 -000 | 10.945 | 12.09 | 1.145 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 600000 |  | 1000000 |  | 3000000 |  | 2010-02-25 16:51 |  | The is a high CRF along this route. It also has poor geometrics and a steep grade. Widen to three lanes.
Y | 2 | Pennyrile ADD | IP20060085 |  |  |  | MAJOR WIDENING OF KY 1007 FROM LITTLE RIVER BRIDGE TO SANDERSON RD INCLUDING A NEW CONNECTOR FROM SANDERSON RD TO THE KY 1682 BYPASS TO INCLUDE PED./BIKE FACILITIES IN HOPKINSVILLE | Major Widening | Christian | 024-KY-1007 -000 | 0.63 | 2.5 | 1.87 | Modernize Roadway-Rural | 26 |  | 0 |  | 2100000 |  | 3100000 |  | 2800000 |  | 12500000 |  | 2019-03-11 11:28 | IMPROVE SAFETY AND TRAFFIC FLOW | This route has strip commercial developmemt that adds to the congestion problems. Left turning vehicles block traffic while waiting on on-coming traffic to clear. | PENNYRILE ADD | West | 51.86 | 8.1787 | 12.5258 | 10.3479 | 0.94502 | 9.7251 | 4.811 | 5.3265 | 52
Y | 2 | Pennyrile ADD | IP20060086 |  |  |  | NEW ROUTE EXTENDING NORTH DRIVE 3 LANE FROM SANDERSON RD TO KY 1682 IN HOPKINSVILLE. | New Route | Christian | 024-KY-1007 -000 | 2.509 | 2.919 | 0.41 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 300000 |  | 300000 |  | 1000000 |  | 2011-02-28 14:08 |  | There is a need for access from KY 1007 to the Hopkinsville Northern Bypass (KY1682) This will provide better traffic flow to the Hopkinsville Community College and Christian Co. High School.
Y | 2 | Pennyrile ADD | IP20060087 | 2-227 |  | A | RECONSTRUCT KY 1007 FROM US 68 TO SANDERSON ROAD IN HOPKINSVILLE.(12CCR)(14CCR)(16CCR)(18CCN) | RECONSTRUCTION(O) | Christian | 024-KY-1007 -000 | 0.785 | 2.509 | 1.724 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 0 |  | 3400000 | 2020 | 6760000 | 2022 | 2019-03-11 07:55 |  | This route has a high ADT and CRF. Congestion problems are caused by left turning vehicles. There are several major traffic generators on this route including a college, a high school and a middle school. | 2 | West | 79.4656 | 8.6323 | 9.8454 | 11.8299 | 4.3127 | 8.11 | 0 | 6.7354 | 50 | 15 | 15
Y | 2 | Green River ADD | IP20060088 |  |  |  | Address safety, condition and service issues at the intersection of KY-69 and Pellville-Lyonia Road. | Safety-Haz-Elm | Hancock | 046-KY-0069 -000 | 0.476 | 0.576 | 0.1 | Realign Intersection | 26 |  | 0 |  | 250000 |  | 300000 |  | 350000 |  | 900000 |  | 2010-06-24 11:27 |  | KY-69 is a AAA rated 10 ft. wide 2-lane route with only a 2 ft. shoulder that provides access to the Hancock County industrial area from the Western Kentucky Parkway via KY 54 in Grayson County. Only one mile of KY-69 is presently a Federal Designated Tr
Y | 2 | Green River ADD | IP20060089 |  |  |  | Address safety concerns of KY-69 from KY-144 to US-60 at Hawesville. | Reconstruction | Hancock | 046-KY-0069 -000 | 4.627 | 13.08 | 8.453 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2500000 |  | 3400000 |  | 21250000 |  | 2017-05-19 11:33 | Address safety issues along KY 69 from KY 144 to US 60. | The following need has been identified for this project: Improve Roadway Safety | GREEN RIVER ADD | West | 45.2698 | 1.9794 | 10.2062 | 11.0567 | 4.7595 | 5.2921 | 2.5945 | 9.3814 | 45
Y | 2 | Green River ADD | IP20060090 |  |  |  | Address safety concerns of the KY-69 and KY-144 intersection to provide for better sight distance. | Safety-Haz-Elm | Hancock | 046-KY-0069 -000 | 4.627 | 4.727 | 0.1 | Realign Intersection | 26 |  | 0 |  | 200000 |  | 200000 |  | 250000 |  | 1000000 |  | 2017-05-19 11:34 | Address safety issues at the KY 69 and KY 144 intersection. | The following need has been identified for this project: Improve Roadway Safety | GREEN RIVER ADD | West | 12.0997 | 1.9794 | 1.8557 | 0 | 2.3024 | 0 | 2.5945 | 3.3677 | 12
Y | 2 | Green River ADD | IP20060091 |  |  |  | Address safety concerns of the KY-69 and B. Rice Road intersection to provide for better sight distance. | Safety-Haz-Elm | Hancock | 046-KY-0069 -000 | 8.903 | 9.193 | 0.29 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 200000 |  | 250000 |  | 1100000 |  | 2017-05-19 11:36 | Address safety issues at the KY 69 and CR 1200 (B. Rice Road) intersection. | The following need has been identified for this project: Improve Roadway Safety | GREEN RIVER ADD | West | 16.8892 | 1.9794 | 3.3505 | 2.3325 | 2.3024 | 0 | 2.5945 | 4.3299 | 17
Y | 2 | Green River ADD | IP20060092 |  |  |  | Address safety and condition concerns of KY-69 from Coal Bank Hollow Rd and Middle Patesville Rd. | Reconstruction | Hancock | 046-KY-0069 -000 | 10.4 | 11.48 | 1.08 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 300000 |  | 400000 |  | 2750000 |  | 2010-06-28 14:55 |  | KY-69 from Coal Bank Hollow Road to Middle Patesville Road consists of several deficiencies. It is a AAA rated 10 ft. wide 2-lane route with only a 2 ft. shoulder that provides access to the Hancock County industrial area from the Western Kentucky Parkw
Y | 2 | Green River ADD | IP20060093 |  |  |  | Address safety and condition concerns of KY-69 near Tick Ridge Rd. | Safety-Haz-Elm | Hancock | 046-KY-0069 -000 | 12 | 13 | 1 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 175000 |  | 400000 |  | 2500000 |  | 2010-06-30 14:35 |  | KY-69 is a AAA rated 10 ft. wide 2-lane route with only a 2 ft. shoulder that provides access to the Hancock County industrial area from the Western Kentucky Parkway via KY 54 in Grayson County. Only one mile of KY-69 is presently a Federal Designated Tru
Y | 2 | Green River ADD | IP20060094 |  |  |  | Address safety concerns on KY 271 from KY 1847 to US 60 in Hancock County | Minor Widening | Hancock | 046-KY-0271 -000 | 3.161 | 4.581 | 1.42 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 500000 |  | 500000 |  | 1800000 |  | 2017-05-19 11:37 | Address safety issues along KY 271 from KY 1847 to US 60 | The following need has been identified for this project: Improve Roadway Safety | GREEN RIVER ADD | West | 20.817 | 0.32302 | 8.7629 | 7.2809 | 4.4502 | 0 | 0 | 0 | 21
Y | 2 | Green River ADD | IP20060095 |  |  |  | Address safety concerns of KY 3543 (formerly KY 271) from US 60 to KY 334 in Hancock County | Minor Widening | Hancock | 046-KY-3543 -000 | 0 | 1.405 | 1.405 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 500000 |  | 600000 |  | 2100000 |  | 2010-07-12 12:06 |  | KY 3542 (formerly KY 271)is a AAA rated 2-lane route with 10 ft lanes and 2ft shoulders that provides access to the Hancock County Industrial sites. Narrow shoulders present a safety concern for commercial and industrial vehicles.
Y | 2 | Green River ADD | IP20060096 |  |  |  | Address safety concerns of the intersection of KY 2181 and Ed Brown Road in Hancock County. | Safety-Haz-Elm | Hancock | 046-KY-2181 -000 | 2.724 | 2.824 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 300000 |  | 300000 |  | 900000 |  | 2010-07-12 15:18 |  | The KY 2181 intersection with Ed Brown Road has limited sight distance. KY 2181 from KY 144 to US 60 is a rural route with 8 & 9 ft. lane widths and 3 ft. earthen shoulders. This route provides access from Pellville to Hawesville.
Y | 2 | Pennyrile ADD | IP20060097 |  |  |  | MAJOR WIDENING OF US 41A FROM CALUMET LN AT MADISONVILLE TO KY 502. SEE AUGUST 2002 MADISONVILLE URBAN AREA TRANSPORTATION STUDY. | Major Widening | Hopkins | 054-US-0041A -000 | 3.722 | 8.794 | 5.072 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 4500000 |  | 2500000 |  | 24300000 |  | 2010-02-25 16:51 | IMPROVE CONGESTION AND TRAFFIC FLOW | There are congestion issues along this route
Y | 2 | Pennyrile ADD | IP20060098 |  |  |  | Reconstruct and Widen KY 70 on southwest side of Madisonville from proposed Southwest Connector to Seminary Street. | Major Widening | Hopkins | 054-KY-0070 -000 | 16.453 | 18.412 | 1.959 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 4500000 |  | 1750000 |  | 12000000 |  | 2010-02-25 16:51 | Improve safety, poor geometrics and traffic flow | There is a high CFR along this section of road with a high IRI. Together with the poor geometrics and narrow 10/2 lanes there are safety issues.
Y | 2 | Pennyrile ADD | IP20060099 |  |  |  | Widen and improve KY 254 from KY 70 to Carraige Lane from MP 0.0 to MP 2.25. | Major Widening | Hopkins | 054-KY-0254 -000 | 0 | 2.25 | 2.25 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 2500000 |  | 5750000 |  | 2017-05-19 12:03 | Improve safety and traffic flow. | KY 254 from KY 70 to Carraige Lane is a narrow 2/9 lane route with no shoulders and deep ditches next to the road. It has a railroad underpass and some drainage problems in this area. | PENNYRILE ADD | West | 29.6136 | 1.9725 | 6.3402 | 8.866 | 2.3024 | 6.0825 | 0 | 4.05 | 30
Y | 2 | Pennyrile ADD | IP20060100 |  |  |  | RECONSTRUCTION FROM E.T. BREATHITT PKY. TO KY 481. SEE AUGUST 2002 MADISONVILLE URBAN AREA TRANSPORTATION STUDY. | Reconstruction | Hopkins | 054-KY-0336 -000 | 1.9 | 3.3 | 1.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 450000 |  | 800000 |  | 1000000 |  | 3500000 |  | 2017-05-19 13:03 | Improve safety and poor road geometrics | Madisonville has three main interchanges with the Pennyrile PKWY which lead to downtown. The Earlington interchange is under utilized due to the poor conditions of KY 336 leading to the Grapevine and southern Madisonville areas. This section also has a h | PENNYRILE ADD | West | 31.5052 | 3.0515 | 4.5361 | 6.9072 | 4.1924 | 5.8763 | 0 | 6.9416 | 32
Y | 2 | Pennyrile ADD | IP20060101 |  |  |  | Reconstruct KY 1069 from US 41A to 0.2 miles north of Brown Badgett Loop intersection near Hanson. | Reconstruction | Hopkins | 054-KY-1069 -000 | 0 | 1.8 | 1.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 1900000 |  | 8000000 |  | 2017-05-19 13:04 | Improve safety and poor road geometrics | KY 1069 is a narrow road with 2/9 lanes and poor geometrics. Due to increasing residential development, the CRF is high and increasing. | PENNYRILE ADD | West | 55.0883 | 3.567 | 11.8041 | 10.683 | 4.3299 | 6.2543 | 0 | 3.45 | 40 | 15
Y | 2 | Green River ADD | IP20060102 |  |  |  | Address condition, safety, and service issues on US 431 from a point just North of KY 136 at Livermore to KY-250 | Major Widening | McLean | 075-US-0431 -000 | 5.9 | 9.852 | 3.952 | Other Improvement Types | 0 |  | 0 |  | 1400000 |  | 1750000 |  | 2250000 |  | 10000000 |  | 2013-05-03 14:21 |  | US 431 is a 12 ft. route with 2 ft. shoulders that has multiple access points thereby creating a safety concern. US 431 provides direct access from McLean County to Daviess County thus is frequently congested with farming vehicles/equipment. US 431 is al
Y | 2 | Green River ADD | IP20060103 |  |  |  | Address condition, safety, and services issues on US 431 from North end of bridge in Livermore in McLean County to a point South of KY 136. Break out from 02 075 B0431 62.00 | Major Widening | McLean | 075-US-0431 -000 | 5.4 | 5.9 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 1000000 |  | 1000000 |  | 2500000 |  | 2011-02-28 14:57 |  | US 431 is a 12 ft. route with 2 ft. shoulders that has multiple access points thereby creating a safety concern. US 431 provides direct access from McLean County to Daviess County thus is frequently congested with farming vehicles/equipment. US 431 is a
Y | 2 | Green River ADD | IP20060104 |  |  |  | Address need for a new truck route from the Green River Bridge to KY 136 in Calhoun in McLean County. | New Route | McLean | 075-KY-0081 -000 | 11.625 | 12.765 | 1.14 | Other Improvement Types | 0 |  | 0 |  | 900000 |  | 2500000 |  | 1500000 |  | 4000000 |  | 2010-07-15 15:49 |  | KY-81 is a rural 2 lane route with 12 ft driving lanes and 2 ft shoulders that provides access from Calhoun, KY (McLean County Seat) to Owensboro, KY. This section of KY-81 runs directly through the City of Calhoun business district presenting a safety
Y | 2 | Green River ADD | IP20060105 |  |  |  | Address safety issue at intersection of KY 81 and KY 140 in McLean County. | Safety-Haz-Elm | McLean | 075-KY-0081 -000 | 17.95 | 18.05 | 0.1 | Improve Intersection | 26 |  | 0 |  | 160000 |  | 300000 |  | 300000 |  | 700000 |  | 2017-05-19 13:07 | Address safety issues on at the KY 81 and KY 140 intersection. | The following need has been identified for this project: Improve Roadway Safety | GREEN RIVER ADD | West | 14.8007 | 5.5739 | 0 | 0 | 0.84192 | 0 | 4.0206 | 4.3643 | 15
Y | 2 | Pennyrile ADD | IP20060106 |  |  |  | RECONSTRUCT INTERSECTION AT US 431 IN CENTRAL CITY | Reconstruction | Muhlenberg | 089-US-0062 -000 | 17.93 | 18.03 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 1000000 |  | 1000000 |  | 1500000 |  | 2010-02-25 16:51 |  | A high CRF indicates a safety issues at this intersection. The intersection's geometrics are substandard for truck traffic.
Y | 2 | Pennyrile ADD | IP20060107 |  |  |  | RECONSTRUCTION FROM GREENVILLE TO SOUTH HIGH SCHOOL | Reconstruction | Muhlenberg | 089-KY-0176 -000 | 0 | 3 | 3 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 1850000 |  | 1250000 |  | 7500000 |  | 2017-05-19 13:11 |  | This route has a high CRF and poor geometrics. A number of school busses travel this route to access Muhlenberg High School. | PENNYRILE ADD | West | 63.5103 | 7.4364 | 9.7423 | 11.4175 | 4.3471 | 7.8351 | 0 | 7.732 | 48 |  | 15
Y | 2 | Pennyrile ADD | IP20060108 |  |  |  | RECONSTRUCTION FROM WESTERN KENTUCKY PKY TO KY 70 | Reconstruction | Muhlenberg | 089-KY-0181 -000 | 15.234 | 18.955 | 3.721 | Other Improvement Types | 0 |  | 0 |  | 900000 |  | 2300000 |  | 1000000 |  | 9250000 |  | 2010-02-25 16:51 |  | This route has poor geometrics and narrow 2/9 lanes that create safety issues.
Y | 2 | Green River ADD | IP20060110 |  |  |  | Address condition, safety and service issues on KY 54 from KY 69N to Marsh Lane at Fordsville. | Major Widening | Ohio | 092-KY-0054 -000 | 6.018 | 8.038 | 2.02 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1200000 |  | 1000000 |  | 7500000 |  | 2010-08-12 16:30 |  | KY 54 from KY 69 N (MP 6.018) to Marsh Lane (MP 7.408) has 10 ft. or less lanes and minimal shoulder widths except one mile within Fordsville that has 12 ft. lanes and 12 ft. shoulder width. KY 54 from KY 69 N (MP 6.018) to KY 69 S (MP 7.408) is used by
Y | 2 | Green River ADD | IP20060111 |  |  |  | Address condition, safety and service issues on KY 69 from William H. Natcher Parkway at Hartford to Sunnydale Road. | Reconstruction | Ohio | 092-KY-0069 -000 | 14.992 | 22 | 7.008 | Other Improvement Types | 0 |  | 0 |  | 1700000 |  | 2000000 |  | 2000000 |  | 17500000 |  | 2010-08-19 08:28 |  | KY 69 from the William Natcher Parkway at Hartford to Sunnydale Dr. is a 9-14 ft. 2-lane connector route with minimum shoulder widths from Hartford to Fordsville. The CRF is 0.90 from MP 14.992 to 15.383 indicating a safety concern. Project provides acce
Y | 2 | Green River ADD | IP20060112 |  |  |  | Address the safety concerns of KY-69 from Sunnydale Road to KY-54 at Fordsville. | Reconstruction | Ohio | 092-KY-0069 -000 | 22 | 31.623 | 9.623 | Other Improvement Types | 0 |  | 0 |  | 2300000 |  | 3500000 |  | 7600000 |  | 24000000 |  | 2010-02-25 16:51 |  | KY-69 from Sunnydale Road to KY-54 at Fordsville is a rural 2 lane route with lane widths ranging from 9 ft to 10 ft with 1 ft and 2 ft shoulders. KY-69 is a "AAA" truck weight class from MP 13.672 to MP 37.339. It is also a Coal Haul Route; part of the
Y | 2 | Green River ADD | IP20060113 |  |  |  | Address safety and service concerns of KY-273 from US-231 in Beaver Dam to Goshen Church Road. | Reconstruction | Ohio | 092-KY-0273 -000 | 2.111 | 3.44 | 1.329 | Modernize Roadway-Rural | 26 |  | 0 |  | 700000 |  | 1000000 |  | 900000 |  | 4500000 |  | 2017-05-19 13:23 | Address safety and access issues along KY 273 from US 231 in Beaver Dam to Goshen Road. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 28.3995 | 4.5636 | 6.4433 | 7.049 | 3.5052 | 6.8385 | 0 | 0 | 28
Y | 2 | Green River ADD | IP20060114 |  |  |  | Address need for additional parkway access at KY 1245 near Rockport on the Western KY Parkway. | New Interchange | Ohio | 092-WK-9001 -000 | 67.32 | 67.42 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 700000 |  | 200000 |  | 200000 |  | 6000000 |  | 2010-02-25 16:51 |  | Need additional access to parkway at KY 1245 near Rockport.
Y | 2 | Green River ADD | IP20060115 |  |  |  | Improve safety and mobility of the Western KY Parkway (WK9001)and the William Natcher Parkway (WN9007) (I-65 Spur) interchange to address interstate standards. | Reconstruction | Ohio | 092-WK-9001 -000 | 76.757 | 76.857 | 0.1 | Innovative Interchange | 40 | Y | 0 |  | 400000 |  | 700000 |  | 500000 |  | 3500000 |  | 2015-03-16 11:21 |  | Inadequate interchange for the type and volumes of traffic. Area has a high rate of crashes. A relatively high percentage of truck traffic has been identified in this area.
Y | 2 | Green River ADD | IP20060116 |  |  |  | Address need for new interchange on the William Natcher Parkway at the Bluegrass Crossings Business Centre. | New Interchange | Ohio | 092-WN-9007 -000 | 40 | 40.1 | 0.1 | Construct Road in New Location | 0 | Y | 0 |  | 700000 |  | 300000 |  | 500000 |  | 6000000 |  | 2010-09-09 14:51 |  | The Bluegrass Crossings Business Centre does not have adequate access to the William N. Natcher Parkway (WN 9007).
Y | 2 | Green River ADD | IP20060117 |  |  |  | Address safety concerns on US 60 from KY 492 to the US 60 Bypass outside Morganfield. | Major Widening | Union | 113-US-0060 -000 | 13.29 | 15.401 | 2.111 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1200000 |  | 2100000 |  | 1300000 |  | 9800000 |  | 2017-05-19 13:26 | Address safety issues along US 60 form KY 492 to the US 60 Bypass outside Morganfield. | The following need has been identified for this project: Improve Roadway Safety. | GREEN RIVER ADD | West | 51.0954 | 6.5636 | 12.6804 | 10.1675 | 0.68729 | 8.4192 | 3.4021 | 9.1753 | 51
Y | 2 | Green River ADD | IP20060118 |  |  |  | Address safety concern at the KY 56 and KY 141 intersection. | Reconstruction | Union | 113-KY-0056 -000 | 19.612 | 19.712 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 200000 |  | 300000 |  | 750000 |  | 2010-09-16 11:14 |  | The KY 56 and KY 141 intersection presents a safety concern due several possible factors. The intersection contains a liquor store and a nightclub and several years ago the intersection was changed from a two-way stop to a four-way stop with traffic on KY
Y | 2 | Green River ADD | IP20060119 |  |  |  | Address condition and safety concerns of US 41A from KY 670 to Bull Creek. | Reconstruction | Webster | 117-US-0041A -000 | 1.324 | 4.133 | 2.809 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 900000 |  | 1200000 |  | 6500000 |  | 2010-10-05 12:19 |  | US 41A from KY 670 to Bull Creek is a rural two-lane route with 10 ft. lanes. IRI is 136 indicating a road surface that is considerably rough. US 41 A is a connector from Dixon to Providence. This segment provides access to the Providence bypass (KY 67
Y | 2 | Green River ADD | IP20060120 |  |  |  | Address condition and safety of the US 41-A intersection at Wright-Clayton/Stan Hope Road near Providence. | Reconstruction | Webster | 117-US-0041A -000 | 3.379 | 3.479 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 100000 |  | 200000 |  | 800000 |  | 2011-02-28 14:49 |  | The US 41-A intersection at Wright-Clayton/Stan Hope Road near Providence has poor sight distance and curvature.
Y | 2 | Green River ADD | IP20060121 |  |  |  | Address condition and safety concerns of US 41A from Bull Creek to Vanderburg-Lisman Road. | Reconstruction | Webster | 117-US-0041A -000 | 4.133 | 6.433 | 2.3 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 400000 |  | 900000 |  | 5700000 |  | 2010-10-11 14:31 |  | US 41A from Bull Creek to Vanderburg-Lisman Road is a rural two-lane route with 10 ft. lanes. IRI indicates a road surface that is considerably rough. US 41 A is a connector from Dixon to Providence. This segment provides access to the Providence bypass
Y | 2 | Green River ADD | IP20060122 |  |  |  | Address safety and service concerns of US 41A from south of Asher Road to KY 56 West near Poole. | Reconstruction | Webster | 117-US-0041A -000 | 11.499 | 15.599 | 4.1 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 800000 |  | 2200000 |  | 12000000 |  | 2010-10-13 15:21 |  | US 41A is a rural two-lane route with 10 ft lanes and 4 ft shoulders. It provides access from Providence and Dixon in Webster County to Henderson County. US 41-A is a AAA rated truck route with ADT of 3,020. The narrow lanes create a safety concern for
Y | 2 | Green River ADD | IP20060123 |  |  |  | Address safety and service concerns of KY 132 from KY 109 to KY 1340. | Reconstruction | Webster | 117-KY-0132 -000 | 7.625 | 10.101 | 2.476 | Other Improvement Types | 0 |  | 0 |  | 480000 |  | 800000 |  | 800000 |  | 6000000 |  | 2010-11-04 16:18 |  | KY 132 is rural two-lane route with 10 ft. lanes and 3 ft. shoulders. The CRF for this section is above 1.0 indicating a safety concern. This route provides access from Clay/Wheatcroft area to the county seat of Dixon.
Y | 2 | Green River ADD | IP20060124 |  |  |  | Address safety, condition and service of KY 132 from US 41A in Dixon to KY 494. | Reconstruction | Webster | 117-KY-0132 -000 | 16.382 | 25.87 | 9.488 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2850000 |  | 2900000 |  | 24000000 |  | 2010-11-08 10:02 |  | KY 132 is rural two-lane route with 10 ft. lanes and 2-4 ft. shoulders. The CRF is somewhat high indicating a possible safety concern. This route provides access from the Sebree area to the county seat of Dixon.
Y | 2 | Green River ADD | IP20060125 | 2-228 | 401783 | A | RECONSTRUCT BETWEEN KY 120 AND RR BRIDGE AT SLAUGHTERS TO ALLEVIATE FLOODING. (12CCR)(18CCN) | RECONSTRUCTION(O) | Webster | 117-KY-0138 -000 | 10.439 | 10.716 | 0.277 | Maintenance Improvement | 10 |  |  |  | 0 |  | 100000 | 2019 | 250000 | 2019 | 1250000 | 2020 | 2019-03-11 07:58 | Address safety issue along KY 138 from KY 120 to the railroad bridge in Slaughters. | The following need has been identified for this project: 1) Improve Roadway Safety. | 2 | West | 2.4682 | 0.24742 | 0 | 1.3789 | 0.84192 | 0 | 0 | 0 | 2
Y | 2 | Green River ADD | IP20060126 |  |  |  | Address safety concern of KY 283 and KY 1191 intersection. | Reconstruction | Webster | 117-KY-0283 -000 | 2.489 | 2.589 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 100000 |  | 200000 |  | 800000 |  | 2015-08-05 13:57 |  | The KY 283 is a rural 2 lane route with 8 ft. lanes. The intersection of KY 283 and KY 1191 intersection has sight distance and alignment deficiencies.
Y | 2 | Pennyrile ADD | IP20070004 |  |  |  | Reduce Congestion on Main Street from Centennial Drive to US 62 at Plum Street in Princeton | Minor Widening | Caldwell | 017-US-0062 -000 | 6.169 | 6.664 | 0.495 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 500000 |  | 1000000 |  | 3000000 |  | 2010-02-25 16:51 | Improve mobility and reduce travel time | The problem with this route is traffic congestion. This section has a high ADT with 2/12 foot lanes. There is a great deal of strip commercial development along this route and traffic flow is blocked by left turning vehicles that have to wait for on-com
Y | 2 | Pennyrile ADD | IP20070005 |  |  |  | RECONSTRUCT CURVE ON US 62 NEAR EAST YOUNG ST (KY 3114) INTERSECTION IN PRINCETON from MP 7.73 to MP 7.83 | Safety-Haz-Elm | Caldwell | 017-US-0062 -000 | 7.733 | 7.833 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 225000 |  | 200000 |  | 250000 |  | 1250000 |  | 2010-02-25 16:51 | IMPROVE SAFETY AND TRUCK ACCESS | This is a safety project involving a curve with substandard geometrics. This section of US 62 is part of the Princeton inter-city truck route. East bound trucks cannot navigate this curve without getting into the on-coming traffic lane.
Y | 2 | Pennyrile ADD | IP20070006 |  |  |  | RELOCATION OF KY 91 WITH NEW BRIDGE OVER RR from MP 7.29 to MP 8.29. | Relocation | Caldwell | 017-KY-0091 -000 | 7.298 | 8.298 | 1 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 750000 |  | 450000 |  | 3500000 |  | 2010-02-25 16:51 |  | This is a safety problem due to poor horizontal geometrics as the highway curves as KY 91 goes under a railroad underpass. The curve causes poor sight problems and the low underpass prohibits some truck traffic from using this major highway route betwee
Y | 2 | Pennyrile ADD | IP20070007 |  |  |  | RECONSTRUCTION FROM KY 139 AT PRINCETON TO US 641 AT FREDONIA from MP 13.4 to MP 23.3 | Reconstruction | Caldwell | 017-KY-0091 -000 | 13.401 | 23.389 | 9.988 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 5800000 |  | 6100000 |  | 26000000 |  | 2010-02-25 16:51 |  | This project will reduce congestion and provide better traffic flow for traffic trying to access the WK Parkway.
Y | 2 | Pennyrile ADD | IP20070008 |  |  |  | RECONSTRUCTION\WIDENING FROM KY 293 AT PRINCETON TO I-24 NEAR TRIGG C\L from MP 0.47 to MP 11.34 | Reconstruction | Caldwell | 017-KY-0139 -000 | 0.47 | 11.347 | 10.877 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 3250000 |  | 4500000 |  | 28000000 |  | 2010-02-25 16:51 | Improve safety and truck access to I-24. | This is a safety and truck access problem. Trucks from Princeton use KY 139 to access I-24. The existing route has 2/10 foot lanes with two (2) foot earth shoulders and is not on the National Truck Network road system. The route has spots with poor vert
Y | 2 | Pennyrile ADD | IP20070009 |  |  |  | RECONSTRUCT KY 2080 (Cadiz RD) AT RR UNDERPASS IN PRINCETON FROM MP 0.34 TO MP 0.57 | Safety-Haz-Elm | Caldwell | 017-KY-2080 -000 | 0.34 | 0.57 | 0.23 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 800000 |  | 400000 |  | 4500000 |  | 2010-02-25 16:51 | Improve safety and pedestrian access. | This is a substandard railroad underpass on KY 2080 that is a safety problem The low clearance height (12 ft.) also prohibits most standard semi-truck box trailers. It also does not have sidewalks and pedestrian traffic must walk in the vehicle traffic l
Y | 2 | Pennyrile ADD | IP20070010 |  |  |  | I69- RECONSTRUCT INTERCHANGE AT KY 91 IN PRINCETON | Reconstruction | Caldwell | 017-I -0069 -000 | 79.519 | 79.949 | 0.43 | Improve Intersection | 26 | Y | 0 |  | 800000 |  | 700000 |  | 800000 |  | 6000000 |  | 2017-06-08 14:28 | Improve safety and geometrics on the KY 91/I-69 Interchange. | There is a sight distance issue at the terimi of the west bound off ramp of I 69. Due to the geometry, stopped vehicles have impeded vision when looking for traffic. | PENNYRILE ADD | West | 21.018 | 4.5017 | 2.4742 | 3.75 | 0.54983 | 0 | 4.9656 | 4.7766 | 21
Y | 2 | Clarksville-Oak Grove MPO | IP20070011 |  |  |  | Improve Safety and reduce congestion on I 24 from US 41A to Kentucky/Tennessee state line. | Major Widening | Christian | 024-I -0024 -000 | 85.563 | 93.373 | 7.81 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 2000000 |  | 2000000 |  | 1300000 |  | 32000000 |  | 2015-02-19 13:56 | To reduce congestion and improve safety on I 24 fro KY /TN line to US 41A | There is traffic congestion along this route. The high ADT supports the need for an additional 2 lanes.
Y | 2 | Clarksville-Oak Grove MPO | IP20070012 |  |  |  | Reduce congestion and improve access on I24 at Carter Road. | New Interchange | Christian | 024-I -0024 -000 | 91.584 | 91.684 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 1000000 |  | 350000 |  | 300000 |  | 11000000 |  | 2010-02-25 16:51 | ? | This proposed interchange is one phase of a 2 phase project. The 2nd phase involves reconstructing Carter road to this proposed I-24 Interchange. This project is needed to releive congestion on KY 115 and US 41A by re-routing some of the Ft. Campbell tra
Y | 2 | Pennyrile ADD | IP20070013 |  |  |  | Reduce congestion and improve access on US 41 from KY 115 at Pembroke to 5 Lane section near John Rivers Road. | Minor Widening | Christian | 024-US-0041 -000 | 2.786 | 3.286 | 0.5 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 0 |  | 350000 |  | 400000 |  | 400000 |  | 2500000 |  | 2010-02-25 16:51 |  | This is an economic development project. This is one phase of a larger project to widen US 41 for better truck access from the Hopkinsville Industrial Park.
Y | 2 | Pennyrile ADD | IP20070014 |  |  |  | Reduce congestion on US 41 at KY 115 intersection in Pembroke. | Reconstruction | Christian | 024-US-0041 -000 | 2.786 | 2.886 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 300000 |  | 400000 |  | 1100000 |  | 2010-02-25 16:51 |  | need to add appropriate turn lanes on US 41 at KY 115 intersection. This is a traffic congestion problem. There are no turn lanes at this lighted intersection. The left turning traffic must wait on on-comming traffic to clear during which time they inhi
Y | 2 | Pennyrile ADD | IP20070015 |  |  |  | Reduce congestion on US 41 at Casky Lane in Hopkinsville. | Spot Improvement | Christian | 024-US-0041 -000 | 7.9 | 8 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 200000 |  | 200000 |  | 600000 |  | 2010-02-25 16:51 |  | Add turn lanes. This is a traffic flow and congestion probelm. Casey Lane is the entrance of the Hopkinsville Industrial Park. There is large peak hour trafic flow through this intersection which creates congestion.
Y | 2 | Pennyrile ADD | IP20070016 |  |  |  | EAST 9 TH STREET - RECONSTRUCT\WIDEN FROM INDIANA CHIEF'S BRIDGE OVER S. FORK LITTLE RIVER TO SKYLINE DR IN HOPKINSVILLE | Reconstruction | Christian | 024-US-0041 -000 | 11.025 | 11.373 | 0.348 | Other Improvement Types | 0 | Y | 0 |  | 400000 |  | 1000000 |  | 1000000 |  | 2500000 |  | 2010-02-25 16:51 |  | This is a congestion problem.
Y | 2 | Pennyrile ADD | IP20070017 |  |  |  | Improve Safety and traffic flow on US 41A at Hopkinsville Southern Bypass. | Reconstruction | Christian | 024-US-0041A -000 | 12.6 | 12.7 | 0.1 | Grade Separated to Interchange | 0 | Y | 0 |  | 2000000 |  | 4000000 |  | 1500000 |  | 25000000 |  | 2010-02-25 16:51 |  | There is traffic congestion at this intersection. Construct a grade seperated interchange.
Y | 2 | Pennyrile ADD | IP20070018 |  |  |  | Reduce congestion on US 41A from the Pennyrile Parkway to KY 380 (Skyline Drive) in Hopkinsville. | Major Widening | Christian | 024-US-0041A -000 | 13.516 | 14.145 | 0.629 | Other Improvement Types | 0 | Y | 0 |  | 1000000 |  | 2000000 |  | 2000000 |  | 4000000 |  | 2015-02-19 14:34 |  | This is a traffic congestion problem with a route that has a high ADT.
Y | 2 | Pennyrile ADD | IP20070019 |  |  |  | MAJOR WIDENING FROM 600' E OF WESTERN STATE HOSPITAL TO US 68 HOPKINSVILLE BYPASS IN HOPKINSVILLE | Major Widening | Christian | 024-US-0068 -000 | 12.629 | 14.129 | 1.5 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 750000 |  | 650000 |  | 1000000 |  | 7500000 |  | 2010-02-25 16:51 |  | This route has traffic congestion problems. Left turning vehicles block traffic flow.
Y | 2 | Pennyrile ADD | IP20070020 |  |  |  | RECONSTRUCT TO 3 LANE FROM US 41 TO 600 FT EAST OF WESTERN STATE HOSPITAL IN HOPKINSVILLE | Major Widening | Christian | 024-US-0068 -000 | 10.93 | 12.629 | 1.699 | Auxiliary Lanes or Operation Improvements | 11 |  | 0 |  | 1100000 |  | 750000 |  | 1000000 |  | 8500000 |  | 2010-02-25 16:51 |  | There is a high CRF and traffic congestion is a problem along this route
Y | 2 | Pennyrile ADD | IP20070022 |  |  |  | RECONSTRUCT TO 3 LANES FROM US 68 TO EVERETTS RD | Minor Widening | Christian | 024-KY-0091 -000 | 0 | 3.29 | 3.29 | Other Improvement Types | 0 |  | 0 |  | 1300000 |  | 1300000 |  | 450000 |  | 10000000 |  | 2010-02-25 16:51 |  | This route has poor geometrics that create safety issues
Y | 2 | Pennyrile ADD | IP20070023 |  |  |  | RECONSTRUCT TO 3 LANES FROM EVERETTS RD TO KY 1349 | Reconstruction | Christian | 024-KY-0091 -000 | 3.29 | 5.43 | 2.14 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 400000 |  | 2000000 |  | 2013-05-03 13:25 |  | This route has poor geometrics
Y | 2 | Pennyrile ADD | IP20070024 |  |  |  | RECONSTRUCT TO 3 LANES FROM KY 1349 TO KY 398 | Reconstruction | Christian | 024-KY-0091 -000 | 5.43 | 11.709 | 6.279 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 3150000 |  | 3150000 |  | 15750000 |  | 2010-02-25 16:51 |  | This route has poor geometrics
Y | 2 | Pennyrile ADD | IP20070025 |  |  |  | RECONSTRUCT TO 3 LANES FROM KY 398 TO PROPOSED PRINCETON EASTERN CONNECTOR | Reconstruction | Christian | 024-KY-0091 -000 | 11.709 | 15.132 | 3.423 | Other Improvement Types | 0 |  | 0 |  | 1400000 |  | 2000000 |  | 2000000 |  | 8750000 |  | 2010-02-25 16:51 |  | This route has poor geometrics
Y | 2 | Pennyrile ADD | IP20070026 |  |  |  | EXTEND KY 91 WITH A 3 LANE SECTION ALONG A NEW ROUTE FROM US 68 TO NORTH DRIVE (KY 1007) VIA OUTER 15 TH STREET BRIDGING LITTLE RIVER NORTH OF THE COUNTY FAIRGROUNDS | New Route | Christian | 024-KY-0091 -000 | 0 | 0.1 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 400000 |  | 4100000 |  | 2010-02-25 16:51 |  | This is one phase of a two phase project. There is severe traffic congestion on Business US 68 in Hopkinsville along W. 7th St. This proposed new route will reduce traffic congestion on West 7th Street. This will include a new bridge over the Little Riv
Y | 2 | Pennyrile ADD | IP20070027 |  |  |  | RECONSTRUCTION FROM PROPOSED NE BYPASS (KY 1682) TO VIRGINIA STREET IN HOPKINSVILLE | Reconstruction | Christian | 024-KY-0107 -000 | 18.834 | 21.642 | 2.808 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1400000 |  | 2200000 |  | 7000000 |  | 2010-02-25 16:51 |  | There is a high CRF on this section of roadway with poor geometrics.
Y | 2 | Pennyrile ADD | IP20070028 |  |  |  | RECONSTRUCTION FROM KY 117 TO I-24 | Reconstruction | Christian | 024-KY-0107 -000 | 8.246 | 10.797 | 2.551 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 2100000 |  | 800000 |  | 5200000 |  | 2010-02-25 16:51 |  | This route has poor geometrics
Y | 2 | Pennyrile ADD | IP20070029 |  |  |  | Reconstruct KY 107 from KY 380 to Jerry Claiborne Way to include Ped./Bike facilities | Major Widening | Christian | 024-KY-0107 -000 | 15.344 | 17.163 | 1.819 | Modernize Roadway-Rural | 26 |  | 0 |  | 950000 |  | 2500000 |  | 2800000 |  | 6250000 |  | 2019-03-11 11:05 | Improve traffic flow and safety | There are safety and congestion problems along this route. | PENNYRILE ADD | West | 51.2466 | 7.4021 | 12.3711 | 11.5077 | 2.3024 | 9.2784 | 0 | 8.3849 | 51
Y | 2 | Pennyrile ADD | IP20070030 |  |  |  | CONSTRUCT TURN LANES AT 18 TH STREET IN HOPKINSVILLE from MP 18.4 to MP 18.5. | Spot Improvement | Christian | 024-KY-0107 -000 | 18.4 | 18.5 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 900000 |  | 750000 |  | 1000000 |  | 2010-02-25 16:51 |  | There is a high CRF at this location. North bound vehicles on KY 107 making left turns block traffic flow while waiting for on-coming traffic to clear. in peak traffic, vehicles have to wait for the light to cycle twice.
Y | 2 | Pennyrile ADD | IP20070031 |  |  |  | RECONSTRUCTION FROM KY 1682 TO WITTY LANE | Reconstruction | Christian | 024-KY-0109 -000 | 12.09 | 15.603 | 3.513 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 1800000 |  | 2800000 |  | 9000000 |  | 2010-02-25 16:51 |  | The is a high CRF along this route. Poor geometrics create a safety issue.
Y | 2 | Pennyrile ADD | IP20070032 |  |  |  | RECONSTRUCTION FROM WITTY LANE TO KY 398 | Reconstruction | Christian | 024-KY-0109 -000 | 15.603 | 29.736 | 14.133 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 6000000 |  | 7000000 |  | 36000000 |  | 2010-02-25 16:51 |  | There is poor geometrics along this route.
Y | 2 | Pennyrile ADD | IP20070033 |  |  |  | RECONSTRUCTION FROM KY 398 TO WESTERN KENTUCKY PKY. EXCLUDES US 62 IN DAWSON SPRINGS. | Reconstruction | Christian | 024-KY-0109 -000 | 29.736 | 33.766 | 4.03 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 3200000 |  | 4000000 |  | 20000000 |  | 2010-02-25 16:51 |  | This route has poor geometrics
Y | 2 | Pennyrile ADD | IP20070035 | 2-8953 |  | A | IMPROVE AND WIDEN KY 115 FROM ANDERSON ROAD (MP 6.87) TO JUST SOUTH OF PEMBROKE (MP 9.625)(16CCN)(18CCN) | MINOR WIDENING(O) | Christian | 024-KY-0115 -000 | 6.87 | 9.635 | 2.765 | Modernize Roadway-Rural | 26 |  |  |  | 1040000 | 2021 | 2020000 | 2025 | 2540000 | 2025 | 10760000 | 2025 | 2019-03-11 10:44 |  | This is one phase of a 3 phase project to provide better truck access to I-24 from the Hopkinsville Industrial Park. The existing lane width of 2/9 lanes prohibits 102 inch wide trailers. This is an economic development projects. | 2 | West | 33.6254 | 1.2371 | 10.2577 | 8.9175 | 1.5808 | 0 | 3.4536 | 8.1787 | 34
Y | 2 | Pennyrile ADD | IP20070036 |  |  |  | RECONSTRUCTION FROM PROPOSED PEMBROKE BYPASS TO US 68 | Reconstruction | Christian | 024-KY-0115 -000 | 9.625 | 16.13 | 6.505 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 3300000 |  | 1800000 |  | 13200000 |  | 2010-02-25 16:51 |  | This route has a high CRF and poor geometrics.
Y | 2 | Clarksville-Oak Grove MPO | IP20070037 |  |  |  | Address safety and congestion issues from KY 911 to I24. | Major Widening | Christian | 024-KY-0115 -000 | 1.261 | 2.663 | 1.402 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1500000 |  | 1000000 |  | 8200000 |  | 2017-05-19 10:20 | To increase safety and improve access | This route has a high CRF, V/SF and ADT. This route provide direct access to Ft. Campbell and is congested during rush-hour traffic. | Clarksville MPO | West | 80.7002 | 7.2852 | 11.5464 | 12.2294 | 0.94502 | 9.0034 | 3.0584 | 6.6323 | 51 | 15 | 15
Y | 2 | Clarksville-Oak Grove MPO | IP20070039 |  |  |  | Improve access and reduce congestion from US 41A to KY 115 by construction a new route from Gate 4/US 41A to KY 115. This project was formerly PIF 024 C000010.0 | New Route | Christian | 024-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 2000000 |  | 1200000 |  | 5000000 |  | 2019-02-05 09:36 | The purpose of this project is to reduce congestion and improve mobility. It will also improve access to Ft. Campbell. | There is a lot of congestion in this area on US 41, KY 911, KY 115 and I-24. This project is needed to provide better traffic flow from Gate 4/ US 41A to KY 115. This project will also relieve congestion on KY 115 in Oak Grove and provide better access
Y | 2 | Pennyrile ADD | IP20070040 |  |  |  | RECONSTRUCTION 3 LANE FROM PETSCH LANE TO US 68B (HOPKINSVILLE BYPASS) from MP 6.24 to MP 7.32. | Reconstruction | Christian | 024-KY-0272 -000 | 6.24 | 7.321 | 1.081 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 1000000 |  | 450000 |  | 2500000 |  | 2010-02-25 16:51 |  | This route has narrow 9/2 lanes woth poor geometrics.
Y | 2 | Pennyrile ADD | IP20070041 |  |  |  | MAJOR WIDENING TO 5 LANES FROM US 68 BYPASS TO KY 380 IN HOPKINSVILLE | Major Widening | Christian | 024-KY-0272 -000 | 8.274 | 9.4 | 1.126 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1100000 |  | 625000 |  | 2200000 |  | 2010-02-25 16:51 |  | This route has traffic congestion cause by left turning vehicles waiting for on-coming traffic to clear.
Y | 2 | Pennyrile ADD | IP20070042 |  |  |  | MAJOR WIDENING FROM KY 380 (COUNTRY CLUB LN.) TO KY 1007 (NORTH DR.) IN HOPKINSVILLE | Major Widening | Christian | 024-KY-0272 -000 | 9.4 | 10.1 | 0.7 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1350000 |  | 1500000 |  | 5000000 |  | 2010-02-25 16:51 |  | This section of road has a problem with left turning vehicles blocking the road while waiting for on-coming traffic to clear.
Y | 2 | Pennyrile ADD | IP20070043 |  |  |  | RECONSTRUCTION FROM KY 107 TO KY 695 | Reconstruction | Christian | 024-KY-0345 -000 | 7.275 | 10.662 | 3.387 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 1000000 |  | 1100000 |  | 3500000 |  | 2010-02-25 16:51 |  | The road has narrow 2/8 lanes with no shoulders that create a safety problem.
Y | 2 | Clarksville-Oak Grove MPO | IP20070045 |  |  |  | Address congestion concerns from US 41A to KY 115. | Major Widening | Christian | 024-KY-0400 -000 | 0 | 1.377 | 1.377 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 500000 |  | 1500000 |  | 7000000 |  | 2010-02-25 16:51 | To improve access and mobility from Gate 4 to KY 115 | The CRF and ADT along this route are high. This route has high peak hour traffic and congestion that causes vehicles to wait for more than one cycle at the stoplight at the US 41A Intersection.
Y | 2 | Pennyrile ADD | IP20070046 |  |  |  | COX MILL RD - RECONSTRUCTION FROM KY 117 TO HOPKINSVILLE SW BYPASS from MP 7.2 to MP 10.8. | Reconstruction | Christian | 024-KY-0695 -000 | 3.513 | 10.807 | 7.294 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2900000 |  | 3700000 |  | 18250000 |  | 2010-02-25 16:51 |  | This route has narrow 9/2 lanes with poor geometrics.
Y | 2 | Pennyrile ADD | IP20070048 |  |  |  | COX MILL RD - RECONSTRUCT TURN LANES AT PYLE LANE IN HOPKINSVILLE | Spot Improvement | Christian | 024-KY-0695 -000 | 10.354 | 10.454 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 750000 |  | 300000 |  | 700000 |  | 2010-02-25 16:51 |  | Left turning vehicles block traffic on KY 695 while waiting for on-coming traffic to clear.
Y | 2 | Pennyrile ADD | IP20070049 |  |  |  | COX MILL RD - CONSTRUCT TWO WAY LEFT TURN LANE FROM PARDUE LANE TO WOOLRIDGE DRIVE IN HOPKINSVILLE | Major Widening | Christian | 024-KY-0695 -000 | 11.833 | 11.866 | 0.033 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 500000 |  | 500000 |  | 1000000 |  | 2010-02-25 16:51 |  | This section of KY 695 has two major roads that intersect it along this section. Left turning vehicles cause traffic congestion at these intersections when they stop and wait for on-coming traffic to clear.
Y | 2 | Clarksville-Oak Grove MPO | IP20070050 |  |  |  | Address congestion and safety concerns from US 41A to KY 115. | Reconstruction | Christian | 024-KY-1453 -000 | 0 | 3.689 | 3.689 | Other Improvement Types | 0 |  | 0 |  | 1300000 |  | 1500000 |  | 1000000 |  | 10400000 |  | 2012-01-27 10:17 | Reduce congestion and improve mobility by providing better access to I 24. | This is an economic development project. This section of KY 1453 will provide access to a major industrial park located in the northeast corner of I-24 and US 41A. The Industrial Park is a Mega Site that targets large industries and has over 1,000 acres
Y | 2 | Pennyrile ADD | IP20070051 |  |  |  | PENNYRILE PKY - CONSTRUCT FULL INTERCHANGE AT WOODBURN/HAY RD. | New Interchange | Christian | 024-EB-9004 -000 | 15.465 | 15.565 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 800000 |  | 500000 |  | 150000 |  | 5000000 |  | 2010-02-25 16:51 |  | There is poor access from the Pennyrile Parkway to northern Christian County. This project proposes a new interchange at Woodburn Hay Road. The existing Parkway does not provide any interchanges between Hopkinsville and Crofton which is approximately 8
Y | 2 | Pennyrile ADD | IP20070052 |  |  |  | GOOD HOPE CEMETERY RD - RECONSTRUCTION FROM KY 115 TO I-24 | New Route | Christian | 024-CS-5060 -000 | 0 | 1.19 | 1.19 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 450000 |  | 600000 |  | 2600000 |  | 2010-02-25 16:51 |  | There are large residential subdivision along this route and this narrow 2/9 road needs to be widen to accomidate the high ADT
Y | 2 | Pennyrile ADD | IP20070053 |  |  |  | CARTER RD - RECONSTRUCTION FROM HUGH HUNTER RD TO I-24 | New Route | Christian | 024-CR-1188 -000 | 2.166 | 3.266 | 1.1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 750000 |  | 400000 |  | 3500000 |  | 2010-02-25 16:51 |  | This is one phase of a larger project. A 2nd phase involve constructing a proposed I-24 interchange at the Carter Rd overpass. This project will releive congestion on KY 115 and US 41A by re-routing some of the Ft Campbell Traffic onto Carter and Hugh H
Y | 2 | Owensboro MPO | IP20070054 |  |  |  | US 231 - Address safety by widening and increasing the width of the shoulders. Project begins at South Burton Rd (CR 1188) and ends near the Owensboro Community College. | Reconstruction | Daviess | 030-US-0231 -000 | 7.807 | 9.985 | 2.178 | Modernize Roadway-Rural | 26 |  | 0 |  | 1300000 |  | 900000 |  | 2000000 |  | 12400000 |  | 2011-02-28 14:37 | The purpose of this project is to improve safety, reliability and mobility along US 231, better control access and reduce congestion. | This section of US 231 does not provide sufficient safety that make drivers feel safe. There are high banks, since the road is in the floodplain, and guard rails. The guard rails force drivers to hug the center line. Residents of the counties south of O
Y | 2 | Owensboro MPO | IP20070055 |  |  |  | US 431 - Improve to provide better traffic flow, provide better access, and improve safety. Project begins at KY 140 East and ends at Marksberry Road (CR 1225). | Reconstruction | Daviess | 030-US-0431 -000 | 2.599 | 5.798 | 3.199 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 3500000 |  | 16000000 |  | 2010-06-22 10:10 | The purpose of this project is to improve safety, reliability and mobility along US 431, better control access and reduce congestion | This section of US 431 does not provide sufficient safety that make drivers feel safe. There are high banks, since the road is in the floodplain, and guard rails. The guard rails force drivers to hug the center line. Residents of the counties south of O
Y | 2 | Owensboro MPO | IP20070056 |  |  |  | US 431 - Reconstruct to provide better traffic flow, provide better access, and improve safety. Project begins at Marksberry Rd (CR 1225) and ends near the Panther Creek Bridge. | Reconstruction | Daviess | 030-US-0431 -000 | 5.798 | 8.588 | 2.79 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3000000 |  | 2500000 |  | 15000000 |  | 2010-06-22 14:47 | The purpose of this project is to improve safety, reliability and mobility along US 431, better control access and reduce congestion. | This section of US 431 does not provide sufficient safety that make drivers feel safe. There are high banks, since the road is in the floodplain, and guard rails. The guard rails force drivers to hug the center line. Residents of the counties south of O
Y | 2 | Green River ADD | IP20070057 |  |  |  | Address safety concerns of KY 2181 from Indian Hill Road to Blackford Creek Bridge in Hancock Co. | Reconstruction | Hancock | 046-KY-2181 -000 | 3.736 | 4.662 | 0.926 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 350000 |  | 300000 |  | 1800000 |  | 2010-07-12 15:59 |  | KY 2181 from Indian Hill Road to Blackford Creek Bridge (MP 3.736 - 4.662) is a rural secondary route with 8 ft. lane widths and 3 ft. earthen shoulders. The narrow lane width and earthen shoulders present a safety concern for this agricultural based co
Y | 2 | Evansville-Henderson MPO | IP20070058 |  |  |  | Improve safety and level of service throughout the corridor | Reconstruction | Henderson | 051-US-0041A -000 | 0 | 5.999 | 5.999 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 2500000 |  | 18000000 |  | 2018-12-11 14:46 | Improve safety and mobility for freight and passenger vehicles. | US 41 A currently has 2, 11-foot lanes with 5% truck volumes. Reconstruct to provide standard geometry and correct vertical and horizontal issues.
Y | 2 | Evansville-Henderson MPO | IP20070059 |  |  |  | Improve safety and level of service throughout the corridor. | Reconstruction | Henderson | 051-US-0041A -000 | 5.999 | 11.306 | 5.307 | Modernize Roadway-Rural | 26 |  | 0 |  | 2100000 |  | 3300000 |  | 1250000 |  | 21200000 |  | 2018-12-11 14:36 | Improve safety and mobility for freight and passenger vehicles. | Reconstruct to provide standard geometry on US 41A from KY 266 to KY 425. Correct vertical and horizontal alignments. The corridor has 9-16% trucks.
Y | 2 | Evansville-Henderson MPO | IP20070061 |  |  |  | Improve safety and level of service. | Major Widening | Henderson | 051-KY-0136 -000 | 19.548 | 20.758 | 1.21 | Modernize Roadway-Urban | 16 |  | 0 |  | 400000 |  | 950000 |  | 1000000 |  | 3600000 |  | 2018-12-11 11:42 | Improve safety and provide better pedestrian access. | Need to widen (including sidewalks)from Green Street (US 41A) To Atkinson Street.
Y | 2 | Evansville-Henderson MPO | IP20070062 |  |  |  | Improve level of service. Road is frequently blocked by flooding. | Reconstruction | Henderson | 051-KY-0136 -000 | 0 | 0.38 | 0.38 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 50000 |  | 50000 |  | 350000 |  | 2010-02-25 16:51 | Improve traffic flow and eliminate flooding hazard. | Relocate or elevate roadway to eliminate flooding hazard.
Y | 2 | Evansville-Henderson MPO | IP20070064 |  |  |  | SUPPORT ECONOMIC DEVELOPMENT EFFORTS. | Reconstruction | Henderson | 051-KY-0136 -000 | 18.665 | 19.548 | 0.883 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 500000 |  | 1000000 |  | 1800000 |  | 2018-12-13 16:24 | Improve traffic flow for freight and provide greater economic development options. | Reconstruct to provide standard geometry for freight traffic on KY 136 from KY 425/US 60 to Industrial Park Dr. This section of roadway has been approved as a critical urban freight corridor.
Y | 2 | Evansville-Henderson MPO | IP20070065 |  |  |  | Improve safety and level of service. | Reconstruction | Henderson | 051-KY-0266 -000 | 0 | 7.904 | 7.904 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 800000 |  | 850000 |  | 19750000 |  | 2018-12-13 14:56 | Improve safety and traffic flow. | Reconstruct this narrow 2-lane road from Corydon to Smith Mills to provide standard geometry.
Y | 2 | Evansville-Henderson MPO | IP20070066 |  |  |  | Improve safety and level of service. | Reconstruction | Henderson | 051-KY-0351 -000 | 2.582 | 3.567 | 0.985 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1250000 |  | 7750000 |  | 2017-05-19 11:42 | Improve safety. | Reconstruct KY 351 from the end of the curb & gutter in Henderson to 0.2 miles south of East Elm St to provide standard geometry | Evansville/Henderson MPO | West | 43.4588 | 5.4777 | 11.701 | 8.5825 | 1.5808 | 7.2509 | 0 | 8.866 | 44
Y | 2 | Evansville-Henderson MPO | IP20070067 |  |  |  | Improve safety and level of service. | Reconstruction | Henderson | 051-KY-0416 -000 | 10.749 | 16.875 | 6.126 | Modernize Roadway-Rural | 26 |  | 0 |  | 1600000 |  | 2500000 |  | 2500000 |  | 15300000 |  | 2018-12-11 15:54 | Improve safety and traffic flow. | Reconstruct KY 416 from KY 136 in Niagara to Audubon Parkway to provide standard geometry and eliminate vertical and horizontal issues. Traffic on this route will most likely increase due to the recent completion of the full interchange on I-69 at KY 416
Y | 2 | Evansville-Henderson MPO | IP20070068 |  |  |  | Improve safety and level of service. | Reconstruction | Henderson | 051-KY-0416 -000 | 16.875 | 19.172 | 2.297 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 750000 |  | 500000 |  | 5750000 |  | 2018-12-14 09:48 | Improve safety and traffic flow. | Reconstruct KY 416 from Audubon Pkwy to KY 351 to provide standard geometry and eliminate vertical and horizontal issues to improve access to the Parkway.
Y | 2 | Evansville-Henderson MPO | IP20070069 |  |  |  | Improve level of service. | Major Widening | Henderson | 051-KY-0425 -000 | 0 | 4.747 | 4.747 | Other Improvement Types | 0 | Y | 0 |  | 1500000 |  | 550000 |  | 400000 |  | 26000000 |  | 2010-02-25 16:51 | Improve traffic flow. | Major widening from US 60 west of Henderson to I-69 to improve access from the industrial areas and the Henderson County Riverport over the designated critical urban freight corridor.
Y | 2 | Evansville-Henderson MPO | IP20070070 |  |  |  | Improve safety and level of service at the intersection. | Reconstruction | Henderson | 051-KY-0812 -000 | 6.975 | 7.1 | 0.125 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 200000 |  | 250000 |  | 1500000 |  | 2019-01-14 14:57 | Improve safety and traffic flow. | The intersection of KY 812 and Garden Mile Road needs to be reconstructed to eliminate a skew in it to improve safty and traffic flow. This intersection is across from the entrance to the Henderson County Road Department and is heavily traveled by high sc
Y | 2 | Evansville-Henderson MPO | IP20070071 |  |  |  | IMPROVE SAFETY. | Reconstruction | Henderson | 051-KY-2247 -000 | 0 | 2.32 | 2.32 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 500000 |  | 7250000 |  | 2019-01-14 15:00 | Improve safety and traffic flow. | RECONSTRUCT\WIDEN FROM KY 812 TO KY 1078 NEAR HENDERSON TO CORRECT GEOMETRY ISSUES SUCH AS SOME 90 DEGREE CURVES THAT NEED TO BE SOFTENED.
Y | 2 | Evansville-Henderson MPO | IP20070072 |  |  |  | Construct a new interchange on I-69 at KY 2678/Rockhouse Rd/Moss & Moss Rd to support economic developement. | New Interchange | Henderson | 051-I -0069 -000 | 138.671 | 138.771 | 0.1 | Grade Separated to Interchange | 0 | Y | 0 |  | 600000 |  | 350000 |  | 400000 |  | 7000000 |  | 2019-01-14 15:03 | Provide access to stimulate economic development options | Construct an interchange at KY 2678 & I-69 to provide access to help promote economic development
Y | 2 | Pennyrile ADD | IP20070073 |  |  |  | MAJOR WIDENING OF US 41A FROM KY 502 TO KY 670 AT PROVIDENCE | Major Widening | Hopkins | 054-US-0041A -000 | 8.794 | 13.278 | 4.484 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 3000000 |  | 4000000 |  | 30000000 |  | 2010-02-25 16:51 | Improve traffic flow and safety | Congestion and traffic flow are issues along this section of road.
Y | 2 | Pennyrile ADD | IP20070074 |  |  |  | Address safety and poor geometrics on KY 70 from KY 85 to Muhlenberg County Line. | Minor Widening | Hopkins | 054-KY-0070 -000 | 23.247 | 26.394 | 3.147 | Modernize Roadway-Rural | 26 |  | 0 |  | 950000 |  | 1300000 |  | 2600000 |  | 8000000 |  | 2017-05-19 12:02 | Improve safety, narrow lanes and poor geometrics | This section has safety problems due to rough road with substandard geometrics and and narrow 2/9 lanes. | PENNYRILE ADD | West | 27.9287 | 2.7354 | 7.6804 | 6.9974 | 2.3024 | 0 | 0 | 8.2131 | 28
Y | 2 | Pennyrile ADD | IP20070075 |  |  |  | RECONSTRUCTION OF KY 109 FROM WESTERN KENTUCKY PKY TO KY 70 from MP 3.8 to MP 9.30. | Reconstruction | Hopkins | 054-KY-0109 -000 | 3.8 | 9.3 | 5.5 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 2100000 |  | 2800000 |  | 13750000 |  | 2010-02-25 16:51 | Improve Safety | This section of road has poor geometrics and narrow lanes. This section is a major accesss road to the WK Parkway for western Hopkins residents.
Y | 2 | Pennyrile ADD | IP20070076 |  |  |  | RECONSTRUCTION OF A SECTION OF KY 109 FROM KY 70 TO KY 814 from MP 9.3 to MP 17.2. SEE KY 814 LISTING FOR CONTINUATION TO US 41A AT PROVIDENCE. | Reconstruction | Hopkins | 054-KY-0109 -000 | 9.3 | 17.223 | 7.923 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 3200000 |  | 4750000 |  | 20000000 |  | 2010-02-25 16:51 | Improve safety | This section of road has poor geometrics and rough pavement.
Y | 2 | Pennyrile ADD | IP20070077 |  |  |  | RECONSTRUCT KY 260 FROM BAILEY ST TO COMPTON RD IN HANSON from MP 0.59 to MP 1.2. | Reconstruction | Hopkins | 054-KY-0260 -000 | 0.59 | 1.2 | 0.61 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 400000 |  | 600000 |  | 1500000 |  | 2010-02-25 16:51 | Improve safety for school buses | This is a safety issues and a school bus access problem. The Hanson Elementay School is located between US 41 and the Pennyrile Parkway just off KY 260. This route has narrow 2/9 lanes with 1 ft shoulders and poor geometrics. A large number of school bu
Y | 2 | Pennyrile ADD | IP20070078 |  |  |  | Improve safety and mobility of KY 260 from the approaches at the Railroad crossing in Hanson to the Southbound on and off ramps of I 69. | Safety-Haz-Elm | Hopkins | 054-KY-0260 -000 | 1.396 | 1.864 | 0.468 | Improve Railroad Crossing | 55 |  | 0 |  | 500000 |  | 1500000 |  | 1100000 |  | 5000000 |  | 2017-05-19 12:57 |  | This is a safety issues and a school bus access problem Hanson Elementay school is located between US 41 and the Pennyrile Parkway just off KY 260. A large number of school buses use this route to access the school. Also, there is an at-grade railroad | 2 | West | 23.3385 | 4.2062 | 10.567 | 5.1289 | 0 | 0 | 3.4364 | 0 | 23
Y | 2 | Pennyrile ADD | IP20070079 |  |  |  | RECONSTRUCTION VETERANS DIVE (KY 260) FROM BAKER RD TO FATE LUTZ RD IN HANSON from MP 2.1 to MP 2.6. | Reconstruction | Hopkins | 054-KY-0260 -000 | 2.108 | 2.635 | 0.527 | Modernize Roadway-Rural | 26 |  | 0 |  | 275000 |  | 400000 |  | 500000 |  | 1500000 |  | 2017-05-19 12:59 | Improve safety | This is a safety issues and a school bus access problem Hanson Elementay school is located between US 41 and the Pennyrile Parkway just off KY 260. A large number of school buses use this route to access the school. | PENNYRILE ADD | West | 29.7818 | 1.2646 | 8.4021 | 3.7113 | 2.3024 | 5.6014 | 0 | 8.5 | 30
Y | 2 | Pennyrile ADD | IP20070080 |  |  |  | RECONSTRUCT KY 630 FROM US 41A TO WEBSTER C\L | Reconstruction | Hopkins | 054-KY-0630 -000 | 2.04 | 8.538 | 6.498 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 2600000 |  | 3200000 |  | 13000000 |  | 2010-02-25 16:51 | Improve safety and poor road geometrics | This section of road has a high CRF and IRI indicating safety issues and rough pavement.
Y | 2 | Pennyrile ADD | IP20070081 |  |  |  | WESTERN KENTUCKY PKY - NEW INTERCHANGE AT US 41 | New Interchange | Hopkins | 054-I -0069 -000 | 104.7 | 105.4 | 0.7 | Other Improvement Types | 0 | Y | 0 |  | 1200000 |  | 500000 |  | 500000 |  | 10000000 |  | 2010-02-25 16:51 | Improve access to School | This is an access problem. The proposed interchange will access three schools on US 41 north of the WK Parkway near Mortons Gap, as well as provide better access to the cities of Mortons Gap and Nortonville in general.
Y | 2 | Green River ADD | IP20070082 |  |  |  | Address condition and service issues of KY-56 from Webster Co Line to KY-136 at Beech Grove. | Major Widening | McLean | 075-KY-0056 -000 | 0 | 5.516 | 5.516 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1300000 |  | 3500000 |  | 11000000 |  | 2017-05-19 13:06 | Address safety and access issues along KY 56 Webster County Line to KY 136 in Beech Grove. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 42.2139 | 2.1581 | 11.2371 | 8.6469 | 4.3986 | 5.9794 | 0 | 9.7938 | 42
Y | 2 | Green River ADD | IP20070083 |  |  |  | Address condition and service issues of KY-56 from KY-136 at Beech Grove to the Daviess C/L. | Major Widening | McLean | 075-KY-0056 -000 | 5.516 | 9.363 | 3.847 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 900000 |  | 2500000 |  | 7600000 |  | 2010-07-14 14:33 |  | KY-56 is a two-lane route that connects McLean County to the Edward Breathitt Pennyrile Parkway at the Webster County Line and Owensboro in Daviess County. Current lane widths range from 9 ft to 10 ft with 1-2 ft. shoulders. Truck weight class is "A" from
Y | 2 | Green River ADD | IP20070084 |  |  |  | Address condition and service issues of KY-81 from KY-136 to Daviess C/L. | Reconstruction | McLean | 075-KY-0081 -000 | 12.765 | 18.087 | 5.322 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1275000 |  | 4400000 |  | 11000000 |  | 2010-08-04 04:27 |  | KY-81 is a rural 2 lane route with 12 ft driving lanes and 2 ft shoulders that provides access from Calhoun, KY (McLean County Seat) to Owensboro, KY. The section from KY-81/KY-136 intersection (MP 12.580) to just south of KY-815 (MP 12.838) is a possib
Y | 2 | Green River ADD | IP20070085 |  |  |  | Address service concerns of the KY-81 and KY-254 intersection in Sacramento. | Safety-Haz-Elm | McLean | 075-KY-0081 -000 | 2.371 | 2.471 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 100000 |  | 350000 |  | 600000 |  | 2010-02-25 16:51 |  | The intersection of KY-81 and KY-254 in Sacramento (MP 2.371 to MP 2.471) consists of two 10-ft. driving lanes with 2 ft. shoulders. KY-81 is a part of the area's Blues to Bluegrass Scenic Byway and is a "AA" rated truck weight class.
Y | 2 | Green River ADD | IP20070086 |  |  |  | Address the service concerns of KY-85 from KY 1412 to the Green River Bridge in McLean County. | Minor Widening | McLean | 075-KY-0085 -000 | 10.1 | 12.169 | 2.069 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 600000 |  | 800000 |  | 900000 |  | 2013-05-03 14:46 |  | KY-85 in McLean County is a rural secondary "A" rated route that has an extended weight and coal haul road classification. This route provides access to a coal mine located near the Green River and the D.B. Wilson power plant located just across the Gre
Y | 2 | Pennyrile ADD | IP20070087 |  |  |  | RECONSTRUCTION FROM US 431 TO OHIO C\L. SEE OHIO CO. LISTING FOR CONTINUATION TO US 231. | Reconstruction | Muhlenberg | 089-US-0062 -000 | 17.93 | 26.005 | 8.075 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 4000000 |  | 6500000 |  | 20250000 |  | 2010-02-25 16:51 |  | There is a high CRF and ADT along this route. It has 2/10 lanes with poor geometrics.
Y | 2 | Pennyrile ADD | IP20070088 |  |  |  | Reconstruction from Skipworth Lane to north of Myers Chapel Rd. See section 3 in April 2002 Corridor Feasibilty Study. | Reconstruction | Muhlenberg | 089-US-0431 -000 | 1.615 | 5.081 | 3.466 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 3000000 |  | 3000000 |  | 12000000 |  | 2015-08-05 12:48 |  | There is a high CRF along this route which indicates safety issues. This project is one phase of a larger project to upgrade safety problems with spot improvements along the route. This section has substandard geometrics with sharp curves.
Y | 2 | Pennyrile ADD | IP20070089 |  |  |  | RECONSTRUCTION FROM N OF MYERS CHAPEL RD TO MASONIC DRIVE. SEE SECTION 4 IN APRIL 2002 CORRIDOR FEASIBILITY STUDY from MP 5,2 to MP 8.7. | Reconstruction | Muhlenberg | 089-US-0431 -000 | 5.2 | 8.71 | 3.51 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2500000 |  | 2500000 |  | 8750000 |  | 2010-02-25 16:51 |  | This is a coal route with 2/10 lanes and poor geometrics. The project involve spot improvements along the route.
Y | 2 | Pennyrile ADD | IP20070090 |  |  |  | RECONSTRUCTION FROM MASONIC DRIVE TO N OF THE POND CREEK BRIDGE from MP 8.7 to MP 12.7. SEE SECTION 5 IN APRIL 2002 CORRIDOR FEASIBILITY STUDY | Reconstruction | Muhlenberg | 089-US-0431 -000 | 8.71 | 12.7 | 3.99 | Other Improvement Types | 0 |  | 0 |  | 1800000 |  | 2500000 |  | 3000000 |  | 13000000 |  | 2011-02-28 15:00 |  | This route is a Coal Haul route. The 10/2 lanes and poor geometrics create safety problems for trucks. This project proposes spot improvements along the route.
Y | 2 | Pennyrile ADD | IP20070091 |  |  |  | RELOCATION FROM N OF THE POND CREEK BRIDGE TO EXISTING 4-LANE SECTION AT WENDELL H. FORD PKY. from MP 12.7 to MP 116.6. SEE SECTION 6 IN APRIL 2002 CORRIDOR FEASIBILITY STUDY | Reconstruction | Muhlenberg | 089-US-0431 -000 | 12.7 | 16.6 | 3.9 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2250000 |  | 3000000 |  | 9750000 |  | 2010-02-25 16:51 | Improve truck access and traffic flow | This is one phase of a larger project. This is a Coal Haul route with 2/10 lanes and poor geometrics. The project involves spot improvements along the route.
Y | 2 | Pennyrile ADD | IP20070092 |  |  |  | RECONSTRUCT C & G FROM W. K. PKY TO CENTRAL PARK ST IN CENTRAL CITY from MP 17.66 to MP 19.4. | Major Widening | Muhlenberg | 089-US-0431 -000 | 17.605 | 18.278 | 0.673 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 2800000 |  | 1400000 |  | 13000000 |  | 2010-02-25 16:51 | Improve safety and traffic flow | This project is one phase of a larger project to improve safety and traffic flow along the entire US 431 route. This section has a high ADT and CRF. This section is in downtown Central City and has strip commercail development with left turning vehicles
Y | 2 | Pennyrile ADD | IP20070093 |  |  |  | RECONSTRUCTION\WIDENING FROM KY 1031 AT CENTRAL CITY TO MCLEAN C\L. SEE MCLEAN CO. LISTING FOR CONTINUATION TO LIVERMORE. | Reconstruction | Muhlenberg | 089-US-0431 -000 | 22.064 | 28.313 | 6.249 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 3000000 |  | 4000000 |  | 16000000 |  | 2010-02-25 16:51 |  | A high CRF indicates safety issues along this section. This section also has substandard curves.
Y | 2 | Pennyrile ADD | IP20070094 |  |  |  | RECONSTRUCTION FROM HOPKINS C/L TO KY 277 IN CENTRAL CITY | Reconstruction | Muhlenberg | 089-KY-0070 -000 | 0 | 14.709 | 14.709 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 6000000 |  | 12000000 |  | 38000000 |  | 2010-02-25 16:51 |  | This route has poor geometrics and a high CRF.
Y | 2 | Pennyrile ADD | IP20070095 |  |  |  | RECONSTRUCTION FROM KY 70 TO KY 81 NEAR BREMEN from MP 18.9 to MP 25.29. | Reconstruction | Muhlenberg | 089-KY-0181 -000 | 18.955 | 25.296 | 6.341 | Other Improvement Types | 0 |  | 0 |  | 1900000 |  | 2500000 |  | 3800000 |  | 16000000 |  | 2010-02-25 16:51 |  | This portion of KY 181 has poor geometrics with 2/9 lanes.
Y | 2 | Pennyrile ADD | IP20070096 |  |  |  | WESTERN KENTUCKY PKY - RECONSTRUCT INTERCHANGE AT US 431 AT CENTRAL CITY | Reconstruction | Muhlenberg | 089-WK-9001 -000 | 57.947 | 58.047 | 0.1 | Innovative Interchange | 40 | Y | 0 |  | 800000 |  | 800000 |  | 800000 |  | 4000000 |  | 2017-06-08 15:56 |  | A high CRF at this interchange indicates a safety issue. The existing US 431 interchange was designed for toll-boths when the Parkway was a tollroad. This cloverleaf design creates a safety hazard because the merge lanes for traffic entering onto the Pa | PENNYRILE ADD | West | 24.4433 | 3.5326 | 2.9897 | 8.866 | 0.54983 | 0 | 5 | 3.5052 | 24
Y | 2 | Green River ADD | IP20070097 |  |  |  | Address service concerns and straighten curvature of US 62 from the Muhlenberg County Line at Rockport to US-231 at Beaver Dam. | Reconstruction | Ohio | 092-US-0062 -000 | 0 | 9.731 | 9.731 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 2000000 |  | 2000000 |  | 24300000 |  | 2010-08-09 09:10 |  | US 62 from MP 0.00 to 9.731 in Ohio Co is a rural secondary major collector route with 10-12 ft lanes and 2 ft shoulders. US 62 is a "AAA" rated truck route that provides access to the WK 9001 and to neighboring Muhlenberg Co.
Y | 2 | Green River ADD | IP20070098 |  |  |  | Address service concerns and straighten curvature of US 62 in Ohio Co. | Safety-Haz-Elm | Ohio | 092-US-0062 -000 | 1 | 1.171 | 0.171 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 450000 |  | 500000 |  | 1750000 |  | 2010-08-10 05:54 |  | This project is a segmentation of the 02 092 B0062 1.00 project from Beaver Dam to the Muhlenburg County Line. US 62 from MP 0.00 to 9.731 in Ohio Co is a rural secondary major collector route with 10-12 ft lanes and 2-3 ft shoulders. This segment of road
Y | 2 | Green River ADD | IP20070099 |  |  |  | Address safety concerns at the intersection of US 62 and Miller Road. | Safety-Haz-Elm | Ohio | 092-US-0062 -000 | 7.312 | 7.413 | 0.101 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 400000 |  | 400000 |  | 1600000 |  | 2017-05-19 13:16 | Address safety issues at the US 62 and Miller Road intersection. | The following need has been identified for this project: Improve Roadway Safety. | GREEN RIVER ADD | West | 25.39 | 2.1856 | 12.2165 | 5.3866 | 2.3024 | 0 | 0 | 3.299 | 25
Y | 2 | Green River ADD | IP20070100 |  |  |  | Address access concerns of KY-54 from Marsh Lane at Fordsville in Ohio County to KY-259/US 62 in Leitchfield in Grayson County. | Reconstruction | Ohio | 092-KY-0054 -000 | 7.995 | 18.244 | 10.249 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2400000 |  | 3000000 |  | 25600000 |  | 2010-08-19 06:19 |  | KY-54 in Ohio Co is a rural 2-lane route with 9 ft lane widths with 3 ft shoulders. This route provides access to Leitchfield in Grayson Co. It is a "AA" truck route from Fordsville to KY 261 and a "A" truck route from KY 261 to the Grayson County Line.
Y | 2 | Green River ADD | IP20070101 |  |  |  | Address safety and correct curve deficiencies of KY 69 from KY 54 in Fordsville in Ohio Co to KY 144 in Hancock Co. | Reconstruction | Ohio | 092-KY-0069 -000 | 31.623 | 37.339 | 5.716 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 3000000 |  | 4200000 |  | 26000000 |  | 2010-08-23 09:14 |  | KY 69 in Ohio Co from KY 54 in Fordsville to KY 144 in Hancock Co is a rural secondary major collector with 9-10 ft. driving lanes and 1-2 ft shoulders. The horizontal alignment of the Ohio Co MP 31.623 to MP 37.339 is rated as 3 indicating infrequent c
Y | 2 | Green River ADD | IP20070102 |  |  |  | Improve turning radius of the KY 54 and KY 69 intersection. | Spot Improvement | Ohio | 092-KY-0069 -000 | 31.623 | 31.723 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 500000 |  | 600000 |  | 1500000 |  | 2010-09-08 11:01 | To improve access and mobility. | The intersection of KY 69 and KY 54 (MP 31.623 to 31.723) in Fordsville has limited turning radius of 45 ft therefore considered "less than adequate" for truck traffic. KY 69 is a two-lane "AAA" rated truck route with 9 ft lanes and 1 ft shoulders. This
Y | 2 | Green River ADD | IP20070103 |  |  |  | Address safety and service concerns of the WK-9001 and US 231 interchange near Beaver Dam. | Reconstruction | Ohio | 092-WK-9001 -000 | 74.56 | 74.66 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 350000 |  | 300000 |  | 300000 |  | 2500000 |  | 2010-09-08 15:06 |  | The WK-9001 interchange at US-231 is a four-legged diamond interchange. The entrance ramps on US-231 contain sharp curves making for unsafe conditions for the significant volume of truck traffic. This interchange provides access to the Bluegrass Crossings
Y | 2 | Green River ADD | IP20070104 |  |  |  | Address need for new interchange access to the William Natcher Parkway at KY-764. | New Interchange | Ohio | 092-WN-9007 -000 | 58.22 | 58.32 | 0.1 | Construct Road in New Location | 0 | Y | 0 |  | 1000000 |  | 200000 |  | 750000 |  | 8000000 |  | 2010-09-09 12:14 |  | A new interchange on the WN Parkway (WN-9007) at KY-764 would improve access to the WN-9007. Currently, the only access from the Daviess and Ohio county line is at MP 47.796 near the City of Hartford. An additional access would improve response time for e
Y | 2 | Green River ADD | IP20070105 |  |  |  | Address need for new interchange to the Wm Natcher Parkway at US-62. | New Interchange | Ohio | 092-WN-9007 -000 | 44.439 | 44.539 | 0.1 | Construct Road in New Location | 0 | Y | 0 |  | 300000 |  | 400000 |  | 250000 |  | 6000000 |  | 2010-09-09 15:59 |  | A new interchange on the WN Parkway (WN-9007) at US-62 would improve access to the WN-9007 from US-62 and US-231. Currently, the only access from the Daviess and Ohio county line is at MP 47.796 near the City of Hartford. An additional access would impro
Y | 2 | Green River ADD | IP20070106 |  |  |  | Address service, safety and horizontal alignment adequacies of US 60 from the proposed Sullivan Bypass to the proposed Sturgis Bypass. | Major Widening | Union | 113-US-0060 -000 | 2.7 | 4.8 | 2.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 1200000 |  | 1000000 |  | 850000 |  | 8200000 |  | 2010-09-13 15:33 |  | US 60 from the proposed Sullivan Bypass (MP 2.700) to the proposed Sturgis Bypass (MP 4.800) is a rural state primary minor arterial with 2 12 ft lanes with 2 ft shoulders. The horizontal alignment for this segment indicates that infrequent curves do not
Y | 2 | Green River ADD | IP20070107 |  |  |  | Address safety and service concerns of US-60 from the proposed Sturgis Bypass to KY-950 in Union County. (MP 8.300 to MP 10.520) | Major Widening | Union | 113-US-0060 -000 | 8.3 | 10.52 | 2.22 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1250000 |  | 2000000 |  | 1800000 |  | 9000000 |  | 2010-09-14 11:08 |  | US-60 from the proposed Sturgis Bypass (MP 8.300) to KY-950 (MP 10.520) is an undivided 2-lane 11-ft. wide "AAA" rated truck route through Union County. The asphalt shoulder widths in this segment are 3-ft. Two horizontal curves (MP 8.95 & 10.76) are in t
Y | 2 | Green River ADD | IP20070108 |  |  |  | Address safety and service concerns of US-60 from the KY-950 to KY-492. | Major Widening | Union | 113-US-0060 -000 | 10.52 | 13.29 | 2.77 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1400000 |  | 2800000 |  | 1700000 |  | 13500000 |  | 2017-05-19 13:25 | Address safety and access issues along US 60 from KY 950 to KY 492. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 51.0301 | 6 | 13.0412 | 11.5077 | 1.2887 | 8.2131 | 3.3505 | 7.6289 | 51
Y | 2 | Green River ADD | IP20070109 |  |  |  | Address safety and service concerns at the intersection of US-60 and KY-1180 near Waverly. | Safety-Haz-Elm | Union | 113-US-0060 -000 | 22.055 | 22.155 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 300000 |  | 350000 |  | 1100000 |  | 2010-09-15 14:58 |  | US-60 and the intersection of KY-1180 near Waverly (MP 22.060 to 22.160) is an undivided 2-lane 12-ft. wide "AAA" rated truck route through Union County. The stabilized shoulder width is 5-ft. Sight distance in this segment is 40%. This project will im
Y | 2 | Green River ADD | IP20070110 |  |  |  | Address the service, safety and condition of KY 56 from Morganfield to KY 141. | Safety-Haz-Elm | Union | 113-KY-0056 -000 | 13.1 | 19.662 | 6.562 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 2580000 |  | 2650000 |  | 16500000 |  | 2017-05-19 13:28 | Address safety issues along KY 56 from US 60 in Morganfield to KY 141. | The following need has been identified for this project: Improve Roadway Safety. | GREEN RIVER ADD | West | 39.8136 | 2 | 8.6598 | 12.2809 | 3.6426 | 0 | 3.3333 | 9.8969 | 40
Y | 2 | Green River ADD | IP20070111 |  |  |  | Address safety and service concerns of KY 109 from US 60 in Sturgis to KY 492 S. | Reconstruction | Union | 113-KY-0109 -000 | 1.536 | 4.857 | 3.321 | Other Improvement Types | 0 |  | 0 |  | 900000 |  | 2000000 |  | 1400000 |  | 8300000 |  | 2010-09-29 14:40 |  | This project is a segmentation of UPL # 02 113 D0109 1.00. KY 109 from US 60 in Sturgis (MP 1.536) to KY 492 South (MP 4.857) is a state secondary rural major collector 2 lane route with 9-10 ft lanes and 2 ft shoulders. This route is a "AAA" truck route
Y | 2 | Green River ADD | IP20070112 |  |  |  | Address safety and service concerns on KY 109 from KY 492 S to KY 130. | Reconstruction | Union | 113-KY-0109 -000 | 4.857 | 9.079 | 4.222 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 1500000 |  | 1000000 |  | 8400000 |  | 2010-09-30 14:29 |  | This project is a segmentation of UPL # 02 113 D0109 1.00. KY 109 from KY 492 South (MP 4.857) to KY 130 (MP 9.070) is a state secondary rural major collector 2 lane route with 9 ft lanes and 2 ft shoulders. This route is a "AAA" truck route and provides
Y | 2 | Green River ADD | IP20070113 |  |  |  | Address safety and service concerns of KY 109 from KY 130 to KY 56 at The Rocks. | Reconstruction | Union | 113-KY-0109 -000 | 9.079 | 13.692 | 4.613 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1750000 |  | 1000000 |  | 9200000 |  | 2017-05-19 13:29 | Address safety and access issues along KY 109 from KY 130 to KY 56 at The Rocks. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 37.067 | 1.1134 | 7.732 | 8.3247 | 2.3024 | 5.3265 | 2.5773 | 9.6907 | 37
Y | 2 | Green River ADD | IP20070114 |  |  |  | Address safety and service conditions at the intersection of KY-130 and KY-141 near Uniontown. | Safety-Haz-Elm | Union | 113-KY-0130 -000 | 14.081 | 14.181 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 250000 |  | 200000 |  | 1100000 |  | 2010-10-01 14:11 |  | KY-130 is a rural two lane route with 10 ft. driving lanes and 2 ft wide combination shoulders. KY-130 is a "AA" Truck Weight Class route. The intersection of KY-130 and KY-141 near Uniontown has limited turning radii for truck traffic.
Y | 2 | Green River ADD | IP20070115 |  |  |  | Address service and safety concerns of KY 360 from KY 56 to KY 947. | Minor Widening | Union | 113-KY-0360 -000 | 0 | 1.945 | 1.945 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 900000 |  | 4000000 |  | 2010-10-04 10:28 |  | KY 360 is a rural major collector with two 9 ft driving lanes with 2 ft shoulders. This route provides access from KY 56 between the city of Morganfield and the Illinois state line and the city of Uniontown. It is classified as a "AA" truck route with a h
Y | 2 | Green River ADD | IP20070116 |  |  |  | Address service and safety concerns of KY 360 from KY 947 to KY 871. | Minor Widening | Union | 113-KY-0360 -000 | 1.945 | 5.482 | 3.537 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1400000 |  | 1400000 |  | 7100000 |  | 2010-10-04 16:02 |  | KY 360 is a rural major collector with two 9 ft driving lanes with 2 ft shoulders. This route provides access from KY 56 between the city of Morganfield and the Illinois state line and the city of Uniontown. It is classified as a "AA" truck route and HIS
Y | 2 | Green River ADD | IP20070117 |  |  |  | Address service and safety concerns of KY 360 from KY 130 to KY 359. | Minor Widening | Union | 113-KY-0360 -000 | 7.318 | 13.612 | 6.294 | Modernize Roadway-Rural | 26 |  | 0 |  | 1400000 |  | 2000000 |  | 1900000 |  | 12600000 |  | 2017-05-19 13:30 | Address safety and access issues along KY 360 from KY 130 to KY 359. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 18.4785 | 0.77663 | 5.9794 | 9.4201 | 2.3024 | 0 | 0 | 0 | 18
Y | 2 | Green River ADD | IP20070118 |  |  |  | Address safety and service concerns of US 41A from KY 56 West to KY 56 East at Poole near the Henderson County Line. | Reconstruction | Webster | 117-US-0041A -000 | 15.599 | 19.528 | 3.929 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 2200000 |  | 1200000 |  | 9700000 |  | 2010-10-14 11:19 |  | US 41A from KY 56 West (MP 15.599) to KY 56 East (MP 19.528) at Poole is a rural two-lane state route that has 10-ft lanes with 4 ft. combination shoulders. US 41A is a "AAA" rated truck route. This route provides access from Dixon, KY the Webster County
Y | 2 | Green River ADD | IP20070119 |  |  |  | Address safety and service concerns of KY 120 from the Crittenden County Line to within the City of Providence. | Minor Widening | Webster | 117-KY-0120 -000 | 0 | 3.768 | 3.768 | Other Improvement Types | 0 |  | 0 |  | 1100000 |  | 1400000 |  | 1400000 |  | 9500000 |  | 2010-11-03 17:26 |  | KY 120 from the Crittenden County Line to the RR crossing near Cedar Street in Providence is a rural major collector with 9 ft. lanes. It is a "AAA" rated truck route and provides access from the City of Providence to Marion, KY in Crittenden County.
Y | 2 | Green River ADD | IP20070120 |  |  |  | Address safety and service concerns of the KY 120 and KY 293 intersection within the City of Providence. | Safety-Haz-Elm | Webster | 117-KY-0120 -000 | 5.26 | 5.362 | 0.102 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 75000 |  | 350000 |  | 900000 |  | 2017-05-19 13:32 | Address safety issues at the KY 120 and KY 293 intersection. | The following need has been identified for this project: Improve Roadway Safety. | GREEN RIVER ADD | West | 21.8522 | 6.6804 | 5 | 3.6082 | 3.2302 | 0 | 0 | 3.3333 | 22
Y | 2 | Green River ADD | IP20070121 |  |  |  | Address safety and service concerns of KY 120 from US 41A to KY 630. | Reconstruction | Webster | 117-KY-0120 -000 | 6.723 | 14.765 | 8.042 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 6500000 |  | 6200000 |  | 8400000 |  | 2017-05-19 13:33 | Address safety and service issues along KY 120 from US 41A to KY 630. | The following needs have been identified for this project: 1) Improve roadway safety; 2) Improve service issues along the route. | GREEN RIVER ADD | West | 27.4047 | 0.43986 | 5.2062 | 8.9304 | 4.5189 | 5.2234 | 0 | 3.086 | 27
Y | 2 | Green River ADD | IP20070122 |  |  |  | Address service and safety concern of KY 132 from the Crittenden County Line to KY 109. | Reconstruction | Webster | 117-KY-0132 -000 | 0 | 7.556 | 7.556 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 2500000 |  | 4500000 |  | 7600000 |  | 2010-11-04 15:54 |  | KY 132 is a rural state secondary route with two 9 ft. lanes from the Crittenden County Line to KY 109 in Clay.
Y | 2 | Green River ADD | IP20070123 |  |  |  | Address service and safety concern of the intersection of KY 132 and KY 270. This is a break out of project 02 117 D0132 88.10 | Safety-Haz-Elm | Webster | 117-KY-0132 -000 | 8.778 | 8.878 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 75000 |  | 300000 |  | 600000 |  | 2010-11-04 16:36 |  | The intersection of KY 132 and KY 270 from MP 8.778 to 8.878 is in need of realignment to improve safety and sight distance. The turning radius creates problems for truck traffic.
Y | 2 | Green River ADD | IP20070124 |  |  |  | Address service and safety concerns of KY 132 from KY 494 to KY 56 in Sebree. | Reconstruction | Webster | 117-KY-0132 -000 | 25.87 | 28.483 | 2.613 | Other Improvement Types | 0 |  | 0 |  | 450000 |  | 2000000 |  | 2100000 |  | 3000000 |  | 2010-11-08 16:36 |  | KY 132 from KY 494 to KY 56 in Sebree is a rural two-lane project with lane widths ranging from 10 ft to 13 ft. A portion of this route is located in the City of Sebree.
Y | 2 | Green River ADD | IP20070125 |  |  |  | Address safety and service condition of KY 138 from KY 132 to KY 120 at Slaughters. | Reconstruction | Webster | 117-KY-0138 -000 | 0 | 10.439 | 10.439 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 3000000 |  | 2250000 |  | 11000000 |  | 2017-05-19 13:37 | Address safety and service issues along KY 138 from KY 132 to KY 120. | The following needs have been identified for this project: 1) Improve roadway safety; 2) Improve service issues along the route. | GREEN RIVER ADD | West | 28.8248 | 0.20619 | 4.7938 | 8.2732 | 4.5876 | 5.189 | 0 | 5.775 | 29
Y | 2 | Green River ADD | IP20070126 |  |  |  | Address safety and service concerns of KY 370 from Hopkins-Webster Co Line to US 41 in Sebree | Reconstruction | Webster | 117-KY-0370 -000 | 0 | 7.976 | 7.976 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 3000000 |  | 2500000 |  | 16000000 |  | 2010-11-09 15:28 |  | KY 370 is a rural secondary minor collector route from the Hopkins-Webster County line to US 41 in the City of Sebree. It is a 2 lane route with 9-19 ft. lanes and 2 ft shoulders. Approximately 2 miles from MP 5 to MP 7.976 is located within the City of
Y | 2 | Green River ADD | IP20070127 |  |  |  | Address service concerns of KY 630 from KY 132 in Dixon to the Hopkins County Line | Reconstruction | Webster | 117-KY-0630 -000 | 0 | 0.965 | 0.965 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 2000000 |  | 1100000 |  | 6000000 |  | 2010-11-09 15:53 |  | KY 630 from KY 132 to the Hopkins County Line is a rural two-lane route with 10 ft lanes and 3 ft shoulders that provides access from Dixon to Madisonville in Hopkins County. KY 630 is a "A" rated truck route.
Y | 2 | Green River ADD | IP20070128 |  |  |  | Address safety concern of the intersection of KY 983 and Lyce Duncan Road | Safety-Haz-Elm | Webster | 117-KY-0983 -000 | 4.562 | 4.662 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 75000 |  | 100000 |  | 650000 |  | 2010-11-09 16:11 |  | The intersection of KY 983 and Lyce Duncan Road is located on a hillcrest and sight distance is impaired. KY 983 is a rural two-lane route with 8 ft lanes and 3 ft. DGA shoulders.
Y | 2 | Owensboro MPO | IP20070249 |  |  |  | Grimes Ave - Construct new connector, 2 12-foot lanes, C/G, to access KY 603 and the US 60 Extension. Project begins at current terminus of Grimes Ave and ends at KY 603. | New Route | Daviess | 030-CS-1027 -000 | 0.537 | 0.547 | 0.01 | Construct Road in New Location | 0 |  | 0 |  | 150000 |  | 150000 |  | 200000 |  | 900000 |  | 2017-05-19 10:38 | The purpose of this project is to improve safety, reliability and mobility along Grimes Avenue, better control access and reduce congestion. | The Grimes Avenue/Alsop Lane area is home to several businesses that use heavy trucks, Lipton Foods for one. The heavy trucks at present travel to the US 60 Bypass by Ragu Drive to KY 54. This creates problems for the trucks having to turn left from Ragu | Owensboro MPO | West | 37.4794 | 8.9141 | 14.433 | 4.5103 | 3.6082 | 6.0137 | 0 | 0 | 38
Y | 2 | Clarksville-Oak Grove MPO | IP20070253 |  |  |  | Improve access and reduce congestion with a new route from Gate 4 to I 24. | New Route | Christian | 024-KY-0400 -000 | 0 | 1.377 | 1.377 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 3500000 |  | 3000000 |  | 35000000 |  | 2012-03-14 10:02 | To reduce traffic at Gate 4 | Gate 4 at US41A is a highly congested area. This is the main entrance to Fort Campbell. This is putting ht traffic leaving or entering the base onto US41A. Construct new route from US41A at Gate 4 to I 24, using some existing alignments of KY 400 and C
Y | 2 | Pennyrile ADD | IP20070254 |  |  |  | Reconstruct Airport Terminal Road from US68 to the Hopkinsville Airport | New Route | Christian | 024-CS-1075 -000 | 0 | 0.6 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 750000 |  | 120000 |  | 1000000 |  | 2012-03-14 10:27 |  | This is an economic development project. The existing city street (Airport Rd) does not meet the width and geometric requirements needed to support the track and multi-modal needs of the air freight industry.
Y | 2 | Clarksville-Oak Grove MPO | IP20070255 |  |  |  | Address congestion with a new route from US41A at Ft. Campbell's Gate 5 to KY 115 | New Route | Christian | 024-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 700000 |  | 1600000 |  | 7500000 |  | 2012-03-15 08:26 | To improve access from US 41A to KY 115 | There is congestion and a need for better traffic flow into the Main Gate (Gate 4) at Ft. Campbell as well as improvement of traffic congestion in Oak Grove from KY 115. This project will provide a connector route between KY 115 and US 41A at the Ft. Camp
Y | 2 | Pennyrile ADD | IP20080050 |  |  |  | EAST 9 TH STREET - ADDRESS CONGESTION ISSUES BY MAJOR WIDENING FROM US 41A (WALNUT ST) TO INDIANA CHIEF'S BRIDGE OVER S. FORK LITTLE RIVER | Major Widening | Christian | 024-US-0041 -000 | 11.373 | 12.114 | 0.741 | Other Improvement Types | 0 | Y | 0 |  | 1200000 |  | 2000000 |  | 2400000 |  | 5000000 |  | 2010-02-25 16:51 |  | This is a congestion problem. left turning vehicles block traffic while waiting for on-coming traffic to clear.
Y | 2 | Pennyrile ADD | IP20080051 |  |  |  | RECONSTRUCTION FROM I-24 TO PETSCH LANE FROM MP 0.75 TO MP 6.24 | Reconstruction | Christian | 024-KY-0272 -000 | 0.757 | 6.24 | 5.483 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 6000000 |  | 3000000 |  | 16500000 |  | 2010-02-25 16:51 |  | This is a narrow 9/2 lane route with poor geometrics.
Y | 2 | Owensboro MPO | IP20080052 |  |  |  | US 60 - Reconstruct and widen roadway. Project begins at Henderson/ Daviess County Line and ends at a point near KY 1554. | Major Widening | Daviess | 030-US-0060 -000 | 0 | 3.51 | 3.51 | Modernize Roadway-Rural | 26 |  | 0 |  | 1300000 |  | 2000000 |  | 3000000 |  | 11000000 |  | 2010-06-10 10:31 | The purpose of this project is to improve safety, reliability and mobility along US 60, better control access and reduce congestion. Project was recommended to be dropped by MPO. | To provide an improved facility to access the West Daviess County Industrial Park in Newman, KY. The CRF in one section of the roadway is approaching 1, although the road is nowhere near capacity. The IRI has increased, indicating that the pavement is d
Y | 2 | Owensboro MPO | IP20080053 |  |  |  | US 60 - Improve traffic flow and safety. Project begins at KY 279 South and ends at KY 331. | Major Widening | Daviess | 030-US-0060 -000 | 6.58 | 10.179 | 3.599 | Modernize Roadway-Rural | 26 |  | 0 |  | 1400000 |  | 3000000 |  | 3000000 |  | 11000000 |  | 2010-06-11 14:29 | The purpose of this project is to improve safety, reliability and mobility along US 60, better control access and reduce congestion | Reconstruct to provide an improved facility to access the West Daviess County Industrial Park in Newman, KY. The CRF in some sections is over 1, and the road is nowhere near capacity according to the V/SF. US 60 provides access from eastern Henderson Cou
Y | 2 | Owensboro MPO | IP20080054 |  |  |  | US 431 - Improve to provide better traffic flow, provide better access, and improve safety. Project begins near the Panther Creek Bridge and ends near Martin Luther King Jr. Blvd. | Major Widening | Daviess | 030-US-0431 -000 | 8.543 | 10.143 | 1.6 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 1000000 |  | 9000000 |  | 2010-06-22 15:17 | The purpose of this project is to improve safety, reliability and mobility along US 431, better control access and reduce congestion. | This project is part of the Long Range Transportation Plan to improve access to major traffic generators and overall upgrade the transportation system in the MPO. This project will improve access to the airport, riverport and commercial sites within the
Y | 2 | Owensboro MPO | IP20080055 |  |  |  | KY 54 - Reconstruct and make improvements from eastern city limits of Whitesville to Daviess/Ohio County Line. | Reconstruction | Daviess | 030-KY-0054 -000 | 15.8 | 17.619 | 1.819 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1400000 |  | 1250000 |  | 6400000 |  | 2010-06-24 10:55 | The purpose of this project is to improve safety, reliability and mobility along 54, better control access and reduce congestion. | A portion of KY 54 to be improved through Whitesville. This is a continuation of the KY 54 project. The MPO has plans to develop KY 54 into 5 lanes from Thurston-Dermont Road to Ohio County. Daviess County continues to grow on the eastern section of the c
Y | 2 | Owensboro MPO | IP20080056 |  |  |  | KY 56 - Improve traffic flow and safety. Projects begins at KY 279 South and ends at KY 81. | Reconstruction | Daviess | 030-KY-0056 -000 | 11.863 | 14.088 | 2.225 | Other Improvement Types | 0 |  | 0 |  | 450000 |  | 2200000 |  | 2750000 |  | 4000000 |  | 2014-12-11 10:15 | The purpose of this project is to improve safety, reliability and mobility along KY 56, better control access and reduce congestion. | Sorgho Elementary School is the reason for the high AM and PM peak hour traffic. The houses along this section are right on the edge of KY 56, to add shoulders, house would have to be taken. There are no shoulders, thereby, causing a situation where scho
Y | 2 | Owensboro MPO | IP20080058 |  |  |  | KY 81 - Improve KY 81 leading toward Owensboro to enhance development and better accommodate future traffic growth. Project begins at Keller Rd (CR 1301) and ends at KY 56. | Major Widening | Daviess | 030-KY-0081 -000 | 7.959 | 11.036 | 3.077 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1750000 |  | 1850000 |  | 10000000 |  | 2014-12-15 11:26 | The purpose of this project is to improve safety, reliability and mobility along KY 81, better control access and reduce congestion. | This project is part of the Outer Blvd, LRP, page 11, GR-02-0025. The Outer Blvd is proposed to open areas outside of the US 60 Bypass to commercial/residential development.
Y | 2 | Owensboro MPO | IP20080059 |  |  |  | KY 144 - The county has asked for a cost estimate for construction of this project. This project will begin near KY 1831 and end near Boteler Rd (CR 1025). | Reconstruction | Daviess | 030-KY-0144 -000 | 7.624 | 9.347 | 1.723 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 500000 |  | 1000000 |  | 4500000 |  | 2014-05-29 10:54 | The purpose of this project is to improve safety, reliability and mobility along KY 144, better control access and reduce congestion. | This section of KY 144 has 8 curves that are a cause for concern with the possibility that the coal mines will open, thereby bringing coal truck traffic back onto KY 144. KY 144 is narrow, 10 foot lanes, 2 foot shoulders, and blind curves. The CRF is near
Y | 2 | Owensboro MPO | IP20080060 |  |  |  | KY 144 - Reconstruct to improve traffic flow and safety. Project begins at Jones Rd (KY 1389) and ends at Knottsville-Mt. Zion Rd (KY 1831). | Reconstruction | Daviess | 030-KY-0144 -000 | 4.966 | 7.624 | 2.658 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 3200000 |  | 3000000 |  | 5400000 |  | 2010-06-24 14:33 | The purpose of this project is to improve safety, reliability and mobility along KY 144, better control access and reduce congestion. | Coal mines are going to reopen in Knottsville. During the time that the mines were open, there was many accidents along KY 144 involving coal trucks. The road is narrow, 10-12 foot lanes, and has problems with horizontal alignments.
Y | 2 | Owensboro MPO | IP20080061 |  |  |  | KY 144 - Reconstruct to improve traffic flow and safety. Project begins at Boteler Rd (CR 1025) and ends at the Hancock\Daviess County Line. The milepoints were changed because of a change to KY 144 milage in October 2014. | Reconstruction | Daviess | 030-KY-0144 -000 | 9.347 | 16.2 | 6.853 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 4500000 |  | 3500000 |  | 15000000 |  | 2010-06-24 14:51 | The purpose of this project is to improve safety, reliability and mobility along KY 144, better control access and reduce congestion. | Coal mines are going to reopen in Knottsville. During the time that the mines were open, there was many accidents along KY 144 involving coal trucks. The road is narrow, 10 - 11 foot lanes, and has problems with horizontal alignments.
Y | 2 | Owensboro MPO | IP20080062 |  |  |  | Old Hartford Rd - Address poor pavement conditions and congestion due to increased volumes and turn movements. Project begins at Burlew Blvd (KY 1432) and ends at Breckenridge St (KY 2155 NB). | Major Widening | Daviess | 030-KY-0298 -000 | 8.986 | 9.927 | 0.941 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1000000 |  | 1000000 |  | 4760000 |  | 2014-12-15 13:25 | The purpose of this project is to improve safety, reliability and mobility along KY 298, better control access and reduce congestion. | The pavement along this section of KY 298 is rough. There are many new and planned subdivisions along this route thereby adding to the congestion. This project is listed in the LRP, project number GR-02-0030, page 8. The CRF is low. accidents. This secti
Y | 2 | Owensboro MPO | IP20080063 |  |  |  | Old Hartford Rd - Widen to improve traffic flow and safety. Project begins at Harriet Ln (CR 1120H) and ends at Burlew Blvd (KY 1432). | Major Widening | Daviess | 030-KY-0298 -000 | 7.042 | 8.986 | 1.944 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 1900000 |  | 2450000 |  | 10500000 |  | 2014-12-11 09:47 | The purpose of this project is to improve safety, reliability and mobility along KY 298, better control access and reduce congestion. | project was proposed to widen driving lanes and add appropriate turn lanes as needed.
Y | 2 | Owensboro MPO | IP20080064 | 2-229 |  | A | RECONSTRUCT INTERSECTION AT FAIRVIEW DRIVE (KY 3143) AND KY 298. (12CCR) (16CCR)(18CCN) | SAFETY(P) | Daviess | 030-KY-0298 -000 | 7.7 | 7.8 | 0.1 | Improve Intersection | 26 |  |  |  | 0 |  | 630000 |  | 1040000 |  | 2000000 | 2019 | 2019-03-11 08:18 | The purpose of this project is to improve safety, reliability and mobility at the intersection of KY 3143 and KY 298 and reduce congestion. | This project will install left turn lanes on all approaches at the intersection. The intersection is a major part of traffic accessing the Owensboro Community College, Daviess County High School, Hillcrest Golf Course, and the KCTCS Vocational School on S | 2 | West | 30.8505 | 4.8454 | 8.299 | 10.7474 | 3.8316 | 0 | 0 | 3.1271 | 31
Y | 2 | Owensboro MPO | IP20080066 |  |  |  | KY 405 - Reconstruct to include shoulders and 12 foot driving lanes. Project begins at KY 144 and ends at KY 2830. | Reconstruction | Daviess | 030-KY-0405 -000 | 0 | 6.729 | 6.729 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 4000000 |  | 21000000 |  | 2010-06-30 14:59 | The purpose of this project is to improve safety, reliability and mobility along KY 405, better control access and reduce congestion. | The shoulder width along KY 405 is 1 foot, while lane width is 9 feet, this needs to be addressed. Although there are many curves and hills, they are not serious, however, they are numerous in nature. Recently, East View Elementary School was built on KY
Y | 2 | Owensboro MPO | IP20080067 |  |  |  | Address substandard roadway geometrics and safety concerns on KY 1456 near Hayden Rd (MP 4.71) to KY 144 (MP 7.30). | Reconstruction | Daviess | 030-KY-1456 -000 | 4.714 | 7.301 | 2.587 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 1700000 |  | 1700000 |  | 7000000 |  | 2014-05-29 11:07 | The purpose of this project is to improve safety, reliability and mobility along KY 1456, better control access and reduce congestion. | The roadway has nine (9) foot driving lanes with no shoulders. The roadway has vertical and horizontal deficiencies, although HIS states that the terrain is flat. The accidents are varied: sideswipes, rear ends and angle. The roadway also has several hidd
Y | 2 | Owensboro MPO | IP20080068 |  |  |  | Southeastern Pkwy - Reconstruct to address safety, widen the road, add curb/gutter, install sidewalks, realign the curves, and install turn lanes where needed. Project begins at New Hartford Rd (US 231) and ends at Old Hartford Rd (KY 298). | Minor Widening | Daviess | 030-KY-2117 -000 | 0 | 0.61 | 0.61 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 1000000 |  | 1000000 |  | 2000000 |  | 2014-12-11 09:57 | The purpose of this project is to improve safety, reliability and mobility along KY 2117, better control access and reduce congestion. | KY 2117 is a major route between the northeast portion of the county and US 231. There are three schools along US 231, Daviess County High School, Owensboro Community College and the Daviess County Campus of KCTCS. The road is narrow, 11 foot lanes, wit
Y | 2 | Owensboro MPO | IP20080069 |  |  |  | Goetz Drive - Extend to Martin Luther King Loop West and provide 12 foot lanes and turn lanes were needed. Project begins at Southtown Blvd (KY 2121) and ends at Martin Luther King Jr Loop (CS 1783). | New Route | Daviess | 030-CR-1705 -000 | 0 | 0.133 | 0.133 | Modernize Roadway-Rural | 26 |  | 30000 |  | 400000 |  | 700000 |  | 300000 |  | 2000000 |  | 2010-07-12 12:35 | The purpose of this project is to improve safety, reliability and mobility along KY 2121, better control access and reduce congestion. | This is a new route that will extend from KY 2121, Southtown Blvd at the Goetz Drive, southward to the Martin Luther King, Jr. Loop West. The new route will give vehicles and alternative route to access the schools along Goetz Drive. There are two schoo
Y | 2 | Owensboro MPO | IP20080070 |  |  |  | Goetz Dr - Reconstruct to provide 12 foot lanes with turn lanes as needed. Project begins at Southtown Blvd (KY 2121) and ends at Frederica St (US 431). | Reconstruction | Daviess | 030-KY-2699 -000 | 0 | 0.741 | 0.741 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 500000 |  | 500000 |  | 2800000 |  | 2010-07-12 15:05 | The purpose of this project is to improve safety, reliability and mobility along KY 2699 (Goetz Drive), better control access and reduce congestion. | Goetz Drive has two 9-foot driving lanes and 2 foot asphalt shoulders. However, once off the shoulders, the ditches are not very deep. There are two schools on Goetz Drive, Burns Elementary and Burns Middle School. There are many busses that travel Goet
Y | 2 | Owensboro MPO | IP20080071 |  |  |  | Settles Road - Minor widening to improve safety. Project begins at Fairview Dr (KY 3143) and ends at Millers Mill Rd (KY 1456). | Minor Widening | Daviess | 030-KY-3335 -000 | 0 | 1.134 | 1.134 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1750000 |  | 1000000 |  | 4000000 |  | 2015-08-05 13:37 | The purpose of this project is to improve safety, reliability and mobility along KY 3335, better control access and reduce congestion. | The road is narrow, with curving hills and no shoulders. The IRI is indicating that the road has problems with the pavement. There are two major subdivisions that have recently extended access to KY 3335, this will put added pressure and traffic on the ro
Y | 2 | Owensboro MPO | IP20080072 |  |  |  | Natcher Pkwy - Construct a new interchange at KY 142. | New Interchange | Daviess | 030-WN-9007 -000 | 63.782 | 63.882 | 0.1 | Grade Separated to Interchange | 0 | Y | 0 |  | 1300000 |  | 800000 |  | 500000 |  | 12000000 |  | 2010-07-12 16:25 | The purpose of this project is to improve safety, reliability and mobility along WN 9007 (William Natcher Pkwy), better control access and reduce congestion. | There is a need to install a new interchange at the intersection of the WN 9007 and KY 142. This is due to a future industrial development near the proposed interchange. There should be a study conducted to determine the exact location of the new intercha
Y | 2 | Owensboro MPO | IP20080073 |  |  |  | Ewing Road - Reconstruct to address safety concerns and provide for 2, 12 foot lanes. Project begins at 2nd Street (CS 1354) and ends at Medley Rd (CS 1068). | Reconstruction | Daviess | 030-CS-1069 -000 | 0.016 | 1.1 | 1.084 | Local Roadway Improvements | 3 |  | 0 |  | 800000 |  | 900000 |  | 900000 |  | 4250000 |  | 2010-02-25 16:51 | The purpose of this project is to improve safety, reliability and mobility along CS 1069 (Ewing Road), better control access and reduce congestion. | The road is a narrow 2 lane with 10 foot lanes and no shoulders. The roadway is utilized by trucks accessing the riverport, warehousing and wholesale businesses along the route. The roadway is also utilized by residential development that share the road
Y | 2 | Owensboro MPO | IP20080074 |  |  |  | East Byers Ave - Extend from existing section in the Heartlands to Old Hartford Rd. Project begins at current terminus of East Byers Ave (CR 1574) and ends at Old Hartford Rd (KY 298). | New Route | Daviess | 030-CS-1574 -000 | 0.893 | 0.993 | 0.1 | Local Roadway Improvements | 3 |  | 0 |  | 300000 |  | 2500000 |  | 2000000 |  | 3000000 |  | 2017-05-19 10:40 | The purpose of this project is to improve safety, reliability and mobility along CS 1574 (East Byers Ave.), better control access and reduce congestion. | This segment of East Byers Avenue needs to be constructed to connect to Byers Ave on the north side of KY 298, onward to KY 54. This new route will provide continuous access from the KY 54 area to the commercial areas along US 431. | Owensboro MPO | West | 1.6254 | 0.23368 | 0 | 1.3918 | 0 | 0 | 0 | 0 | 2
Y | 2 | Owensboro MPO | IP20080075 |  |  |  | 18th Street - Reconstruct to allow for center turn lanes where needed. Project begins at JR Miller Blvd (CS 1262) and ends at Breckenridge St (KY 2155 NB). | Reconstruction | Daviess | 030-CS-1770 -000 | 0.864 | 1.387 | 0.523 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 400000 |  | 350000 |  | 500000 |  | 2000000 |  | 2017-05-19 10:44 | The purpose of this project is to improve safety, reliability and mobility along CS 1770 (East 18th Street), better control access and reduce congestion | This project is part of the MTP. The project is intended to widen East 18th Street from a 2 lane road to a 3 lane cross section. East 18th Street is a major cross street between US 431 and KY 54, with both roads being highly commercialized or in the proce | Owensboro MPO | West | 41.2749 | 8.3368 | 13.7629 | 10.9278 | 0 | 8.2474 | 0 | 0 | 41
Y | 2 | Owensboro MPO | IP20080076 |  |  |  | 18th Street (CS 1770) - Reconstruct to allow for center turn lanes where needed. Project begins at Breckenridge St (KY 2155 NB) and ends at Leitchfield Rd (CS 1033). | Reconstruction | Daviess | 030-CS-1770 -000 | 0.159 | 0.864 | 0.705 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4250000 |  | 2017-05-19 10:45 | The purpose of this project is to improve safety, reliability and mobility along CS 1770 (East 18th Street), better control access and reduce congestion | This project is part of the MTP. The project is intended to widen East 18th Street from a 2 lane road to a 3 lane cross section. East 18th Street is a major cross street between US 431 and KY 54, with both roads being highly commercialized or in the proce | Owensboro MPO | West | 39.6589 | 9.354 | 11.134 | 10.6314 | 0.73883 | 7.8007 | 0 | 0 | 40
Y | 2 | Owensboro MPO | IP20080077 |  |  |  | RECONSTRUCTION FROM HOSPITAL ENTRANCE TO HAYDEN RD NEAR OWENSBORO TO WIDEN TO TWO 12 FOOT LANES, CONSTRUCT SHOULDERS AND CONTINUOUS TURN LANE. THE SECTION FROM KY 144(FORMERLY US 60) TO THE HOSPITAL HAS BEEN COMPLETED. THE REMAINDER AS DESCRIBED ABOVE HA | Reconstruction | Daviess | 030-CR-1090 -000 | 0 | 1 | 1 | Local Roadway Improvements | 3 |  | 0 |  | 400000 |  | 1500000 |  | 1500000 |  | 3200000 |  | 2010-07-15 14:12 | The purpose of this project is to improve safety, reliability and mobility along CR 1090 (Daniels Lane), better control access and reduce congestion. | The rural road is narrow without shoulders. This road is directly next to the Daviess County East Industrial Park. The road will also be a direct connection between the new US 60 Bypass Extension and US 60 East. The Owensboro Medical Health System is bui
Y | 2 | Owensboro MPO | IP20080078 |  |  |  | Keller Rd - Reconstruct to provide for 2, 12 foot lanes and wider shoulders. Project begins at KY 81 and ends at Carter Rd (KY 2698). | Reconstruction | Daviess | 030-CR-1301 -000 | 0 | 1.293 | 1.293 | Local Roadway Improvements | 3 |  | 0 |  | 500000 |  | 1000000 |  | 1100000 |  | 7250000 |  | 2017-05-19 10:48 | The purpose of this project is to improve safety, reliability and mobility along CH 1301 (Keller Road), better control access and reduce congestion. | This is part of the MTP. This project is a part of the Outer Blvd GR-02-0040. The road is a narrow 2 lane facility with 10 foot lanes. The road is a major short cut from south Daviess County and McLean County to the commercial area along south US 431. The | Owensboro MPO | West | 12.3318 | 0 | 0 | 6.9588 | 1.323 | 0 | 0 | 4.05 | 12
Y | 2 | Owensboro MPO | IP20080079 |  |  |  | East 26th Street - Straighten curve and minor improvements to provide for safer travel. Project begins at Old Hartford Rd (KY 298) and ends at Strawbridge Place (CS 1598). | Minor Widening | Daviess | 030-CS-1577 -000 | 0.456 | 0.883 | 0.427 | Local Roadway Improvements | 3 |  | 0 |  | 400000 |  | 1500000 |  | 1500000 |  | 4000000 |  | 2014-12-15 11:32 | The purpose of this project is to improve safety, reliability and mobility along CS 1577 (East 26th Street), better control access and reduce congestion. | The project will alleviate a double "S" curve along East 26th Street and realign the intersection of East 26th Street and Strawbridge Place. The project will also allow more direct access from Old Hartford Road to KY 54. The improvement will allow more a
Y | 2 | Evansville-Henderson MPO | IP20080080 |  |  |  | IMPROVE SAFETY AND LEVEL OF SERVICE AT THE INTERSECTION | Reconstruction | Henderson | 051-PF-9999 - |  |  |  | Improve Intersection | 26 |  | 0 |  | 210000 |  | 1000000 |  | 1200000 |  | 2000000 |  | 2018-12-11 14:58 | Improve safety and level of service at the intersection. | Reconstruct the US 41 and KY 812/Clay St/Airline Rd intersection to provide dedicated left turn lanes and protected left turn signal phasing.
Y | 2 | Evansville-Henderson MPO | IP20080081 |  |  |  | Improve safety and level of service throughout the corridor. | Major Widening | Henderson | 051-US-0041A -000 | 11.306 | 13.235 | 1.929 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 1300000 |  | 1800000 |  | 2000000 |  | 7600000 |  | 2018-12-13 14:53 | Improve safety and level of service. | This corridor needs major widening from KY 425 to US 60.
Y | 2 | Evansville-Henderson MPO | IP20080082 |  |  |  | Improve safety and level of service throughout the corridor. | Major Widening | Henderson | 051-US-0060 -000 | 13.087 | 15.25 | 2.163 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 900000 |  | 1100000 |  | 5500000 |  | 2010-02-25 16:51 | ? | Widen to four lanes from RR bridge East of Wathen Lane to Hollway Rucker near Henderson to address the volume of traffic on US 60 in this area to improve traffic flow and safety.
Y | 2 | Evansville-Henderson MPO | IP20080083 |  |  |  | Improve safety and level of service throughout the corridor. | Major Widening | Henderson | 051-US-0060 -000 | 15.25 | 16.927 | 1.677 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 450000 |  | 600000 |  | 1000000 |  | 4250000 |  | 2018-12-11 11:29 | Improve traffic flow and safety. | Widen US 60 from KY 2183/Holloway-Rucker Rd to KY 1078/Baskett LN from 2 to 4 lanes.
Y | 2 | Evansville-Henderson MPO | IP20080084 |  |  |  | Improve safety by addressing sight distance issues at the intersection of US60 with KY 1078. | Safety-Haz-Elm | Henderson | 051-US-0060 -000 | 15.964 | 16.164 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 350000 |  | 400000 |  | 1500000 |  | 2015-08-05 13:42 | Improve safety at the intersection. | Reconstruct US 60 at the intersection of KY 1078 to correct the sight distance issue.
Y | 2 | Evansville-Henderson MPO | IP20080087 |  |  |  | Improve roadway and pedestrian/bicyclist safety and overall level of service in preparation of interchange with proposed I-69. Create gateway to the city. | Reconstruction | Henderson | 051-KY-0351 -000 | 5.672 | 10.37 | 4.698 | Modernize Roadway-Urban | 16 |  | 0 |  | 2000000 |  | 3000000 |  | 3000000 |  | 15000000 |  | 2018-12-11 16:11 | Improve safety and traffic flow for bicycle, pedestrian and vehicular traffic. Provide economic development options. | Reconstruct KY 351 from 0.2 miles east of East Elm St to Briscoe Benton Rd to provide a standard geometry and correct vertical and horizontal deficiencies. Add sidewalks and bike lanes from East Elm St to Holloway Ln to provide multi-modal options and com
Y | 2 | Evansville-Henderson MPO | IP20080088 |  |  |  | Recontruct KY 416 to improve safety and level of service. | Reconstruction | Henderson | 051-KY-0416 -000 | 0 | 7.363 | 7.363 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 4000000 |  | 3000000 |  | 22100000 |  | 2019-01-14 14:34 | Improve safety. | KY416 from US41A to US41 is narrow with a lot of curves. Traffic on this route will most likely increase due to the recent completion of the full interchange at I 69. KY 416 will become a direct connection between The Audubon Parkway and the I69. | Evansville/Henderson MPO | West | 12.0017 | 3.1615 | 2.5773 | 1.4691 | 4.7938 | 0 | 0 | 0 | 12
Y | 2 | Evansville-Henderson MPO | IP20080089 |  |  |  | Improve safety and level of service. | Reconstruction | Henderson | 051-KY-0416 -000 | 7.363 | 10.749 | 3.386 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 4000000 |  | 3500000 |  | 10200000 |  | 2018-12-11 11:14 | Improve traffic flow and safety for expected traffic increase due to the interchange improvements at I-69. Provide economic development options. | Reconstruct KY 416 from I-69 to KY 136 at Niagara to provide standard geometry for expected growth.
Y | 2 | Evansville-Henderson MPO | IP20080090 |  |  |  | Improve safety and level of service. | Reconstruction | Henderson | 051-KY-0416 -000 | 7.363 | 7.463 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 300000 |  | 350000 |  | 1500000 |  | 2017-05-19 11:45 | Improve safety. | Correct alignment and sight distance issues at intersection with US 41.
Y | 2 | Evansville-Henderson MPO | IP20080091 |  |  |  | Improve safety and level of service. NOTE:The interchange was recently reconstructed (2014)and some of these areas were improved. These may change the limits of this project. | Reconstruction | Henderson | 051-KY-0416 -000 | 7.363 | 7.825 | 0.462 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 300000 |  | 350000 |  | 350000 |  | 2000000 |  | 2018-12-11 13:52 | Improve traffic flow and safety for expected growth from I-69 interchange improvements. | Reconstruct to provide standard geometry on KY 416 from US 41 to I-69. Note: In 2014 a reconstruction of the interchange made some improvements to the ramps. This project may need to be adjusted to reflect this.
Y | 2 | Evansville-Henderson MPO | IP20080092 |  |  |  | Improve sight distance. | Reconstruction | Henderson | 051-KY-0812 -000 | 3.021 | 3.121 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 200000 |  | 400000 |  | 1600000 |  | 2010-02-25 16:51 | ? | RECONSTRUCT INTERSECTION AT TOY-ANTHOSTON RD TO RESOLVE SITE DISTANCE ISSUE.
Y | 2 | Evansville-Henderson MPO | IP20080093 |  |  |  | Improve safety. | Reconstruction | Henderson | 051-KY-1078 -000 | 8.226 | 8.797 | 0.571 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 1500000 |  | 1500000 |  | 12500000 |  | 2019-01-14 14:59 | Improve safety and traffic flow. | This route is a well traveled cut through from KY 351 to US 60. It needs to be recontructed to correct some geometric issues.
Y | 2 | Evansville-Henderson MPO | IP20080094 |  |  |  | Improve safety. | Reconstruction | Henderson | 051-KY-1078 -000 | 12.791 | 13.697 | 0.906 | Modernize Roadway-Rural | 26 |  | 0 |  | 200000 |  | 350000 |  | 200000 |  | 1500000 |  | 2019-01-14 14:58 | Improve safety. | RECONSTRUCT\WIDEN FROM US 60 TO DOCTOR HODGE RD AT BASKETT TO ADDRESS SIGHT DISTANCE ISSUES.
Y | 2 | Evansville-Henderson MPO | IP20080095 |  |  |  | Reconstruct the roadway to a standard cross section improve safety. | Reconstruction | Henderson | 051-KY-1539 -000 | 0 | 0.882 | 0.882 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 600000 |  | 650000 |  | 3000000 |  | 2018-12-11 11:37 | Improve traffic flow and safety. | Reconstruct Larue Rd from KY 351 to Kimsey Ln to provide a standard cross section.
Y | 2 | Evansville-Henderson MPO | IP20080096 |  |  |  | Improve safety by providing adequate sight distance. | Relocation | Henderson | 051-KY-2183 -000 | 0 | 0.8 | 0.8 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 650000 |  | 400000 |  | 2000000 |  | 2010-02-25 16:51 | Improve safety. | RELOCATE INTERSECTION FROM KY 351 TO MP 0.8 APPROX. 0.9 MI S OF LARUE-ZION RD (KY 1539) NEAR HENDERSON TO ADDRESS SIGHT DISTANCE ISSUES.
Y | 2 | Evansville-Henderson MPO | IP20080097 |  |  |  | Address safety issues and improve mobility from US 60 to Shady Hollow Dr | Reconstruction | Henderson | 051-KY-2183 -000 | 0.786 | 3.756 | 2.97 | Modernize Roadway-Rural | 26 |  | 0 |  | 1200000 |  | 1500000 |  | 1000000 |  | 9000000 |  | 2017-05-19 11:46 | Improve safety. | RECONSTRUCT KY-2183 HOLLOWAY RUCKER RD FROM KY-1539 ZION LARUE RD TO US-60 TO IMPROVE CURVE AND GEOMETRIC ISSUES. PARTIAL NEW ROUTE SHOULD BE CONSIDERED AT THE SOUTH END. | Evansville/Henderson MPO | West | 43.7552 | 1.2165 | 7.8866 | 9.6521 | 4.6735 | 5.3265 | 0 | 0 | 29 |  | 15
Y | 2 | Evansville-Henderson MPO | IP20080098 |  |  |  | Reconstruction Elm St to improve level of service and pedestrian safety and mobility. | Reconstruction | Henderson | 051-CS-1115 -000 | 1.573 | 2.898 | 1.325 | Modernize Roadway-Urban | 16 |  | 0 |  | 400000 |  | 1200000 |  | 2000000 |  | 4000000 |  | 2019-01-14 15:13 | Improve vehicular traffic flow and improve safety for all modes. | Elm street from Watson Lane to Hi-Y Drive is narrow and does not have sidewalks to accomadate the pedestrian traffic. This route is in the area of golf course, park etc. This route needs to be reconstructed to provide a standard cross section with sidewal | Evansville/Henderson MPO | West | 37.305 | 9.1134 | 9.433 | 10.3737 | 0 | 8.3849 | 0 | 0 | 37
Y | 2 | Pennyrile ADD | IP20080100 |  |  |  | Remove the median on US 41 (South Main Street) from MP 13.646 to MP 15.521 | Reconstruction | Hopkins | 054-US-0041 -000 | 13.646 | 15.521 | 1.875 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 0 |  | 0 |  | 2000000 |  | 2017-05-19 12:00 | Improve safety and traffic flow | There are safety issues caused by vehicles ramdomly crossing a mountable raised center median. The mountable median causes confusion and hesitation. | 2 | West | 25.9381 | 8 | 0 | 14.0206 | 0 | 0 | 3.9175 | 0 | 26
Y | 2 | Pennyrile ADD | IP20080102 |  |  |  | CORRECT HORIZONTAL AND VERTICAL DEFICIENCIES TO IMPROVE DRIVER SAFETY AND OPERATIONAL USE OF TRUCKS ON KY-70 FROM KY-109 TO KY-1337 | Reconstruction | Hopkins | 054-KY-0070 -000 | 7.09 | 12.431 | 5.341 | Other Improvement Types | 0 |  | 0 |  | 1900000 |  | 1900000 |  | 2100000 |  | 18500000 |  | 2010-02-25 16:51 | Improve safety and poor geometrics | This section of road has poor geometrics with 2/10 lane. Trucks have difficulty driving the route with the narrow lanes and substandard geometrics.
Y | 2 | Pennyrile ADD | IP20080103 |  |  |  | Improve congestion at the intersection of KY 70 and KY 254. | Major Widening | Hopkins | 054-KY-0070 -000 | 19.78 | 20 | 0.22 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 350000 |  | 1100000 |  | 10000000 |  | 2010-02-25 16:51 | Improve congestion and traffic flow | There is a lot of traffic congestion and a high CFR around the Pennyrile PKWY ramps. This congestion is likely to increase with the new development in the area that is currently underway.
Y | 2 | Pennyrile ADD | IP20080104 | 2-384 |  | A | IMPROVE KY-281 FROM ISLAND PARK DRIVE TO CARRIAGE LANE (KY-2281). | MAJOR WIDENING(O) | Hopkins | 054-KY-0281 -000 | 0.996 | 1.759 | 0.763 | Modernize Roadway-Rural | 26 |  |  |  | 590000 | 2023 | 1280000 | 2024 | 1220000 | 2024 |  |  | 2019-03-11 08:46 | Improve safety, congestion and traffic flow. | This section of roadway has narrow 2/9 lanes with poor geometrics. There are safety issues with a high CRF along the route. | PENNYRILE ADD | West | 62.2534 | 4.5086 | 11.9588 | 7.384 | 0.94502 | 7.457 | 0 | 0 | 32 | 15 | 15
Y | 2 | Pennyrile ADD | IP20080105 |  |  |  | Realign the intersection of KY 1069 and JD Buchanan Rd and add guardrail | Safety-Haz-Elm | Hopkins | 054-KY-1069 -000 | 2.286 | 2.486 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 100000 |  | 250000 |  | 1750000 |  | 2010-02-25 16:51 | Improve safety | There is a large drop off into a creekbed at the intersection on KY 1069 and JD Buchanan Rd. There has been a recent falitality at this location.
Y | 2 | Pennyrile ADD | IP20080106 |  |  |  | ADDRESS SAFETY BY RECONSTRUCTING THE NORTHBOUND ON-RAMP FROM KY-813 TO THE PENNYRILE PKWY. | Reconstruction | Hopkins | 054-I -0069 -000 | 108.89 | 109.09 | 0.2 | Other Improvement Types | 0 | Y | 0 |  | 350000 |  | 100000 |  | 125000 |  | 1500000 |  | 2010-02-25 16:51 |  | The current northbound loop at the KY 813 interchange at Morton's Gap does not have the merge/excel length needed for safe access to the Pennyrile PKWY, which creates safety problems for vehicles trying to merge onto the Parkway. The existing bridge over
Y | 2 | Pennyrile ADD | IP20080108 |  |  |  | Add a separate left turn lane on US-62 at Clyde Dee Brown Jr. Blvd (Campus entrance) from MP 17.5 to MP 17.8. | Minor Widening | Muhlenberg | 089-US-0062 -000 | 17.5 | 17.8 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 125000 |  | 100000 |  | 225000 |  | 900000 |  | 2015-03-17 11:15 |  | Traffic turning left into the Community College is being delayed to a point that this intersection meets warrents for a left turn lane. There has been a 2003 Planning SDtudy completed on this project.
Y | 2 | Pennyrile ADD | IP20080109 |  |  |  | Reconstruct intersection of US 431 and US 62 to improve left turning north/south line of sight issues. This is a breakout of an existing US 62 project # 02 089 B0062 72.00 | Safety-Haz-Elm | Muhlenberg | 089-US-0431 -000 | 18.278 | 18.378 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 1200000 |  | 1500000 |  | 2000000 |  | 2010-02-25 16:51 |  | The current lane alignment causes a visibility problems on US 431. Southbound traffic on US 431 that is trying to turn left onto US 62 has their view hindered from northbound traffic stopped at the light in the west US 62 turn lane. A high CRF inidcates
Y | 2 | Pennyrile ADD | IP20080110 |  |  |  | RECONSTRUCT INTERSECTION OF KY 176 AND KY 246 TO CORRECT SIGHT DISTANCE FROM 5.700 TO 5.720. | Safety-Haz-Elm | Muhlenberg | 089-KY-0176 -000 | 5.7 | 5.72 | 0.02 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 150000 |  | 200000 |  | 1000000 |  | 2013-08-08 13:24 |  | This intersection is a safety problem due to poor sight distance issues on KY 176 when vehicles are approching the intersection of KY 246. Vehicles pulling out onto KY 176 from KY 246 do not have the needed sight distance due to horizontal and vertical c
Y | 2 | Pennyrile ADD | IP20080111 |  |  |  | ADDRESS HORIZONTAL, VERTICAL AND WIDTH DEFICIENCIES TO IMPROVE SAFETY ON KY-181 FROM KY-1163 TO US-60. | Reconstruction | Muhlenberg | 089-KY-0181 -000 | 10.103 | 11.881 | 1.778 | Other Improvement Types | 0 |  | 0 |  | 650000 |  | 700000 |  | 1000000 |  | 6300000 |  | 2010-02-25 16:51 |  | Narrow 9/2 lanes and poor geometrics are safety problems
Y | 2 | Pennyrile ADD | IP20080112 |  |  |  | ADDRESS TRAFFIC FLOW ISSUES AND ROAD WIDTH DEFICIENCIES FROM US 62 IN GREENVILLE TO KY 601 | Major Widening | Muhlenberg | 089-KY-0181 -000 | 11.881 | 12.767 | 0.886 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1800000 |  | 1500000 |  | 3500000 |  | 2017-05-19 13:13 |  | This is the main access route from Greenville to access the WK Parkway. The road is stripped with commercial and residential development, which has left turning vehicles slowing traffic. | PENNYRILE ADD | West | 43.732 | 6.7354 | 9.0206 | 8.9948 | 2.3024 | 8.1787 | 0 | 8.5 | 44
Y | 2 | Green River ADD | IP20080113 |  |  |  | Address left turn lane issues on US-231 at Cromwell Road. | Safety-Haz-Elm | Ohio | 092-US-0231 -000 | 3.039 | 3.189 | 0.15 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 275000 |  | 200000 |  | 300000 |  | 2000000 |  | 2017-05-19 13:18 | Address mobility and access issues at the US 231 and Cromwell Road intersection.l | The following needs have been identified for this project: 1) Improve mobility; 2) Improve Access. Truck traffic associated with Perdue Farms chicken processing plant utilize Cromwell Rd to access US 231. This intersection of US 231 and Cromwell Road | GREEN RIVER ADD | West | 35.6959 | 5.0172 | 8.3505 | 6.4691 | 1.5808 | 6.8729 | 2.8007 | 4.6048 | 36
Y | 2 | Green River ADD | IP20080114 |  |  |  | Address left turn lane issues on US-231 at Perdue main entrance. | Safety-Haz-Elm | Ohio | 092-US-0231 -000 | 3.82 | 3.83 | 0.01 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 300000 |  | 400000 |  | 500000 |  | 900000 |  | 2010-08-11 15:34 |  | Truck traffic associated with Perdue Farms chicken processing plant utilize this entrance to access US 231. This entrance onto US 231 is not built for heavy truck traffic. The area has 9.8 percent truck traffic, with a high percentage of these going to
Y | 2 | Green River ADD | IP20080115 |  |  |  | Improve turning radius of the KY 54 and KY 69 N intersection. | Safety-Haz-Elm | Ohio | 092-KY-0054 -000 | 6.018 | 6.118 | 0.1 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 300000 |  | 1500000 |  | 2017-05-19 13:22 | Address safety and mobility issues at the KY 54 and KY 69 N intersection. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 22.2457 | 5.8282 | 3.9175 | 4.3041 | 1.5808 | 0 | 3.0069 | 3.6082 | 22
Y | 2 | Green River ADD | IP20080116 |  |  |  | Address sight distance concerns at intersection with Hilltop Rd. | Safety-Haz-Elm | Union | 113-KY-0666 -000 | 5.492 | 5.592 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 100000 |  | 250000 |  | 800000 |  | 2015-08-05 14:02 |  | Hilltop Road intersects KY 666 just east of the crest of a vertical curve. The result is poor sight distance to the west.
Y | 2 | Green River ADD | IP20080117 |  |  |  | Address service and safety concern of KY-56 from US-41A in Poole to KY 283. | Minor Widening | Webster | 117-KY-0056 -000 | 5.332 | 9.241 | 3.909 | Other Improvement Types | 0 |  | 0 |  | 1100000 |  | 1200000 |  | 2000000 |  | 9750000 |  | 2010-10-14 13:56 |  | KY-56 from US-41A in Poole to KY 283 is a rural two-lane route with 10 ft. lane widths and 3 ft. shoulders. KY-56 is a "AAA" rated truck route as well as an extended weight and coal haul route. This section also was recently designated as part of the "Bl
Y | 2 | Green River ADD | IP20080118 |  |  |  | Address service and safety concern of KY-56 from KY 283 in Poole to US 41 in Sebree. This is a breakout of Project 02 117 D0056 1.00 | Major Widening | Webster | 117-KY-0056 -000 | 9.241 | 12.47 | 3.229 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 900000 |  | 1500000 |  | 7300000 |  | 2010-10-19 14:18 |  | KY-56 from KY-283 to US-41 is a rural two-lane route with 10-11 ft. lane widths and 0-16 ft. shoulders. Shoulder types range from curbed to 16 ft. paved bituminous. KY-56 is a "AAA" rated truck route as well as an extended weight and coal haul route. Thi
Y | 2 | Green River ADD | IP20080119 |  |  |  | Address service and safety concern of KY-56 from US-41 in Sebree to the McLean County Line. This is a breakout of Project 02 117 D0056 1.00 | Minor Widening | Webster | 117-KY-0056 -000 | 12.47 | 14.671 | 2.201 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 660000 |  | 1100000 |  | 5500000 |  | 2010-10-19 15:23 |  | KY-56 from US-41 to the McLean County Line is a rural two-lane route with 2-10 ft. shoulders. KY-56 is a "AAA" rated truck route as well as an extended weight and coal haul route. This section also was recently designed as part of the "Blues to Bluegrass
Y | 2 | Green River ADD | IP20080120 |  |  |  | Address safety and service concerns of the KY 120 and KY 630 intersection. This is a breakout of Project 02 117 D0120 3.00 | Reconstruction | Webster | 117-KY-0120 -000 | 14.765 | 14.865 | 0.1 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 400000 |  | 400000 |  | 1000000 |  | 2010-11-03 17:59 |  | The intersection of KY 120 and KY 630 has several deficiencies. KY-120 is a two-lane rural highway with 9 ft lanes and 3 ft earth shoulders. A large ditch at this intersection is a safety concern. This is a breakout of Project 02 117 D0120 3.00
Y | 2 | Green River ADD | IP20080121 |  |  |  | Address safety and service concern of KY 132 from KY 1340 to KY 857. | Reconstruction | Webster | 117-KY-0132 -000 | 10.101 | 12.379 | 2.278 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 700000 |  | 1200000 |  | 6000000 |  | 2017-05-19 13:34 | Address safety and service issues along KY 132 from KY 1340 to KY 857. | The following needs have been identified for this project: 1) Improve roadway safety; 2) Improve service along the route. | GREEN RIVER ADD | West | 61.4158 | 0.76289 | 6.7526 | 5.8247 | 3.2646 | 5.5326 | 0 | 9.2784 | 31 | 15 | 15
Y | 2 | Green River ADD | IP20080122 |  |  |  | Address safety and service concerns of KY 132 from KY 857 to US 41A. | Reconstruction | Webster | 117-KY-0132 -000 | 12.379 | 16.452 | 4.073 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1300000 |  | 2100000 |  | 10000000 |  | 2017-05-19 13:36 | Address safety and service issues along KY 132 from KY 857 to US 41A. | The following needs have been identified for this project: 1) Improve roadway safety; 2) Improve service along the route. | GREEN RIVER ADD | West | 37.2878 | 0.76289 | 9.4845 | 8.4665 | 3.5911 | 5.5326 | 0 | 9.4502 | 37
Y | 2 | Owensboro MPO | IP20080732 |  |  |  | Wrights Landing Rd - Minor widening to include 2 12-foot driving lanes and 6 foot shoulders. Project begins at KY 2830 and ends at KY 405. | Minor Widening | Daviess | 030-KY-1831 -000 | 0 | 1.179 | 1.179 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 750000 |  | 1000000 |  | 3600000 |  | 2018-11-14 14:13 | The purpose of this project is to improve safety, reliability and mobility along KY 1831 (Wrights Landing Road), better control access and reduce congestion. | The road is narrow, 2 9-foot driving lanes, and 2 foot shoulders. The road is a major route to the Summit Country Club, located on KY 1831. The ditches are located directly on the edge of the pavement.
Y | 2 | Owensboro MPO | IP20080733 |  |  |  | West 5th Street Rd - Reconstruct to a 3 lane cross section with shared use paths. Project begins at Worthington Rd (CR 1336) and ends at the US 60 overpass. | Minor Widening | Daviess | 030-CR-1339 -000 | 4.404 | 5.231 | 0.827 | Local Roadway Improvements | 3 |  | 0 |  | 350000 |  | 500000 |  | 500000 |  | 2800000 |  | 2010-08-23 04:58 | The purpose of this project is to improve safety, reliability and mobility along CR 1339 (West Fifth Street Road), better control access and reduce congestion. | West Fifth Street is narrow with deep ditches on either side. West Fifth Street is the only access to the Jack Fisher Park. The softball fields host state, regional and national tournements, that generate traffic. The City of Owensboro recently complete
Y | 2 | Owensboro MPO | IP20080734 |  |  |  | East 9th Street - Reconstruct road away from the railroad tracks and provide a clear zone for vehicles traveling along the road. Project begins at Breckenridge St (KY 2155 NB) and ends at Leitchfield Road (CS 1033). | Reconstruction | Daviess | 030-CS-1790 -000 | 0.638 | 0.911 | 0.273 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 1000000 |  | 500000 |  | 2000000 |  | 2017-05-19 10:46 | The purpose of this project is to improve safety, reliability and mobility along CS 1790 (East Ninth Street), better control access and reduce congestion. | East 9th Street runs along the railroad tracks, and there is not much clearance between the roadway and the tracks. East 9th Street provides a major access road for the hospital. | Owensboro MPO | West | 28.018 | 8.2543 | 4.9485 | 6.7397 | 2.3024 | 5.7732 | 0 | 0 | 28
Y | 2 | Owensboro MPO | IP20080735 |  |  |  | New construction to connect the new interstate spurs and the US 60 Bypass Extension. This project is proposed to begin at KY 2698 and end at US 60 East. | New Route | Daviess | 030-US-0060 -000 | 20.884 | 20.886 | 0.002 | Construct Road in New Location | 0 | Y | 0 |  | 5000000 |  | 12000000 |  | 6000000 |  | 40000000 |  | 2010-08-24 09:18 | The purpose of this project is to improve safety, reliability and mobility along US 60, better control access and reduce congestion. | The new Outer Loop provides a route that would connect the new interstate spurs and connect with the US 60 Bypass Extension. This project would keep through traffic, especially heavy truck traffic, out of the urban area and provide safer travel on the exi
Y | 2 | Green River ADD | IP20100009 |  |  |  | Address safety concern of curvature of US-62 just west of James St in McHenry. | Safety-Haz-Elm | Ohio | 092-US-0062 -000 | 5.5 | 5.9 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 150000 |  | 250000 |  | 800000 |  | 2010-11-10 15:44 |  | US 62 from MP 5.5 to 5.9 in Ohio Co is a rural secondary major collector route with 10 ft. lanes and 2 ft shoulders. The horizontal alignment of this segment is rated a 3 indicating there are infrequent curves with design speeds less that the prevailing
Y | 2 | Green River ADD | IP20100010 |  |  |  | Address service, safety concern and future congestion and economic development needs along US 60 near the City of Sturgis in Union Co. (new route) | New Route | Union | 113-US-0060 -000 | 0 | 3.5 | 3.5 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 1600000 |  | 1200000 |  | 14000000 |  | 2010-11-10 17:19 |  | US 60 through Sturgis is a rural state primary minor arterial with 2 12 ft lanes with 2 ft shoulders. This route has a high percentage of truck traffic. The horizontal alignment for this segment indicates that infrequent curves do not meet design standard
Y | 2 | Green River ADD | IP20100011 |  |  |  | Address safety concerns of KY 2181 from KY 144 to US 60 at Hawesville. | Reconstruction | Hancock | 046-KY-2181 -000 | 0 | 11.932 | 11.932 | Modernize Roadway-Rural | 26 |  | 0 |  | 2300000 |  | 3000000 |  | 3000000 |  | 23800000 |  | 2017-05-19 11:39 | Address safety and access issues along KY 2181 from KY 144 to US 60. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | GREEN RIVER ADD | West | 30.1212 | 0.19244 | 6.3918 | 10.3995 | 4.9313 | 5.1203 | 0 | 3.086 | 30
Y | 2 | Green River ADD | IP20100012 |  |  |  | Address safety concern of reduced sight distance at the intersection of US 62 and Middle Rd. | Safety-Haz-Elm | Ohio | 092-US-0062 -000 | 4.994 | 4.995 | 0.001 | Improve Intersection | 26 |  | 0 |  | 110000 |  | 200000 |  | 250000 |  | 600000 |  | 2010-11-17 15:11 |  | US 62 at Miller Rd (MP 4.994) in Ohio Co is a rural secondary major collector route with 10 ft. lanes and 2 ft shoulders. A landfill is located on Miller Rd resulting in increased truck traffic.
Y | 2 | Pennyrile ADD | IP20100017 |  |  |  | New Connector between KY 85 and KY 281 east of the Pennyrile PKWY. | New Route | Hopkins | 054-I -0069 -000 | 114.254 | 116.173 | 1.919 | Other Improvement Types | 0 | Y | 0 |  | 900000 |  | 1750000 |  | 1750000 |  | 9500000 |  | 2012-01-27 10:20 | Improve Traffic flow | There is poor north/south traffic corridors on the east side ofthe Pennyrile Parkway. This will help inprove north/south access.
Y | 2 | Pennyrile ADD | IP20100018 |  |  |  | New Hanson Connector (Phase I) from approx. 800 feet north of the Brown St/US 41 intersection westward 0.3 MI to the Compton/Livingston St. intersection. | New Route | Hopkins | 054-KY-0260 -000 | 0.614 | 1.794 | 1.18 | Other Improvement Types | 0 |  | 0 |  | 450000 |  | 500000 |  | 250000 |  | 2950000 |  | 2012-01-27 10:21 | improve safety and traffic flow | There is a problem with trains parked on a siding track that blocks KY 260 for extended periods. This blocks access to the School on the east side of US 41. This proposed new route will include a railroad overpass just north of KY 260.
Y | 2 | Pennyrile ADD | IP20100019 |  |  |  | New Hanson Connector (Phase II) from the Compton Rd./Livingston St. intersection to KY 260 in Hanson. | New Route | Hopkins | 054-KY-0260 -000 | 0.614 | 1.794 | 1.18 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1500000 |  | 1200000 |  | 4600000 |  | 2012-01-27 10:22 | This is one phase of a proposed 2 phase project involving a new route with a new bridge over a railroad. The main goal is to get a rail overpass just north of the at-grade KY 260 RR crossing in Hanson. | There is a rail road siding track that runs north/south next to US 41 that blocks traffic on KY 260. This is the 2nd phase of a 2 phase road to route traffic north to a new railroad overpass that will advoid the delays with the train block KY 260.
Y | 2 | Pennyrile ADD | IP20100020 |  |  |  | Conduct study to develop a new route along the proposed abandoned CSXT Mainline in Madisonville. | New Route | Hopkins | 054-US-0041 -000 | 15.738 | 16.8 | 1.062 | Other Improvement Types | 0 |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2012-01-27 10:23 | Reduce traffic congestion in downtown Madisonville. | There is traffic congestion on north/south roads in Madisonville. If this CSX rail line is relocated, it would provide an opertunity to have another north/south road in downtown Madisonville to reduce traffic congestion.
Y | 2 | Pennyrile ADD | IP20100021 |  |  |  | New southwest connector for Madisonville from US 41 (S. Main St.) to KY 262. | New Route | Hopkins | 054-US-0041 -000 | 14.213 | 16.124 | 1.911 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 700000 |  | 7000000 |  | 2012-01-27 10:23 | Improve congestion and traffic flow | There is traffic congestion in downtown Madisonville and poor truck access in the older city streets. This connector route will provide better traffic flow and truck access aound the west side of the city.
Y | 2 | Pennyrile ADD | IP20100022 |  |  |  | New western connector for Madisonville from KY 262 to US 41 (Nebo Rd). | New Route | Hopkins | 054-US-0041 -000 | 16.124 | 17.548 | 1.424 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 550000 |  | 900000 |  | 3250000 |  | 2012-01-27 10:23 | Improve traffic congestion and improve traffic flow | There is major traffic congestion in downtown Madisonville and poor truck access in the narrow/older city streets.
Y | 2 | Pennyrile ADD | IP20100023 |  |  |  | New northwest connector for Madisonville from US 41A (Nebo Rd) to US 41 (Main St.). | New Route | Hopkins | 054-US-0041A -000 | 0 | 4.249 | 4.249 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2500000 |  | 1200000 |  | 17500000 |  | 2012-01-27 10:24 | Improve traffic congestion | There is traffic congestion in downtown Madisonville and poor truck access within the older/narrower city streets. This route will provide better access around the north side of the city.
Y | 2 | Green River ADD | IP20100024 |  |  |  | Address condition, safety and service issues on KY 69 SW of Fordsville to KY 54/KY 69 intersection in Fordsville by constructing a Bypass from KY 54 SW of Fordsville to KY 54/KY 69 intersection. | New Route | Ohio | 092-KY-0069 -000 | 0 | 0.8 | 0.8 | Construct Road in New Location | 0 |  | 0 |  | 400000 |  | 250000 |  | 250000 |  | 3500000 |  | 2010-11-22 12:27 |  | KY 69 is a narrow 9-12 ft. route with minimum shoulder widths that travels through the City of Fordsville. The KY 69 and KY 54 intersection has poor turning radius for truck traffic. Trucks overtake the opposing traffic lane upon making right hand turns
Y | 2 | Green River ADD | IP20100026 |  |  |  | Address safety and service concerns of US 41A near the City of Dixon in Webster Co. (New system mileage) | New Route | Webster | 117-US-0041A -000 | 0 | 4.8 | 4.8 | Construct Road in New Location | 0 |  | 0 |  | 1100000 |  | 1000000 |  | 250000 |  | 14500000 |  | 2010-11-22 14:45 |  | US 41A is a state secondary rural minor arterial with two 10 ft - 14 ft lanes and 2 ft shoulders. US 41A is a "AAA" rated truck route with 9.8% truck traffic. ADT ranges from 3,020 to 4,132. The IRI for this segment ranges from 87 to 223 indicating a so
Y | 2 | Pennyrile ADD | IP20100028 |  |  |  | New Princeton Southern Connector from KY 293 (South Jefferson St.) to KY 139. | New Route | Caldwell | 017-KY-0293 -000 | 5.6 | 6.151 | 0.551 | Other Improvement Types | 0 |  | 0 |  | 900000 |  | 800000 |  | 500000 |  | 6000000 |  | 2013-05-03 13:10 | Improve truck access to south side of Princeton. | The existing Truck Route through the City of Princeton has narrow lanes and poor truck turning radius. The existing truck route goes through city residential streets that have poor geometrics. The Truck Route is routed to avoid two (2) railroad underpa
Y | 2 | Pennyrile ADD | IP20100029 |  |  |  | New Princeton Southern Connector from KY 139 to KY 91 | New Route | Caldwell | 017-US-0062 -000 | 7.037 | 7.345 | 0.308 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 600000 |  | 800000 |  | 3600000 |  | 2014-05-29 09:29 | Improve truck access to the south side of Princeton | The existing Truck Route through the City of Princeton has narrow lanes and poor truck turning radius. The existing truck route goes through city residential streets that have poor geometrics. The Truck Route is routed to avoid two (2) railroad underpa
Y | 2 | Pennyrile ADD | IP20100030 |  |  |  | New Princeton Parkway Connector - New route from US 62 to Old Fredonia RD west of Princeton includes a new Parkway interchange. | New Route | Caldwell | 017-US-0062 -000 | 3.3 | 5.919 | 2.619 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 900000 |  | 800000 |  | 12550000 |  | 2012-01-27 10:09 | Improve traffic flow and access to the US 62 commercial corridor from I-69 | Reduce traffic congestion on US 62 inside the City of Princeton
Y | 2 | Pennyrile ADD | IP20100031 |  |  |  | New Princeton Noprtheast connector from old Fredonia Rd to KY 91 at Beckner RD N of princeton. | New Route | Caldwell | 017-KY-0091 -000 | 12.292 | 13.379 | 1.087 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 1750000 |  | 5400000 |  | 2012-01-27 10:09 | Improve traffic flow to the Caldwell County High School | Improve traffic congestion on KY 91 from from the I-69 Interchange to the High School.
Y | 2 | Pennyrile ADD | IP20100032 |  |  |  | New princeton Northern Connector from KY 91 at Beckner RD to KY 293 N of Princeton | New Route | Caldwell | 017-I -0069 -000 | 79.771 | 81.189 | 1.418 | Construct Road in New Location | 0 | Y | 0 |  | 900000 |  | 650000 |  | 700000 |  | 6700000 |  | 2017-05-19 09:41 | To provide better access to the Caldwell County High School | Improve congestion on KY 91 | PENNYRILE ADD | West | 37.0206 | 5.079 | 12.4227 | 4.1753 | 0.54983 | 9.8625 | 4.9313 | 0 | 37
Y | 2 | Pennyrile ADD | IP20100033 |  |  |  | New Walnut to Campbell St Connector route from the Walnut St. (US 41A( and E. 19th St intersection to S. Campbell St. in Hopkinsville | New Route | Christian | 024-US-0041A -000 | 15.412 | 15.58 | 0.168 | Other Improvement Types | 0 | Y | 0 |  | 350000 |  | 750000 |  | 750000 |  | 3200000 |  | 2012-01-27 10:11 |  | This will improve congestion on Walnut St. and improve north/south traffic flow.
Y | 2 | Pennyrile ADD | IP20100034 |  |  |  | Lover's lane- reconstruct/relocation from Pennyrile PKWY to KY 107 | Reconstruction | Christian | 024-CS-1652 -000 | 0 | 0.95 | 0.95 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 1500000 |  | 800000 |  | 2000000 |  | 2012-01-27 10:14 |  | Lover's Lane is a narrow 2/9 lane with poor geometrics
Y | 2 | Pennyrile ADD | IP20100035 |  |  |  | New route from 107/Rozelle Ave intersection to US 68 in Hopkinsville | New Route | Christian | 024-US-0068 -000 | 11.59 | 12.185 | 0.595 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 600000 |  | 600000 |  | 1200000 |  | 2012-01-27 10:14 |  | This will reduce traffic congestion on KY 107.
Y | 2 | Pennyrile ADD | IP20100036 |  |  |  | New route from US 68/US 41 intersection to US 41A/14th St intersection in Hopkinsville. | New Route | Christian | 024-US-0041 -000 | 11.909 | 12.114 | 0.205 | Other Improvement Types | 0 | Y | 0 |  | 800000 |  | 1000000 |  | 1000000 |  | 1400000 |  | 2012-02-01 14:33 |  | This project will reduce traffic congestion on 9th St and redesign the US 68/US 41 intersection.
Y | 2 | Pennyrile ADD | IP20100037 |  |  |  | New route fropm US 41/14th St intersection to 7th/9th St intersection in Hopkinsville | New Route | Christian | 024-US-0041 -000 | 12.438 | 12.636 | 0.198 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 3900000 |  | 1100000 |  | 4000000 |  | 2012-01-27 10:15 |  | The Little River creates "choke points" for east/west raffic in Hopkinsville due to the limited bridges over the river. This route will provide another bridge over the Little River and reduce east/west traffic congestion on downtown 9th street.
Y | 2 | Pennyrile ADD | IP20100038 | 2-381 |  | A | CONSTRUCT NEW CONNECTOR FROM US 41 NEAR THE INDUSTRIAL PARK TO KY 115 SOUTH OF PEMBROKE. (16CCR)(18CCN) | NEW ROUTE(O) | Christian | 024-US-0041 -000 | 2.787 | 4.396 | 1.609 | Improve Railroad Crossing | 55 |  |  |  | 490000 | 2020 | 400000 | 2022 | 730000 | 2022 | 5200000 | 2023 | 2019-03-11 08:33 |  | This is one phase of a 3 phase plan to improve truck access to I-24. The trucks from the Hopkinsville Industrial Park need to use KY 115 to access I-24. Furthermore, the intersection of KY 115 and US 41 in Prembroke does not have the required truning radi | 2 | West | 28.8247 | 4.7698 | 11.9072 | 5.7216 | 1.9759 | 0 | 4.4502 | 0 | 29
Y | 2 | Pennyrile ADD | IP20100039 |  |  |  | New Connector from KY 176 to US 62 on the east side of Greenville. | New Route | Muhlenberg | 089-US-0062 -000 | 10.541 | 12.386 | 1.845 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 1600000 |  | 800000 |  | 4000000 |  | 2012-01-27 10:25 |  | This is traffic congestion in downtown Greenville and poor turing radius for trucks at intersection. This will bypass those congested areas.
Y | 2 | Pennyrile ADD | IP20100043 |  |  |  | Upgrade the Edward T. Breathitt PKY to accommodate I-69. | Reconstruction | Hopkins | 054-EB-9004 -000 | 28.095 | 34.256 | 6.161 | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 75000000 |  | 2012-02-01 15:22
Y | 2 | Pennyrile ADD | IP20110105 |  |  |  | Reduce congestion with a new route from US 41A/Gate 4 entrance to KY 115 in Oak Grove | New Route | Christian | 024-KY-0400 -000 | 0 | 1.377 | 1.377 | Construct Road in New Location | 0 |  | 0 |  | 700000 |  | 2000000 |  | 1200000 |  | 5000000 |  | 2017-05-19 10:03 |  | There is severe peak-hour traffic congestion problems on KY 911 and State Line Road between KY 115 and US 41A in the City of Oak Grove. These are east west routes that lead into and away from the main gates of US Army Ft. Campbell Military Base. This pro | Clarksville MPO | West | 36.8574 | 8.1031 | 4.8454 | 10.2835 | 4.8282 | 8.7973 | 0 | 0 | 37
Y | 2 | Evansville-Henderson MPO | IP20110120 |  |  |  | Address safety issues and improve mobility at the intersection of KY 351 and Garden Mile Road. | Minor Widening | Henderson | 051-CS-1132 -000 | 0 | 0.1 | 0.1 | Improve Intersection | 26 |  | 0 |  | 350000 |  | 500000 |  | 1000000 |  | 1500000 |  | 2019-01-14 15:17 | Improve intersection efficiency. | Install an additional lane on Garden Mile Rd at KY 351/2nd St to separate right-turn and left-turn traffic. This intersection is near the High School and is congested.
Y | 2 | Owensboro MPO | IP20110168 |  |  |  | Look at access Management and make intersection improvements along this section | Reconstruction | Daviess | 030-KY-2831 -000 | 0 | 1.641 | 1.641 | Access Consolidation | 25 | Y | 250000 |  | 400000 |  | 1000000 |  | 1000000 |  | 2350000 |  | 2014-12-09 11:37 | The purpose of this project is to improve safety, reliability and mobility along KY 2831 (Frederica Street), better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 2 | Green River ADD | IP20120014 |  |  |  | Address safety concerns of intersection of KY 140 and KY 815 in McLean County. | Safety-Haz-Elm | McLean | 075-KY-0140 -000 | 7.239 | 7.259 | 0.02 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 400000 |  | 400000 |  | 900000 |  | 2017-05-19 13:10 | Address safety issues on KY 140 at the intersection with KY 185. | The following need has been identified for this project: Improve Roadway Safety | GREEN RIVER ADD | West | 19.2285 | 0.19931 | 10.6186 | 4.8711 | 3.5395 | 0 | 0 | 0 | 19
Y | 2 | Green River ADD | IP20120015 |  |  |  | Address curvature of KY 69 from Grove Rd to Goshen Rd. | Safety-Haz-Elm | Ohio | 092-KY-0069 -000 | 9.626 | 11.301 | 1.675 | Other Improvement Types | 0 |  | 0 |  | 450000 |  | 650000 |  | 700000 |  | 5000000 |  | 2013-05-03 14:52 |  | KY-69 is a rural secondary road with 10 ft lanes and 2 ft paved shoulders. This section of roadway contains numerous curves.
Y | 2 | Green River ADD | IP20120035 |  |  |  | Improve safety and service concerns of KY 69 from Kirk Lane/Combs Bridge Road to Marvins Chapel Road/Humble Valley Road. | Safety-Haz-Elm | Ohio | 092-KY-0069 -000 | 19.319 | 21.292 | 1.973 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 560000 |  | 700000 |  | 5000000 |  | 2013-05-03 14:57 |  | KY-69 is a rural secondary road with 10 ft lanes and 2 ft paved shoulders. This section of roadway contains numerous curves and hills with vertical and horizontal deficiencies.
Y | 2 | Green River ADD | IP20120038 |  |  |  | Address flooding issues from Ben Vise Road to 1/4 mile south toward Morganfield. | Safety-Haz-Elm | Union | 113-KY-0130 -000 | 11.312 | 11.437 | 0.125 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 100000 |  | 500000 |  | 1200000 |  | 2013-05-03 15:09 |  | KY-130 is a rural 10 ft wide 2 lane route that provides access from the City of Uniontown to the City of Morganfield, the county seat. The area along the route is low lying farmland that floods easily.
Y | 2 | Green River ADD | IP20120039 |  |  |  | Improve turning radius of KY 130 north of KY 141. | Reconstruction | Union | 113-KY-0130 -000 | 14.2 | 14.4 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 150000 |  | 250000 |  | 800000 |  | 2013-05-06 09:18 |  | KY-130 is a rural two lane route with 10 ft lanes and 2 ft shoulders. This route provides access from the City of Uniontown to the City of Morganfield which is the county seat.
Y | 2 | Green River ADD | IP20120040 |  |  |  | Address flooding issues from Hilltop Road to 6th St in Uniontown. | Safety-Haz-Elm | Union | 113-KY-0130 -000 | 15.219 | 15.45 | 0.231 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 150000 |  | 250000 |  | 1200000 |  | 2013-05-06 09:16 |  | KY-130 is a rural two lane roadway with 10 ft lanes and 2 ft shoulders. This project is located within the City of Uniontown and provides access to the Uniontown Park. No sidewalks exist.
Y | 2 | Green River ADD | IP20120041 |  |  |  | Address need for new truck route from US 41 to KY 370 reducing truck traffic through the City of Sebree. *This will have new state number. it is not an extention of US 41. | New Route | Webster | 117-US-0041 -000 | 8.743 | 9.461 | 0.718 | Construct Road in New Location | 0 |  | 0 |  | 600000 |  | 400000 |  | 250000 |  | 2000000 |  | 2013-05-03 15:24 |  | There is a significant percentage of trucks that traverse through the City of Sebree creating a safety concern.
Y | 2 | Green River ADD | IP20120042 |  |  |  | Access safety and service of the KY 132 and KY 494 intersection. | Safety-Haz-Elm | Webster | 117-KY-0132 -000 | 25.94 | 26 | 0.06 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 75000 |  | 250000 |  | 500000 |  | 2013-05-06 09:15 |  | KY 132 from KY 494 to KY 56 in Sebree is a rural two-lane project with lane widths ranging from 10 ft to 13 ft.
Y | 2 | Pennyrile ADD | IP20120048 |  |  |  | New Connector route from US 68 Bypass, just east of Lowes, northward to the Wal-Mart parking lot. | New Route | Christian | 024-US-0041A -000 | 12.68 | 13.19 | 0.51 | Other Improvement Types | 0 | Y | 0 |  | 500000 |  | 800000 |  | 500000 |  | 4000000 |  | 2013-05-03 13:20 |  | New Connector route from US 68 Bypass, just east of Lowes, northward to the Wal-Mart parking lot to relieve traffic congestion at the intersection of Clinic Dr. and US 41A which is mainly generated by the traffic trying to access the Wal-Mart store. The
Y | 2 | Pennyrile ADD | IP20130002 |  |  |  | Address geometric and safety issues at US 41A/Skyline Dr and Old Clarksville Pike intersection | Reconstruction | Christian | 024-US-0041A -000 | 14.045 | 14.245 | 0.2 | Other Improvement Types | 0 | Y | 0 |  | 250000 |  | 500000 |  | 2000000 |  | 500000 |  | 2015-08-05 13:53 |  | The intersection has a high CFR and traffic in the north bound lane on Old Clarksville Pike has to wait for the traffic light to cycle twice to get throught the intersection.
Y | 2 | Green River ADD | IP20130012 |  |  |  | Address flooding issues of KY-85 just east of KY-2226 intersection. | Safety-Haz-Elm | McLean | 075-KY-0085 -000 | 6.65 | 6.85 | 0.2 | Maintenance Improvement | 10 |  | 0 |  | 250000 |  | 100000 |  | 250000 |  | 1200000 |  | 2017-05-19 13:09 | Address safety issues along KY 85 east of KY 2226 intersection. | The following need has been identified for this project: Improve Roadway Safety. | GREEN RIVER ADD | West | 3.0137 | 0.90034 | 2.1134 | 0 | 0 | 0 | 0 | 0 | 3
Y | 2 | Green River ADD | IP20130028 |  |  |  | Address condition, safety and service issues of US-431 from KY-250 to the Daviess County Line. Breakout project of 02 075 B0431 62.00. | Major Widening | McLean | 075-US-0431 -000 | 9.852 | 11.573 | 1.721 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 750000 |  | 900000 |  | 4500000 |  | 2015-08-05 14:03 |  | US 431 is a 12 ft. route with 2 ft. shoulders that has multiple access points thereby creating a safety concern. US 431 provides direct access from McLean County to Daviess County thus is frequently congested with farming vehicles/equipment. US 431 is al
Y | 2 | Green River ADD | IP20130032 |  |  |  | Address flooding issues on KY-130 just north of KY-666. | Safety-Haz-Elm | Union | 113-KY-0130 -000 | 12.5 | 12.677 | 0.177 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 100000 |  | 250000 |  | 1200000 |  | 2013-05-03 15:12 |  | KY-130 is a rural 10 ft wide 2 lane route that provides access from the City of Uniontown to the City of Morganfield, the county seat. The area along the route is low lying farmland that floods easily.
Y | 2 | Green River ADD | IP20130033 |  |  |  | Address the service, safety and condition of KY-56 from KY-141 to Webster C/L. | Major Widening | Union | 113-KY-0056 -000 | 19.662 | 23.209 | 3.547 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1380000 |  | 1450000 |  | 8900000 |  | 2013-05-03 15:08 |  | KY 56 from Morganfield (MP 13.035) to US 41A in Webster Co (MP 5.332) is a rural state secondary minor arterial with two 9 ft. driving lanes and 2 ft. shoulders to the Union/Webster Co line and 10 ft lanes from MP 0.000 to 5.332 in Webster Co. This route
Y | 2 | Green River ADD | IP20130034 |  |  |  | Address the safety and service concerns of KY-56 from Union C/L to US 41A. | Major Widening | Webster | 117-KY-0056 -000 | 0 | 5.332 | 5.332 | Other Improvement Types | 0 |  | 0 |  | 1750000 |  | 3000000 |  | 4000000 |  | 13500000 |  | 2013-05-03 15:19 |  | KY 56 from Morganfield (MP 13.035) to US 41A in Webster Co (MP 5.332) is a rural state secondary minor arterial with two 9 ft. driving lanes and 2 ft. shoulders to the Union/Webster Co line and 10 ft lanes from MP 0.000 to 5.332 in Webster Co. This route
Y | 2 | Green River ADD | IP20130046 |  |  |  | Improve sight distance at Heflin Road intersection. | Safety-Haz-Elm | Ohio | 092-KY-2668 -000 | 1.816 | 2.016 | 0.2 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 75000 |  | 200000 |  | 500000 |  | 2013-05-08 15:43 |  | The intersection of KY 2668 and Heflin Road is located at the bottom of a slight vertical rise that contributes to the sight distance concern.
Y | 2 | Green River ADD | IP20130047 |  |  |  | Address need for new interchange access to the Western KY Parkway at KY-505. | New Interchange | Ohio | 092-WK-9001 -000 | 81.95 | 82.25 | 0.3 | Construct Road in New Location | 0 | Y | 0 |  | 1000000 |  | 750000 |  | 100000 |  | 5000000 |  | 2013-05-08 15:41 |  | Need additional interchange at KY 505 near Rosine to provide access to home of Bill Monroe to promote tourism and economic growth in the area.
Y | 2 | Pennyrile ADD | IP20130152 |  |  |  | To correct Safety Issues at the intersection of KY 293 and Olney Rd. | Safety-Haz-Elm | Caldwell | 017-KY-0293 -000 | 9.035 | 9.235 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 250000 |  | 250000 |  | 2000000 |  | 2014-12-08 11:25 | Improve safety | There is a lot of truck traffic entyering the highway at this intersection and it needs to be improved to address safety concerns.
Y | 2 | Owensboro MPO | IP20130153 |  |  |  | Foors Lane -- To improve traffic flow and safety | Reconstruction | Daviess | 030-KY-3143 -000 | 0 | 1.829 | 1.829 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 3500000 |  | 3000000 |  | 12000000 |  | 2014-12-08 11:29 | The purpose of this project is to improve safety, reliability and mobility along KY 3143 (Foors Lane), better control access and reduce congestion. | This is a heavily traveled (including a lot of school traffic) route between US 231 and KY 54. It is a narrow route with some vertical and horizontal deficiencies that need to be reconstructed to provide for safety.
Y | 2 | Pennyrile ADD | IP20130154 |  |  |  | Address ditch erosion concerns on KY 1380 | Drainage Improvement | Muhlenberg | 089-KY-1380 -000 | 0.204 | 0.404 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 250000 |  | 100000 |  | 400000 |  | 2019-02-28 10:52 | Address ditch erosion | There is a large ditch near the end of a recently completed Safe Routes to School project that will bring more pedestrians to the area.
Y | 2 | Evansville-Henderson MPO | IP20140010 |  |  |  | Improve sight distance in both directions near the entrance to South Heights Elementary School for drivers and pedestrians. | Reconstruction | Henderson | 051-KY-0136 -000 | 20.309 | 20.401 | 0.092 | Modernize Roadway-Urban | 16 |  | 0 |  | 250000 |  | 350000 |  | 350000 |  | 2000000 |  | 2018-12-11 15:19 | Improve safety at school entrance and proposed pedestrian crossing. | Reconstruct KY 136/Madison St at the South Heights Elementary School entrance to eliminate the vertical curve and improve sight distance.
Y | 2 | Evansville-Henderson MPO | IP20140012 |  |  |  | Provide standard geometry. | Reconstruction | Henderson | 051-KY-1078 -000 | 6.46 | 8.226 | 1.766 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 600000 |  | 6500000 |  | 2019-01-14 14:50 | Improve safety | Improve safety by providing standard geometry and cross section.
Y | 2 | Evansville-Henderson MPO | IP20140013 |  |  |  | Upgrade the route to provide a standard geometric cross section. | Reconstruction | Henderson | 051-KY-1539 -000 | 0.882 | 2 | 1.118 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 500000 |  | 600000 |  | 4200000 |  | 2018-12-11 11:39 | Improve traffic flow and safety. | Reconstruct Zion-Larue Rd from Kimsey Ln to the curve to provide a standard cross section.
Y | 2 | Evansville-Henderson MPO | IP20140014 |  |  |  | Construct new connector from KY 1539 near curve to Wathen Lane to Provide access. | New Route | Henderson | 051-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 25000 |  | 1000000 |  | 650000 |  | 250000 |  | 6000000 |  | 2018-12-11 13:44 | Provide a secondary connection between a busy section of US 60 to KY 1539 to provide economic development options and reduce congestion on the existing network. | Construct a new alignment with a grade separated rail crossing between a area of growth to adjacent office and retail facilities.
Y | 2 | Pennyrile ADD | IP20140021 |  |  |  | To break out a small section of PIF # 02 017 D0091 4.00 and expand it to address issues with overpass structure and ramp approaches. | Safety-Haz-Elm | Caldwell | 017-KY-0091 -000 | 12.2 | 12.433 | 0.233 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 200000 |  | 1000000 |  | 3000000 |  | 2015-08-05 13:54 | Improve safety | There is a sight distance issue with the ramps since the overpass structure is on a skew. Improvements are needed to provide a safer route around the interchange.
Y | 2 | Pennyrile ADD | IP20140022 |  |  |  | To reconstruct KY 91 from MP 12.433 near the I-69 interchange to the KY 139 Intersection. | Reconstruction | Caldwell | 017-KY-0091 -000 | 12.433 | 13.905 | 1.472 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 1500000 |  | 1750000 |  | 5000000 |  | 2017-05-19 09:47 | Improve congestion and traffic flow along KY 91. | This project is needed to reduce congestion and provide better traffic flow during peak traffic hours. This section has 2/9 lanes with a high ADT. This is the main access route to the Caldwell County High School and reconstruction will provide better acce | PENNYRILE ADD | West | 67.9321 | 5.8488 | 7.4227 | 10.3995 | 0 | 7.8694 | 0 | 6.3918 | 38 | 15 | 15
Y | 2 | Green River ADD | IP20140029 |  |  |  | Address safety concern of curvature and elevation of the KY 132 from just west of a bridge (B17B0064N) to the intersection of KY 857. This project is a breakout of 02 117 D0132 88.20 | Safety-Haz-Elm | Webster | 117-KY-0132 -000 | 12.2 | 12.379 | 0.179 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 250000 |  | 250000 |  | 1000000 |  | 2015-02-06 13:37 |  | KY 132 is a two lane roadway with 9 ft. lanes and 3 ft. combination shoulders. The roadway from KY 857 to the Nall Creek bridge (117B00064N) has an elevated curvature creating a potential safety hazard.
Y | 2 | Green River ADD | IP20140039 |  |  |  | Address safety concerns of narrow bridges, box culverts and lack of shoulders on KY 492 from US 60 to KY 109. | Safety-Haz-Elm | Union | 113-KY-0492 -000 | 2.482 | 5.154 | 2.672 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 1000000 |  | 1000000 |  | 8000000 |  | 2015-02-03 15:14 |  | KY 492 from US 60 to KY 109 is a rural two-lane route with 9 ft. lanes and 4 ft. shoulders. Four narrow bridges located create passage problems for movement of farming equipment. Three of the bridges are classified as structurally deficient.
Y | 2 | Green River ADD | IP20140040 |  |  |  | Address safety concerns of narrow lane and shoulder widths from KY 132 to KY 56 | Minor Widening | Webster | 117-KY-0283 -000 | 0 | 5.624 | 5.624 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 750000 |  | 1000000 |  | 6000000 |  | 2015-02-06 13:44 |  | KY 283 is a rural two lane route with narrow 8 ft. lanes and 2 ft. shoulders. There are several poultry operations located along this route.
Y | 2 | Pennyrile ADD | IP20150008 |  |  |  | Reconstruct the Five-leg intersection at KY 91 (Main St.) and East Washington St. to improve safety and traffic flow issues. see Project Z on the 2014 Princeton SUAS. | Reconstruction | Caldwell | 017-KY-0091 -000 | 11.589 | 11.728 | 0.139 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 200000 |  | 500000 |  | 2600000 |  | 2015-01-29 08:39 | Improve geometrics and reduce hazards | The KY 91 and E. Washington/Hawthorne Street intersection has poor geometrics for trucks as well as poor sight distances for traffic feeding into the intersection from E. Washington St. The traffic flow at this intersection is poor due to the current 5-wa
Y | 2 | Pennyrile ADD | IP20150009 |  |  |  | Reconstruct intersection CS-1102 (W. Green ST.) and CS-1109 (N. Seminary St) on the designated intercity truck route to improve truck turning geometrics. | Reconstruction | Caldwell | 017-CS-1102 -000 | 0.075 | 0.152 | 0.077 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 300000 |  | 900000 |  | 1050000 |  | 2015-01-29 13:58 | Improve truck access and poor geometrics. | Trucks do not have an adequate turning radius at this intersection. These streets are part of the designated Princeton Truck Route.
Y | 2 | Owensboro MPO | IP20150011 |  |  |  | To provide a left turn lane at the intersection of KY 298 (Old Hartford Road) and East 26th Street. This project will be made in active, and 02 D0298 9.00 will cover this proposed turn lane. Cost are current and will be moved to new PIF. | Minor Widening | Daviess | 030-KY-0298 -000 | 9.458 | 9.658 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 500000 |  | 750000 |  | 1000000 |  | 2015-02-20 13:03 | This project will be made in active, and 02 D0298 9.00 will cover this proposed turn lane. | This project will be made in active, and 02 D0298 9.00 will cover this proposed turn lane.
Y | 2 | Owensboro MPO | IP20150027 |  |  |  | US 60 - Increase the length of the on-ramp from US 60 to the Audubon Parkway to improve safety. | Reconstruction | Daviess | 030-US-0060 -000 | 10.837 | 10.839 | 0.002 | Innovative Interchange | 40 | Y | 0 |  | 200000 |  | 150000 |  | 250000 |  | 700000 |  | 2018-11-14 14:31 | The purpose of this project is to improve safety, reliability and mobility through the intersection of US 60 and the Audubon Parkway, better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 2 | Owensboro MPO | IP20150028 |  |  |  | US 60 - Increase the length of the on-ramp from US 60 to the Natcher Parkway to improve safety. | Reconstruction | Daviess | 030-US-0060 -000 | 17.498 | 17.499 | 0.001 | Innovative Interchange | 40 | Y | 0 |  | 200000 |  | 100000 |  | 250000 |  | 700000 |  | 2015-02-20 12:59 | The purpose of this project is to improve safety, reliability and mobility through the intersection of US 60 and the William Natcher Parkway, better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 2 | Owensboro MPO | IP20150046 |  |  |  | Improve Safety and Mobility along the Natcher Parkway between the interchange with the Western KY Parkway,to US 60, near Owensboro, by providing improvements that will bring the Natcher Parkway to interstate standards. | Spot Improvement | Daviess | 030-WN-9007 -000 | 61.553 | 72.264 | 10.711 | Full Control to Interstate | 10 | Y | 0 |  | 2500000 |  | 2500000 |  | 2500000 |  | 3640000 |  | 2015-03-16 11:10 | The purpose of this project is to improve safety, reliability and mobility along WN 9007 (William Natcher Parkway), better control access and reduce congestion. | this project includes upgrades to the Natcher Parkway in order to get it designated an Interstate spur. See I-65/I-66/I-69 Spur Study 2014. Note- the estimate does not include costs for any of the interchanges.
Y | 2 | Green River ADD | IP20150069 |  |  |  | Improve safety and mobility of the KY 69 and William Natcher Parkway interchange to address interstate highway standards. | Reconstruction | Ohio | 092-WN-9007 -000 | 49.885 | 49.888 | 0.003 | Innovative Interchange | 40 | Y | 0 |  | 1500000 |  | 1000000 |  | 750000 |  | 11000000 |  | 2015-08-05 12:50 |  | The William Natcher (WN 9007) and the KY 69 interchange was designed as a toll interchange and does not meet interstate highway design standards. I-65/I-66/I-69 Spur Study 2014
Y | 2 | Green River ADD | IP20150085 |  |  |  | Improve safety and mobility of the William Natcher Parkway (WN 9007) from the Western Kentucky Parkway (WK 9001)interchange in Ohio County to the Ohio/Butler County Line. | Reconstruction | Ohio | 092-WN-9007 -000 | 37.143 | 43.343 | 6.2 | Modernize Roadway-Rural | 26 | Y | 0 |  | 250000 |  | 150000 |  | 150000 |  | 675000 |  | 2015-03-16 11:17 |  | The William Natcher Parkway (WN 9007) does not meet interstate highway design standards. I-65/I-66/I-69 Spur Study 2014
Y | 2 | Green River ADD | IP20150141 | 2-8852 |  | A | CORRECT LINE OF SIGHT WITH INTERSECTION OF KY 56 & KY 1233. (14CCN)(18CCN) | RECONSTRUCTION(O) | McLean | 075-KY-0056 -000 | 6 | 6.33 | 0.33 | Improve Intersection | 26 |  |  |  | 0 |  | 60000 |  | 60000 |  | 1670000 | 2020 | 2019-03-11 09:54 | Address safety issues at the intersection of KY 56 and KY 1233. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 57.6478 | 1.8832 | 14.7423 | 3.634 | 1.5808 | 0 | 0 | 5.8076 | 28 | 15 | 15
Y | 2 | Pennyrile ADD | IP20150165 | 2-153 |  | A | NEW CONNECTOR FROM HOPKINSVILLE ROAD (KY-91) TO WILSON WAREHOUSE ROAD (KY-293) NORTHEAST OF PRINCETON. (06CCR)(10CCR)(12CCR)(14CCR)(16CCR)(18CCN) | NEW ROUTE(O) | Caldwell | 017-KY-0293 -000 | 6.151 | 6.971 | 0.82 | Construct Road in New Location | 0 | [5 empty] | 1910000 | 2021 | 1450000 | 2023 | 11980000 | 2024 | 2019-03-08 10:57 | Provide a new Truck Route to the south side of the City of Princeton which will bypass an inter city truck route with poor geometrics. This project is recommended by the Princeton Comprehensive Plan. | The existing Truck Route through the City of Princeton has narrow lanes and poor truck turning radius. The existing truck route goes through city residential streets that have poor geometrics. The Truck Route is routed to avoid two (2) railroad underpa | 2 | West | 28.3436 | 2.0893 | 6.9588 | 7.0103 | 2.3024 | 6.7354 | 3.2474 | 0 | 28
Y | 2 | Pennyrile ADD | IP20150190 | 2-8703 |  | A | IMPROVE KY-107 FROM GATEWAY LANE TO KY-380.(12CCN)(14CCR) | MINOR WIDENING(O) | Christian | 024-KY-0107 -000 | 16.823 | 17.169 | 0.346 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 960000 | 2022 | 1210000 | 2023 | 2000000 | 2024 | 2019-03-11 09:29 |  |  | 2 | West | 78.128 | 7.4708 | 12.1649 | 10.5541 | 2.3024 | 9.6907 | 0 | 5.945 | 48 | 15 | 15
Y | 2 | Pennyrile ADD | IP20150211 | 2-8305 |  | A | IMPROVE NORTH MAIN STREET FROM HOSPITAL DRIVE TO KY-281. (06CCN)(12CCR)(18CCR) | MAJOR WIDENING(O) | Hopkins | 054-US-0041 -000 | 16.989 | 17.548 | 0.559 | Modernize Roadway-Rural | 26 |  |  |  | 770000 | 2021 | 970000 | 2021 | 1230000 | 2022 | 7580000 | 2024 | 2019-03-11 09:20 | Improve congestion, safety and traffic flow | This is a congested route with strip commercial development along the route. | 2 | West | 89.1907 | 9.457 | 12.5773 | 13.3247 | 3.7801 | 9.9656 | 4.3127 | 5.7732 | 59 | 15 | 15
Y | 2 | Green River ADD | IP20150230 | 2-8400 | 401783 | A | SPOT IMPROVEMENTS AT THE INTERSECTION OF US-431 AND KY-250. (08CCN)(12CCR)(18CCN) | SPOT IMPROVEMENTS(O) | McLean | 075-US-0431 -000 | 9.8 | 9.9 | 0.1 | Improve Intersection | 26 |  |  |  | 0 |  | 200000 | 2019 | 180000 | 2019 | 940000 | 2020 | 2019-03-11 09:22 | Address safety issues at the intersection of US 431 and KY 250. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 55.6993 | 6.6873 | 14.1753 | 9.6649 | 1.9759 | 0 | 3.8316 | 4.3643 | 41 |  | 15
Y | 2 | Pennyrile ADD | IP20150259 | 2-193 |  | A | SOUTHERN CONNECTOR FROM KY 139 TO KY 91, CALDWELL COUNTY. (2005HPP-KY162) | NEW ROUTE(O) | Caldwell | 017-KY-0139 -000 | 10.4 | 11.347 | 0.947 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 770000 | 2025 | 520000 | 2025 | 6490000 | 2025 | 2019-03-08 10:52 | Improve truck access. | This is a proposed New Connector route for Truck Traffic to bypass two low Railroad underpasses on KY 293 (S. Jefferson St) and Cadiz St. Both the Rail Underpasses restrict trucks over 12 feet high. | 2 | West | 20.2388 | 3.8557 | 0 | 7.7577 | 2.3024 | 6.323 | 0 | 0 | 20
Y | 2 | Pennyrile ADD | IP20150263 | 2-8802 |  | A | WIDEN KY-181 BY FOUR FEET ON EACH SIDE FROM INTERSECTION 601 TO WENDELL FORD CENTER. (14CCN)(18CCN) | MINOR WIDENING(O) | Muhlenberg | 089-KY-0181 -000 | 12.767 | 15.751 | 2.984 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 790000 | 2020 | 1900000 | 2021 | 3490000 | 2022 | 2019-03-11 09:34 |  |  | 2 | West | 56.2363 | 2.6323 | 11.7526 | 10.2706 | 1.5808 | 0 | 0 | 0 | 26 | 15 | 15
Y | 2 | Owensboro MPO | IP20150271 | 2-8854 |  | A | IMPROVE KY-3143 FROM KY-3335 TO KY 54. (14CCN) | MINOR WIDENING(O) | Daviess | 030-KY-3143 -000 | 1.829 | 2.958 | 1.129 | Install Two-way Left Turn Lane | 28 |  |  |  | 820000 | 2021 | 3160000 | 2024 | 3650000 | 2024 | 7600000 | 2025 | 2019-03-11 09:58 | The purpose of this project is to improve safety, reliability and mobility along KY 3143, better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 2 | West | 78.6538 | 8.4605 | 10.9278 | 11.5851 | 4.2784 | 6.9416 | 0 | 6.4605 | 49 | 15 | 15
Y | 2 | Pennyrile ADD | IP20150275 |  |  |  | WIDEN US-41A FROM YORKWOOD PLACE TO US 41 / KY 281. (SECTION 2) (2012BOP) | Major Widening | Hopkins | 054-US-0041A -000 | 0 | 1.246 | 1.246 | Arterial to Partial Control | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11000000 |  | 2016-09-08 08:48
Y | 2 | Pennyrile ADD | IP20150320 | 2-8803 |  | A | STRAIGHTEN DEAN ROAD INTERSECTION OF 189 BYPASS TO KY 181 NORTH NEAR THE INTERSECTION WITH THE WKY PARKWAY, WENDELL FORD NATIONAL GUARD CENTER, AND JOB CORP. (14CCN)(18CCN) | RECONSTRUCTION(O) | Muhlenberg | 089-KY-2533 -000 | 0 | 2.023 | 2.023 | Modernize Roadway-Rural | 26 |  |  |  | 750000 | 2019 | 530000 | 2020 | 820000 | 2021 | 6750000 | 2022 | 2019-03-11 09:41 | Improve safety of intersection | Improve safety | PENNYRILE ADD | West | 31.5 | 3.244 | 8.6082 | 8.9433 | 4.8969 | 5.8076 | 0 | 0 | 32
Y | 2 | Pennyrile ADD | IP20150322 |  |  |  | WIDEN US-41A FROM INDUSTRIAL DRIVE TO YORKWOOD PLACE. (SECTION 1) (2012BOP) | Major Widening | Hopkins | 054-US-0041A -000 | 1.246 | 3.275 | 2.029 | Arterial to Partial Control | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 11000000 |  | 2016-10-26 15:12 | Improve traffic congestion and safety. | This is a major truck route and an access road to a major industrial park.
Y | 2 | Pennyrile ADD | IP20150342 | 2-804 / 2-804.20 |  | A | CONSTRUCT CENTER ST CONNECTOR RD BEGIN AT CENTER ST/PROCEED TO CSX RR, SECT.1, 5,173 LI. FT.PROCEED THRU PORTION OF SECT. 2,END AT I-SECTION OF CONNECTOR RD BEING CONSTRUCTED WITH ISLAND FD DR.ALL DEEDED TO CITY-MADISONVILLE, ALL 100FT WIDE.(14CCR)(18CCN) | NEW ROUTE(O) | Hopkins | 054-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 | 2018 | 3000000 | 2019 | 2600000 | 2020 | 7580000 | 2021 | 2018-12-04 08:34 | Reduce traffic congestion on Main St in Madisonville and improve traffic flow. | This new route will provide a new North/South Connector between Center Street (KY 70) and Island Ford Rd (KY 281), as well as a new route over the CSX Railroad. It will connect two (2) major commercial areas in the City of Madisonville | PENNYRILE ADD | West | 41.5095 | 9.2715 | 0 | 14.3686 | 3.7801 | 9.9313 | 4.1581 | 0 | 42
Y | 2 | Pennyrile ADD | IP20150363 | 2-136 |  | A | EXTEND KY-1682 FROM THE E.T. BREATHITT PARKWAY TO US-68/KY-80 EAST OF HOPKINSVILLE (HOPKINSVILLE NORTHEAST BYPASS). (16CCR) (18CCN) | NEW ROUTE(O) | Christian | 024-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y |  |  | 0 | 2024 | 3500000 | 2025 | 1900000 | 2025 | 28080000 |  | 2019-03-11 07:49 |  |  | 2 | West | 57.3969 | 7.2852 | 8.7113 | 11.2113 | 0.65292 | 9.8969 | 4.6392 | 0 | 42 |  | 15
Y | 2 | Green River ADD | IP20150371 | 2-8812 |  | A | REPLACE, IMPROVE ALIGNMENTS AND APPROACHES, AND ADDRESS SAFETY ISSUES WITH BRIDGES ON KY-136 FROM KY-56 IN MCLEAN COUNTY TO US-231 IN OHIO COUNTY. (14CCN) | RECONSTRUCTION(O) | McLean | 075-KY-0136 -000 | 0 | 19.334 | 19.334 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 490000 | 2022 | 1350000 | 2022 | 14730000 | 2024 | 2019-03-11 09:51 | Address safety issues of bridges approaches and alignments along KY 136 in McLean County and Ohio County. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 79.1375 | 1.6976 | 13.1443 | 14.0206 | 4.6048 | 5.6701 | 0 | 10 | 49 | 15 | 15
Y | 2 | Green River ADD | IP20150396 |  |  |  | RECONSTRUCT AND WIDEN FROM MCLEAN/MUHLENBURG COUNTY LINE) TO LIVERMORE. (08CCN)(10CCR) | Minor Widening | McLean | 075-US-0431 -000 | 0 | 5.5 | 5.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1500000 |  | 1250000 |  | 4000000 |  | 2015-08-05 14:07
Y | 2 | Green River ADD | IP20150399 |  |  |  | Widen/reconstruct KY from Centertown to Hartford. (14CCN) | Minor Widening | Ohio | 092-KY-0069 -000 | 7.556 | 13.317 | 5.761 | Modernize Roadway-Rural | 26 |  | 0 |  | 1750000 |  | 2500000 |  | 4800000 |  | 15250000 |  | 2015-09-18 08:34
Y | 2 | Evansville-Henderson MPO | IP20150435 |  |  |  | PADUCAH-HENDERSON; RECONSTRUCT US-60 FROM THE CORYDON BYPASS (CORYDON-GENEVA ROAD) TO THE HENDERSON BYPASS (KY-425).(04CCR) | Major Widening | Henderson | 051-US-0060 -000 | 5.531 | 8.707 | 3.176 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1560000 |  | 5760000 |  | 4880000 |  | 24200000 |  | 2016-10-17 14:32 | Improve traffic flow and safety. | RECONSTRUCT US-60 FROM THE CORYDON BYPASS (CORYDON-GENEVA ROAD) TO THE HENDERSON BYPASS (KY-425).(04CCR).
Y | 2 | Pennyrile ADD | IP20150442 |  |  |  | U.S. 41A PHASE II DESIGN AND RIGHT-OF-WAY. (2005HPP-KY135)(SEE 2-137.01 FOR "STP" COMPONENT). | Major Widening | Hopkins | 054-US-0041A -000 | 0 | 3.426 | 3.426 | Arterial to Partial Control | 23 |  | 0 |  | 0 |  | 0 |  | 0 |  | 321000 |  | 2017-03-09 09:49 | Improve congestion, traffic flow and safety | This is one of the most congested routes in the region.
Y | 2 | Green River ADD | IP20160022 |  |  |  | INSTALL INTERSECTION CONFLICT WARNING SYSTEM (ICWS) AT THE INTERSECTION OF US 431 AND KY 85. (2016BOP) | Safety-Haz-Elm | McLean | 075-US-0431 -000 | 2.75 | 2.8 | 0.05 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 99000 |  | 2016-12-09 10:54
Y | 2 | Green River ADD | IP20160024 | 2-8951 |  | A | IMPROVE SAFETY ON KY 54 BY UPGRADING MP 7.0 TO MP 8.0 TO THREE LANES INCLUDING CURB AND GUTTER AND ADDRESSING TWO SHARP TURNS. (16CCN)(18CCN) | MINOR WIDENING(O) | Ohio | 092-KY-0054 -000 | 7.047 | 7.995 | 0.948 | Modernize Roadway-Rural | 26 |  |  |  | 820000 | 2021 | 1220000 | 2023 | 2440000 | 2024 | 7300000 | 2024 | 2019-03-11 10:01 | Address safety issues along KY 54 from KY 1700 to Marsh Lane in Fordsville. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 62.7921 | 5.3265 | 7.0619 | 9.5103 | 4.6048 | 0 | 0 | 6.2887 | 33 | 15 | 15
Y | 2 | Green River ADD | IP20160026 |  |  |  | PADUCAH-HENDERSON; RECONSTRUCT US-60 FROM WAVERLY BYPASS TO CORYDON BYPASS. (PRIORITY SECTION)(08CCR)(12CCR)(14CCR) | Reconstruction | Union | 113-US-0060 -000 | 23.86 | 26.069 | 2.209 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1740000 |  | 5680000 |  | 2250000 |  | 17100000 |  | 2016-12-09 11:14
Y | 2 | Green River ADD | IP20160027 |  |  |  | PADUCAH-HENDERSON; MORGANFIELD BYPASS TO WAVERLY (08CCR)(12CCR)(14CCR) | Major Widening | Union | 113-US-0060 -000 | 17.6 | 21.5 | 3.9 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 0 |  | 3680000 |  | 2610000 |  | 27020000 |  | 2016-12-09 11:16
Y | 2 | Green River ADD | IP20160028 |  |  |  | PADUCAH-HENDERSON; WAVERLY BYPASS. (12CCR)(14CCR) | Bypass | Union | 113-US-0060 -000 | 21.013 | 23.231 | 2.218 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 1730000 |  | 1480000 |  | 20550000 |  | 2016-12-09 11:18
Y | 2 | Green River ADD | IP20160029 | 2-8955 |  | A | IMPROVE ROADWAY TO REDUCE FLOODING ON US-60 FROM EAST OF HOUSE BRIDGE ROAD (CR-1027) TO UNION/HENDERSON COUNTY LINE. (16CCN) | RECONSTRUCTION(O) | Union | 113-US-0060 -000 | 23.8 | 25.2 | 1.4 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2019 | 190000 | 2023 | 240000 | 2023 | 5480000 | 2024 | 2019-03-11 10:47 | Address safety issues along US 60 from East of CR 1027 (House Bridge Road) to the Henderson County Line. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 76.1237 | 6.7079 | 12.1134 | 5.4639 | 2.268 | 8.5223 | 4.6907 | 6.3574 | 46 | 15 | 15
Y | 2 | Evansville-Henderson MPO | IP20160034 |  |  |  | (I-69 CORRIDOR) EXTENDING I-69 CORRIDOR IMPROVEMENTS FROM (MP 73.40) NORTH TO KY 425 (MP 76.267). (2014BOP) | Reconstruction | Henderson | 051-I -0069 -000 | 137.141 | 148.09 | 10.949 | Modernize Roadway-Rural | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 14:27 | ? | ?
Y | 2 | Evansville-Henderson MPO | IP20160035 |  |  |  | INSTALLATION OF HIGH FRICTION SURFACE ON NB US 41 FROM MP 20.090 TO MP 20.290. (2016BOP) | Safety-Haz-Elm | Henderson | 051-US-0041 -000 | 20.09 | 20.29 | 0.2 | Modernize Roadway-Rural | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 14:30 | ? | ?
Y | 2 | Evansville-Henderson MPO | IP20160038 |  |  |  | PADUCAH-HENDERSON; CONSTRUCT US-60 BYPASS OF CORYDON.(04CCR)(12CCR) | New Route | Henderson | 051-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 2600000 |  | 3900000 |  | 2000000 |  | 30066000 |  | 2019-02-15 14:44 | ? | ?
Y | 2 | Evansville-Henderson MPO | IP20160039 |  |  |  | WIDEN AND IMPROVE US 60 FROM WEST OF HENDERSON COMMUNITY COLLEGE (MP 7.7) EXTENDING EAST TO KY 425 (MP 8.7). (BOP2012) | Major Widening | Henderson | 051-US-0060 -000 | 7.7 | 8.707 | 1.007 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-01-14 15:33 | Improve traffic flow. | WIDEN AND IMPROVE US 60 FROM WEST OF HENDERSON COMMUNITY COLLEGE (MP 7.7) EXTENDING EAST TO KY 425 (MP 8.7). (BOP2012)
Y | 2 | Pennyrile ADD | IP20160214 | 2-898 |  | A | RECONSTRUCT THE BREATHITT PARKWAY INTERCHANGE AT KY 1682 NORTH OF HOPKINSVILLE. (BREATHITT PARKWAY/FUTURE INTERSTATE SPUR PROJECT) (16CCR)(18CCN) | RECONSTRUCTION(O) | Christian | 024-EB-9004 -000 | 11.39 | 11.99 | 0.6 | Innovative Interchange | 40 | Y |  |  | 970000 | 2019 | 1050000 | 2020 | 1040000 | 2021 | 9360000 | 2023 | 2019-03-11 08:56 |  | Improve the geometrics of the old interchange which was designed for toll booths | 2 | West | 65.2509 | 7.622 | 5.8763 | 10.9278 | 0.65292 | 0 | 4.8797 | 5.2921 | 35 | 15 | 15
Y | 2 | Pennyrile ADD | IP20160221 |  |  |  | REHAB AND UPGRADE SIDEWALKS ALONG S MAIN ST (KY-109) FROM MUNN STREET TO MEADOWS HILL DR AND ALONG MEADOWS HILL DR FROM S MAIN ST TO MP 0.302 IN DAWSON SPRINGS | Spot Improvement | Hopkins | 054-KY-0109 -000 | 1.741 | 1.942 | 0.201 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-31 10:56 | Improve safety for pedistrians | Need sidewalks
Y | 2 | Green River ADD | IP20160257 |  |  |  | UPGRADE KY 54 TO A 3 LANE AND PROVIDE NEW CURB AND GUTTER AND ADDRESS TWO DANGEROUS CURVES AT FORDSVILLE ON EAST SIDE OF ROADWAY. (16CCN) | Major Widening | Ohio | 092-KY-0054 -000 | 0 | 18.244 | 18.244 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-11-03 10:04
Y | 2 | Pennyrile ADD | IP20170012 |  |  |  | To improve safety by addressing geometric deficiencies of intersection and improving traffic control through the intersection with Pyle/Major Lane by constructing a roundabout. | Reconstruction | Christian | 024-KY-0272 -000 | 8.1 | 8.4 | 0.3 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 750000 |  | 250000 |  | 2200000 |  | 2017-05-19 10:27 |  | This route is super elevated at the intersection which poses a problem with signalizing it even though it meets warrants 7 out of 8 hours. It currently has a caution light but does have a crash history.
Y | 2 | Pennyrile ADD | IP20170054 |  |  |  | Widen of KY 695 from Sterling Dr. to Gary Ln. to include Ped/Bike facilities | Minor Widening | Christian | 024-KY-0695 -000 | 9.695 | 12.179 | 2.484 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 2000000 |  | 8000000 |  | 2017-05-19 10:29 | Improve safety and traffic flow | Improve safety | PENNYRILE ADD | West | 40.2448 | 5.2234 | 11.1856 | 12.1005 | 3.8316 | 0 | 0 | 7.9038 | 40
Y | 2 | Pennyrile ADD | IP20170055 |  |  |  | Widen KY 107 to 3 lanes with Ped-Bike facilities from KY 345 (Huffman Mill RD) (BMP 12.566) north to Jerry Claiborne Way (EMP 15.353). | Minor Widening | Christian | 024-KY-0107 -000 | 12.566 | 15.353 | 2.787 | Modernize Roadway-Rural | 26 |  | 0 |  | 550000 |  | 2500000 |  | 1200000 |  | 6000000 |  | 2017-05-19 10:05 |  | widen KY 107 to improve traffic flow and construct a bike/Ped path in ROW. | PENNYRILE ADD | West | 27.8273 | 2.3505 | 8.1443 | 7.2294 | 2.3024 | 0 | 0 | 7.8007 | 28
Y | 2 | Pennyrile ADD | IP20170056 |  |  |  | Widen KY 272 from KY 1007 (EMP 10.151) to KY 164 (Newstead Rd) (BMP 6.82) with Ped-bike facilities. | Minor Widening | Christian | 024-KY-0272 -000 | 6.82 | 10.151 | 3.331 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 3500000 |  | 2500000 |  | 10500000 |  | 2017-05-19 10:24 |  | Widen KY 272 to improve traffic flow and create a bike/Ped facility | PENNYRILE ADD | West | 22.8265 | 5.9794 | 0 | 13.0155 | 3.8316 | 0 | 0 | 0 | 23
Y | 2 | Pennyrile ADD | IP20170057 |  |  |  | Widen US 68/80 (east of PKWY) from Pennyrile PKWY to the US 68 Bypass to include Ped/Bike facilities. | Major Widening | Christian | 024-US-0068 -000 | 11.419 | 14.107 | 2.688 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 500000 |  | 600000 |  | 1000000 |  | 7000000 |  | 2017-05-19 09:57 |  | Widen US 68 to improve traffic flow and increase bike/Ped safety with a new bike/Ped trail in ROW | PENNYRILE ADD | West | 53.0498 | 4.5361 | 13.0928 | 11.0567 | 3.8316 | 8.0756 | 4.4158 | 8.0412 | 53
Y | 2 | Pennyrile ADD | IP20170058 |  |  |  | Widen KY 107 from the KY 107/KY 507 Intersection (BMP 19.841) north to the KY 1683 intersection (EMP 21.642). This also includes a new connector from near the KY 107/KY 507/Rozelle Ct. intersection (EMP 0.2) southward to US 68/80. (BMP 0.0) | Major Widening | Christian | 024-KY-0107 -000 | 19.841 | 21.642 | 1.801 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 1000000 |  | 1200000 |  | 5000000 |  | 2017-05-19 10:08 |  | Widen KY 1683 to improve safety and traffic flow, as well as provide a bike/ped facility in the ROW for pedestrian safety. This project also includes a new connector from KY | PENNYRILE ADD | West | 21.7002 | 7.4777 | 0 | 11.9201 | 2.3024 | 0 | 0 | 0 | 22
Y | 2 | Pennyrile ADD | IP20170059 |  |  |  | Widen KY 109 from US 68/80 (BMP 10.945) to Spain Lane (EMP 12.552) with Ped./Bike facilities | Major Widening | Christian | 024-KY-0109 -000 | 10.945 | 12.552 | 1.607 | Modernize Roadway-Rural | 26 |  | 0 |  | 550000 |  | 1000000 |  | 1500000 |  | 4500000 |  | 2017-05-19 10:12 |  | Widen KY 109 to improve safety and traffic flow, as well as improve pedestrian safety with a new Bike/Ped facility in the ROW | PENNYRILE ADD | West | 38.4192 | 2.4742 | 8.0928 | 10.2577 | 4.5017 | 6.5292 | 0 | 6.5636 | 38
Y | 2 | Owensboro MPO | IP20170074 |  |  |  | 18th Street - Reconstruct to allow for center turn lanes as needed. Project begins at Frederica St (KY 2831) and ends at JR Miller Blvd (CS 1262). | Reconstruction | Daviess | 030-CS-1771 -000 | 0 | 0.111 | 0.111 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 300000 |  | 300000 |  | 300000 |  | 1500000 |  | 2017-05-19 10:42 | The purpose of this project is to improve safety, reliability and mobility along CS 1770 (East 18th Street), better control access and reduce congestion | This project is part of the MTP. The project is intended to widen East 18th Street from a 2 lane road to a 3 lane cross section. East 18th Street is a major cross street between US 431 and KY 54, with both of these roads are either highly commercialized o | Owensboro MPO | West | 28.1924 | 9.7388 | 5.1546 | 5.0515 | 0 | 8.2474 | 0 | 0 | 28
Y | 2 | Evansville-Henderson MPO | IP20180010 |  |  |  | Improve safety and level of service | Reconstruction | Henderson | 051-KY-0416 -000 | 7.363 | 7.463 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 | 2018 | 300000 | 2020 | 350000 | 2020 | 1500000 | 2021 | 2018-08-07 10:47 | Improve Safety and Level of Service | improve Safety
Y | 2 | Pennyrile ADD | IP20180011 |  |  |  | To improve safety by addressing geometric deficiencies of intersection and improving traffic control through the intersection with Pyle/Major Lane by constructing a roundabout. | Reconstruction | Christian | 024-KY-0272 -000 | 8.1 | 8.4 | 0.3 | Realign Intersection | 26 |  | 0 |  | 500000 | 2019 | 750000 | 2021 | 250000 | 2021 | 2200000 | 2023 | 2018-08-07 10:35 | To improve safety by addressing geometric deficiencies of intersection and improving traffic control through the intersection | improved safety
Y | 2 | Pennyrile ADD | IP20180058 |  |  |  | Upgrade the southern portion of the I-69/Pennyrile/ WK Parkway interchange to meet Interstate Standards | Reconstruction | Hopkins | 054-EB-9004 -000 | 34.056 | 34.256 | 0.2 |  |  | Y | [11 empty] | Upgrade to Interstate Standards and Improve Safety | Upgrade the southern half of this Parkway Interchange to meet Interstate Standards
Y | 2 | Pennyrile ADD | IP20180059 |  |  |  | Upgrade the US 62 Interchange (Exit 33) on the Pennyrile Parkway near the City of Nortonville to Interstate Standards. | Reconstruction | Hopkins | 054-EB-9004 -000 | 32.65 | 33.05 | 0.4 |  |  | Y | [11 empty] | Improve Safety | Upgrade the Parkway Interchanges to meet Interstate Standards
Y | 2 | Pennyrile ADD | IP20180060 |  |  |  | Upgrade the US 41 overpass and ramps (Exit 30) on the Pennyrile Parkway to meet Interstate Standards | Reconstruction | Hopkins | 054-EB-9004 -000 | 29.359 | 29.759 | 0.4 |  |  | Y | [11 empty] | Improve Safety | Upgrade Parkway to Interstate Standards
Y | 2 | Pennyrile ADD | IP20180061 |  |  |  | Upgrade the KY 800 Interchange ( Exit 23) on the Pennyrile Parkway to meet Interstate Standards | Reconstruction | Christian | 024-EB-9004 -000 | 22.449 | 22.849 | 0.4 |  |  | Y | [11 empty] | Upgrade interchange to meet Interstate standards | Upgrade interchange to meet Interstate standards
Y | 2 | Pennyrile ADD | IP20180062 |  |  |  | Upgrade US 68 Interchange (Exit 9) on the Pennyrile Parkway to Interstate Standards | Reconstruction | Christian | 024-EB-9004 -000 | 9.147 | 9.547 | 0.4 |  |  | Y | [11 empty] | Upgrade Interchange to meet interstate Standards | Upgrade Interchange to meet interstate Standards
Y | 2 | Pennyrile ADD | IP20180063 |  |  |  | Upgrade US 41 Interchange (EX 8) on Pennyrile Parkway to Interstate Standards | Reconstruction | Christian | 024-EB-9004 -000 | 7.715 | 8.115 | 0.4 |  |  | Y | [11 empty] | Upgrade US 41 Interchange to meet Interstate Standards | Upgrade US 41 Interchange to meet Interstate Standards
Y | 2 | Pennyrile ADD | IP20180064 |  |  |  | Upgrade US 41A Interchange on Pennyrile Parkway to meet Interstate Standards | Reconstruction | Christian | 024-EB-9004 -000 | 6.626 | 7.026 | 0.4 |  |  | Y | [11 empty] | Upgrade US 41A Interchange to meet Interstate Standards | Upgrade US 41A Interchange to meet Interstate Standards
Y | 2 | Pennyrile ADD | IP20180065 |  |  |  | Upgrade the Lovers Lane and US 68 Bypass interchanges on the Pennyrile Parkway to Interstate standards | Reconstruction | Christian | 024-EB-9004 -000 | 4.975 | 6.007 | 1.032 |  |  | Y | [11 empty] | Upgrade interchange to Interstate Standards | Upgrade interchange to Interstate Standards
Y | 2 | Pennyrile ADD | IP20180067 |  |  |  | Upgrade Pennyrile Parkway to meet Interstate standards from I-24 to the Hopkins County Line | Reconstruction | Christian | 024-EB-9004 -000 | 0 | 28.095 | 28.095 |  |  | Y | [11 empty] | Upgrade Parkway to meet Interstate Standards as per FHWA agreement | Upgrade Parkway to meet Interstate Standards as per FHWA agreement
Y | 2 | Pennyrile ADD | IP20180084 |  |  |  | New Eastern Connector Route from N. 293 just south of the I-69 Interchange to KY 91 | New Route | Caldwell | 017-KY-0293 -000 | 6.151 | 6.518 | 0.367
Y | 2 | Pennyrile ADD | IP20190021 |  |  |  | Minor widening of Rocky Creek Bridge on US 431 and northern approach to the bridge. | Minor Widening | Muhlenberg | 089-US-0431 -000 | 3.4 | 3.7 | 0.3 | [14 empty] | To improve safety and traffic flow | safety
Y | 2 | Pennyrile ADD | IP20190025 |  |  |  | West Kentucky Parkway Interstate Conversion Study from the I-69 interchange in Hopkins Co. (BMP 38.326) to the Natcher PKWY interchange in Ohio Co. (EMP 76.777) This is a Planning Study to identify what elements or sections of the WK Parkway need to be up | Transportation Study | Muhlenberg | 089-WK-9001 -000 | 43.424 | 65.675 | 22.251 | Transportation Studies | 0 |  | 400000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-01 15:49 | To fund a Planning Study to identify what elements or sections of the WK Parkway need to be upgraded before it can be accepted and converted into an Interstate. | Improve truck access, safety and economic development.
Y | 2 | Green River ADD | IP20190044 |  |  |  | Address turning issues at entrance of McLean County High School. | Spot Improvement | McLean | 075-KY-0136 -000 | 11.3 | 11.45 | 0.15 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 180000 |  | 400000 |  | 500000 |  | 900000 |  | 2019-02-15 14:11 | Address safety issues on KY 136 in front of McLean County High School | to improve road safety
Y | 2 | Green River ADD | IP20190075 |  |  |  | Improve intersection of US 60 and KY 1078. This is a breakout of IP2008083. It the eastern intersection and is not a duplication of IP2008084. | Reconstruction | Henderson | 051-US-0060 -000 | 16.5 | 16.7 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 350000 |  | 400000 |  | 1500000 |  | 2019-02-28 13:23 | To improve safety at the intersection of US 60 and KY 1078 | To improve sight distance issues
Y | 2 | Pennyrile ADD | IP20190086 |  |  |  | Reconstruct Rock Springs Curve on KY 139 | Safety-Haz-Elm | Caldwell | 017-KY-0139 -000 | 7.7 | 8 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 500000 |  | 400000 |  | 1750000 |  | 2019-02-28 09:51 | Improve substandard geometrics of section of KY 139 | Improve safety
Y | 2 | Pennyrile ADD | IP20190166 |  |  |  | Reconstruct KY 1069 from 0.2 miles north of Brown Badgett Loop to KY 260 near Hanson | Reconstruction | Hopkins | 054-KY-1069 -000 | 1.8 | 3.9 | 2.1 | [14 empty] | Improve geometric, safety and traffic flow | Improve safety and traffic flow
Y | 2 | Green River ADD | IP20190168 |  |  |  | Reconstruct KY 1539/Zion Larue Rd from KY 351 to Henderson city limits | Reconstruction | Henderson | 051-KY-1539 -000 | 0 | 0.727 | 0.727
Y | 2 | Green River ADD | IP20190173 |  |  |  | Reconstruct South Main St (CS-1227) from Drury Ln (CS-1107) to Yeaman Av (CS-1390) to improve safety and level of service. | Reconstruction | Henderson | 051-CS-1227 -000 | 0 | 0.599 | 0.599
Y | 3 | Barren River ADD | IP20000008 |  |  |  | Improve safety and address the horizontal and vertical alignment deficiencies on KY 2593 from the Tennessee State Line (MP 0.0) to KY 1008 (MP 4.874) in Simpson County. | Reconstruction | Simpson | 107-KY-2593 -000 | 0 | 4.874 | 4.874 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 3500000 |  | 2500000 |  | 12000000 |  | 2010-02-25 16:51 | Improve safety. | Ky2593 is a narrow two lane facility, This route provides a direct link from KY 1008, a truck route, to US-31W into Tennessee. An industry is located at the intersection of KY 2593 and kY 1008. Large trucks are entering and exiting onto this .0500 mile st
Y | 3 | Bowling Green MPO | IP20010001 |  |  |  | Improve access on I-65 from the L. B. Nunn Parkway to the William H. Natcher Parkway. | New Route | Warren | 114-PF-9999 - |  |  |  | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 485000000 |  | 2018-10-15 14:33 | Improve access. | In 1991, the United States Congress passed a bill about an idea for new interstate highway from Washington, D.C. to southern California. Engineer, planners, and officials investigated the need for a new coast to coast highway to allieviate the stress on
Y | 3 | Bowling Green MPO | IP20020006 |  |  |  | Modernize the Louie B. Nunn parkway for possible utilization as a portion of I 66. | Reconstruction | Barren | 005-LN-9008 -000 | 0 | 22.357 | 22.357 | Other Improvement Types | 0 | Y | 0 |  | 27000000 |  | 5000000 |  | 7000000 |  | 620000000 |  | 2018-10-11 14:10 | Modernization. | The Louie B. Nunn Parkway between Warren County and Somerset is a four lane, fully controlled access facility. It provides a link between Bowling Green and Somerset. Although the traffic volume is not high for this type of facility, the truck volume is
Y | 3 | Bowling Green MPO | IP20040043 |  |  |  | Improve mobility with the Southwest Parkway - New Construction from US 31W to Interstate-65 (Phase II), in Bowling Green. See 2000 Bowling Green transportation plan. *Cost Estimates do not reflect Phase II and need to be updated *Milepoints are not a | New Route | Warren | 114-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 0 |  | 640000 |  | 250000 |  | 1850000 |  | 21800000 |  | 2018-10-15 14:42 | Improve mobility. | Traffic along the US 68 West (Russellville Road) Corridor and US 31W South (Nashville Road) Corridor have experienced a high amount of stress due to congestion. A major mixed-use development has been proposed in cooperation with the city and local plann
Y | 3 | Barren River ADD | IP20040044 |  |  |  | IMPROVE SAFETY AND MOBILITY ON US-431 FROM RUSSELLVILLE BYPASS TO KY 2146 IN RUSSELLVILLE. | Major Widening | Logan | 071-KY-3240 -000 | 0 | 1.1 | 1.1 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 2000000 |  | 1500000 |  | 5000000 |  | 2019-03-05 11:43 | Improve safety and mobility. | Presently, US 431 is a two lane facility in this area. There are businesses, residences, and the city cemetery located adjacent to the roadway. It serves as a link for the trucks using US 431 and US 68. The combination of turning movements, large truck
Y | 3 | Barren River ADD | IP20060127 |  |  |  | IMPROVE SAFETY AT THE INTERSECTION OF US 31E AND KY 100 IN SCOTTSVILLE. | Reconstruction | Allen | 002-US-0031E -000 | 7.29 | 7.54 | 0.25 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 150000 |  | 100000 |  | 350000 |  | 2019-03-04 14:56 | Improve safety. | The US 31E - KY 100 intersection is a signalized intersection. Much of the traffic is school traffic, since US31E provides access to three schools and kY 100 provides access to one school. The intersection also has a large amount of traffic generated by t
Y | 3 | Barren River ADD | IP20060128 |  |  |  | IMPROVE SAFETY AND MOBILITY ON US 31E FROM KY 100 TO US 231 IN SCOTTSVILLE. | Major Widening | Allen | 002-US-0031E -000 | 7.415 | 8.607 | 1.192 | Modernize Roadway-Rural | 26 | Y | 0 |  | 500000 |  | 200000 |  | 400000 |  | 4400000 |  | 2019-03-04 14:56 | Improve safety and mobility. | US31E between KY100 and KY101 serves as a Northern Byass around Scottsville. The portion of the road between US231 and KY100 is on the National Highway System. The ADT is 4095 with 24.4% trucks. The route also provides direct access to three schools. Cong
Y | 3 | Barren River ADD | IP20060129 |  |  |  | Improve safety and mobility on KY 100 from KY 3500 to John Kelly Drive in Scottsville. | Major Widening | Allen | 002-KY-0100 -000 | 13.1 | 14.1 | 1 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 750000 |  | 1500000 |  | 2500000 |  | 5000000 |  | 2019-03-04 14:31 | Improve safety and mobility. | Presently KY 100 is a two lane facility with 12' lanes and 6' shoulders. There are numerous businesses adjacent to the road. The lack of turning lanes requires vehicles making a left turn into these businesses yield to opposing traffic, thus queues and t
Y | 3 | Barren River ADD | IP20060130 |  |  |  | Improve safety and reduce congestion along KY100 (Franklin Rd) from US31E to KY3500 (Old Gallatin Rd). | Minor Widening | Allen | 002-KY-0100 -000 | 12.654 | 13.1 | 0.446 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 400000 |  | 1200000 |  | 1100000 |  | 2000000 |  | 2019-03-04 14:56 | Improve safety and reduce congestion. | Presently KY 100 is a two lane facility with 12' lanes and 6' shoulders. There are numerous businesses adjacent to the road. The lack of turning lanes requires vehicles making a left turn into these businesses yield to opposing traffic, thus queues and t | BARREN RIVER ADD | West | 37.3789 | 7.2371 | 6.0825 | 6.2242 | 1.323 | 8.1443 | 3.2818 | 5.0859 | 37
Y | 3 | Barren River ADD | IP20060131 |  |  |  | Improve safety and mobility on KY 100 from KY 980 to Locust Street in Scottsville. | Reconstruction | Allen | 002-KY-0100 -000 | 14.441 | 14.641 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 200000 |  | 300000 |  | 800000 |  | 2019-03-04 14:57 | Improve safety and mobility. | Presently KY 100 is a two lane facility with 12' lanes 6' shoulders. There a re numerous businesses adjacent to the road. The lack of turning lanes requires vehicles make a left turn into these businesses yield to opposing traffic, thus queues and traffic
Y | 3 | Barren River ADD | IP20060132 |  |  |  | Improve safety at the intersection of KY 98 and KY 3499 in Scottsville. | Reconstruction | Allen | 002-KY-0098 -000 | 0.3 | 0.4 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 250000 |  | 300000 |  | 250000 |  | 2019-03-04 14:31 | Improve safety and reduce congestion. | The Ky 100 - KY 98 intersection in Scottsville is a "T" intersection. There is a entrance to a shopping center near the intersection. It is close enough that many motorists act as if it is part of the intersection. There are no turning lanes on any of th
Y | 3 | Barren River ADD | IP20060133 |  |  |  | Improve safety and mobility on KY 100 between KY 98 and KY 1421. | Major Widening | Allen | 002-KY-0100 -000 | 15.141 | 17.244 | 2.103 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 2000000 |  | 1000000 |  | 7500000 |  | 2019-03-04 14:57 | Improve safety and mobility. | KY 100 between KY 98 and KY 1421 is a narrow two lane facility with numerous horizontal and vertical curves. IT has a significant amount of traffic and large trucks; especially for this area. Due to the large number of residences located adjacent to the r
Y | 3 | Barren River ADD | IP20060134 |  |  |  | IMPROVE SAFETY AND MOBILITY ON KY 101 FROM US 31E IN SCOTTSVILLE TO WARREN C\L. SEE SEGMENT 1.1 IN DECEMBER, 1999 CORRIDOR FEASIBILITY STUDY. | Reconstruction | Allen | 002-KY-0101 -000 | 1.2 | 13.347 | 12.147 | Other Improvement Types | 0 |  | 0 |  | 4400000 |  | 5000000 |  | 4000000 |  | 43600000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 101 between US 31E and the Warren County Line is a two lane facility with horizontal and vertical curves. This route serves as a connection between US 31E at Scottsville and I 65 at Smiths Grove. Much of the traffic is commuter traffic. This is expe
Y | 3 | Barren River ADD | IP20060135 |  |  |  | Improve safety along KY 101 from Gainesville Road (MP 7.314) to KY 1533 (MP 10.028), including a rock cut issue on KY 101 near the intersection with Gainsville Road. | Safety-Haz-Elm | Allen | 002-KY-0101 -000 | 7.314 | 10.028 | 2.714 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 1500000 |  | 6500000 |  | 2010-02-25 16:51 | Improve safety. | KY 101 between US 31E and the Warren County Line is a two lane facility with horizontal and vertical curves. This route serves as a connection between US 31E at Scottsville and I 65 at Smiths Grove. Much of the traffic is commuter traffic. Historically
Y | 3 | Barren River ADD | IP20060136 |  |  |  | Improve safety and mobility on KY 1533 from KY 101 to KY 252. | Reconstruction | Allen | 002-KY-1533 -000 | 2.721 | 5.779 | 3.058 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 1000000 |  | 500000 |  | 6000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 1533 between KY 101 and KY 252 is a narrow, two lane facility with numerous horizontal and vertical curves. IN many locations the shoulder very narrow. The traffic volume on this route is high for this area. The road provides access to Barren River Dam
Y | 3 | Barren River ADD | IP20060137 |  |  |  | Reduce congestion and increase mobility on US 31E from Aberdeen Drive to Trojan Trail, including reconstruction of the interchange with Nunn Parkway to a Single Point Urban Interchange. | Major Widening | Barren | 005-US-0031E -000 | 12.3 | 12.6 | 0.3 | Innovative Interchange | 40 |  | 0 |  | 2000000 |  | 250000 |  | 1500000 |  | 20000000 |  | 2019-03-04 14:29 | Reduce congestion and increase mobility. | This portion of US 31E is a well traveled section between Glasgow and Scottsville. It is a two-lane facility with small shoulders. This section of US 31E sees truck traffic and with ADT between 4,222 and 13,386 there is a need for widening. | BARREN RIVER ADD | West | 44.5833 | 8.9003 | 7.4742 | 14.0335 | 0.94502 | 0 | 4.7423 | 8.488 | 45
Y | 3 | Barren River ADD | IP20060138 |  |  |  | Reduce congestion and increase mobility on US 31E from Lexington Drive to Glasgow Outer Loop. | Major Widening | Barren | 005-US-0031E -000 | 15.3 | 17.4 | 2.1 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 0 |  | 1750000 |  | 5000000 |  | 5000000 |  | 12000000 |  | 2019-03-04 15:06 | Reduce congestion and increase mobility. | US31E between Lexington Drive and the Glasgow Outer Loop is a two lane facility with turning lanes only at the Lexington Drive and Outer Loop intersections. US 31E is the major north-south route through Barren County. The traffic volume is high. Traffic v | BARREN RIVER ADD | West | 41.5859 | 5.9588 | 3.4021 | 12.4485 | 0 | 8.9347 | 3.7285 | 7.1134 | 42
Y | 3 | Barren River ADD | IP20060139 |  |  |  | Improve safety and mobility of the intersection of US 31E with US 31E Business on the north side of Glasgow. | Reconstruction | Barren | 005-US-0031E -000 | 15.811 | 15.911 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 50000 |  | 150000 |  | 325000 |  | 2010-02-25 16:51 | Improve safety and mobility. | Presently the US31E - US31EX intersection is a "T' intersection with a traffic signal and no turning lanes on US31E. The intersection is also located below the crest of a vertical curve. US31EX serves as the access to the T.J. Sampson Hospital and several
Y | 3 | Barren River ADD | IP20060140 |  |  |  | Improve safety and mobility along KY 63 from Nunn Pkwy to US 31E Business in Glasgow. | Reconstruction | Barren | 005-KY-0063 -000 | 13.153 | 14.569 | 1.416 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 800000 |  | 500000 |  | 3000000 |  | 2019-03-04 15:06 | Improve safety and mobility. | KY 63 between the Louie B. Nunn Parkway and US31EX is a narrow, two lane facility with numerous horizontal and vertical curves. While the area is primarily residential in nature, some commercial facilities do exist. There are no turning lanes on this rout
Y | 3 | Barren River ADD | IP20060141 |  |  |  | Improve safety and mobility on KY 87 from Peter Creek Road to Ramp Road. | Reconstruction | Barren | 005-KY-0087 -000 | 8.192 | 9.68 | 1.488 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 500000 |  | 350000 |  | 2750000 |  | 2010-02-25 16:51 | Improve safety and mobility. | Ky 87 between Peter Creek Road and Ramp Road is a two lane facility with 9' lanes and 2' shoulder. There are numerous horizontal and vertical curves on the road. Due to the farming activities in this area, large vehicles do use this road. The road provide
Y | 3 | Barren River ADD | IP20060142 |  |  |  | Improve safety and mobility on KY 87 from Ramp Road to US 31E. | Reconstruction | Barren | 005-KY-0087 -000 | 9.68 | 12.255 | 2.575 | Other Improvement Types | 0 |  | 0 |  | 850000 |  | 750000 |  | 500000 |  | 4500000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 87 between Ramp Road and US31E is a two lane facility with 9' lanes and 2' shoulders. There are numerous horizontal and vertical curves on the road. Due to farming activities in the area, large vehicles do use the road. The road provides direct access
Y | 3 | Barren River ADD | IP20060144 |  |  |  | Reduce congestion and improve safety on KY 90 from its intersection with Max Wagner Drive to Reynolds Road in Glasgow. | Major Widening | Barren | 005-KY-0090 -000 | 8.713 | 9.395 | 0.682 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 1000000 |  | 1000000 |  | 5000000 |  | 2018-10-11 14:14 | Reduce congestion and improve safety. | KY 90 between the Glasgow Outer Loop and Reynolds Road multilane (3 and 4 lanes) facility with 12' lanes. A portion of the road is in a curb and gutter section with the remainder having 10' shoulders. These voumes are expected to increase as motorists beg
Y | 3 | Barren River ADD | IP20060145 |  |  |  | Improve safety and mobility of KY-249 from Elmo Road to 0.3 mile south of KY 1318, including a new bridge over Rose Creek. | Spot Improvement | Barren | 005-KY-0249 -000 | 8.3 | 8.75 | 0.45 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 350000 |  | 500000 |  | 1200000 |  | 2017-03-27 09:34 | Improve safety and mobility. | KY 249 between 8.3 and Riddle Road is a narrow, two lane facility with numerous horizontal and vertical curves. Some large vehicles do use the road due to the farming activities in the area. Several chicken farms are being developed in the area that will | BARREN RIVER ADD | West | 23.1357 | 1.5464 | 11.8557 | 3.2732 | 1.5808 | 0 | 0 | 4.8797 | 23
Y | 3 | Barren River ADD | IP20060146 |  |  |  | Improve safety along KY 252 by correcting the vertical and horizontal alignments, especially at the Beaver Point Road Intersection; (from Beaver Point Road at mile point 7.8 to US 31 E at mile point 11.115). | Safety-Haz-Elm | Barren | 005-KY-0252 -000 | 7.8 | 11.115 | 3.315 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2000000 |  | 2500000 |  | 7500000 |  | 2010-02-25 16:51 | Improve safety. | A specific concern with motorist safety has been expressed for KY 252 at Beaver Point Road Intersection; (from Beaver Point Road at mile point 7.8 to USE at mile point 11.115). KY 252 is a heavy traveled two lane facility. This road also provides access t
Y | 3 | Barren River ADD | IP20060147 | 3-80002 |  | A | NEW INTERCHANGE ON THE LOUIE NUNN CUMBERLAND PARKWAY AT KY-249 IN GLASGOW(18CCN) | NEW INTERCHANGE(O) | Barren | 005-PF-9999 - |  |  |  | Other Improvement Types | 0 | Y |  |  | 1630000 | 2020 | 2320000 | 2021 | 850000 | 2022 | 18860000 | 2024 | 2019-03-01 10:58 | Reduce congestion and increase mobility. | At present there is no interchange on the Louie B. Nunn Parkway at KY 249. Anyone wishing to access the Louie B. Nunn Cumberland Parkway in this area must travel through Glasgow to US 31E or KY90. Also anyone on the Parkway that wishes to access this area | General Assembly | West | 12.8151 | 4.6301 | 0 | 2.7226 | 0.65068 | 0 | 4.8116 | 0 | 13
Y | 3 | Barren River ADD | IP20060148 |  |  |  | Improve safety and mobility on US 231 from KY 79 to WN 9007. | Major Widening | Butler | 016-US-0231 -000 | 8.199 | 8.947 | 0.748 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 400000 |  | 500000 |  | 500000 |  | 3600000 |  | 2019-03-12 09:05 | Improve safety and mobility. | US231 between KY79 and the Natcher Parkway is a two lane Facility with 10'-12' lanes and 2' shoulders, Development is beginning to occur in this area. A shopping center, fast food restaurants, and a motel have been built. KY1468 intersects US231 in this s
Y | 3 | Barren River ADD | IP20060149 |  |  |  | IMPROVE SAFETY AND MOBILITY ON KY 70 FROM MP 1.019 TO 1.319. | Reconstruction | Butler | 016-KY-0070 -000 | 1.019 | 1.319 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 70000 |  | 100000 |  | 600000 |  | 2010-02-25 16:51 | Improve safety and mobility. | Presently KY 70 in this area is a two lane facility. This area is a wetland thus drainage is poor. A heavy rainfall will result in flooding to the point that the roadway in under water for an extended period of time. Detour routes consist of secondary roa
Y | 3 | Barren River ADD | IP20060150 |  |  |  | Improve safety at the KY 70 - KY 1117 intersection. | Spot Improvement | Butler | 016-KY-0070 -000 | 9.8 | 10.1 | 0.3 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 150000 |  | 100000 |  | 650000 |  | 2019-03-12 09:07 | Improve safety. | KY 70 at the intersection with KY 1117 is a two lane facility with no turning lanes. KY 70 is the major east west route through Butler County. The traffic volume on KY 70 is significant for this area. A vertical curve exists on KY 70 just west of this int
Y | 3 | Barren River ADD | IP20060151 |  |  |  | Improve safety and mobility along KY-70 from the intersection of US-231 to the Natcher Parkway. | Major Widening | Butler | 016-KY-0070 -000 | 12.83 | 14.419 | 1.589 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 4000000 |  | 4000000 |  | 7000000 |  | 2019-03-12 09:08 | Improve safety and mobility. | KY 70 from Natcher PKwy to US 231 in Morgantown is a two lane facility with 9' lanes and 2' shoulders. Industry exists on the west end, commercial businesses exist on the east end, and the central portion is residential, thus various types of vehicles use | BARREN RIVER ADD | West | 41.1005 | 6.9897 | 9.5876 | 9.7809 | 4.2955 | 0 | 3.3677 | 7.079 | 41
Y | 3 | Barren River ADD | IP20060152 |  |  |  | Improve safety and sight distance at the intersection of KY 79 and KY 1328. | Spot Improvement | Butler | 016-KY-0079 -000 | 12.723 | 12.923 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 200000 |  | 250000 |  | 500000 |  | 2010-02-25 16:51 | Improve safety. | Both KY79 and KY1328 are two lane facilities in this area. The roads intersect at the crest of a verticle curve. The geometry of the roadway results in limited sight distance on all approaches to the intersection. A project was constructed with HES funds
Y | 3 | Barren River ADD | IP20060153 |  |  |  | Improve safety and sight distance at the intersections of KY 79 and KY 340. | Spot Improvement | Butler | 016-KY-0079 -000 | 19.002 | 19.446 | 0.444 | Other Improvement Types | 0 |  | 0 |  | 70000 |  | 200000 |  | 150000 |  | 700000 |  | 2010-02-25 16:51 | Improve safety. | The intersection of KY 79 and KY 340 is a junction/ disjunction situation. Both roads are two lane facilities in this area. At the southern intersection, KY 340 intersects KY 79 at a severe skew. There is a hill on KY 70 north of the northern intersection
Y | 3 | Barren River ADD | IP20060154 |  |  |  | IMPROVE SAFETY AND MOBILITY ON KY 403 FROM MP 3.622 TO MP 3.822. | Reconstruction | Butler | 016-KY-0403 -000 | 3.622 | 3.822 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 50000 |  | 75000 |  | 250000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 403(Between Woodbury and Morgantown) is a two lane facility in this area. After a heavy rainfall this area of the road in under water for extended periods of time. A detour route does not exist in the area. Vehicles from either direction must go to the
Y | 3 | Barren River ADD | IP20060155 |  |  |  | Improve safety and mobility on KY 70 from Shelby Street to KY 2184 in Brownsville. | Minor Widening | Edmonson | 031-KY-0070 -000 | 11.144 | 11.748 | 0.604 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 200000 |  | 500000 |  | 500000 |  | 2019-03-05 09:33 | Improve safety and mobility. | KY70 is a two lane facility in this area with parking on both sides. Numerous commercial establishments, residences, a school, the Community Center, and County Courthouse are located on the route. Due to the number of left turns into many of these establi
Y | 3 | Barren River ADD | IP20060156 |  |  |  | Improve safety by addressing the horizontal and vertical alignments on KY 259 from I 65 to US 31W. | Reconstruction | Edmonson | 031-KY-0259 -000 | 0 | 2.083 | 2.083 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 1000000 |  | 30000000 |  | 2010-02-25 16:51 | Improve safety. | KY 259 between I 65 and Warren County and US 31W in Edmonson County is a narrow two lane facility with numerous horizontal and vertical curves. The lane width in Warren County is 7' with 3' shoulders and the lane width in Edmonson County is 9'with 4' shou
Y | 3 | Barren River ADD | IP20060157 |  |  |  | Improve safety on KY 728 from KY 259 to KY 1827. | Reconstruction | Edmonson | 031-KY-0728 -000 | 0 | 6.952 | 6.952 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1500000 |  | 800000 |  | 8500000 |  | 2010-02-25 16:51 | Improve safety. | KY 728 is a two lane facility. There aare numerous horizontal and vertical curves along the roadway. There are certain areas where, historically, crashes have been a problem. One such location is the intersection of KY 728 and KY 259. There is a heavy vol
Y | 3 | Barren River ADD | IP20060158 |  |  |  | Improve safety on KY 1015 from MP 1.1 to MP 1.7. | Reconstruction | Edmonson | 031-KY-1015 -000 | 1.1 | 1.7 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 175000 |  | 250000 |  | 125000 |  | 900000 |  | 2010-02-25 16:51 | Improve safety. | This route is a narrow lane facility with numerous vertical and horizontal curves. Sight distance is limited due to the alignment of the road, thus the potential for a crash exists along the entire roadway. The area between MP 1.1 and MP 1.7 is the locati
Y | 3 | Barren River ADD | IP20060159 |  |  |  | Improve safety on KY 1827 from Nolin River Lake to KY 728. | Reconstruction | Edmonson | 031-KY-1827 -000 | 0 | 3.039 | 3.039 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 1000000 |  | 750000 |  | 6000000 |  | 2010-02-25 16:51 | Improve safety. | KY 1827 is a two lane facility with numerous horizontal and vertical curves. Nolin Lake State Park and Brier Creek Boat Ramp (Nolin Lake) are located on this road. There is a large volume of water sports vehicles transported along this roadway. Much of th
Y | 3 | Barren River ADD | IP20060160 |  |  |  | Improve safety and mobility on US 431 from Epleys to Diamond Springs Road. | Reconstruction | Logan | 071-US-0431 -000 | 18.433 | 25.819 | 7.386 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 4000000 |  | 2000000 |  | 20000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | US431 between Lewisburg and the Diamond Springs Road is a two lane facility with 9' lanes and 4' shoulders. There are numerous horizontal and vertical curves on this road. US431 is the major north-south route through Logan County. It provides a link betwe
Y | 3 | Barren River ADD | IP20060161 |  |  |  | Improve safety and mobility on US 431 from Hollow Bill to the Muhlenberg County Line. | Reconstruction | Logan | 071-US-0431 -000 | 27.547 | 28.747 | 1.2 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 2500000 |  | 1500000 |  | 12500000 |  | 2010-02-25 16:51 | Improve safety and mobility. | US431 is a narrow two lane facility with numerous horizontal and vertical curves. US431 is the major north-south route through Logan County. It provides a link between the Western Kentucky Parkway and I 2 in Tennessee. The section of US 431 between Russel
Y | 3 | Barren River ADD | IP20060162 |  |  |  | Improve safety and mobility on US-431 between the Tennessee State Line and KY-664. | Reconstruction | Logan | 071-US-0431 -000 | 0 | 8.252 | 8.252 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 8000000 |  | 4000000 |  | 30000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | US431 between the Tenessee State Line and KY664 is a two lane facility with 11' lanes. A portion of the road is in a curb and gutter section and the shoulder width on the remainder is 2'-10'. This is the major north-south route through Logan County. US431
Y | 3 | Barren River ADD | IP20060163 |  |  |  | Improve safety and mobility on US 431 from KY 664 to the intersection with the Southern Russellville Bypass. | Major Widening | Logan | 071-US-0431 -000 | 8.252 | 11.5 | 3.248 | Other Improvement Types | 0 |  | 0 |  | 1750000 |  | 3000000 |  | 2000000 |  | 13500000 |  | 2015-03-12 12:26 | Improve safety and mobility. | US 431 between KY 664 and KY 96 is a two lane facility with 11'lanes and 2' shoulders. The ADT is 5,770 with 9.0% trucks. US 431 is the major north-south route through Logan County and provides a link between the Western Kentucky Parkway and I-24 in Ten
Y | 3 | Barren River ADD | IP20060164 |  |  |  | Improve safety at the KY 79 - Marshall Road intersection. | Spot Improvement | Logan | 071-KY-0079 -000 | 5.4 | 6 | 0.6 | Improve Intersection | 26 |  | 0 |  | 75000 |  | 75000 |  | 75000 |  | 300000 |  | 2019-03-05 11:49 | Improve safety. | The intersection of KY79 and the Marshall Road is an unsignalized intersection. KY79 at this intersection is a two lane facility with 9' lanes and 4' shoulders. There are no turning lanes at this intersection. There is a vertical curve on KY 79 north of t | BARREN RIVER ADD | West | 25.8196 | 3.4227 | 7.3711 | 3.9948 | 4.1581 | 0 | 0 | 6.8729 | 26
Y | 3 | Barren River ADD | IP20060165 |  |  |  | Increase mobility on this section of KY100 between US 79 and the Simpson County Line, improving the access between Russellville and I-65 in Franklin. | Major Widening | Logan | 071-KY-0100 -000 | 0 | 9.016 | 9.016 | Modernize Roadway-Rural | 26 |  | 0 |  | 3600000 |  | 6500000 |  | 12000000 |  | 23000000 |  | 2019-03-05 11:49 | Increase mobility. | KY 100 between and US 79 and the Simpson County Line is a two lane facility. This route provides the link between Russellville and Franklin. It also provides direct access to the Logan County Airport. The truck volume on this section is significant. Many | BARREN RIVER ADD | West | 56.8084 | 2.8866 | 5.9278 | 10.6057 | 3.677 | 6.3918 | 2.9725 | 9.3471 | 42 |  | 15
Y | 3 | Barren River ADD | IP20060166 | 3-8908 |  | A | IMPROVE SAFETY BY IMPROVING SIGHT LINES CROSSING RAILROAD BETWEEN STOCKYARDS AND INDUSTRIAL PARK. (16CCN)(18CCN) | SAFETY(P) | Logan | 071-KY-2349 -000 | 0 | 0.643 | 0.643 | Modernize Roadway-Rural | 26 |  |  |  | 170000 | 2021 | 120000 | 2022 | 170000 | 2022 | 1000000 | 2023 | 2019-03-01 09:27 | Improve safety. | KY2349 between the Simpson County Line and US68 is a two lane facility with lane widths ranging between 9' and 11'. The shoulder width is 2'. It provides access to US68 for the industries, particularly R.J. Cormans's multimodal facility, located adjacent | BARREN RIVER ADD | West | 11.4734 | 1.134 | 4.1237 | 1.817 | 4.3986 | 0 | 0 | 0 | 12
Y | 3 | Barren River ADD | IP20060167 |  |  |  | Improve safety and mobility on US 68 from Nunn Parkway to KY 861. | Reconstruction | Metcalfe | 085-US-0068 -000 | 5.539 | 7 | 1.461 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 1000000 |  | 7000000 |  | 2019-03-05 14:08 | Improve safety and mobility. | US 68 is a two lane facility in this area. It serves as a link between the Louie B. Nunn Parkway and the various factories, commercial activities, schools, etc in Edmonton. This combination of Large trucks, school traffic, etc. creates congestion and safe
Y | 3 | Barren River ADD | IP20060168 |  |  |  | Address geometric deficiencies to improve the safety and mobility on US 68 from south of the intersection with Foundation Mitchell Road and northward for 0.7 miles (2015 US 68 Scoping Study). | Reconstruction | Metcalfe | 085-US-0068 -000 | 13.1 | 13.9 | 0.8 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 450000 |  | 425000 |  | 3700000 |  | 2015-03-12 12:36 | Improve safety and mobility. | The section of US 68 between KY 544 and KY 543 is a narrow two lane facility with numerous horizontal and vertical curves. Safety is a concern on this roadway. Large trucks going to and from Green County are common on this road. Most of US 68 between the
Y | 3 | Barren River ADD | IP20060169 |  |  |  | Address geometric deficiencies to improve safety and mobility on this section of US 68 north of KY 543 to a point south of the intersection with Chastine Simone Road (2015 US 68 Planning Study) | Spot Improvement | Metcalfe | 085-US-0068 -000 | 14.5 | 15.2 | 0.7 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 300000 |  | 250000 |  | 2300000 |  | 2015-03-12 12:39 | Improve safety and mobility. | US 68 between KY 543 and the Pink Ridge Road is a narrow two lane facility with numerous horizontal and vertical curves. Safety is a concern on this roadway. Large trucks going to and from Green County are common on this road. Most of US 68 from the Blueg | BARREN RIVER ADD | West | 18.7466 | 0.90722 | 3.0412 | 3.3376 | 4.1753 | 0 | 0 | 7.2852 | 19
Y | 3 | Barren River ADD | IP20060170 |  |  |  | Address geometric deficiencies to improve the alignment and safety on US 68 from south of Denzil Park Road to south of Beechville Road intersection (2015 US 68 Planning Study). | Spot Improvement | Metcalfe | 085-US-0068 -000 | 15.5 | 16.2 | 0.7 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 450000 |  | 420000 |  | 3100000 |  | 2015-03-12 12:43 | Improve safety. | US 68 (Beechville Rd-KY 70) is a two lane facility in this area with numerous horizontal and vertical curves. Crashes are a concern on this section of roadway. Large trucks going to and from Green County are common on this road. Most of US 68 from the Blu | BARREN RIVER ADD | West | 24.2689 | 0.91409 | 6.6495 | 4.6778 | 4.7423 | 0 | 0 | 7.2852 | 24
Y | 3 | Barren River ADD | IP20060171 | 3-8706 |  | A | SPOT IMPROVEMENTS ON US-68 FROM THE CUMBERLAND PARKWAY TO THE GREEN/METCALFE COUNTY LINE.(12CCN)(16CCN)(18CCN) | SPOT IMPROVEMENTS(O) | Metcalfe | 085-US-0068 -000 | 17.835 | 20.016 | 2.181 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 900000 | 2021 | 1100000 | 2022 | 10130000 | 2023 | 2019-03-05 09:35 | Improve safety. | US 68 between KY 745 and the Green County Line is a narrow two lane facility with numerous horizontal and vertical curves. Safety is a concern on this roadway. Large trucks going to and from Green County are common on this road. Most of US 68 between the | 3 | West | 62.6916 | 0.79725 | 10 | 8.5954 | 4.055 | 0 | 0 | 9.244 | 33 | 15 | 15
Y | 3 | Barren River ADD | IP20060172 |  |  |  | Improve safety and mobility on KY 70 between KY 869 and US 68 near Sulphur Well. | Reconstruction | Metcalfe | 085-KY-0070 -000 | 6.99 | 8.869 | 1.879 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1250000 |  | 2500000 |  | 5000000 |  | 2019-03-05 14:13 | Improve safety and mobility. | KY 70 between the Little Barren RIver at Sulphur Well and US 68 is a narrow two lane facility with numerous horizontal and vertical curves. Historically crash problems have existed at certain locations, especiailly at the intersection with US 68. This sit
Y | 3 | Barren River ADD | IP20060173 |  |  |  | Improve safety on KY 70 at the intersection of KY 869. | Spot Improvement | Metcalfe | 085-KY-0070 -000 | 6.8 | 7 | 0.2 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 400000 |  | 500000 |  | 700000 |  | 2019-03-05 15:53 | Improve safety. | Both KY 70 and KY 869 are two lane facilities at the intersection the two roads. This is a "T" intersection. The KY 869 approach has a severe negative grade. Both the KY 70 approaches have severe horizontal curves. The westbound approach has a severe posi
Y | 3 | Barren River ADD | IP20060175 |  |  |  | Improve safety of KY 90 from MP 2.512 to MP 2.612. | Safety-Haz-Elm | Metcalfe | 085-KY-0090 -000 | 2.512 | 2.612 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 200000 |  | 150000 |  | 500000 |  | 2019-03-05 14:14 | Improve safety. | KY 90 at the curve east of Summer Shade is a two lane facility. KY 90 serves as a link between the Louie Nunn Parkway and US 127 in Clinton County; both routes are on the national highway system. Both the traffic and truck volumes are significant, especia
Y | 3 | Barren River ADD | IP20060177 |  |  |  | Improve safety and the alignment on KY 1243 from Wayne Porter Road to Ratliff Mitchell Road. | Safety-Haz-Elm | Metcalfe | 085-KY-1243 -000 | 6.011 | 9.09 | 3.079 | Other Improvement Types | 0 |  | 0 |  | 900000 |  | 2500000 |  | 1500000 |  | 7000000 |  | 2010-02-25 16:51 | Improve safety. | KY 1243 is a two lane facility with narrow lanes in this area. There are numerous horizontal and vertical curves which limit distance in many locations, especially at intersections. There is a sharp curve near the intersection with KY 70 which has been th
Y | 3 | Barren River ADD | IP20060178 |  |  |  | Improve safety on KY 1243 at the intersection of KY 314. | Spot Improvement | Metcalfe | 085-KY-1243 -000 | 11.87 | 11.97 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 65000 |  | 180000 |  | 100000 |  | 350000 |  | 2010-02-25 16:51 | Improve safety. | KY 1243 is a two lane facility with narrow lanes in this area. KY 1243 intersects with KY 314 at an acute angle thus making turns especially for large vehicles very difficult. Safety is a concern due to the difficulty and time needed to make turns at this
Y | 3 | Barren River ADD | IP20060179 |  |  |  | Improve safety and mobility on KY 63 between the Tennessee State Line and KY 1366. | Reconstruction | Monroe | 086-KY-0063 -000 | 0 | 8.089 | 8.089 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 4000000 |  | 2500000 |  | 22000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY63 between the Tennessee State Line and KY1366 us a narrow two lane facility with numerous horizontal and vertical curves. This route provides a direct link between Gamaliel and Tompkinsville. It also provides a link between the Louie Nunn Cumberland Pa
Y | 3 | Barren River ADD | IP20060180 |  |  |  | Improve mobility on KY 63 from KY 1366 to Emberton Street in Tompkinsville. | Minor Widening | Monroe | 086-KY-0063 -000 | 8.089 | 9.93 | 1.841 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 500000 |  | 2500000 |  | 1500000 |  | 7500000 |  | 2019-03-08 09:09 | Improve mobility. | KY 63 between KY 1366 and Emberton Street is a two lane facility with 10' lanes and 2' shoulders. The section of roadways travels through downtown Tompkinsville. It provides access to residential areas, commercial facilities, governmental facilities and s
Y | 3 | Barren River ADD | IP20060181 |  |  |  | Improve safety at the intersection of KY 63 and Cemetery Road. | Spot Improvement | Monroe | 086-KY-0063 -000 | 8.25 | 8.45 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 600000 |  | 300000 |  | 600000 |  | 2019-03-08 09:09 | Improve safety. | KY63 in the area of the intersection with the Cemetery Road is a two lane facility with 10' lane and 2' shoulders. There are numerous vertical and horizontal curves. There are no turning lanes on either road. The sight distance at the intersection is limi | BARREN RIVER ADD | West | 19.7388 | 7.5052 | 3.9691 | 2.3196 | 1.5808 | 0 | 0 | 4.3643 | 20
Y | 3 | Barren River ADD | IP20060182 |  |  |  | Improve safety and mobility on KY 63 between KY 100/KY 63 in Tompkinsville and the Barren County Line. | Reconstruction | Monroe | 086-KY-0063 -000 | 9.457 | 21.214 | 11.757 | Other Improvement Types | 0 |  | 0 |  | 8500000 |  | 13000000 |  | 5000000 |  | 60000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 63 between KY 100/KY 163 in Tompkinsville and US 31EX Glasgow is a two lane facility with numerous horizontal and vertical curves. The road is known locally as "the roller coaster road". As indicated by the termini of the project, this road provides a
Y | 3 | Barren River ADD | IP20060184 |  |  |  | Improve safety of the KY-63 - KY-870 intersection. | Spot Improvement | Monroe | 086-KY-0063 -000 | 16.058 | 16.258 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 600000 |  | 300000 |  | 600000 |  | 2018-09-28 13:48 | Improve safety. | KY 63 in the area of the intersection with KY 870 is a two lane facility with 10' lanes and 2' shoulders. There are numerous horizontal and vertical curves on the road. There are no turning lanes on either road. The sight distance at the intersection is l | 3 | West | 12.0378 | 1.299 | 2.9381 | 1.8041 | 1.9072 | 0 | 0 | 4.0893 | 12
Y | 3 | Barren River ADD | IP20060185 |  |  |  | Improve safety and mobility and address deficiencies with Town Creek bridge on KY-100 from KY-163 to KY-3144 in Tompkinsville. Includes Bridge ID 086B00005 | Reconstruction | Monroe | 086-KY-0100 -000 | 14.402 | 14.902 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 2000000 |  | 2500000 |  | 3000000 |  | 2019-03-08 09:10 | Improve safety and mobility. | KY 100 between KY 163 and KY 3144 is a two lane facility with 9' lanes and 2' shoulders. Several commercial establishments exist adjacent to this facility. Due to the lack of turning lanes, queues develop which can creat congestion at certain times. The f | 3 | West | 70.1632 | 6.9416 | 8.4536 | 5.8119 | 4.1409 | 9.1753 | 0 | 5.64 | 40 | 15 | 15
Y | 3 | Barren River ADD | IP20060186 |  |  |  | Improve safety and mobility along KY 163 at School Drive. | Spot Improvement | Monroe | 086-KY-0163 -000 | 8.279 | 8.379 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 300000 |  | 300000 |  | 300000 |  | 2018-09-28 14:00 | Improve safety and mobility. | The entrance to Tompkinsville Elem. School is located on KY163 at this location. KY 163 is a two lane facility with 11' lanes and 2' shoulders. There are no turning lanes at this location. During the morning and afternoon, there is a long queue of traffic | BARREN RIVER ADD | West | 28.055 | 3.3814 | 14.8969 | 0 | 3.1959 | 0 | 3.2131 | 3.3677 | 28
Y | 3 | Barren River ADD | IP20060187 |  |  |  | Improve safety of the KY1049 -Drag Strip Road Intersection. | Spot Improvement | Monroe | 086-KY-1049 -000 | 3.65 | 3.85 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 150000 |  | 100000 |  | 550000 |  | 2010-02-25 16:51 | Improve safety. | KY1049 in the area of the intersection with the Drag-strip Road is a two lane facility with 9' lanes and 3' shoulders. Nermous horizontal and vertical curves exist on the road. There are no turning lanes on either road. The sight distance at the intersect
Y | 3 | Barren River ADD | IP20060188 |  |  |  | Improve safety at the KY 1049 - T. Poland/Cornwell Roads intersection. | Spot Improvement | Monroe | 086-KY-1049 -000 | 4.358 | 4.558 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 150000 |  | 100000 |  | 550000 |  | 2010-02-25 16:51 | Improve safety. | KY 1049 in the area of the intersection with T. Poland and Cornwell Roads is a two lane facility with 9' lanes and 3' shoulders. There are numerous horizontal and vertical curves on the road. The sight distance at the intersection is limited due to the al
Y | 3 | Barren River ADD | IP20060189 |  |  |  | Improve safety on KY 1366 from MP 7.6 to MP 7.9. | Spot Improvement | Monroe | 086-KY-1366 -000 | 7.6 | 7.9 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 100000 |  | 100000 |  | 500000 |  | 2010-02-25 16:51 | Improve safety. | KY 1366 between MP 7.6 and MP 7.9 is a two lane facility with 10' lanes and 2' shoulders. There are horizontal and vertical curves on the road. Although current, accurate crash data is not available, this area is known to be the site of crashes. This is t
Y | 3 | Barren River ADD | IP20060190 |  |  |  | Improve safety on KY 3144 between KY 163 and the Cool Spring Church Road. | Reconstruction | Monroe | 086-KY-3144 -000 | 1.373 | 2.925 | 1.552 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 750000 |  | 400000 |  | 3500000 |  | 2010-02-25 16:51 | Improve safety. | Reconstruction to increase the access to commercial and industrial facilities. Also improvements are needed to increase the safety along this segment.
Y | 3 | Barren River ADD | IP20060191 |  |  |  | Improve access to I-65 via a new interchange at KY 585 for Eastern Simpson County and Northern Allen County. | New Interchange | Simpson | 107-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 1750000 |  | 2000000 |  | 2000000 |  | 7000000 |  | 2010-02-25 16:51 | Improve access. | I-65 between KY100 in Simpson County and the Natcher Parkway in Warren County is a heavily traveled facility. Currently two I65 Interchanges exist in Simpson County, Exit 6 a KY 100 and Exit 2 at US 31W. The only option for motorists traveling KY 585 fr
Y | 3 | Barren River ADD | IP20060192 |  |  |  | Reduce congestion and improve safety on US 31W between KY 1171 and KY 1008 north of Franklin. | Major Widening | Simpson | 107-US-0031W -000 | 6.995 | 8.477 | 1.482 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 1000000 |  | 1500000 |  | 5000000 |  | 2019-03-08 09:30 | Reduce congestion and improve safety. | US 31W between KY 1171 and KY 1009 is predominantly a two lane facility. There is a .5 mile section with 3 lanes and turning lanes do exist at some locations. US31W is the major noninterstate north-south route through Simpson County. There is also a signi
Y | 3 | Barren River ADD | IP20060193 |  |  |  | Improve safety and mobility on US 31W between KY 1008 (south) and Industrial Drive. | Reconstruction | Simpson | 107-US-0031W -000 | 5.278 | 5.753 | 0.475 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 300000 |  | 400000 |  | 2500000 |  | 2019-03-08 09:32 | Improve safety and mobility. | US 31W and KY 1008 (south) and the end of the sidewalks at MP 5.725 is a three lane facility. Numerous commercial facilities are located along this route as well as Franklin Municipal building and subdivisions. Pedestrian activity is significant with peop
Y | 3 | Barren River ADD | IP20060194 |  |  |  | Improve safety and mobility on KY 73 from New Salem Road to Glen Vaughn Road. | Spot Improvement | Simpson | 107-KY-0073 -000 | 14.911 | 15.581 | 0.67 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 75000 |  | 75000 |  | 2000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 73 between the New Salem Road and Glen Vaughn Road is a two lane facility with 9' lanes and 4' shoulders. There are numerous horizontal curves on the road. There is also a significant amount of large slow moving farm machinery. Although this has not be
Y | 3 | Barren River ADD | IP20060197 |  |  |  | Improve safety by addressing vertical alignment deficiencies on KY-585 from the intersection with KY-73 to the intersection with Roark Road. | Reconstruction | Simpson | 107-KY-0585 -000 | 0 | 1.165 | 1.165 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 750000 |  | 1500000 |  | 3000000 |  | 2018-09-28 14:33 | Improve safety. | KY 585 from KY 73 to Roark Road is a narrow 2 lane facility with numerous horizontal curves. A sustantial amount of residential development currently exists in the area and has the potential for additional growth. There is a significant volume of large , | BARREN RIVER ADD | West | 30.7741 | 2.7629 | 11.3402 | 7.9768 | 3.2646 | 5.4296 | 0 | 0 | 31
Y | 3 | Barren River ADD | IP20060198 |  |  |  | Improve safety by addressing horizontal alignment deficiencies on KY 585 from Roark Road (MP 1.165) to I-65 overpass (MP 2.229). | Reconstruction | Simpson | 107-KY-0585 -000 | 1.165 | 2.229 | 1.064 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 1000000 |  | 1000000 |  | 2500000 |  | 2010-02-25 16:51 | Improve safety. | KY 585 from Roark Road to I 65 overpass is a narrow two lane facility with numerous horizontal curves. A substantial amount of residential development currently exists in the area and has the potential for additional growth. There is a significant volume
Y | 3 | Barren River ADD | IP20060199 |  |  |  | Reduce congestion and improve mobility along KY-1008 from US-31W south of Franklin to KY-100 west of Franklin. | Major Widening | Simpson | 107-KY-1008 -000 | 0 | 2.276 | 2.276 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1600000 |  | 6000000 |  | 5500000 |  | 10500000 |  | 2019-03-08 10:02 | Reduce congestion and increase mobility. | This section has numerous residential and commercial entrances. KY 1008 serves as a bypass for Franklin and has been designated by the Kentucky Department of Highways as a truck route in an attempt to reduce the truck traffic in downtown Franklin. Many | 3 | West | 72.1692 | 7.6632 | 3.5052 | 11.6366 | 2.3024 | 5.9107 | 3.6254 | 7.5258 | 42 | 15 | 15
Y | 3 | Bowling Green MPO | IP20060202 | 3-8904 / 3-8904 / 3-8904.10 |  | A | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | MINOR WIDENING(O) | Warren | 114-US-0031W -000 | 14.25 | 14.669 | 0.419 | Major Widening-Urban Streets | 25 |  |  |  | 1600000 | 2017 | 6660000 | 2019 | 7900000 | 2019 | 20470000 | 2020 | 2016-05-24 07:21 | Reduce congestion and increase mobility. | US 31W between KY 234 and US 68 is a four lane facility with 9' lanes. This section of roadway is a curb and gutter section. The ADT is 21,465 with 8.8% trucks. The original road was constructed as a two lane facility with parking on both sides, but was | 3 | West | 90.3428 | 9.1959 | 14.0206 | 14.0335 | 2.3024 | 9.3127 | 3.9863 | 7.4914 | 60 | 15 | 15
Y | 3 | Bowling Green MPO | IP20060204 |  |  |  | Improve safety and mobility on US 68 from Scotty's Way to I-65. | Reconstruction | Warren | 114-US-0068 -000 | 15.649 | 20.64 | 4.991 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 3000000 |  | 2000000 |  | 10000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | US 68 between Scotty's Way and I-65 is a two lane facility with 9' lanes and 4' shoulders. A number of horizontal curves exist on the road. This route provide access to I-65 for the Multimodal Transpark. It also provides a link to Bowling Green for peopl
Y | 3 | Bowling Green MPO | IP20060206 |  |  |  | Improve safety and mobility on US 231X from US 231 to US 31W. | Major Widening | Warren | 114-US-0231X -000 | 0 | 2.066 | 2.066 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 1000000 |  | 1500000 |  | 8000000 |  | 2019-03-08 12:01 | Improve safety and mobility. | US 231X between US 231/ KY 880 and US 31W is a four lane facility. A portion of the road is in a curb and gutter section and the remainder has 9' shoulders. Although some residences still exist along the roadway, the area is heavily commercial. The road p
Y | 3 | Bowling Green MPO | IP20060207 |  |  |  | Improve safety and mobility on US 231X between US 68 and US 68X. | Major Widening | Warren | 114-US-0231X -000 | 2.526 | 3.918 | 1.392 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 800000 |  | 1500000 |  | 3500000 |  | 2019-03-08 12:01 | Improve safety and mobility. | US 231X between US 68 and US 68X is a heavily used three lane facility. This route provides access to the Natcher Parkway. Land use along the route is mixed. An industry, restaurants, commercial facilities, a high school, and a technical school are locate
Y | 3 | Bowling Green MPO | IP20060208 |  |  |  | Improve safety and mobility on Smallhouse Road (CS-1334/CR-1235) from Cave Mill Road (CS-1401) to Campbell Lane (US-231). | Minor Widening | Warren | 114-CS-1334 -000 | 0.656 | 0.879 | 0.223 | Modernize Roadway-Urban | 16 |  | 0 |  | 1500000 |  | 5000000 |  | 5000000 |  | 8000000 |  | 2019-03-08 12:02 | Improve safety and mobility. | With the further development of this area and corresponding increase in traffic, improvements are needed on this route to increase safety and mobility. | Bowling Green MPO | West | 39.4631 | 8.8316 | 12.732 | 13.4149 | 4.4845 | 0 | 0 | 0 | 40
Y | 3 | Bowling Green MPO | IP20060209 |  |  |  | Improve safety and mobility on KY 526 between KY 1320 and US 31W. | Major Widening | Warren | 114-KY-0526 -000 | 5.665 | 6.388 | 0.723 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 800000 |  | 800000 |  | 1750000 |  | 2019-03-08 12:02 | Improve safety and mobility. | KY 526 between KY 1320 and US 31W is a two lane faciltity. This road was originally a farm to market road but the residential development that has occurred on this route has changed that function. The road now acts as a "cut through road" for motorists at
Y | 3 | Bowling Green MPO | IP20060210 |  |  |  | Improve safety and mobility on KY 622 from Plano-Richpond Road to US 231. | Reconstruction | Warren | 114-KY-0622 -000 | 5.262 | 8.332 | 3.07 | Other Improvement Types | 0 |  | 0 |  | 1700000 |  | 5000000 |  | 4900000 |  | 9600000 |  | 2019-03-08 12:03 | Improve safety and mobility. | KY 622 between the Plano - Richpond Road and US 231 is a two lane facility. There are a number of horizontal curves on the road. One reverse turn situation is especially an area of concern. The road was originally a farm to market road, but has experience
Y | 3 | Bowling Green MPO | IP20060211 |  |  |  | Improve safety and provide a facility for pedestrians on KY 957 from US 31W to Redbird Trail. | Major Widening | Warren | 114-KY-0957 -000 | 0 | 1.42 | 1.42 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 500000 |  | 500000 |  | 3000000 |  | 2019-03-08 12:03 | Improve safety. | KY 957 between US 31W and Redbird Trail is a narrow, two lane facility. This road provides the link between the City of Plum Springs and US 31W. The road is used as a "cut through" route for motorists from the north central portion of Warren County. There
Y | 3 | Barren River ADD | IP20060300 |  |  |  | Improve access and mobility by providing a connection between US 31W south and the Portland Industrial Authority and the potential Southern Simpson County Industrial Park including the new interchange of TN 109 at I 65. | New Route | Simpson | 107-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2500000 |  | 2000000 |  | 10000000 |  | 2010-12-27 15:50 | Improve access and mobility. | Improve access and mobility by providing a connection between US 31W south and the Portland Industrial Authority and the potential Southern Simpson County Industrial Park including the new interchange of TN 109 at I 65.
Y | 3 | Bowling Green MPO | IP20060301 |  |  |  | Improve safety and mobility on Beech Bend Road from MP 0 to MP 0.428 to allow better access for pedestrians and vehicles to a major tourist attraction and other points in the area. | Major Widening | Warren | 114-CS-1333 -000 | 0 | 0.428 | 0.428 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1500000 |  | 1000000 |  | 8000000 |  | 2019-03-08 12:03 | Improve safety and mobility. | Access to Beech Bend Park, a major tourist attraction, is severely limited. Annual attendance is approaching 1,000,000, with some individual events attracting 100,000. The park is served by a narrow two lane urban collector street, which at peak periods
Y | 3 | Bowling Green MPO | IP20060302 |  |  |  | Provide a secondary connection from US 31W to Beech Bend Park to improve access and mobility; ensure the safety and security of the visitors; and maintain the economic viability of this attraction. | New Route | Warren | 114-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 650000 |  | 350000 |  | 6000000 |  | 2011-01-06 12:15 | Improve access, mobility, safety, and economic development. | A secondary access is needed for Beech Bend Park. Current access is limited to the Beech Bend Park via Beech Bend Road off of US31W. This existing narrow two lane road is inadequate to handle the 1,000,000 tourists that visit the park each year. To reli
Y | 3 | Barren River ADD | IP20070129 |  |  |  | Provide connection, improve safety, increase mobility, and address geometric deficiencies on KY-185 from the Green River bridge to the Edmonson County line. | Minor Widening | Butler | 016-KY-0185 -000 | 0.002 | 6.61 | 6.608 | Modernize Roadway-Rural | 26 |  | 250000 |  | 3500000 |  | 4500000 |  | 4500000 |  | 18000000 |  | 2018-09-26 13:57 | Provide connection, improve safety, increase mobility, and address geometric deficiencies. | KY185 (Green River Bridge-KY70) is a two lane facility with numerous horizontal and vertical curves. The road serves as a major travel route for commuters from Butler, western Edmonson, and western Grayson to workplaces and shopping areas in Warren County | BARREN RIVER ADD | West | 33.2079 | 2.0825 | 9.1237 | 10.3866 | 2.3024 | 0 | 0 | 9.3127 | 33
Y | 3 | Barren River ADD | IP20070130 |  |  |  | Improve safety and mobility on US-31W between KY-621 and the Warren County line. | Major Widening | Simpson | 107-US-0031W -000 | 10.779 | 13.984 | 3.205 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 0 |  | 1200000 |  | 2000000 |  | 3200000 |  | 8500000 |  | 2018-09-28 14:20 | Improve safety and mobility. | US31W between KY 621 in Simpson County and KY 240 in Warren County is with one exception a two lane facility. The Kentucky Dept of Highways constructed turning lanes on a .5 mile section in an industrial development area. Industrial and commercial develop | BARREN RIVER ADD | West | 36.4416 | 5.5052 | 2.6804 | 8.8918 | 0.75601 | 6.4605 | 4.1753 | 7.9725 | 36
Y | 3 | Barren River ADD | IP20070131 | 3-8855 / 3-8855.01 |  | A | IMPROVE KY-1008 FROM KY-73 TO NORTH FRANKLIN STREET. (14CCN) | MAJOR WIDENING(O) | Simpson | 107-KY-1008 -000 | 3.688 | 4.333 | 0.645 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 3240000 | 2022 | 3980000 | 2022 | 5680000 | 2023 | 2019-02-27 11:39 | Reduce congestion and increase mobility. | Ky 1008 between KY 73 and KY 3498 is a two lane facility with numerous residential and commercial entrances. KY 1008 serves as an eastern bypass for Franklin and had been designated by the Kentucky Department of Highways as a truck route in an attempt to | 3 | West | 72.7131 | 6.811 | 7.5258 | 8.1701 | 2.3024 | 7.354 | 4.4674 | 6.0825 | 43 | 15 | 15
Y | 3 | Pennyrile ADD | IP20070132 |  |  |  | Improve safety and access on KY 181 from US 41 in Guthrie (MP 0.21) to Elkton City Limits (MP 10.955). | Reconstruction | Todd | 110-KY-0181 -000 | 0.21 | 10.955 | 10.745 | Other Improvement Types | 0 |  | 0 |  | 3500000 |  | 7500000 |  | 6000000 |  | 24000000 |  | 2010-02-25 16:51 | Improve safety and access. | This section of KY 181 has narrow 9/2 lanes and poor geometrics. There is a great deal of commuter traffic on this route to access the Clarksville, TN job market. There is also safety issues with the lack of shoulders that need to be utilized by the Ami
Y | 3 | Bowling Green MPO | IP20070133 |  |  |  | Improve access with a new interchange on I-65 at KY 240. | New Interchange | Warren | 114-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 |  | 0 |  | 900000 |  | 1000000 |  | 700000 |  | 8000000 |  | 2019-01-23 11:41 | Improve access. | I 65 between KY 100 (Exit # 6) in Simpson County and the Natcher Parkway (Exit #20) in Warren County is a heavily traveled facility. This section has recently been widened to six lanes. The barrier median wall could possibly hamper efforts by emergency
Y | 3 | Bowling Green MPO | IP20070134 |  |  |  | IMPROVE SAFETY AND MOBILITY ON US 31W BYPASS FROM UNIVERSITY BLVD TO FAIRVIEW AVE (KY 234) IN BOWLING GREEN. | Reconstruction | Warren | 114-US-0031W -000 | 11.805 | 13.699 | 1.894 | Modernize Roadway-Urban | 16 |  | 0 |  | 1500000 |  | 12000000 |  | 12000000 |  | 7500000 |  | 2019-03-08 13:03 | Improve safety and mobility. | US 31W between US 231X (University Blvd.) and KY 234 (Cemetary Rd.) is a four lane facility with narrow lanes. Turning lanes exist only at locations (intersection with Cabell Drive and between Lehman Ave. and KY 234) that were reconstructed as safety (H
Y | 3 | Bowling Green MPO | IP20070135 |  |  |  | Provide bicycle and pedestrian facilities in order to improve the safety on US 31W between KY 957 and US 68. | Reconstruction | Warren | 114-US-0031W -000 | 18.085 | 20.905 | 2.82 | Bike and Pedestrian Improvements | 13 |  | 0 |  | 400000 |  | 100000 |  | 300000 |  | 2500000 |  | 2019-03-08 13:04 | Improve safety. | US 31W between KY 957 and US 68 is a four lane facility. US 31W is a major route through this area, as indicated by the traffic volume. US 31W has been designated by the Kentucky Department of Highways as the route in this region to be the focus of a ye
Y | 3 | Bowling Green MPO | IP20070136 |  |  |  | Improve safety and mobility on US 31W from US 68 in Warren County to KY 255 in Barren County. | Major Widening | Warren | 114-US-0031W -000 | 20.905 | 28.793 | 7.888 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 5000000 |  | 14000000 |  | 10000000 |  | 65000000 |  | 2018-12-10 10:11 | Improve safety and mobility. | US 31W between US 68 in Warren County and KY 255 in Barren County is primarily a two lane facility. Much of the traffic is commuter traffic to employment sites in and around Bowling Green. It serves as a major travel route for people in Edmonson County an
Y | 3 | Bowling Green MPO | IP20070137 |  |  |  | Reduce congestion and improve safety on US 68X from US 231 to US 231X. | Major Widening | Warren | 114-US-0068X -000 | 0 | 1.524 | 1.524 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2000000 |  | 4000000 |  | 8000000 |  | 2010-02-25 16:51 | Reduce congestion and improve safety. | US 68 between US 231 and US 231X (University Blvd.) provides a direct link between the William H. Natcher Parkway and Western Kentucky University. Panel signs on the William H. Natcher Parkway direct motorists to use this route to access Western Kentucky
Y | 3 | Bowling Green MPO | IP20070138 |  |  |  | Improve safety of the intersection at US 231 and KY 626 (west). | Spot Improvement | Warren | 114-US-0231 -000 | 21.5 | 21.7 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 120000 |  | 80000 |  | 300000 |  | 2010-02-25 16:51 | Improve safety. | The US 231 - KY 626 (West) intersection is located below the crest of a verticle curve. This is a "T" intersection. This intersection is located south of a verticle curve known locally as "Hadley Hill." Sight distance is limited due to the verticle curve
Y | 3 | Bowling Green MPO | IP20070139 |  |  |  | Improve safety of the intersection at US 231 and KY 626 (east). | Spot Improvement | Warren | 114-US-0231 -000 | 22.6 | 22.8 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 120000 |  | 80000 |  | 300000 |  | 2010-02-25 16:51 | Improve safety. | The US 231 - KY 626 (East) intersection is located near the crest of a long vertical curve. This vertical curve is known locally as Hadley Hill. A safety (HES) construction project has been completed on a portion of this hill south of this intersection. T
Y | 3 | Bowling Green MPO | IP20070140 |  |  |  | Improve safety and mobility on KY 101 between the Allen County Line and I-65. | Reconstruction | Warren | 114-KY-0101 -000 | 0 | 7.865 | 7.865 | Other Improvement Types | 0 |  | 0 |  | 2600000 |  | 2600000 |  | 1500000 |  | 26100000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 101 between the Allen County Line and I-65 is a two lane facility with horizontal and verticle curves. This route serves as a connection between US 31E in Scottsville and I-65 at Smiths Grove. Much of the traffic is commuter traffic. This is expected
Y | 3 | Bowling Green MPO | IP20070141 |  |  |  | Improve safety and mobility on KY 234 between Drakes Creek and the Allen County Line. | Reconstruction | Warren | 114-KY-0234 -000 | 0 | 9.553 | 9.553 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 7000000 |  | 5000000 |  | 30000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 234 between Drakes Creek and the Allen County Line is a two lane facility with numerous vertical and horizontal curves. This route provides a primary access to the Barren River Lake, thus much of the traffic is recreational in nature with trailers, boa
Y | 3 | Bowling Green MPO | IP20070142 |  |  |  | Improve safety and mobility at the intersection of KY 242 and KY 884. | Spot Improvement | Warren | 114-KY-0242 -000 | 5.033 | 5.233 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 50000 |  | 125000 |  | 250000 |  | 2011-10-17 09:33 | Improve safety and mobility. | The KY 242 - KY 884 intersection is an intersection of narrow, two lane roads. There are no left turn lanes, but bifurcated right turn lanes do exist. Safety is a concern. This intersection was identified by the Kentucky Transportation Center as being o
Y | 3 | Bowling Green MPO | IP20070143 |  |  |  | Improve safety and mobility on KY 526 from KY 185 to the eastern intersection of Garrett Hollow Road. | Reconstruction | Warren | 114-KY-0526 -000 | 0 | 2.803 | 2.803 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 2500000 |  | 1870000 |  | 5500000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 526 between KY 185 and the eastern intersection with Garrett Hollow road is a narrow two lane facility with numerous horizontal and vertical curves. This road was originally a farm to market road but has now become a collector due to the residential d
Y | 3 | Bowling Green MPO | IP20070144 |  |  |  | Improve safety and mobility on KY 526 from the eastern intersection of Garrett Hollow Road to KY 957. | Reconstruction | Warren | 114-KY-0526 -000 | 2.803 | 3.793 | 0.99 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 800000 |  | 800000 |  | 2500000 |  | 2019-03-08 13:16 | Improve safety and mobility. | KY 526 between the eastern intersection with the Garrett Hollow Road and KY 957 is a narrow two lane facility with numerous horizontal and verticle curves. The road was originally a farm to market road but has become a collector due to the residential de
Y | 3 | Bowling Green MPO | IP20070145 |  |  |  | Improve safety and mobility on KY 526 from KY 957 to KY 1320. | Reconstruction | Warren | 114-KY-0526 -000 | 3.793 | 5.553 | 1.76 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 1200000 |  | 1190000 |  | 3500000 |  | 2019-03-08 13:17 | Improve safety and mobility. | KY 526 between KY 957 and KY 1320 is a narrow, two lane facitity. This road was originally a farm to market road but now the area around the KY 526 - KY 957 intersection is developing rapidly with substantial residential uses that spread into the City of
Y | 3 | Bowling Green MPO | IP20070146 |  |  |  | Improve safety of the intersection at KY 622 and KY 242. | Spot Improvement | Warren | 114-KY-0622 -000 | 2.786 | 2.986 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 25000 |  | 35000 |  | 75000 |  | 100000 |  | 2010-02-25 16:51 | Improve safety. | The intersection of KY 622 and KY 242 is a "T" intersection. KY 242 intersects in a skew which makes turning movements difficult, especially for large vehicles. There are horizontal curves on the KY 242 approach and the northbound KY 622 approach. There i
Y | 3 | Bowling Green MPO | IP20070147 |  |  |  | Improve safety and mobility on KY 622 from 0.1 mile south of Collett Road to Dewey Lake Road. | Spot Improvement | Warren | 114-KY-0622 -000 | 6.454 | 6.895 | 0.441 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 200000 |  | 200000 |  | 1450000 |  | 2015-08-19 18:01 | Improve safety and mobility. | KY 622 between a point 0.10 mile south of Collett Road and Dewey Lake Road is a narrow, two lane facility. The road was originally a farm to market road but has experienced a tremendous growth pattern as evidenced by the traffic volume. It is possible tha | 3 | West | 31.3076 | 6.11 | 7.3196 | 7.0876 | 4.4674 | 0 | 0 | 6.323 | 31
Y | 3 | Bowling Green MPO | IP20070148 |  |  |  | Improve safety and mobility on KY 957 from Red Bird Trail to KY 526. | Minor Widening | Warren | 114-KY-0957 -000 | 1.416 | 3.331 | 1.915 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1500000 |  | 2410000 |  | 4500000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 957 between Red Bird Trail and KY 526 is a narrow, two lane facility. Residential development has increased dramatically. Once a farm to market road, this roadway is now a collector for the subdivisions along the road, as well as, those motorists usi
Y | 3 | Bowling Green MPO | IP20070149 |  |  |  | Improve safety of KY 2632 from Whitestone Quarry Road to US 231 and the KY 2632/US 231 intersection. | Reconstruction | Warren | 114-KY-2632 -000 | 4.11 | 5.057 | 0.947 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 650000 |  | 500000 |  | 2000000 |  | 2010-02-25 16:51 | Improve safety. | KY 2632 between US 231 and Whitestone Quarry Road is a long vertical curve with several horizontal curves along the way. The road has recently been resurfaced and 18" penetrated shoulders added where possible. Although the truck percentage is unknown, it
Y | 3 | Bowling Green MPO | IP20070252 |  |  |  | Improve mobility on KY 2158 to US 231 by connecting KY 2158 to Cherry Farm Lane. | Relocation | Warren | 114-PF-9999 - |  |  |  | Install Two-way Left Turn Lane | 28 |  | 0 |  | 450000 |  | 2000000 |  | 500000 |  | 2000000 |  | 2019-03-08 13:20 | Improve mobility. | KY 2158 is a two lane facility with a high ADT of 8,610. This route is a commuter route for numerous traffic generators adjacent to it. There is limited distance (approximatley 400 feet) between KY 2158 and the I 65 Northbound ramps. Lanes on both KY 21
Y | 3 | Barren River ADD | IP20080124 |  |  |  | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-100 | Reconstruction | Allen | 002-KY-0100 -000 | 0.4 | 3.1 | 2.7 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 580000 |  | 1300000 |  | 8700000 |  | 2010-02-25 16:51 | Improve safety and reduce congestion. | KY 100 is a rural two-lane facility with 10' lanes and 2' shoulders. Heavy vehicles make up a relatively large proportion of the traffic composition on this route, and there is also a significant amount of horse and buggy traffic due to the large number
Y | 3 | Barren River ADD | IP20080125 | 3-320 |  | A | IMPROVEMENTS TO KY 100: CURVE, BRIDGE, AND INTERSECTION IMPROVEMENTS FROM NEAR THE STONY POINT ROAD INTERSECTION TO EAST OF THE ALONZO LONG HOLLOW ROAD INTERSECTION (12CCR)(18CCN) | RECONSTRUCTION(O) | Allen | 002-KY-0100 -000 | 3.1 | 4.2 | 1.1 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1620000 | 2020 | 1160000 | 2021 | 10770000 | 2023 | 2019-02-27 11:42 | Improve safety. | Improve safety on KY100 by completing spot impovements between MP 2.7 and 4.5. This project includes improvements to two bridges--The Long Hollow Branch Bridge, located at Mile Point 4.129, and the Middle Fork Drakes Creek Bridge, located at Mile Point 3 | 3 | West | 68.8875 | 4.0206 | 8.8144 | 9.2655 | 1.323 | 6.2887 | 2.7491 | 6.4261 | 39 | 15 | 15
Y | 3 | Barren River ADD | IP20080126 |  |  |  | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-100. | Reconstruction | Allen | 002-KY-0100 -000 | 7.5 | 8.2 | 0.7 | Other Improvement Types | 0 |  | 0 |  | 170000 |  | 93000 |  | 210000 |  | 1400000 |  | 2010-02-25 16:51 | Improve safety and reduce congestion. | KY 100 is primarily a rural two-lane facility with 10' lanes and 2' shoulders. Heavy vehicles make up a relatively large proportion of the traffic composition on this route, and there is also a significant amount of horse and buggy traffic due to the lar
Y | 3 | Barren River ADD | IP20080127 |  |  |  | Improve safety and mobility on KY 100 at the intersection with Oliver Street. | Spot Improvement | Allen | 002-KY-0100 -000 | 11.885 | 11.985 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 300000 |  | 275000 |  | 400000 |  | 2019-03-04 14:31 | Improve safety and mobility. | KY 100 is a rural two-lane facility with 10' lanes and 2' shoulders. Heavy vehicles make up a relatively large proportion of the traffic composition on this route, and there is also a significant amount of horse and buggy traffic due to the large number | BARREN RIVER ADD | West | 24.5335 | 5.3196 | 4.6392 | 4.4716 | 1.5464 | 0 | 2.9553 | 5.6014 | 24
Y | 3 | Barren River ADD | IP20080128 | 3-8802 |  | A | WIDENING OF KY 100 (FRANKLIN ROAD) TO 3 LANES WITH URBAN SECTION FROM OLIVER STREET TO US 31E TO INCREASE CAPACITY/SAFETY. MP 11.800-12.700 (14CCN)(18CCN) | MAJOR WIDENING(O) | Allen | 002-KY-0100 -000 | 11.8 | 12.7 | 0.9 | Install Two-way Left Turn Lane | 28 |  |  |  | 260000 | 2021 | 310000 | 2022 | 330000 | 2023 | 450000 | 2024 | 2019-02-28 14:12 | Improve safety and mobility. | KY 100 is primarily a rural two-lane facility with 10' lanes and 2' shoulders. Heavy vehicles make up a relatively large proportion of the traffic composition on this route, and there is also a significant amount of horse and buggy traffic due to the la | BARREN RIVER ADD | West | 37.8162 | 6.0893 | 5.8247 | 7.5 | 1.323 | 7.732 | 3.1271 | 6.2199 | 38
Y | 3 | Barren River ADD | IP20080129 |  |  |  | Lane departure safety improvements on KY-79 between the KY-70 crossroads and the Grayson County line. | Safety-Haz-Elm | Butler | 016-KY-0079 -000 | 12.538 | 24.901 | 12.363 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 500000 |  | 500000 |  | 2500000 |  | 2018-09-26 13:54 | Improve safety and mobility. | KY 79 between the intersection of US 231 and the Grayson County Line is a two-lane facility. There are numerous horizontal and vertical curves. KY 79 provides a link to the Western Kentucky Parkway. There is some concern in the community that trucks are | 3 | West | 45.4442 | 2.811 | 14.3299 | 13.6469 | 4.8969 | 0 | 0 | 9.7595 | 45
Y | 3 | Barren River ADD | IP20080130 |  |  |  | Improve safety and mobility on KY 259 from north of Kyrock Road to the Grayson County Line. | Safety-Haz-Elm | Edmonson | 031-KY-0259 -000 | 15.633 | 22.24 | 6.607 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 250000 |  | 250000 |  | 1500000 |  | 2018-09-26 14:29 | Improve safety and mobility. | KY 259 between Old Kyrock Road and the Edmonson/Grayson County Line is a narrow two-lane facility. There are numerous horizontal and vertical curves along the roadway. There are locations along the corridor segment where, historically, crashes have been | BARREN RIVER ADD | West | 46.7397 | 3.8832 | 14.7938 | 11.482 | 4.6564 | 0 | 2.7835 | 9.1409 | 47
Y | 3 | Barren River ADD | IP20080131 |  |  |  | Improve safety at the intersection split of US 68 and KY 80 in Edmonton. | Safety-Haz-Elm | Metcalfe | 085-US-0068 -000 | 8.77 | 9.24 | 0.47 | Improve Intersection | 26 |  | 0 |  | 75000 |  | 150000 |  | 200000 |  | 400000 |  | 2015-03-12 12:31 | Improve safety. | This section os US 68 is a two-lane facility with 12' lane with the exception of mile points 9.0 to 9.24 which has 10' lanes. Mile points 8.77 to 8.9 have 6' stablized shoulders while mile points 8.9 to 9.24 have 2' combination shoulders. The change in ro | 3 | West | 34.6924 | 5.354 | 13.6082 | 5.7474 | 0.94502 | 0 | 3.1615 | 5.8763 | 35
Y | 3 | Barren River ADD | IP20080134 |  |  |  | Improve safety and reduce congestion along KY 163 from MP 3.22 to MP 3.55. | Reconstruction | Metcalfe | 085-KY-0163 -000 | 3.22 | 3.55 | 0.33 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 100000 |  | 345000 |  | 600000 |  | 2010-02-25 16:51 | Improve safety and reduce congestion. | This segment of KY 163 is a two lane facility with 9' lanes and 2' shoulders. A vertical curve in this segment exceeds the 7% maximum grade limitation. The grade of this section is &.8%/ Slow moving trucks and other large vehicles traveling northbound cre
Y | 3 | Barren River ADD | IP20080135 |  |  |  | Improve safety and sight distance issues on KY 163 from MP 8.98 to MP 9.58. | Reconstruction | Metcalfe | 085-KY-0163 -000 | 8.98 | 9.58 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 350000 |  | 400000 |  | 2000000 |  | 2010-02-25 16:51 | Improve safety. | KY 163 at Cedar Flats is a two lane facility with 9' lanes and 2' shoulders. This segment is a heavily traveled northsouth corridor. There are many horizontal and vertical curves in this area that cause difficulties with stopping sight distance. Currentl
Y | 3 | Barren River ADD | IP20080136 |  |  |  | IMPROVE SAFETY ALONG KY-163 IN THE AREA NORTH OF THE PROPOSED TOMPKINSVILLE BYPASS. | Reconstruction | Monroe | 086-KY-0163 -000 | 7.4 | 8 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 400000 |  | 200000 |  | 2000000 |  | 2010-02-25 16:51 | Improve safety. | KY 163 between the Tennessee state line and Tompkinsville is a rural, 2-lane corrdior with 11' lanes and 2' shoulders. Large commercial vehicles use this route as a connector between I-40 in Tennessee and the Louie B. Nunn Cumberland Parkway in Kentucky
Y | 3 | Barren River ADD | IP20080137 |  |  |  | Improve safety on KY 163 from the Tennessee State Line to 0.465 mile north of Denton Murphy Road. | Safety-Haz-Elm | Monroe | 086-KY-0163 -000 | 0 | 1.9 | 1.9 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1300000 |  | 2500000 |  | 5000000 |  | 2019-03-08 09:12 | Improve safety. | KY 163 between the Tennessee state line and Tompkinsville is a rural, 2-lane corrdior with 11' lanes and 2' shoulders. Large commercial vehicles use this route as a connector between I-40 in Tennessee and the Louie B. Nunn Cumberland Parkway in Kentucky | 3 | West | 21.3454 | 3.0034 | 2.3196 | 2.5 | 3.7457 | 0 | 2.7663 | 7.0103 | 21
Y | 3 | Barren River ADD | IP20080138 |  |  |  | Improve safety along KY-163 at Ned Jackson Road in the Hestand area. | Minor Widening | Monroe | 086-KY-0163 -000 | 2 | 4.1 | 2.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 850000 |  | 1400000 |  | 2700000 |  | 5500000 |  | 2018-09-28 13:57 | Improve safety. | KY 163 between the Tennessee State Line and Tompkinsville is a rural, 2-lane corridor with 11' lanes and 2' shoulders. Large commercial vehicles use this route as a connector between I-40 in Tennessee and the Louie B Nunn Cumberland Parkway in Kentucky. T | BARREN RIVER ADD | West | 21.4622 | 3.0859 | 2.3711 | 2.6031 | 3.2474 | 0 | 2.8694 | 7.2852 | 22
Y | 3 | Barren River ADD | IP20080139 |  |  |  | Improve safety of the KY-163 intersection with KY-3144 (Capp Harlan Rd). | Spot Improvement | Monroe | 086-KY-0163 -000 | 6.14 | 6.16 | 0.02 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 150000 |  | 200000 |  | 500000 |  | 2018-09-28 13:58 | Improve safety. | KY 163 between the Tennessee state line and rural 2-lane corridor with 11' lanes and 2' shoulders. Large Commercial vehicles use this route as a connector between I-40 in Tennessee and the Louie B Nunn Cumberland Parkway in Kentucky. This segment includes | 3 | West | 10.7801 | 3.4433 | 0 | 0 | 1.323 | 0 | 2.9897 | 3.0241 | 11
Y | 3 | Barren River ADD | IP20080140 |  |  |  | Improve safety on KY 163 from KY 3144 to Jane Yokley Cemetery Road near Tompkinsville. | Reconstruction | Monroe | 086-KY-0163 -000 | 6.15 | 7.05 | 0.9 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 700000 |  | 300000 |  | 3000000 |  | 2010-02-25 16:51 | Improve safety. | KY 163 between the TN state line and Tompkinsville is a rural, 2-lane corridor with 11' lane and 2' shoulders, Large commercial vehicles use this route as a connector between I-40 in Tennessee and the Louie B Nunn Cumberland Parkway. This area known as Ma
Y | 3 | Barren River ADD | IP20080141 | 3-8856 |  | A | IMPROVE US-31W FROM KY-1008 TO KY-621. (14CCN)(16CCR) | MAJOR WIDENING(O) | Simpson | 107-US-0031W -000 | 8.477 | 11.937 | 3.46 | Install Two-way Left Turn Lane | 28 |  |  |  | 1560000 | 2021 | 1740000 | 2023 | 4870000 | 2025 | 12660000 | 2025 | 2019-03-13 08:58 | Improve safety and mobility. | US 31W between KY 1008 and the north industrial park is predominantly a two lane facility. There is a .6 mile section of this roadway that was widened to four lanes to accommodate the turning movements at a factory. US31W is the major non-interstate, nort | 3 | West | 77.5601 | 4.8454 | 11.4433 | 12.4742 | 0.94502 | 6.4605 | 4.1753 | 7.2165 | 48 | 15 | 15
Y | 3 | Pennyrile ADD | IP20080143 |  |  |  | Address safety issues with the curve on KY 106 from Hadden Mill Road to east of the intersection with KY 181. | Safety-Haz-Elm | Todd | 110-KY-0106 -000 | 0.35 | 0.74 | 0.39 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 750000 |  | 550000 |  | 1000000 |  | 2019-03-08 10:07 | Improve safety. | This section of the road is a hill with an "S" curve. This has a high CRF and most accidents go unreported. | PENNYRILE ADD | West | 17.8857 | 1.0859 | 3.8144 | 4.1881 | 4.1237 | 0 | 0 | 4.6735 | 18
Y | 3 | Pennyrile ADD | IP20080144 |  |  |  | Improve safety and address deficiencies concerning vertical and horizontal alignments from US 68 TO KY 171 north of Elkton. | Reconstruction | Todd | 110-KY-0181 -000 | 13.042 | 16.17 | 3.128 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 1200000 |  | 4000000 |  | 11000000 |  | 2010-02-25 16:51 | Improve safety. | KY 181 is a 2-lane road that has vertical and horizontal alignment problems. The alignment problems together with the existing 2/9 lanes create unsafe conditions for truck traffic and other vehicles.
Y | 3 | Bowling Green MPO | IP20080145 |  |  |  | REDUCE CONGESTION AND INCREASE SAFETY AND MOBILITY ON US-31W AT THE INTERSECTION OF 10TH AVENUE. | Reconstruction | Warren | 114-US-0031W -000 | 13 | 13.1 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 500000 |  | 400000 |  | 600000 |  | 2019-03-08 13:21 | Reduce congestion and increase safety and mobility. | US 31W is one of the major non-interstate north-south routes through Warren County and has been designated as a safety corridor by Kentucky Transportation Cabinet. US 31W is a four lane facility with 10' lanes and curbed shoulder. The turning movements, l | Bowling Green MPO | West | 44.6168 | 9.2646 | 14.6907 | 10.799 | 2.3024 | 0 | 3.4708 | 4.0893 | 45
Y | 3 | Bowling Green MPO | IP20080146 |  |  |  | IMPROVE SAFETY AND MOBILITY ON US 231 BETWEEN WILLIAM H. NATCHER PARKWAY AND KY-2632. | Major Widening | Warren | 114-US-0231 -000 | 15 | 16.8 | 1.8 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 700000 |  | 2700000 |  | 12000000 |  | 2019-03-08 13:22 | Improve safety and mobility. | US 231 between the William H. Natcher Parkway and KY 2632 is predominantly a two lane facility with an ADT over 6,500. There are no turning lanes on the two lane portion of this roadway. There are several horizontal and verticle curves that limit sight di
Y | 3 | Bowling Green MPO | IP20080147 |  |  |  | IMPROVE SAFETY ON KY-234 AT PLEASANT HILL ROAD INTERSECTION. | Spot Improvement | Warren | 114-KY-0234 -000 | 6 | 6.3 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 160000 |  | 130000 |  | 420000 |  | 2010-02-25 16:51 | Improve safety. | KY 234 is a narrow two lane facility with 9' lanes and 4' shoulders. This route provides direct access to the Barren River Lake, which creates significant recreational traffic hauling trailers, boats, and campers. A December 6, 2007 Road Safety Audit wa
Y | 3 | Bowling Green MPO | IP20080148 |  |  |  | IMPROVE SAFETY AND MOBILITY ON KY 263 FROM AMBER WHITE ROAD TO KY 185. | Reconstruction | Warren | 114-KY-0263 -000 | 0 | 12.579 | 12.579 | Other Improvement Types | 0 |  | 0 |  | 4500000 |  | 3600000 |  | 6000000 |  | 50000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 263 is a narrow two lane facility with 9' lanes that extends from northern Warren County near Butler County to Richardsville. The Barren River runs parallel to KY 263, acting as a natural divide by cutting off easy access to northern Warren County an
Y | 3 | Bowling Green MPO | IP20080149 |  |  |  | IMPROVE SAFETY AND MOBILITY ON KY-884 FROM THE INTERSECTION WITH KY-242 TO INTERSECTION WITH LONG ROAD. | Reconstruction | Warren | 114-KY-0884 -000 | 3.616 | 5.516 | 1.9 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 500000 |  | 2000000 |  | 3000000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 884 between KY 242 and Long Road is a narrow two lane facility with 9' lanes and 2' shoulders with an ADT of 3,350. KY 884 is developing rapidly with numerous large subdivisions emerging, as well as private residences and small commercial development
Y | 3 | Bowling Green MPO | IP20080151 |  |  |  | IMPROVE SAFETY AND MOBILITY ON KY-1435 FROM US-231 TO THE PROPOSED KY-263 BRIDGE CONNECTOR IN WARREN AND BUTLER COUNTIES. | Reconstruction | Warren | 114-KY-1435 -000 | 0 | 14.039 | 14.039 | Other Improvement Types | 0 |  | 0 |  | 1100000 |  | 1500000 |  | 1700000 |  | 13300000 |  | 2010-02-25 16:51 | Improve safety and mobility. | KY 1435 is a narrow two lane facility that extends from US 231 in Butler County to US 68 (Veteran's Memorial Boulevard) in Bowling Green. The Barren River runs parallel to KY 1435, acting as a natural divide by cutting off easy access to northern Warren
Y | 3 | Bowling Green MPO | IP20080152 |  |  |  | Improve safety and mobility on KY 2629 (Old Scottsville Road) from KY 2158 (Cumberland Trace Road) to Blue Springs Drive. | Reconstruction | Warren | 114-KY-2629 -000 | 5.995 | 6.536 | 0.541 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 300000 |  | 600000 |  | 2000000 |  | 2019-03-08 13:24 | Improve safety and mobility. | KY 2629 (Old Scottsville Road) between KY 2158 (Cumberland Trace Road) and Blue Springs Drive is a narrow two lane facility with numerous signficant horizontal and vertical curves, no turning lanes and narrow earth shoulders. This area has been developed
Y | 3 | Bowling Green MPO | IP20080153 |  |  |  | IMPROVE ACCESS ON WILLIAM H NATCHER PARKWAY AT KY-626 FOR WESTERN WARREN COUNTY AND EASTERN BUTLER. | New Interchange | Warren | 114-PF-9999 - |  |  |  | Other Improvement Types | 0 | Y | 0 |  | 1000000 |  | 1250000 |  | 1250000 |  | 16500000 |  | 2010-02-25 16:51 | Improve access. | William Natcher Parkway is a four lane fully controlled access facility that provides a link between Bowling Green and Owensboro. The existing four interchanges in Warren County on the Natcher Parkway are located near or within the city limits of Bowlin
Y | 3 | Bowling Green MPO | IP20080751 |  |  |  | Improve safety on US-68X from the Kentucky/Adams Street split to US-68/KY-234. | Minor Widening | Warren | 114-US-0068X -000 | 2.118 | 3.249 | 1.131 | Modernize Roadway-Urban | 16 |  | 225000 |  | 1000000 |  | 6000000 |  | 4000000 |  | 4000000 |  | 2019-03-08 13:25 | Improve safety. | The US 68X corridor provides a direct between Bowling Green and Russellville, as well as providing a direct connection to Western Kentucky University. This portion of US 68X is a four lane heavily traveled roadway with a mixed land use of commercial, sing | Bowling Green MPO | West | 43.0842 | 8.4536 | 3.2474 | 11.6753 | 1.8729 | 8.488 | 4.3643 | 4.9828 | 43
Y | 3 | Barren River ADD | IP20080753 |  |  |  | Improve access by providing a route for vehicles, particularly trucks, to bypass the center of Scottsville. | Bypass | Allen | 002-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 0 |  | 3000000 |  | 5000000 |  | 2500000 |  | 26000000 |  | 2016-11-03 15:57 | Improve access. | Presently there is no route for vehicles (especially large vehicles) on the southeastern side of Scottsville to bypass the center of town. Vehicles must use KY 100 through the center of town or city streets that were not designed for the volume or weight
Y | 3 | Barren River ADD | IP20080754 | 3-8859 |  | A | RECONSTRUCT KY 163 AS A NEW ROUTE ON WEST SIDE OF EDMONTON FROM KY 163 AT GARY BELL RD (MP 10.0) S OF EDMONTON CROSSING US 68 (STOCKTON ST) 2000 FT WEST OF THE COURTHOUSE SQ, TO US 68 (GREENSBURG ST) AT I-CHNG WITH NUNN PKWY (MP 9.8).(14CCN)(16CCR)(18CCN) | RECONSTRUCTION(O) | Metcalfe | 085-KY-0163 -000 | 9.777 | 11.22 | 1.443 | Construct Road in New Location | 0 |  |  |  | 1090000 | 2020 | 3480000 | 2021 | 2470000 | 2022 | 13980000 | 2023 | 2019-03-01 09:18 | Improve safety and mobility. | US 68 and KY 80 are currently used to access the City of Edmonton from the North. These roads have high volumes of truck traffic (9-12 percent) as well as documented crash histories. This route will connect to a new Northern route which, when completed, | BARREN RIVER ADD | West | 22.5034 | 3.2165 | 1.9072 | 5.3866 | 1.9759 | 7.1821 | 2.8351 | 0 | 22
Y | 3 | Barren River ADD | IP20110031 |  |  |  | Improve safety and mobility on US 31W in Park City from KY 255 North intersection to the new KY 255 South intersection. | Spot Improvement | Barren | 005-US-0031W -000 | 0.733 | 0.925 | 0.192 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 150000 |  | 150000 |  | 300000 |  | 2019-03-04 15:07 | Improve safety and mobility. | Resulting from the recent D-3 mini-prioritization, this project is proposing the addition of left turn lanes on US 31W for the soon to be realigned intersection with KY 255 South and also at the existing intersection with KY 255 North near the I-65 interc | 3 | West | 18.921 | 1.6357 | 5.3608 | 4.8969 | 1.9759 | 0 | 0 | 5.0515 | 19
Y | 3 | Barren River ADD | IP20110033 |  |  |  | Improve safety on KY-621 from MP 0 to MP 1.5. | Reconstruction | Simpson | 107-KY-0621 -000 | 0 | 1.5 | 1.5 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 3500000 |  | 2018-10-15 11:43 | Improve safety. | This section of KY 621 has numerous curves which present a safety concern for vehicles traveling along this route.
Y | 3 | Pennyrile ADD | IP20110055 |  |  |  | Address geometric deficiencies to improve sight distance and increase safety (vertical curve) on KY-181 south of the intersection with KY-507 near North Todd Elementary School. | Spot Improvement | Todd | 110-KY-0181 -000 | 19 | 19.311 | 0.311 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 200000 |  | 400000 |  | 800000 |  | 2019-03-12 10:18 | Improve safety. | There is a sight distance problem at this intersection with KY 507. Vehicles at this intersection do not have adequate site distance to pull onto KY 181 safely. | PENNYRILE ADD | West | 14.4734 | 1.5739 | 3.4536 | 2.4356 | 2.3024 | 0 | 0 | 4.7079 | 14
Y | 3 | Bowling Green MPO | IP20110058 |  |  |  | Improve mobility on KY 240 from US 31W in Woodburn to the proposed interchange with I-65. | Reconstruction | Warren | 114-KY-0240 -000 | 5.47 | 10.048 | 4.578 | Other Improvement Types | 0 |  | 0 |  | 2200000 |  | 3500000 |  | 2800000 |  | 22000000 |  | 2019-03-08 13:26 | Improve mobility. | Rapid residential and commercial growth is occurring on the southern side of Bowling Green, southern Warren County, and northern Simpson County. Motorists and commercial trucks have limited options for accessing I-65 in Southern Bowling Green and Warren C
Y | 3 | Barren River ADD | IP20110176 |  |  |  | Improve safety on KY 101 from KY 234 to the Warren County Line. | Safety-Haz-Elm | Allen | 002-KY-0101 -000 | 5.862 | 13.347 | 7.485 | Other Improvement Types | 0 |  | 0 |  | 650000 |  | 800000 |  | 1500000 |  | 6000000 |  | 2019-03-04 11:37 | Improve safety. | KY 101 is a two-lane facility with horizontal and vertical curves. This project addresses safety along KY 101, specifically steep shoulders in the area near the intersection with KY 1533.
Y | 3 | Barren River ADD | IP20110177 |  |  |  | Improve safety and mobility issues related to geometric deficiencies on US 68 from Highland Glen Industrial Park to KY 2189. | Reconstruction | Barren | 005-US-0068 -000 | 7.9 | 9.52 | 1.62 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2500000 |  | 3000000 |  | 9500000 |  | 2018-10-11 14:08 | Improve safety and mobility. | US 68 to Glasgow is a narrow two lane facility. There are a number of verticle curves on this section of road that restrict sight distance near the intersection of KY 685. US 68 serves as a connection to the Highland Glen Industrial Park and furthers impr
Y | 3 | Barren River ADD | IP20110178 |  |  |  | Improve safety and address geometric deficiencies of the cloverleaf interchange of US 231 in Butler County with the Natcher Parkway north of Morgantown. | Reconstruction | Butler | 016-WN-9007 -000 | 35.887 | 35.987 | 0.1 | Innovative Interchange | 40 | Y | 0 |  | 1500000 |  | 1000000 |  | 500000 |  | 8000000 |  | 2017-02-10 16:47 | Improve safety. | This project is located along the William Nathcher Parkway near the Cromwell Bridge that addressed the interechane with US 231. The current interchange is a cloverleaf interchange. Previously this interchange was a toll booth exit that allowed for slower
Y | 3 | Barren River ADD | IP20110179 |  |  |  | Improve safety and mobility at the intersection of US 68X and KY 103. | Spot Improvement | Logan | 071-US-0068X -000 | 4.925 | 4.941 | 0.016 | Improve Intersection | 26 |  | 0 |  | 75000 |  | 75000 |  | 200000 |  | 250000 |  | 2018-09-27 11:43 | Improve safety and mobility. | This project addresses an offset interchange at US 68 and KY 103. KY 103 is the main connection between Auburn and the bypass and well as Simpson County. This section inludes heavy school bus traffic. | BARREN RIVER ADD | West | 16.9897 | 1.4914 | 5.0515 | 8.1443 | 2.3024 | 0 | 0 | 0 | 17
Y | 3 | Barren River ADD | IP20110180 |  |  |  | Improve safety and mobility on KY 100 between KY 87 in Tompkinsville to KY 1366 in Fountain Run. | Reconstruction | Monroe | 086-KY-0100 -000 | 0.751 | 7.39 | 6.639 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 5500000 |  | 3750000 |  | 24000000 |  | 2019-03-08 09:14 | Improve safety and mobility. | This project addresses KY 100 between KY 87 in Tompkinsville to KY 1366 in Fountain Run. KY 100 is a two lane facility. There are several commercial establishments located along this section of road.
Y | 3 | Barren River ADD | IP20110197 |  |  |  | Improve safety on US 79 at Vicks Branch from MP 2.7 to MP 3.1. | Spot Improvement | Logan | 071-US-0079 -000 | 2.7 | 3.1 | 0.4 | Modernize Roadway-Rural | 26 | Y | 0 |  | 250000 |  | 300000 |  | 500000 |  | 1250000 |  | 2018-10-12 11:12 | Improve safety. | US 79 is currently a heavily traveled route for commuter and freight traffic. This bridge is one of several along the route which are narrow and create hazards for motorists and trucks along this important connection from US 68 down to I-24 and the fast- | BARREN RIVER ADD | West | 29.0713 | 4.11 | 9.2784 | 3.3634 | 3.4364 | 0 | 3.9347 | 4.9485 | 29
Y | 3 | Bowling Green MPO | IP20110200 |  |  |  | Improve safety and address the horizontal and vertical curve alignment issues on KY-1402 from MP 3.3 to MP 3.5. | Spot Improvement | Warren | 114-KY-1402 -000 | 3.3 | 3.5 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 200000 |  | 400000 |  | 500000 |  | 2019-03-08 13:27 | Improve safety. | KY 1402 provides a connection to eastern Warren County as well as an alternative route to Glasgow in Barren County and is a two lane facility with horizontal and vertical curves. This project addresses the horizontal and vertical curve alignment issues o
Y | 3 | Bowling Green MPO | IP20110201 |  |  |  | Improve safety and mobility on KY 242 from the intersection with US 31W (MP 3.463) to the intersection with KY 884 (MP 5.133). | Reconstruction | Warren | 114-KY-0242 -000 | 3.463 | 5.133 | 1.67 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 500000 |  | 500000 |  | 3000000 |  | 2019-03-08 13:28 | Improve safety and mobility. | KY 242 from the intersection with US 31W (MP 3.463) to the intersection with KY 884 (MP 5.133) provides access to the residential and commercial activities in the community of Richpond and Richpond Elementary School and South Warren High & Middle Schools.
Y | 3 | Bowling Green MPO | IP20110202 | 3-8818 |  | A | THREE SPRINGS ROAD EXTENSION FROM FLEALAND TO THE NATCHER PARKWAY INCLUDING BRIDGE OVER PARKWAY. (14CCN)(18CCN) | MINOR WIDENING(O) | Warren | 114-KY-0884 -000 | 7.302 | 8.622 | 1.32 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 2560000 | 2019 | 3520000 | 2021 | 10450000 | 2023 | 2019-02-28 08:52 | Improve safety and mobility. | KY 884 from the Natcher Parkway overpass to MP 8.700 near Flealand is a major urban connection from the developing residential area in southern Warren County to the US 231 (Scottsville Road) commercial/entertainment neighborhood. Faced with increasing tr | 3 | West | 68.0936 | 7.5395 | 7.1649 | 8.8531 | 2.3024 | 0 | 3.6426 | 8.5911 | 38 | 15 | 15
Y | 3 | Bowling Green MPO | IP20110203 |  |  |  | Improve safety and mobility on US 31W from Old Porter Pike (MP 16.559) to KY 957 (MP 18.085), including the reconstruction of the interchange with KY 446. | Minor Widening | Warren | 114-US-0031W -000 | 16.558 | 18.085 | 1.527 | Modernize Roadway-Urban | 16 | Y | 0 |  | 1500000 |  | 5000000 |  | 5210000 |  | 8500000 |  | 2018-12-10 10:08 | Increase safety and mobility. | US 31W is a major urban and regional connection in Bowling Green. Currently the interchange with KY 446 and several signalized intersections and access points along this section of US 31W from Old Porter Pike (MP 16.559) to KY 957 (MP 18.085) create safe | 3 | West | 64.951 | 9.2165 | 14.2784 | 14.2397 | 0 | 0 | 4.6564 | 7.5601 | 50 | 15
Y | 3 | Pennyrile ADD | IP20120003 |  |  |  | Improve access and mobility from US 68X west of Elkton to KY 181 South of Elkton (Planning Study funding required) | New Route | Todd | 110-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 500000 |  | 250000 |  | 5000000 |  | 2012-09-07 08:24 | Improve truck access and mobility. | The existing route for truck traffic eastbound on US 68X, or southbound from US 68/80, routes traffic around the courthouse square in downtown Elkton. There are substandard turns that are difficult for trucks traffic to negotiate around this square. The
Y | 3 | Pennyrile ADD | IP20120004 |  |  |  | Improve access and mobility with a new connector route from KY 181 (South Main St) to KY 102 (Allensville RD) will improve truck access around downtown on US 68X in Elkton (Planning Study Funding Required). | New Route | Todd | 110-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 250000 |  | 100000 |  | 2500000 |  | 2012-09-07 08:35 | Improve truck access and mobility. | Truck traffic traveling westbound on US 68X and KY 102 have to maneuver through the courthouse square with substandard turns. There is also congestion around the square at peak times.
Y | 3 | Pennyrile ADD | IP20120050 |  |  |  | Reduce congestion and improve safety and mobility on US-68X from MP 2.192 to 2.402 in Elkton. | Spot Improvement | Todd | 110-US-0068X -000 | 2.192 | 2.402 | 0.21 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 150000 |  | 300000 |  | 300000 |  | 850000 |  | 2019-03-12 10:13 | Reduce congestion and improve safety and mobility. | This section has a high CRF and traffic is congested durning peak morning and afternoon hours because of the school. | PENNYRILE ADD | West | 17.7723 | 1.6082 | 5.4124 | 4.8582 | 1.323 | 0 | 0 | 4.5704 | 18
Y | 3 | Pennyrile ADD | IP20120051 |  |  |  | Improve safety and mobility on KY 181 from the Elk Fork Bridge north to US 68 north of Elkton | Minor Widening | Todd | 110-KY-0181 -000 | 12.241 | 13.042 | 0.801 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 650000 |  | 900000 |  | 1200000 |  | 4000000 |  | 2019-03-08 10:09 | Improve safety and mobility. | Improve truck access into the City of Elkton and provide sidewalks for pedestrians
Y | 3 | Barren River ADD | IP20120060 |  |  |  | REDUCE CONGESTION AND INCREASE MOBILITY ON KY 63 FROM KY 90 TO KY 249. | New Route | Barren | 005-PF-9999 - |  |  |  | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 1100000 |  | 800000 |  | 5200000 |  | 2018-10-11 14:01 | Reduce congestion and increase mobility. | KY 249 AND KY 90 DO NOT CURRENTLY HAVE ANY EFFECTIVE CONNECTIONS WITHOUT HAVING TRAFFIC ENTER DOWNTOWN GLASGOW. A CONNECTOR ROAD WILL REDUCE SOME CONGESTION WITHIN THE CITY AND DECREASE TRAVEL TIME FOR THOSE USING THESE HIGHWAYS.
Y | 3 | Pennyrile ADD | IP20140006 |  |  |  | Improve mobility and address drainage issues on West Main Street (US 68X) from Davis Mill Road to Street Avenue in Elkton. | Minor Widening | Todd | 110-US-0068X -000 | 1.33 | 2.599 | 1.269 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1000000 |  | 1500000 |  | 2000000 |  | 4200000 |  | 2019-03-08 10:10 | Improve mobility. | To reconstruct West Main St (US 68X) to improve traffic flow with turn lanes at key locations, and drainage improvements with curb and gutters and pedestrian access with sidewalks. Also, there is a large amount of buggy traffic along this route, and the
Y | 3 | Pennyrile ADD | IP20140007 |  |  |  | Improve mobility and address drainage issues on South Main St. (KY 181) starting just south of the Todd County High School then northward to Washington Street in Elkton. | Minor Widening | Todd | 110-KY-0181 -000 | 10.95 | 11.96 | 1.01 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1000000 |  | 1500000 |  | 3000000 |  | 3750000 |  | 2019-03-08 10:10 | Improve safety and mobility. | To reconstruct South Main St (KY 181) to improve traffic flow with turn lanes at key locations, and drainage improvements with curb and gutters and pedestrian access with sidewalks. Also, there is a large amount of buggy traffic along this route, and the
Y | 3 | Barren River ADD | IP20140035 |  |  |  | Improve safety and reduce congestion along KY 100 (Old Gallatin Rd) from KY 3500 at Old Franklin Rd north to Woodland Circle Drive in Scottsville. | Minor Widening | Allen | 002-KY-0100 -000 | 13.1 | 13.475 | 0.375 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 400000 |  | 250000 |  | 750000 |  | 1000000 |  | 2019-03-04 15:00 | Improve safety and reduce congestion. | Presently KY 100 is a two lane facility with 12' lanes and 6' shoulders. There are numerous businesses adjacent to the road. The lack of turning lanes requires vehicles making a left turn into these businesses yield to opposing traffic, thus queues and t | 3 | West | 53.2543 | 8.3574 | 14.3814 | 8.9175 | 1.323 | 9.8282 | 4.3299 | 6.1168 | 53
Y | 3 | Barren River ADD | IP20140036 |  |  |  | Improve safety and reduce congestion along KY 100 (Old Gallatin Rd) from the intersection with Woodland Circle Drive to John Kelly Drive in Scottsville. | Reconstruction | Allen | 002-KY-0100 -000 | 13.475 | 14.1 | 0.625 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 400000 |  | 900000 |  | 1500000 |  | 2019-03-04 15:00 | Improve safety and reduce congestion. | Presently KY 100 is a two lane facility with 12' lanes and 6' shoulders. There are numerous businesses adjacent to the road. The lack of turning lanes requires vehicles making a left turn into these businesses yield to opposing traffic, thus queues and t | BARREN RIVER ADD | West | 65.171 | 6.5842 | 13.9175 | 7.8995 | 1.323 | 9.4158 | 4.1237 | 6.9072 | 50 |  | 15
Y | 3 | Barren River ADD | IP20140041 |  |  |  | Provide connectivity and improve mobility on CS-1174 from Virginia Drive to KY-3499. | Reconstruction | Allen | 002-CS-1174 -000 | 0 | 0.313 | 0.313 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 2500000 |  | 1500000 |  | 6500000 |  | 2019-03-04 11:02 | Provide connectivity and improve mobility. | Economic development, particularly Dollar General, has created the need for a better connector route to improve truck mobility in this area.
Y | 3 | Barren River ADD | IP20140042 |  |  |  | Improve safety and truck mobility at the intersections of Cartertown Rd with US31E and with KY3500 south of Scottsville. | Spot Improvement | Allen | 002-CS-1008 -000 | 0 | 0.379 | 0.379 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 100000 |  | 100000 |  | 200000 |  | 2018-10-09 15:09 | Improve safety and truck mobility. | Truck traffic from local industries on KY-3500 use this route to get to and from US-31E. Improving the intersections and widening the road are needed to improve safety and mobility.
Y | 3 | Barren River ADD | IP20140043 |  |  |  | Improve safety and mobility along US-231 in Morgantown from the intersection with KY-70 to north of the intersection with North Maple Street. | Minor Widening | Butler | 016-US-0231 -000 | 11.521 | 11.688 | 0.167 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 300000 |  | 150000 |  | 450000 |  | 2250000 |  | 2018-09-26 13:40 | Improve safety and mobility. | Increased congestion in this area has created the need for a two-way left turn lane throughout this corridor. | BARREN RIVER ADD | West | 37.433 | 7.7595 | 8.5567 | 5.4639 | 1.9759 | 9.7938 | 0 | 3.8832 | 37
Y | 3 | Barren River ADD | IP20140044 |  |  |  | Increase safety and mobility for motor vehicles and pedestrians on US 231 from the intersection with Bell Street to the intersection with KY 2161 in Morgantown. | Minor Widening | Butler | 016-US-0231 -000 | 10.683 | 10.95 | 0.267 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 100000 |  | 100000 |  | 250000 |  | 500000 |  | 2019-03-04 14:42 | Increase safety and mobility. | Increased congestion in this area has created the need for a left turn lane at KY 2161, and sidewalks are needed to improve pedestrian safety to and from local businesses. | BARREN RIVER ADD | West | 59.1082 | 4.3918 | 13.3505 | 7.1907 | 1.5808 | 9.3814 | 3.9519 | 4.2612 | 44 |  | 15
Y | 3 | Barren River ADD | IP20140045 |  |  |  | Improve safety and address geometric deficiencies at the intersection of KY 259 and KY 2336. | Spot Improvement | Edmonson | 031-KY-0259 -000 | 20.614 | 20.814 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 600000 |  | 500000 |  | 750000 |  | 2015-03-04 14:26 | Improve safety. | Industries in close proximity of the intersection have caused safety issues that need to be addressed.
Y | 3 | Barren River ADD | IP20140046 |  |  |  | Improve safety and address geometric deficiencies on KY 259 from MP 8.35 to MP 8.65. | Spot Improvement | Edmonson | 031-KY-0259 -000 | 8.35 | 8.65 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 300000 |  | 250000 |  | 750000 |  | 2015-03-04 14:28 | Improve safety. | Safety issues need to be addressed in this curve to reduce the crash rate. | BARREN RIVER ADD | West | 16.6959 | 0.84536 | 10.8247 | 1.2113 | 3.8144 | 0 | 0 | 0 | 17
Y | 3 | Barren River ADD | IP20140050 |  |  |  | Improve safety and address geometric deficiencies on the Louie B. Nunn Parkway at the Exit 27 interchange. | Reconstruction | Metcalfe | 085-LN-9008 -000 | 27.143 | 27.681 | 0.538 | Innovative Interchange | 40 | Y | 0 |  | 750000 |  | 600000 |  | 500000 |  | 8500000 |  | 2018-10-15 10:00 | Improve safety. | Cloverleaf interchange configurations are no longer desirable due to safety concerns of drivers entering and exiting the roadway from the ramps.
Y | 3 | Barren River ADD | IP20140051 |  |  |  | Improve safety and reduce congestion along US-68 from Rogers Creek Bridge to KY-861. | Reconstruction | Metcalfe | 085-US-0068 -000 | 7.26 | 7.697 | 0.437 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 750000 |  | 400000 |  | 800000 |  | 1750000 |  | 2019-03-12 09:46 | Improve safety and reduce congestion. | Numerous entrances to local businesses along the route have created the need for a two-way left turning lane.
Y | 3 | Barren River ADD | IP20140052 |  |  |  | Improve safety and address geometric deficiencies (reconstruct "Marshall Curves") on KY-100 from the KY-2170 intersection to the Duncan Road intersection. | Reconstruction | Monroe | 086-KY-0100 -000 | 1.13 | 2.052 | 0.922 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 900000 |  | 750000 |  | 2500000 |  | 2015-03-04 14:35 | Improve safety. | Improvements are needed throughout this corridor to improve the safety for vehicles traveling to and from Fountain Run. | BARREN RIVER ADD | West | 25.4338 | 2.921 | 2.8866 | 2.6675 | 4.8282 | 6.1168 | 0 | 6.0137 | 25
Y | 3 | Barren River ADD | IP20140053 |  |  |  | Improve safety and address geometric deficiencies on KY 100 from MP 9.325 to MP 10.323. | Reconstruction | Monroe | 086-KY-0100 -000 | 9.325 | 10.323 | 0.998 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 1100000 |  | 750000 |  | 3000000 |  | 2018-10-15 10:51 | Improve safety. | High crash area due to geometric deficiencies in curves along the roadway.
Y | 3 | Barren River ADD | IP20140055 |  |  |  | Improve mobility for motor vehicles and pedestrians along KY-1171 (North Street) from the intersection with US-31W to the intersection with KY-3498 in Franklin. | Minor Widening | Simpson | 107-KY-1171 -000 | 0 | 0.907 | 0.907 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 750000 |  | 1000000 |  | 1000000 |  | 3250000 |  | 2019-03-08 09:41 | Improve mobility. | A better connection is needed through this section to accommodate vehicular and pedestrian traffic. | BARREN RIVER ADD | West | 31.6469 | 6.488 | 6.5979 | 8.4923 | 4.2268 | 5.8419 | 0 | 0 | 32
Y | 3 | Barren River ADD | IP20140056 |  |  |  | Improve mobility for motor vehicles and pedestrians on KY 3498 (North Street) from the intersection with KY 1171 to the intersection with KY 1008 in Franklin. | Reconstruction | Simpson | 107-KY-3498 -000 | 0 | 0.246 | 0.246 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 350000 |  | 750000 |  | 1250000 |  | 2019-03-08 09:42 | Improve mobility. | A large residential area has created the need to give pedestrians a safer way to travel in the area.
Y | 3 | Barren River ADD | IP20140057 |  |  |  | Improve safety and mobility on KY-100 from Russellville to I-65 east of Franklin. | Minor Widening | Simpson | 107-KY-0100 -000 | 0 | 9.742 | 9.742 | Modernize Roadway-Rural | 26 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-08 09:43 | Improve safety and mobility. | An increase in vehicular and truck AADT has created the need for the modernization of this roadway.
Y | 3 | Barren River ADD | IP20140058 |  |  |  | Improve safety and address geometric deficiencies in the curve along KY 259 between Kinslow Cemetery Rd and KY 2325 (Silent Grove Church Rd) | Spot Improvement | Edmonson | 031-KY-0259 -000 | 6.75 | 7 | 0.25 | Modernize Roadway-Rural | 26 |  | 0 |  | 200000 |  | 150000 |  | 150000 |  | 300000 |  | 2015-03-04 14:23 | Improve safety. | Safety issues need to be addressed in this curve to reduce the crash rate. | BARREN RIVER ADD | West | 13.4914 | 0.84536 | 5.5155 | 3.7113 | 3.4192 | 0 | 0 | 0 | 14
Y | 3 | Barren River ADD | IP20140059 |  |  |  | Improve safety and reduce congestion at the intersections of US 68X with KY 3240 and Franklin St. | Reconstruction | Logan | 071-US-0068X -000 | 2.874 | 2.93 | 0.056 | Improve Intersection | 26 |  | 0 |  | 750000 |  | 1500000 |  | 1000000 |  | 2000000 |  | 2018-10-12 11:06 | Improve safety and reduce congestion. | Congestion in the area combined with the unique design of these intersections have created a safety issue that needs to be addressed with a reconstruction project.
Y | 3 | Barren River ADD | IP20150010 |  |  |  | Improve safety and address geometric deficiencies on the Natcher Parkway between the interchanges with US 231 and KY 70 in Morgantown in anticipation of designation of an interstate spur route from I-65 to Owensboro. | Spot Improvement | Butler | 016-WN-9007 -000 | 27 | 31 | 4 | Other Improvement Types | 0 | Y | 0 |  | 750000 |  | 3000000 |  | 1000000 |  | 5000000 |  | 2017-02-10 16:50 | Improve safety. | To meet interstate standards, geometric deficiencies must be addressed on this roadway.
Y | 3 | Bowling Green MPO | IP20150070 |  |  |  | Improve safety and mobility on US 231X northbound at the intersection with US 68 and Avenue of Champions. | Minor Widening | Warren | 114-US-0231X -000 | 2.445 | 2.526 | 0.081 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 150000 |  | 750000 |  | 900000 |  | 2019-03-08 13:30 | Improve safety and mobility. | Congestion in the area has led to long traffic queues at the intersection due to the lack of a dedicated left-turn lane on US 231X.
Y | 3 | Bowling Green MPO | IP20150071 |  |  |  | Improve safety and mobility on US 68X southbound at the intersection with US 231X and Avenue of Champions. | Minor Widening | Warren | 114-US-0068X -000 | 1.524 | 1.626 | 0.102 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 150000 |  | 750000 |  | 900000 |  | 2019-03-08 13:31 | Improve safety and mobility | Congestion in the area has led to long traffic queues at the intersection due to the lack of two dedicated through lanes combined with a dedicated right-turn lane on US 68.
Y | 3 | Bowling Green MPO | IP20150072 |  |  |  | Improve safety and mobility at the US 31W intersection with Broadway Avenue. | Reconstruction | Warren | 114-US-0031W -000 | 12.789 | 12.834 | 0.045 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 500000 |  | 800000 |  | 1500000 |  | 2019-03-08 13:31 | Improve safety and mobility. | Congestion in the area has led to long traffic queues at the intersection due to the lack of dedicated left-turn lanes on each side of US 31W.
Y | 3 | Bowling Green MPO | IP20150073 |  |  |  | Improve mobility of I-65 at US 68 to include a full interchange. | Reconstruction | Warren | 114-I -0065 -000 | 35.5 | 35.6 | 0.1 | Innovative Interchange | 40 |  | 0 |  | 500000 |  | 300000 |  | 800000 |  | 5500000 |  | 2015-03-12 17:55 | Improve mobility. | Higher AADTs on both I-65 and US-68 have created the need for a full interchange at this location.
Y | 3 | Bowling Green MPO | IP20150074 |  |  |  | Improve access with a new interchange on I-65 at KY-242. | New Interchange | Warren | 114-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 | Y | 0 |  | 1200000 |  | 1000000 |  | 900000 |  | 8000000 |  | 2019-01-23 11:41 | Improve access. | With the growing population of Bowling Green, especially in the Richpond area, a new interchange is needed on I-65 to provide residents with a more efficient transportation system.
Y | 3 | Bowling Green MPO | IP20150075 |  |  |  | Improve safety and mobility on KY 622 between Dye Ford Road and Larmon Mill Road/Plano-Richpond Road. | Minor Widening | Warren | 114-KY-0622 -000 | 3.518 | 5.262 | 1.744 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 2000000 |  | 4200000 |  | 2019-03-08 13:33 | Improve safety and mobility. | Development in the Plano area has created the need for a modernized roadway, including turn lanes, shoulders, and sidewalks.
Y | 3 | Bowling Green MPO | IP20150076 |  |  |  | Improve safety and mobility on KY 1402 (Porter Pike) from US 31W to Grimes Road, including realigning Parker Avenue to the adjacent shopping center entrance. | Minor Widening | Warren | 114-KY-1402 -000 | 0 | 1.423 | 1.423 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1300000 |  | 2000000 |  | 5750000 |  | 2019-03-08 13:33 | Improve safety and mobility. | Numerous entrances along the corridor have created the need for a two-way left turning lane to be constructed along the full distance of the corridor.
Y | 3 | Bowling Green MPO | IP20150077 |  |  |  | Modernize US 68 (Veterans Memorial Lane) from US 231/US 231X to US 68/KY 234. | Reconstruction | Warren | 114-US-0068 -000 | 10.816 | 14.771 | 3.955 | Modernize Roadway-Urban | 16 | Y | 0 |  | 500000 |  | 100000 |  | 200000 |  | 5100000 |  | 2019-03-08 13:34 | Modernization. | Corridor needs numerous improvements, including curb, gutter, sidewalk, greenways connection, street lights, storm sewer/drainage, and landscaping.
Y | 3 | Bowling Green MPO | IP20150078 |  |  |  | Improve access on US 231 from KY 622 to US 231X/KY 880. | Reconstruction | Warren | 114-US-0231 -000 | 7.885 | 10.455 | 2.57 | Other Improvement Types | 0 | Y | 0 |  | 750000 |  | 6500000 |  | 13000000 |  | 24700000 |  | 2015-03-13 13:09 | Improve access. | The increase in population combined with economic demand, especially in this area, has created the need to develop an access management plan to be implemented and constructed.
Y | 3 | Bowling Green MPO | IP20150079 |  |  |  | Improve access on US 231X from US 231/KY 880 to South Park Drive. | Reconstruction | Warren | 114-US-0231X -000 | 0 | 1.313 | 1.313 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 5000000 |  | 10000000 |  | 17100000 |  | 2015-03-13 13:12 | Improve access. | The increase in population combined with economic demand, especially in this area, has created the need to develop an access management plan to be implemented and constructed.
Y | 3 | Bowling Green MPO | IP20150081 |  |  |  | Improve safety at the US 31W intersection with KY 3225/State Street. | Reconstruction | Warren | 114-US-0031W -000 | 14.382 | 14.452 | 0.07 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 50000 |  | 100000 |  | 250000 |  | 2019-03-08 13:35 | Improve safety. | Reconfiguration of the intersection is needed to accommodate two-way traffic on State Street.
Y | 3 | Bowling Green MPO | IP20150082 |  |  |  | Improve safety at the intersection of Gary Farms Boulevard and the Greenwood Mall Access Road. | Spot Improvement | Warren | 114-US-0231 -000 | 10.674 | 10.684 | 0.01 | Other Improvement Types | 0 |  | 0 |  | 50000 |  | 75000 |  | 250000 |  | 250000 |  | 2019-03-08 13:35 | Improve safety. | The right-turn lane from Gary Farms Boulevard onto Campbell Lane has been identified as a safety problem. Widening the lane and reconstructing the radius is needed.
Y | 3 | Bowling Green MPO | IP20150086 |  |  |  | Improve safety and mobility on Nashville Road (US 31W) at the intersections with Highland Way and Emmett Avenue. | Reconstruction | Warren | 114-US-0031W -000 | 10.9 | 11 | 0.1 | Realign Intersection | 26 |  | 0 |  | 300000 |  | 750000 |  | 250000 |  | 1250000 |  | 2019-03-12 10:25 | Increase safety and mobility. Provide connectivity between schools, employment, and residential areas. | Realignment of these intersections is needed to improve safety. Pedestrian facilities may need to be explored for Highland Way. | Bowling Green MPO | West | 43.7852 | 8.8454 | 13.8144 | 14.2526 | 0 | 0 | 2.921 | 3.9519 | 44
Y | 3 | Bowling Green MPO | IP20150089 |  |  |  | Modernize US 31W (Louisville Road) from KY 3225 to KY 1402. | Reconstruction | Warren | 114-US-0031W -000 | 16.121 | 17.088 | 0.967 | Modernize Roadway-Urban | 16 | Y | 0 |  | 750000 |  | 300000 |  | 1500000 |  | 4500000 |  | 2019-03-08 13:36 | Modernization. | Corridor needs numerous improvements, including curb, gutter, sidewalk and/or greenways connection, street lights, storm sewer/drainage, and landscaping.
Y | 3 | Barren River ADD | IP20150092 |  |  |  | Improve safety and mobility along KY 1297 from the Glasgow Outer Loop near the Louie B Nunn Pkwy overpass to Donnelley Drive. | Reconstruction | Barren | 005-KY-1297 -000 | 9.681 | 11.085 | 1.404 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 900000 |  | 1200000 |  | 3500000 |  | 2015-03-12 11:52 | Improve safety and mobility. | Lane and shoulder widening is needed to improve the safety and mobility of this corridor. | 3 | West | 33.1211 | 1.9656 | 8.0412 | 8.4407 | 2.3024 | 5.7045 | 0 | 6.6667 | 33
Y | 3 | Bowling Green MPO | IP20150093 |  |  |  | Enhance economic development on the new I-65 Connector by extending it north toward Fairview Boiling Springs Road. | New Route | Warren | 114-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 1250000 |  | 5000000 |  | 2750000 |  | 15000000 |  | 2019-03-08 13:36 | Enhance economic development. | This extension would accommodate major development possibilities north of Bowling Green. | Bowling Green MPO | West | 41.3866 | 8.1306 | 4.433 | 14.201 | 0.94502 | 9.1065 | 4.5704 | 0 | 41
Y | 3 | Bowling Green MPO | IP20150094 |  |  |  | Improve safety and mobility on the Natcher Parkway in Warren County to meet interstate highway standards (I-65/I-66/I-69 Spur Study 2014). | Reconstruction | Warren | 114-WN-9007 -000 | 2.079 | 20.246 | 18.167 | Full Control to Interstate | 10 | Y | 0 |  | 500000 |  | 300000 |  | 500000 |  | 2000000 |  | 2017-02-10 16:56 | Improve safety and mobility to meet interstate compliancy. | Making improvements to the Natcher Parkway to enable it to meet interstate standards will further increase economic development in the region.
Y | 3 | Pennyrile ADD | IP20150196 | 3-8811 |  | A | RECONSTRUCT KY-181 (ELKTON ROAD) FROM US-79 (MP 0.000) TO NORTH OF INTERSECTION WITH US-41 (MP 0.214) TO INCLUDE A NEW INTERSECTION WITH KY-294. (MP 0.000-0.400) (14CCN)(18CCN) | RECONSTRUCTION(O) | Todd | 110-KY-0181 -000 | 0 | 0.4 | 0.4 | Construct Road in New Location | 0 |  |  |  | 0 |  | 280000 | 2021 | 730000 | 2021 | 2820000 | 2023 | 2019-02-28 12:49 | Improve safety, truck access and mobility. | Safety improvements along the corridor and at intersections are needed due to increased congestion. | 3 | West | 17.4579 | 2.7973 | 0 | 6.1727 | 2.3024 | 6.1856 | 0 | 0 | 18
Y | 3 | Barren River ADD | IP20150199 | 3-7030.10 |  | A | RECONSTRUCT KY-70/KY-259 FROM 0.36 MILE NORTH GREEN RIVER BRIDGE AT BROWNSVILLE TO 0.42 MILE NORTH OF THE KY-70/KY-259 INTERSECTION.(06CCR)(2004BOPC)(12CCR)(14CCR)(18CCN) | SPOT IMPROVEMENTS(O) | Edmonson | 031-KY-0259 -000 | 11.676 | 12.096 | 0.42 | Modernize Roadway-Rural | 26 | [5 empty] | 2170000 | 2019 | 1930000 | 2020 | 6930000 | 2021 | 2019-03-01 08:50 | Reduce congestion and increase mobility. | Reconstruction is needed to modernize this roadway to improve mobility for vehicles. | BARREN RIVER ADD | West | 38.1581 | 6.0275 | 11.0309 | 9.1237 | 3.677 | 0 | 3.1443 | 5.1546 | 38
Y | 3 | Barren River ADD | IP20150299 | 3-8821 / 3-8821.01 |  | A | IMPROVE KY-1297 FROM CR-1366 (DONNELLY DRIVE) TO US-31E (ROGER WELLS), AND IMPROVE CR-1366 (DONNELLY DRIVE) FROM KY-1297 TO US-68 IN GLASGOW. (14CCN) (16CCN) | MAJOR WIDENING(O) | Barren | 005-KY-1297 -000 | 11.085 | 12.806 | 1.721 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 10940000 | 2022 | 9360000 | 2022 | 21320000 | 2025 | 2019-02-28 12:54 | Reduce congestion and increase mobility. | Growth in this area combined with a high number of approach roads and driveway entrances has created the need for a two-way left turn lane on this corridor. | 3 | West | 79.829 | 5.2371 | 10.8763 | 13.0799 | 2.3024 | 7.5258 | 3.4192 | 7.3883 | 50 | 15 | 15
Y | 3 | Bowling Green MPO | IP20160011 |  |  |  | Reduce congestion and increase mobility on Russellville Road (US 68X) from Old Morgantown Road (US 231X) to University Drive (US 231X/US 68X). | Reconstruction | Warren | 114-US-0068X -000 | 1.196 | 1.524 | 0.328 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 2000000 |  | 500000 |  | 1000000 |  | 2019-03-05 11:35 | Reduce congestion and increase mobility. | Reconstruct the intersection of US 68X with US 231X. Provide safe modes of travel for pedestrians and bicyclists with a sidewalk on Russellville Road. | Bowling Green MPO | West | 44.8849 | 9.7045 | 11.2887 | 13.2216 | 0 | 0 | 4.8282 | 5.8419 | 45
Y | 3 | Barren River ADD | IP20160168 | 3-8955 |  | A | IMPROVE HIGHWAY SAFETY AND SYSTEMS MOBILITY IN THE KY 163 CORRIDOR BETWEEN KY 90 (MP 2.907) AND THE PROPOSED WEST EDMONTON BYPASS (MP 9.777). (16CCN)(18CCN) | CONGESTION MITIGTN(O) | Metcalfe | 085-KY-0163 -000 | 2.907 | 9.777 | 6.87 | Modernize Roadway-Rural | 26 |  |  |  | 2710000 | 2021 | 12870000 | 2025 | 10130000 | 2025 | 43800000 | 2025 | 2019-03-01 10:53 | Improve safety and mobility. | With the potential construction of the West Edmonton Bypass, safety improvements are needed on this corridor to accommodate a higher traffic volume and to improve their safety and mobility. | BARREN RIVER ADD | West | 31.6692 | 2.9622 | 4.2268 | 10.2706 | 1.9759 | 0 | 2.7148 | 9.5189 | 32
Y | 3 | Barren River ADD | IP20160233 |  |  |  | PLANNING STUDY FOR NEW ROUTE BETWEEN KY 100 WEST OF FRANKLIN OR US 31W SOUTH OF FRANKLIN AND THE KENTUCKY/TENN LINE NEAR WITT ROAD IN SIMPSON CO. (16CCN) | New Route | Simpson | 107-PF-9999 - |  |  |  | Transportation Studies | 0 |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-12-09 10:15 | Planning study. | A new route in this area could help alleviate some of the truck traffic on other alternative routes in the area.
Y | 3 | Barren River ADD | IP20160270 | 3-8901 |  | A | IMPROVE ACCESS ROAD ON EACH END OF INDUSTRIAL ACCESS ROAD IN SCOTTSVILLE. (16CCN)(18CCN) | SAFETY(P) | Allen | 002-KY-3499 -000 | 0.4 | 0.6 | 0.2 | Local Roadway Improvements | 3 | [9 empty] | 320000 | 2020 |  | Improve safety and mobility. | The heavy truck traffic in this area has created the need for safety improvements to this corridor. | General Assembly | West | 17.5668 | 4.0822 | 0 | 6.7038 | 3.7671 | 0 | 0 | 3.0137 | 18
Y | 3 | Barren River ADD | IP20170034 |  |  |  | Lane departure safety improvements on KY-70 between the KY-79 crossroads and the Edmonson County line. | Safety-Haz-Elm | Butler | 016-KY-0070 -000 | 15.15 | 29.977 | 14.827 | Modernize Roadway-Rural | 26 |  | 0 |  | 550000 |  | 500000 |  | 500000 |  | 3000000 |  | 2018-09-26 13:50 | Improve safety and mobility. | Safety improvements are needed throughout this corridor to improve high crash rate spots. | 3 | West | 41.0155 | 1.6082 | 14.2268 | 12.1907 | 3.2646 | 0 | 0 | 9.7251 | 41
Y | 3 | Bowling Green MPO | IP20170035 |  |  |  | Reduce congestion and increase safety and mobility on Dishman Lane Ext. (CS-6010) from MP 0.570 to just east of Grider Pond Road on Cave Mill Road (CS-1432). | Minor Widening | Warren | 114-CS-6010 -000 | 0.57 | 0.943 | 0.373 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1500000 |  | 5000000 |  | 5000000 |  | 10000000 |  | 2019-03-12 14:31 | Reduce congestion and increase safety and mobility. | Minor widening (2 + 1 concept) to accommodate increased traffic and improve safety and mobility along Dishman Lane Ext. and Cave Mill Road. Widen the section of Dishman Lane Ext. (CS-6010) from MP 0.572, extending to Cave Mill Road (CS-1432 MP 1.035 - 1.5 | Bowling Green MPO | West | 16.5464 | 9.622 | 3.7629 | 2.2165 | 0.94502 | 0 | 0 | 0 | 16
Y | 3 | Bowling Green MPO | IP20170039 |  |  |  | Improve safety at the intersection of KY 234 and Greenhill Road. | Spot Improvement | Warren | 114-KY-0234 -000 | 5.2 | 5.4 | 0.2 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 150000 |  | 250000 |  | 500000 |  | 2018-10-16 09:38 | Improve safety. | The skewed intersection combined with a vertical crest curve just to the east of the intersection has created safety issues and a need to address them. | 3 | West | 13.5722 | 1.5876 | 3.1959 | 1.366 | 2.3024 | 0 | 0 | 5.1203 | 14
Y | 3 | Barren River ADD | IP20170040 |  |  |  | Improve safety at the intersection of KY 79 and KY 103. | Spot Improvement | Logan | 071-KY-0079 -000 | 9 | 9.15 | 0.15 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 150000 |  | 200000 |  | 400000 |  | 2018-10-12 10:56 | Improve safety. | Geometric deficiencies need to be addressed to improve safety at this intersection. Sight distance is an issue in both directions for motorists on KY 103. Excess pavement is also an issue. | 3 | West | 29.3024 | 1.7938 | 13.1959 | 7.268 | 2.3024 | 0 | 0 | 4.7423 | 29
Y | 3 | Barren River ADD | IP20170095 |  |  |  | Improve mobility on KY 249 from the proposed interchange with LN 9008 to South Lewis Street in Glasgow. | Major Widening | Barren | 005-KY-0249 -000 | 14.95 | 16.05 | 1.1 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 0 |  | 2200000 |  | 4500000 |  | 3250000 |  | 14750000 |  | 2017-08-29 09:51 | Improve mobility. | With the proposed interchange with LN 9008, an increase in traffic volume is expected to develop on this section of KY 249.
Y | 3 | Pennyrile ADD | IP20180026 | 3-80001 |  | A | US 79 WIDENING FROM MP 0 TO MP 3. (18CCN) | MINOR WIDENING(O) | Todd | 110-US-0079 -000 | 0 | 3 | 3 | Modernize & Widen Roadway-Rural | 26 | Y |  |  | 0 | 2019 | 2100000 | 2021 | 3120000 | 2021 | 8660000 | 2022 | 2019-02-27 11:55 | Reduce congestion and increase mobility. | Widening is needed through this corridor to improve the mobility of vehicles around the heavy volume of truck traffic. | General Assembly | West | 37.3459 | 4.4521 | 9.7089 | 9.0925 | 1.9349 | 0 | 4.4521 | 7.7055 | 37
Y | 3 | Bowling Green MPO | IP20180028 | 3-80005 |  | A | ADD LEFT TURNING LANE ON KY 242 INTO RICHPOND ELEMENTARY SCHOOL AT MP 3.8 TO 3.95(18CCN) | SAFETY(P) | Warren | 114-KY-0242 -000 | 3.8 | 3.95 | 0.15 | Other Improvement Types | 0 |  |  |  | 0 | 2019 | 140000 | 2020 | 260000 | 2020 | 260000 | 2020 | 2019-02-28 13:08 | Improve safety and mobility. | The congestion in this area during the peak travel periods in the morning and afternoon has created the need for a left turning lane on KY-242 into Rich Pond Elementary School. | General Assembly | West | 11.0274 | 6.1644 | 0 | 3.2877 | 1.5753 | 0 | 0 | 0 | 11
Y | 3 | Bowling Green MPO | IP20180029 | 3-80051 |  | A | SAFETY IMPROVEMENTS AND REHABILITATION ON KY-3225. KEEP EXISTING FOOTPRINT BY REPLACING CURBLINE IN SAME LOCATION FROM MP 0 TO MP 1(18CCN) | SAFETY(P) | Warren | 114-KY-3225 -000 | 0 | 1 | 1 | Modernize Roadway-Urban | 16 |  |  |  | 210000 | 2020 | 1230000 | 2021 | 110000 | 2021 | 1350000 | 2022 | 2019-03-01 11:29 | Safety improvements and rehabilitation. | The general congestion paired with the existing narrow driving lanes and crash rate have created the need for safety improvements and rehabilitation to this section of KY-3225. | General Assembly | West | 43.6575 | 8.8288 | 14.1781 | 10.9932 | 0.92466 | 0 | 0 | 8.7329 | 44
Y | 3 | Barren River ADD | IP20180033 | 3-80004 |  | A | CONSTRUCT A NEW TURN LANE ON US 231 AT JOHNSON ROAD TO IMPROVE ACCESS TO INDUSTRIAL PARK(18CCN) | SAFETY(P) | Allen | 002-US-0231 -000 | 7.6 | 7.7 | 0.1 | Improve Intersection | 26 | Y | [8 empty] | 250000 | 2020 |  | Improve mobility. | Economic development has created the need for a left turn on US-231 at Johnson Road. | General Assembly | West | 26.3973 | 4.274 | 6.4212 | 6.7295 | 0.54795 | 0 | 4.4863 | 3.9384 | 26
Y | 3 | Bowling Green MPO | IP20180054 | 3-80052 |  | A | EXTEND THE 5 LANE SECTION ON KY-234 FROM MP 11.9 TO 12.4. IMPROVEMENTS MAY INCLUDE A ROUNDABOUT, TURN LANE, AND A SIGNAL AT HAMPTON DR.(18CCN) | MINOR WIDENING(O) | Warren | 114-KY-0234 -000 | 11.9 | 12.4 | 0.5 | Modernize Roadway-Urban | 16 |  |  |  | 290000 | 2022 | 220000 | 2023 | 1760000 | 2023 | 1710000 | 2024 | 2019-03-01 12:14 | Reduce congestion and increase mobility. | Extend the 5 lane section on KY-234 from MP 11.9 to 12.4 to reduce congestion and improve mobility. Improvements may include a roundabout, turn lane, and signal modification at Hampton Dr.
Y | 3 | Bowling Green MPO | IP20180055 | 3-8904.10 |  | A | WIDEN US 31W FROM PARK AVENUE TO FAIRVIEW AVENUE MP 13.7-14.25. (18CCN) | MINOR WIDENING(O) | Warren | 114-US-0031W -000 | 13.7 | 14.25 | 0.55 | Modernize Roadway-Urban | 16 |  |  |  | 0 | 2019 | 1660000 | 2020 | 1900000 | 2020 | 4870000 | 2021 | 2019-02-28 09:06 | Reduce congestion and improve mobility. | The corridor is experiencing a higher crash rate than other similar type facilities in Kentucky, and growth is anticipated in this area from the establishment of the University of Kentucky College of Medicine's regional campus.
Y | 3 | Barren River ADD | IP20180056 | 3-80003 |  | A | REPLACE BRIDGE ON KY-100 BETWEEN MP 14.7 AND 14.9. (18CCN) | BRIDGE REPLACEMENT(P) | Monroe | 086-KY-0100 -000 | 14.7 | 14.9 | 0.2 | Other Improvement Types | 0 |  |  |  | 280000 | 2019 | 180000 | 2020 | 570000 | 2020 | 790000 | 2021 | 2019-03-01 11:06 | Improve safety and mobility. | Replacing this bridge in place with a wider bridge will improve safety and mobility for vehicles on this route.
Y | 3 | Barren River ADD | IP20180057 | 3-80050 |  | A | WIDEN US-79 TO 3 LANES FROM TODD COUNTY LINE TO INTERSECTION WITH RUSSELLVILLE BYPASS.(18CCN) | MINOR WIDENING(O) | Logan | 071-US-0079 -000 | 0 | 10.713 | 10.713 | Modernize Roadway-Rural | 26 | Y |  |  | 4660000 | 2021 | 7530000 | 2022 | 12520000 | 2023 | 34190000 | 2024 | 2019-03-01 11:26 | Improve safety and mobility. | A high volume of truck traffic has created the need for an additional lane to accommodate them and to improve the safety and mobility for other vehicles.
Y | 3 | Barren River ADD | IP20180094 |  |  |  | Improve safety at the intersection of US-79 and KY-1041. | Spot Improvement | Logan | 071-US-0079 -000 | 7.3 | 7.4 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 200000 |  | 100000 |  | 250000 |  | 400000 |  | 2019-03-11 08:43 | Improve safety. | Current stop bar placement and turning radii are issues that could be addressed to improve safety at this intersection.
Y | 3 | Barren River ADD | IP20180095 |  |  |  | Improve safety at the intersection of US-79 and Joe Montgomery Road. | Spot Improvement | Logan | 071-US-0079 -000 | 9.588 | 9.688 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 200000 |  | 100000 |  | 100000 |  | 250000 |  | 2019-03-12 09:39 | Improve safety. | Geometric deficiencies at this intersection have created safety concerns that need to be addressed.
Y | 3 | Bowling Green MPO | IP20190004 |  |  |  | Improve safety and mobility on Smallhouse Road (CS-1334) from Ridgecrest Way (CS-1308) to Scottsville Road (US-231X). | Minor Widening | Warren | 114-CS-1334 -000 | 2.542 | 3.227 | 0.685 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 600000 |  | 3000000 |  | 3000000 |  | 4000000 |  | 2019-03-14 09:15 | Improve safety and mobility. | This continues a city project that is widening Smallhouse Road from Campbell Lane to Ridgecrest Way. It would provide a two-way left turn lane, curb and gutter, and installation of sidewalk or shared-use path on one side of roadway. This section handles
Y | 3 | Bowling Green MPO | IP20190005 |  |  |  | Improve safety and mobility on Elrod Road (CS-1214) from US-31W to Smallhouse Road (CR-1235). *Milepoints are not accurate | Reconstruction | Warren | 114-CS-1214 -000 | 0 | 0.949 | 0.949 | Modernize Roadway-Urban | 16 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-01-14 11:57 | Improve safety and mobility. | With the need of a new interchange on I-65 in the future, Elrod Road needs to be upgraded to handle the increased traffic load that a new interchange would create. It would be beneficial to upgrade Elrod Road first to make it more feasible to construct a
Y | 3 | Bowling Green MPO | IP20190006 |  |  |  | Improve safety and mobility on US-31W from Old Porter Pike to KY-1402. | Minor Widening | Warren | 114-US-0031W -000 | 16.558 | 17.088 | 0.53 | Access Consolidation | 25 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-01-14 11:23 | Improve safety and mobility. | US 31W is a major urban and regional connection in Bowling Green. Currently the interchange with KY 446 and several signalized intersections and access points along this section of US 31W from Old Porter Pike (MP 16.559) to KY 1402 (MP 17.088) create saf
Y | 3 | Bowling Green MPO | IP20190007 |  |  |  | Reduce congestion and improve mobility on US-231 and US-231X between CS-1432 (Cave Mill Road) and CS-1593 (South Park Drive). | Spot Improvement | Warren | 114-US-0231 -000 | 9.877 | 10.455 | 0.578 | Access Consolidation | 25 |  | 0 |  | 300000 |  | 250000 |  | 750000 |  | 2000000 |  | 2019-03-12 14:27 | Reduce congestion and improve mobility. | US 231 and US 231X are five lane facilities with 12' lanes and 10' shoulders. The center lane is designated as a left turn only lane. The route is a major commuter facility with the Greenwood Mall and numerous other traffic generators located adjacent to
Y | 3 | Barren River ADD | IP20190009 |  |  |  | Improve safety and mobility on KY 185 from MP 3 to MP 4.8. | Reconstruction | Butler | 016-KY-0185 -000 | 3 | 4.8 | 1.8 | Construct Road in New Location | 0 |  | 0 |  | 1500000 |  | 1250000 |  | 500000 |  | 5250000 |  | 2019-03-05 14:00 | Improve safety and mobility. | KY185 (Green River Bridge-KY70) is a two lane facility with numerous horizontal and vertical curves. The road serves as a major travel route for commuters from Butler, western Edmonson, and western Grayson to workplaces and shopping areas in Warren County
Y | 3 | Bowling Green MPO | IP20190020 |  |  |  | Improve access with a new interchange on I-65 at Carter-Sims Road. | New Interchange | Warren | 114-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 |  | 0 |  | 1200000 |  | 1000000 |  | 900000 |  | 8000000 |  | 2019-01-23 15:53 | Improve access. | With the growing population of Bowling Green, especially in the Plano area, a new interchange is needed on I-65 to provide residents with a more efficient transportation system.
Y | 3 | Pennyrile ADD | IP20190024 |  |  |  | Improve safety and mobility on KY-181 at the intersection of US-68. | Spot Improvement | Todd | 110-KY-0181 -000 | 13 | 13.1 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 50000 |  | 150000 |  | 250000 |  | 2019-03-14 10:27 | Improve safety and mobility. | Safety for right-turners at this intersection has been an expressed concern of the people of Elkton and Todd County.
Y | 3 | Barren River ADD | IP20190026 |  |  |  | Improve safety on KY 70 from MP 11.18 to MP 12.18. | Reconstruction | Butler | 016-KY-0070 -000 | 11.18 | 12.18 | 1 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-06 14:49 | Improve safety. | Safety concerns are voiced by the locals at these curves. Reconstruction is needed to straighten out this section of roadway.
Y | 3 | Barren River ADD | IP20190027 |  |  |  | Improve safety at the intersection of US 431 and KY 663. | Spot Improvement | Logan | 071-US-0431 -000 | 4.09 | 4.19 | 0.1 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 150000 |  | 200000 |  | 750000 |  | 2019-03-11 09:43 | Improve safety. | Heavy traffic, particularly trucks, in the area have led to crashes and general safety concerns at the intersection.
Y | 3 | Pennyrile ADD | IP20190029 |  |  |  | Improve safety and mobility at the US-79/KY-181, US-79/US-41, and US-41/KY-181 intersections ("Guthrie Knot"). | Reconstruction | Todd | 110-US-0079 -000 | 0.2 | 0.6 | 0.4 | Realign Intersection | 26 |  | 0 |  | 200000 |  | 150000 |  | 300000 |  | 375000 |  | 2019-03-08 10:13 | Improve safety and mobility. | Safety improvements along the corridor and at intersections are needed due to increased congestion.
Y | 3 | Barren River ADD | IP20190037 |  |  |  | Improve safety and mobility at the intersection of KY 1008 and US 31W. | Spot Improvement | Simpson | 107-KY-1008 -000 | 2.1 | 2.4 | 0.3 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 350000 |  | 300000 |  | 1000000 |  | 2019-03-13 14:21 | Improve safety and mobility. | Widening to add an extra lane on the western side of KY 1008 is needed to reduce congestion and make the traffic signal more effective.
Y | 3 | Barren River ADD | IP20190038 |  |  |  | Improve mobility by completing the KY 1008 Bypass around Franklin. | Bypass | Simpson | 107-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-13 11:03 | Improve mobility. | Completing the bypass would further reduce the truck traffic entering the city of Franklin.
Y | 3 | Bowling Green MPO | IP20190040 |  |  |  | Improve safety on US 231 at the Exit 22 interchange with I 65. | Spot Improvement | Warren | 114-US-0231 -000 | 8.97 | 9.18 | 0.21 | Interchange Safety Improvements | 35 |  | 0 |  | 150000 |  | 0 |  | 0 |  | 250000 |  | 2019-03-11 15:41 | Improve safety. | Reconfiguration of the SPUI is needed to lessen the size of the intersection to improve safety.
Y | 3 | Barren River ADD | IP20190042 |  |  |  | Improve safety and mobility on KY 249 near Trojan Trail from MP 15.47 to MP 15.65. | Spot Improvement | Barren | 005-KY-0249 -000 | 15.47 | 15.65 | 0.18 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 250000 |  | 100000 |  | 500000 |  | 1000000 |  | 2019-03-04 14:30 | Improve safety and mobility. | A high volume of traffic makes left turns into Trojan Trail, mainly during peak hours due to the school on the route. This had created a need for a turn lane on KY 249, which would require the bridge over South Fork Beaver Creek to be replaced.
Y | 3 | Barren River ADD | IP20190094 |  |  |  | Improve safety and sight distance at the intersection of KY 98 and KY 671. | Spot Improvement | Allen | 002-KY-0098 -000 | 8.85 | 8.95 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 50000 |  | 100000 |  | 300000 |  | 2019-03-04 14:31 | Improve safety and sight distance. | A vertical crest on the eastern side of KY 98 limits sight distance and makes this intersection dangerous for drivers trying to turn left onto KY 98 from KY 671.
Y | 3 | Barren River ADD | IP20190095 |  |  |  | Improve safety at the intersection of KY 740 and Tick Ridge Road. | Spot Improvement | Barren | 005-KY-0740 -000 | 3.14 | 3.19 | 0.05 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 100000 |  | 100000 |  | 300000 |  | 2019-03-04 14:33 | Improve safety. | Sight distance and the geometry of the roadway are issues that need to be addressed to improve safety at the intersection.
Y | 3 | Barren River ADD | IP20190098 |  |  |  | Improve safety and mobility on US 68 at the truck stop on W. H. Brown Road. | Spot Improvement | Logan | 071-US-0068 -000 | 11.35 | 11.55 | 0.2 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 50000 |  | 50000 |  | 250000 |  | 2019-03-08 14:14 | Improve safety and mobility. | The truck stop/gas station along with some other businesses are accessed via W. H. Brown Road by many vehicles, including trucks. A left turn lane is needed on eastbound US 68 to improve safety and mobility.
Y | 3 | Barren River ADD | IP20190099 |  |  |  | Improve safety and sight distance at the intersection of US 68 and KY 2399. | Spot Improvement | Metcalfe | 085-US-0068 -000 | 11.45 | 11.55 | 0.1 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 250000 |  | 500000 |  | 2019-03-13 08:25 | Improve safety and sight distance. | A vertical crest on the eastern side of US 68 limits sight distance and makes this intersection dangerous for drivers trying to turn left onto US 68 from KY 2399.
Y | 3 | Barren River ADD | IP20190105 |  |  |  | Improve safety at the intersection of KY 100 and Henry Clay Smith Road. | Spot Improvement | Simpson | 107-KY-0100 -000 | 17.39 | 17.49 | 0.1 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 150000 |  | 150000 |  | 300000 |  | 2019-03-13 15:57 | Improve safety. | A vertical crest on KY 100 at this intersection creates a safety issue for drivers turning left onto Henry Clay Smith Road.
Y | 3 | Pennyrile ADD | IP20190106 |  |  |  | Improve safety on KY 181 from MP 23.8 to MP 24.2. | Reconstruction | Todd | 110-KY-0181 -000 | 23.8 | 24.2 | 0.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-28 10:23 | Improve safety. | Address geometric deficiencies throughout this section of KY 181.
Y | 3 | Pennyrile ADD | IP20190107 |  |  |  | Improve safety at the intersection of KY 171 and KY 507. | Spot Improvement | Todd | 110-KY-0171 -000 | 7.48 | 7.58 | 0.1 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-28 13:42 | Improve safety | Address geometric deficiencies at this intersection.
Y | 3 | Bowling Green MPO | IP20190109 |  |  |  | Reduce congestion and increase mobility on US 31W at the Exit 6 interchange with the Natcher Parkway. | Spot Improvement | Warren | 114-US-0031W -000 | 8.85 | 9.05 | 0.2 | Modernize Roadway-Urban | 16 |  | 0 |  | 250000 |  | 0 |  | 350000 |  | 500000 |  | 2019-03-11 12:50 | Reduce congestion and increase mobility. | The left turn lanes do not have enough capacity to handle the traffic load during the peak hours. Extending each left turn lane to enable traffic to queue up side by side would help alleviate some of these issues.
Y | 3 | Bowling Green MPO | IP20190110 |  |  |  | Reduce congestion and increase mobility at the US 231 intersection with US 68 and US 68X. | Spot Improvement | Warren | 114-US-0231 -000 | 13.832 | 13.882 | 0.05 | Improve Intersection | 26 |  | 0 |  | 1500000 |  | 4000000 |  | 2500000 |  | 5000000 |  | 2019-03-14 14:50 | Reduce congestion and increase mobility. | Heavy congestion occurs on US 231 at this intersection due to the number of vehicles trying to turn onto US 68 or US 68X. Adding an extra lane on US 231 is needed to help with this issue.
Y | 3 | Bowling Green MPO | IP20190111 |  |  |  | Reduce congestion and increase mobility on KY 234 from the Exit 26 interchange with I 65 to KY 880. | Spot Improvement | Warren | 114-KY-0234 -000 | 10.2 | 10.8 | 0.6 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 50000 |  | 50000 |  | 500000 |  | 2019-03-11 10:02 | Reduce congestion and increase mobility. | The left turn lane capacity on KY 234 at KY 880 and at the Exit 26 interchange is insufficient during the peak hours of the day, so extending those lanes is needed.
Y | 3 | Bowling Green MPO | IP20190113 |  |  |  | Planning study to determine best location for new interchange on I 65. | New Interchange | Warren | 114-I -0065 -000 | 14.8 | 19.3 | 4.5 | Innovative Interchange | 40 |  | 500000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-08 13:45 | Planning study. | A new interchange is needed to alleviate some of the congestion on US 231 and KY 884. The growing residential communities in the area will continue to make those congestion issues worse on those routes until a better alternative is constructed to get tho
Y | 3 | Barren River ADD | IP20190148 |  |  |  | Improve safety and mobility at the intersection of KY 101 and KY 743. | Spot Improvement | Edmonson | 031-KY-0101 -000 | 0.78 | 0.88 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 150000 |  | 300000 |  | 300000 |  | 2019-03-08 11:56 | Improve safety and mobility. | Congestion in the area, particularly trucks, has created the need for a left turn lane on KY 101 onto KY 743.
Y | 4 | Barren River ADD | IP20000090 |  |  |  | CONSTRUCT A SOUTHEASTERN BYPASS OF HORSE CAVE FROM KY 218 TO US 31W TO IMPROVE SAFETY AND REDUCE CONGESTION. | New Route | Hart | 050-US-0031W -000 | 1.78 | 2.667 | 0.887 | Grade Seperation of Highway/Railroad Crossing | 90 |  | 250000 |  | 1000000 |  | 2000000 |  | 1000000 |  | 8500000 |  | 2019-01-04 11:03 | Address safety, congestion, and truck traffic from US 31W in southern Horse Cave to KY 218 in eastern Horse Cave. | At present there is no route that serves as a southern bypass for Horse Cave. Motorists traveling between US 31W South and KY 218 East must travel through the center of the city. There is a significant amount of large truck traffic and farm vehicles tha
Y | 4 | Lincoln Trail ADD | IP20040013 |  |  |  | INTERSECTION IMPROVEMENTS AT KY 737 AND KY 259 IN LEITCHFIELD | Reconstruction | Grayson | 043-KY-0259 -000 | 13.3 | 13.459 | 0.159 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 1100000 |  | 200000 |  | 900000 |  | 2019-01-04 11:15 | Address safety at the intersection of KY 259 ant KY 737 in Leitchfield. | Potential sight distance issues combined with high crash rates are present at the intersection of KY 259 and KY 737. This roadway segment of KY 259 provides access to the north side of Leitchfield and is a main access point for people from Breckinridge C
Y | 4 | Lincoln Trail ADD | IP20040040 |  |  |  | CONSTRUCT NORTHEASTERN BYPASS OF BARDSTOWN FROM US 31E N TO US 62 TO RELIEVE CONGESTION AND IMPROVE CONNECTIVITY. TOTAL LENGTH: 3.0 MILES. | Bypass | Nelson | 090-US-0031E -000 | 15.4 | 16.729 | 1.329 | Construct Road in New Location | 0 |  | 500000 |  | 2200000 |  | 2750000 |  | 1100000 |  | 13200000 |  | 2019-01-04 13:13 | Address congestion and mobility along KY 245 and US 31E. | Relieve congestion on alternate roadways by constructing a new route around the City of Bardstown. New System could provide linkage and improve traffic circulation on roadways from US 31E N to US-62. This project is one of three sections of a proposed byp
Y | 4 | Lincoln Trail ADD | IP20040041 |  |  |  | CONSTRUCT NORTHWESTERN BYPASS OF BARDSTOWN FROM KY 245 TO US 31E NORTH TO RELIEVE CONGESTION AND IMPROVE CONNECTIVITY. Total length: 2.0 miles. | Bypass | Nelson | 090-US-0031E -000 | 15.4 | 16.729 | 1.329 | Construct Road in New Location | 0 |  | 500000 |  | 1500000 |  | 1500000 |  | 500000 |  | 8000000 |  | 2019-01-04 13:13 | Address congestion in downtown Bardstown | Relieve congestion on alternate roadways by constructing a new route around the City of Bardstown. New System could provide linkage and improve traffic circulation on roadways from KY-245 to US-31E north. This project is one of three sections of a propos
Y | 4 | Lake Cumberland ADD | IP20050004 | 4-397.12 |  | A | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM 1600 FEET WEST OF SOUTH THURLOW RD (MP 9.682) EXTENDING TO THE RUSSELL CREEK BRIDGE (MP 10.775) (3-203.00 STUDY RECOMMENDATION #11)(DESIGN UNDER 4-397)(2016BOP)(18CCN) | RECONSTRUCTION(O) | Green | 044-US-0068 -000 | 9.682 | 10.775 | 1.093 | Modernize Roadway-Rural | 26 | [5 empty] | 400000 | 2019 | 720000 | 2019 | 4100000 | 2020 | 2018-07-10 08:18 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG RUSSELL CREEK HILL ON US 68 FROM NEAR SOUTH THURLOW RD EXTENDING TO THE RUSSELL CREEK BRIDGE. | This section of US 68 in Green County includes a long hill with curves on a typical rural highway. Local drivers say that this section is difficult to manuever due to the geometry and the narrowness of the roadway. The project limits begin just west of S | LAKE CUMBERLAND ADD | South | 25.6754 | 2.7488 | 7.9621 | 2.5948 | 1.7536 | 5.8294 | 0 | 4.7867 | 26
Y | 4 | Elizabethtown-Radcliff MPO | IP20050005 |  |  |  | CONSTRUCT A RIGHT TURN LANE ON KY 710 AT KY 448 IN BRANDENBURG | Safety-Haz-Elm | Meade | 082-KY-0710 -000 | 8.143 | 8.243 | 0.1 | Improve Intersection | 26 |  | 0 |  | 85000 |  | 55000 |  | 90000 |  | 550000 |  | 2019-01-04 13:15 | Address safety on KY 710 at the intersection with KY 448 | The intersection of KY 710 and KY 448 is located in downtown Brandenburg. This intersection has geometric deficiencies causing awkward turning onto KY 448 which carries nearly 5,400 vehicles per day. Meade County Schools are located on KY 710. Buses ha
Y | 4 | Lincoln Trail ADD | IP20050034 |  |  |  | CONSTRUCT WESTERN LEITCHFIELD BYPASS FROM KY 737 TO KY 54. ESTIMATED TOTAL LENGTH: 2.8 MILES. SEE RECOMMENDED PHASE 3 OF 2005 NORTHWEST LEITCHFIELD BYPASS STUDY. | Bypass | Grayson | 043-KY-0054 -000 | 17.15 | 18.466 | 1.316 | Construct Road in New Location | 0 |  | 0 |  | 1200000 |  | 4000000 |  | 150000 |  | 10000000 |  | 2019-01-04 13:34 | Address safety, mobility, and congestion along KY 259 in downtown Leitchfield. | Currently, trucks must travel through the city of Leitchfield to reach the businesses and industrial plants located north and west of town. The Northwest Leitchfield Bypass will provide better circulation for trucks as well as better connections with th
Y | 4 | Lincoln Trail ADD | IP20050035 |  |  |  | CONSTRUCT WESTERN LEITCHFIELD BYPASS FROM KY 259 TO KY 737. ESTIMATED TOTAL LENGTH: 1.7 MILES. SEE RECOMMENDED PHASE 2 OF 2005 NORTHWEST LEITCHFIELD BYPASS STUDY. | Bypass | Grayson | 043-KY-0737 -000 | 0 | 1.5 | 1.5 | Construct Road in New Location | 0 |  | 0 |  | 700000 |  | 1200000 |  | 200000 |  | 5000000 |  | 2019-01-04 13:35 | Address safety, congestion and mobility along KY 259 in downtown Leitchfield. | This project is the second of five projects recommended by the NW Leitchfield Bypass Study. It extends from KY 259N, across from KY 3155, to KY 737 (Lilac Road), near Cave Mill Road. Currently, trucks must travel through the city of Leitchfield to reach
Y | 4 | Lincoln Trail ADD | IP20050037 |  |  |  | EXTEND WAREHOUSE ROAD TO KY 2154 (LEBANON BYPASS). ESTIMATED TOTAL LENGTH: 0.8 MILES. | Reconstruction | Marion | 078-CS-1091 -000 | 0.35 | 0.37 | 0.02 | Local Roadway Improvements | 3 |  | 0 |  | 880000 |  | 550000 |  | 550000 |  | 3300000 |  | 2019-01-04 13:40 | Improve connectivity form Warehouse Road to the Lebanon Bypass. | System connectivity and access to industrial areas is inadequate. This causes large trucks to enter the downtown area creating congestion and unsafe driving conditions. This project would construct a new connector between Warehouse Street along the aban
Y | 4 | Lincoln Trail ADD | IP20060213 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 79 FROM MCCOY-ROFF ROAD TO 600' N OF SAND ROCK PASS ROAD. | Reconstruction | Breckinridge | 014-KY-0079 -000 | 8.1 | 10.1 | 2 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1400000 |  | 1000000 |  | 8000000 |  | 2015-01-09 08:56 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 79 FROM MCCOY-ROFF ROAD TO 600' N OF SAND ROCK PASS ROAD. | SECOND OF THREE PROJECTS IN A PLAN TO IMPROVE KY 79 FROM US 60 AT HARNED TO KY 259 AT AXTEL, TOTAL LENGTH OF 9.7 MILES. THIS PROJECT BEGINS AT MCCOY-ROFF ROAD AND EXTENDS TO 600' N OF SAND ROCK PASS ROAD. KY 79 PROVIDES DIRECT ACCESS TO THE AXTEL AND NO | LINCOLN TRAIL ADD | South | 35.0628 | 3.7536 | 8.1754 | 4.6742 | 1.8246 | 5.4028 | 2.9384 | 8.2938 | 35
Y | 4 | Lincoln Trail ADD | IP20060214 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 79 FROM 600' NORTH OF SAND ROCK PASS ROAD TO US 60 AT HARNED. | Reconstruction | Breckinridge | 014-KY-0079 -000 | 10.1 | 14.99 | 4.89 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3400000 |  | 2500000 |  | 15600000 |  | 2019-01-04 13:41 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 79 FROM 600' NORTH OF SAND ROCK PASS ROAD TO US 60 AT HARNED. | FINAL OF THREE PROJECTS IN A PLAN TO IMPROVE KY 79 FROM US 60 AT HARNED TO KY 259 AT AXTEL, TOTAL LENGTH OF 9.7 MILES. THIS SEGMENT BEGINS AT 600' NO OF SAND ROCK PASS ROAD AND ENDS AT US 60 AT HARNED. KY 79 PROVIDES DIRECT ACCESS TO THE AXTEL AND NORTH
Y | 4 | Lincoln Trail ADD | IP20060216 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 259 FROM THE NORTHERN INTERSECTION OF KY 3155 (LEITCHFIELD BYPASS) TO HANGING ROCK CHURCH RD | Reconstruction | Grayson | 043-KY-0259 -000 | 14.465 | 15.553 | 1.088 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4000000 |  | 2019-01-04 13:46 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 259 FROM THE NORTHERN INTERSECTION OF KY 3155 (LEITCHFIELD BYPASS) TO HANGING ROCK CHURCH RD | This project would upgrade the existing roadway of KY 259 between the Leitchfield Bypass and the Goff Industrial Park. This segment is located on the North side of the City of Leitchfield. Freight traffic is common on this narrow two lane roadway. The
Y | 4 | Lake Cumberland ADD | IP20060219 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 61 FROM 0.2 MILES SOUTH OF GREEN/LARUE COUNTY LINE TO KY 1906 AT MT SHERMAN IN LARUE CO | Reconstruction | Green | 044-KY-0061 -000 | 24.144 | 24.344 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 450000 |  | 900000 |  | 1000000 |  | 4300000 |  | 2016-09-08 13:56 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 61 FROM 0.2 MILES SOUTH OF GREEN/LARUE COUNTY LINE TO KY 1906 AT MT SHERMAN IN LARUE COUNTY | KY 61 in Green County is a typical rural highway with 9’ lanes and minimal to no shoulders. Crash data from 2000- 2004 shows a significant number of crashes along the corridor. Another problem is that there is currently no truck network roads in Green Co
Y | 4 | Elizabethtown-Radcliff MPO | IP20060222 |  |  |  | Address lane width, shoulders, and maintenance issues along KY 434 between US 31W and KY 251. | Minor Widening | Hardin | 047-KY-0434 -000 | 0.025 | 3.158 | 3.133 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2200000 |  | 1200000 |  | 7500000 |  | 2019-01-04 13:55 | Address lane width, shoulders, and maintenance issues along KY 434 between US 31W and KY 251. | This section of KY 434 provides an important connection from KY 251 (MP 3.158) to US 31W (MP 0.025). KY 434 also provides a connection to Interstate 65 by way of KY 313, to the east of this section. The two 10-foot lanes are inadequate to serve the truck
Y | 4 | Elizabethtown-Radcliff MPO | IP20060223 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 1600 FROM KY 361 TO THE ROUNDABOUT AT KY 220 IN RINEYVILLE | Reconstruction | Hardin | 047-KY-1600 -000 | 0 | 3.316 | 3.316 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4000000 |  | 2017-05-05 08:57 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 1600 FROM KY 361 TO THE ROUNDABOUT AT KY 220 IN RINEYVILLE | This project on KY 1600 extends from KY 361 to KY 220 at south Rineyville. Safety and congestion along KY 1600 are key community concerns due to residential growth along the corridor. The CRF for this section of KY 1600 is 1.02 indicating potential safety | Radcliff/Elizabethtown MPO | South | 48.5806 | 2.7867 | 14.5735 | 12.1919 | 4.6682 | 5.545 | 0 | 8.8152 | 49
Y | 4 | Elizabethtown-Radcliff MPO | IP20060225 |  |  |  | ACCESS IMPROVEMENTS ALONG KY 1815 (WEST LINCOLN TRAIL BLVD) IN RADCLIFF FROM US 31W TO KY 313 | Congestion Management | Hardin | 047-KY-1815 -000 | 0 | 2.439 | 2.439 | Access Consolidation | 25 |  | 100000 |  | 175000 |  | 550000 |  | 475000 |  | 900000 |  | 2019-01-07 10:13 | ADDRESS ACCESS MANAGEMENT ALONG KY 1815 (WEST LINCOLN TRAIL BLVD) IN RADCLIFF FROM US 31W TO KY 313 | KY 1815 (Lincoln Trail Blvd) is a major thoroughfare in the City of Radcliff and connects US 31W with KY 313. KY 1815 currently carries 16,000 vehicles per day and has a volume/service flow ratio of 1.01. The critical rate factor on this approximate 2.5 m
Y | 4 | Barren River ADD | IP20060227 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1846 (SHORT CUT ROAD) FROM KY 218 TO US 31W NORTH OF HORSE CAVE. | Reconstruction | Hart | 050-KY-1846 -000 | 2.26 | 3.802 | 1.542 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 500000 |  | 800000 |  | 3000000 |  | 2017-05-05 10:09 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1846 (SHORT CUT ROAD) FROM KY 218 TO US 31W NORTH OF HORSE CAVE. | KY 1846 is a narrow two lane facility between US 31W and KY 218. It presently serves as a bypass for those traveling between US 31W North and KY 218 East. The local name for this road is the "Short Cut Road". There are several large trucks that use this r | BARREN RIVER ADD | South | 16.8412 | 0.92891 | 7.3934 | 1.7417 | 2.6066 | 4.1706 | 0 | 0 | 17
Y | 4 | Lincoln Trail ADD | IP20060229 | 4-8911 | 2019-12-13 | A | SPOT IMPROVEMENTS ON KY 84 FROM HODGENVILLE TO I-65. (16CCN)(18CCN)(COMBINED WORK UNDER 4-8909) | SPOT IMPROVEMENTS(O) | Larue | 062-KY-0084 -000 | 0 | 6.561 | 6.561 | Modernize Roadway-Rural | 26 |  |  |  | 130000 | 2020 | 20000 | 2025 | 100000 | 2025 | 1750000 | 2020 | 2018-12-26 10:05 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 FROM US 31W AT SONORA TO KY 357 SOUTHWEST OF HODGENVILLE. | KY 84 provides a direct link from Interstate 65 to Hodgenville. This road is utilized by freight traffic frequently. Narrow lanes and little shoulders combined with numerous horizontal curves presents potential problem areas.
Y | 4 | Lincoln Trail ADD | IP20060230 | 4-8911 | 2019-12-13 | A | SPOT IMPROVEMENTS ON KY 84 FROM HODGENVILLE TO I-65. (16CCN)(18CCN)(COMBINED WORK UNDER 4-8909) | SPOT IMPROVEMENTS(O) | Larue | 062-KY-0084 -000 | 6.561 | 8.449 | 1.888 | Modernize Roadway-Rural | 26 |  |  |  | 130000 | 2020 | 20000 | 2025 | 100000 | 2025 | 1750000 | 2020 | 2018-12-26 10:05 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 FROM KY 357 TO KY 61 (LINCOLN PARKWAY) NEAR HODGENVILLE | KY 84 provides a direct link from Interstate 65 to Hodgenville. Concern exists about the horizontal and vertical alignment on this segment, from KY 357 to KY 61. The lane width and shoulder width on this section is better on average than the remainder o
Y | 4 | Lincoln Trail ADD | IP20060232 |  |  |  | ADDRESS CONGESTION ALONG US 62 IN BARDSTOWN FROM KY 245 TO KY 605. | Major Widening | Nelson | 090-US-0062 -000 | 15.919 | 17.234 | 1.315 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 2250000 |  | 1250000 |  | 8000000 |  | 2017-05-05 14:05 | ADDRESS CONGESTION ALONG US 62 IN BARDSTOWN FROM KY 245 TO KY 605. | Several local schools and industries are located along this section of US 62. | 4 | South | 53.1351 | 8.5972 | 13.2938 | 12.1209 | 1.327 | 7.7725 | 4.5261 | 5.4976 | 53
Y | 4 | Lincoln Trail ADD | IP20060233 |  |  |  | ADDRESS CONGESTION ALONG US 62 IN BARDSTOWN FROM US 150 TO GUTHRIE DRIVE. | Reconstruction | Nelson | 090-US-0062 -000 | 14.633 | 15.262 | 0.629 | Major Widening-Urban Streets | 25 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4000000 |  | 2019-01-04 14:22 | ADDRESS CONGESTION ALONG US 62 IN BARDSTOWN FROM US 150 TO GUTHRIE DRIVE. | Several local businesses are located along this section of US 62, which has a high CRF.
Y | 4 | Lake Cumberland ADD | IP20060236 |  |  |  | HEARTLAND PARKWAY - UPGRADE US68\KY 55 CORRIDOR FROM KY 1799 (Airport Road) TO MARION C\L. SEE OPTION 2, SEGMENT 5, SECTION F IN 2005 HEARTLAND PARKWAY STUDY. | Minor Widening | Taylor | 109-US-0068 -000 | 7.404 | 13.531 | 6.127 | Modernize & Widen Roadway-Rural | 26 | Y | 0 |  | 600000 |  | 300000 |  | 500000 |  | 6000000 |  | 2018-12-04 11:08 | Address safety, mobility, and capacity along US 68 from KY 1799 to the Marion County line. | The US 68/KY 55/KY 555 corridor links the cities of Columbia, Campbellsville, Lebanon and Springfield to both the Louie B. Nunn/Cumberland Parkway and the Martha Layne Collins/Bluegrass Parkway. The study of this Heartland Parkway corridor was completed | LAKE CUMBERLAND ADD | South | 64.019 | 7.0521 | 14.0758 | 7.7488 | 0.47393 | 7.8673 | 3.9336 | 7.8673 | 49 |  | 15
Y | 4 | Lincoln Trail ADD | IP20060239 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 EAST OF SPRINGFIELD FROM 0.3 MILES EAST OF THE BEECH FORK BRIDGE TO KELLY SHOP ROAD. | Reconstruction | Washington | 115-KY-0152 -000 | 12.5 | 14.206 | 1.706 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1500000 |  | 1000000 |  | 1000000 |  | 6000000 |  | 2019-01-04 14:28 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 EAST OF SPRINGFIELD FROM 0.3 MILES EAST OF THE BEECH FORK BRIDGE TO KELLY SHOP ROAD. | This roadway is a linkage between the City of Springfield and the City of Harrodsburg. It is a two-lane highway with 9 foot wide lanes with little or no shoulders and numerous horizontal curves.
Y | 4 | Lincoln Trail ADD | IP20060240 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 528 FROM US 150 (SPRINGFIELD BYPASS) TO KY 438. | Reconstruction | Washington | 115-KY-0528 -000 | 3.117 | 7.144 | 4.027 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 700000 |  | 8200000 |  | 2017-05-05 14:18 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 528 FROM US 150 (SPRINGFIELD BYPASS) TO KY 438. | This segment of roadway is a two lane facility with narrow 8' wide lanes. | LINCOLN TRAIL ADD | South | 29.673 | 0.83412 | 8.3886 | 5.6872 | 3.5308 | 4.0284 | 0 | 7.2038 | 30
Y | 4 | Lincoln Trail ADD | IP20070150 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 79 FROM KY 259 TO MCCOY-ROFF ROAD. | Reconstruction | Breckinridge | 014-KY-0079 -000 | 5.294 | 8.1 | 2.806 | Modernize Roadway-Rural | 26 |  | 0 |  | 1200000 |  | 1900000 |  | 1400000 |  | 9000000 |  | 2017-05-04 13:38 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 79 FROM KY 259 TO MCCOY-ROFF ROAD. | KY 79 IS A NARROW, TWO-LANE ROAD WITH LITTLE OR NO SHOULDERS. IT PROVIDES DIRECT ACCESS TO THE AXTEL AND NORTH FORK RECREATIONAL AREAS, OWNED BY THE CORP OF ENGINEERS, AND THE ROUGH RIVER DAM STATE RESORT PARK. RECREATIONAL TRUCK/BOAT TRAFFIC AND TRUCK/ | LINCOLN TRAIL ADD | South | 35.1398 | 3.7536 | 5.6161 | 6.5047 | 1.8246 | 5.4028 | 2.9384 | 9.0995 | 35
Y | 4 | Lincoln Trail ADD | IP20070153 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND DRAINAGE ALONG US 62 FROM THE PROPOSED LEITCHFIELD WESTERN BYPASS TO THE SOUTHERN INTERSECTION OF KY 259 IN LEITCHFIELD. | Reconstruction | Grayson | 043-US-0062 -000 | 19.85 | 20.787 | 0.937 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1000000 |  | 2000000 |  | 1800000 |  | 8000000 |  | 2019-01-04 14:29 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND DRAINAGE ALONG US 62 FROM THE PROPOSED LEITCHFIELD WESTERN BYPASS TO THE SOUTHERN INTERSECTION OF KY 259 IN LEITCHFIELD. | This segment of US 62 connects the City of Leitchfield at KY 259 to the proposed Leitchfield Western bypass, including area known as Rock Crusher Hill. This roadway provides access to two county schools, national guard armory, concrete plant, and a rock
Y | 4 | Lincoln Trail ADD | IP20070155 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 259 FROM HANGING ROCK CHURCH RD TO TUG HOWARD RD IN BRECKINRIDGE COUNTY | Reconstruction | Grayson | 043-KY-0259 -000 | 15.553 | 21.459 | 5.906 | Modernize Roadway-Rural | 26 |  | 500000 |  | 2400000 |  | 4100000 |  | 3000000 |  | 24000000 |  | 2019-01-04 14:29 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 259 FROM HANGING ROCK CHURCH RD TO TUG HOWARD RD IN BRECKINRIDGE COUNTY | The horizontal alignment is rated a 3 along the section from MP 17.954 to MP 21.459 indicating infrequent curves requiring reduced speed to navigate safely. The vertical alignment is a 4 from MP 15.553 to 20.831 indicating definite sight distance and spe
Y | 4 | Lincoln Trail ADD | IP20070156 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 920 FROM US 62 TO KY 3155 (LEITCHFIELD BYPASS) | Reconstruction | Grayson | 043-KY-0920 -000 | 0 | 1.5 | 1.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1100000 |  | 750000 |  | 6000000 |  | 2019-01-04 14:30 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 920 FROM US 62 TO KY 3155 (LEITCHFIELD BYPASS) | This segment of KY 920 provides traffic connection from US 62 to the Leitchfield Bypass (KY 3155). This roadway segment provides direct access for truck traffic to connect to the bypass, US 62, and industries.
Y | 4 | Lincoln Trail ADD | IP20070157 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1214 FROM KY 3155 (LEITCHFIELD BYPASS) TO US 62. | Reconstruction | Grayson | 043-KY-1214 -000 | 14.028 | 14.86 | 0.832 | Modernize Roadway-Rural | 26 |  | 200000 |  | 650000 |  | 700000 |  | 500000 |  | 3500000 |  | 2019-01-04 14:31 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1214 FROM KY 3155 (LEITCHFIELD BYPASS) TO US 62. | KY 1214 is a two lane roadway that has narrow, nine foot wide lanes and no shoulders. Traffic on this section of KY 1214 is increasing due to accessing the schools, shopping, and other destination points along and off of US 62.
Y | 4 | Lincoln Trail ADD | IP20070158 |  |  |  | CONSTRUCT NEW INTERCHANGE ALONG THE WESTERN KENTUCKY PKY AT KY 1214 | New Interchange | Grayson | 043-WK-9001 -000 | 109.275 | 109.375 | 0.1 | Modernize Roadway-Rural | 26 | Y | 200000 |  | 1500000 |  | 1500000 |  | 1000000 |  | 6000000 |  | 2019-01-04 14:42 | Address congestion along KY 259 from Western KY Parkway to US 62 in Leitchfield. | New interchange on WK-9001 at KY 1214. This project would need to be combined with reconstruction of KY 1214 from WK 9001 to the Leitchfield Bypass. Together, these projects could reduce congestion at other intersections leading into the City of Leitchf
Y | 4 | Elizabethtown-Radcliff MPO | IP20070159 |  |  |  | WIDEN US 31W FROM BISHOP LANE TO VALLEY CREEK BRIDGE IN ELIZABETHTOWN. (EXTENSION OF 6YP ITEM 04-189.00) | Major Widening | Hardin | 047-US-0031W -000 | 16.005 | 16.466 | 0.461 | Major Widening-Urban Streets | 25 |  | 0 |  | 450000 |  | 1200000 |  | 1500000 |  | 2900000 |  | 2019-01-04 14:43 | Address safety and congestion along US 31W between Bishop Lane and the Valley Creek Bridge in Elizabethtown | This section of US 31W begins at Bishop Lane and extends to Valley Creek Bridge and leads directly into downtown Elizabethtown. It also connects with a recently upgraded section of US 31W just south of this project area. This section is 4-10' lanes that c
Y | 4 | Elizabethtown-Radcliff MPO | IP20070161 |  |  |  | Convert from 4-lane undivided to 3-lane divided from New Glendale Road (KY 1136) to the Elizabethtown square | Congestion Management | Hardin | 047-US-0031W -000 | 15.769 | 16.585 | 0.816 | Road Diet | 37 |  | 0 |  | 250000 |  | 3200000 |  | 1500000 |  | 2500000 |  | 2019-01-04 14:44 | Address safety and congestion along US 31W between KY 1136 and the Elizabethtown square. | The recommendation is to convert US 31W to a three-lane section with a continuous two-way left-turn lane, from New Glendale Road (KY 1136) to the Elizabethtown square. The KYTC previously converted the 4-lane segment, from US 62 to KY 1357 to 3 lanes. Pre
Y | 4 | Elizabethtown-Radcliff MPO | IP20070165 |  |  |  | IMPROVE ROADWAY DRAINAGE ALONG US 31WX IN WEST POINT FROM RAILROAD TRACKS TO 14TH STREET. | Drainage Improvement | Hardin | 047-US-0031WX-000 | 1.22 | 1.91 | 0.69 | Maintenance Improvement | 10 |  | 0 |  | 220000 |  | 330000 |  | 330000 |  | 880000 |  | 2019-01-08 08:36 | IMPROVE ROADWAY DRAINAGE ALONG US 31WX IN WEST POINT FROM RAILROAD TRACKS TO 14TH STREET. | US 31WX runs directly through the City of West Point. Along this 0.7 mile section drainage problems exist that affect the roadway as well as local residences and businesses.
Y | 4 | Elizabethtown-Radcliff MPO | IP20070166 |  |  |  | CONSTRUCT CURB AND GUTTER ALONG US 62 FROM NEAR BROOKS STREET TO I-65 IN ELIZABETHTOWN. CONNECTS TWO EXISTING CURB AND GUTTER SECTIONS (DRAINAGE IMPROVEMENT). | Drainage Improvement | Hardin | 047-US-0062 -000 | 18.841 | 20.065 | 1.224 | Maintenance Improvement | 10 |  | 0 |  | 660000 |  | 1100000 |  | 1000000 |  | 3300000 |  | 2019-01-08 08:37 | Address drainage issues along US 62 from Brooks Street to the I-65 ramps. | This project extends from Brooks St. (MP 18.841) to SB I-65 ramps (MP 20.065). This section of US 62 has a history of drainage issues especially in the underpass of the CSX railroad bridge at MP 16.698.
Y | 4 | Elizabethtown-Radcliff MPO | IP20070167 | 4-442 |  | A | IMPROVE SAFETY, MOBILITY AND GEOMETRICS ON US-62 FROM I-65 TO UPPER COLESBURG ROAD (CR-1038) | RECONSTRUCTION(O) | Hardin | 047-US-0062 -000 | 20.104 | 23.351 | 3.247 | Modernize Roadway-Rural | 26 |  |  |  | 1500000 | 2022 | [6 empty] | 2018-07-10 08:17 | Improve safety , mobility, and geometrics on US-62 from I-65 to Upper Colesburg Road | US 62 has 2 lanes with little to no shoulders with vertical and horizontal curves. Increased traffic and development creating congestion and safety issues. | Radcliff/Elizabethtown MPO | South | 60.3081 | 3.8389 | 12.0142 | 12.8673 | 2.2275 | 5.0237 | 0 | 9.3365 | 45 |  | 15
Y | 4 | Elizabethtown-Radcliff MPO | IP20070169 |  |  |  | SAFETY IMPROVEMENTS ALONG KY 144 IN RADCLIFF FROM KY 1646 TO US 31W INCLUDING RECONSTRUCTING THE INTERSECTIONS AT WOODLAND DRIVE AND AT KY 1646. | Safety-Haz-Elm | Hardin | 047-KY-0144 -000 | 3.835 | 4.85 | 1.015 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 500000 |  | 1000000 |  | 2000000 |  | 2017-05-05 08:36 | Address safety, capacity, pedestrian facilities along KY 144 between KY 1646 and US 31W. | This project extends from KY 1646 (MP 3.835) to US 31W (MP 4.850). KY 144 is a narrow, two-lane road in the City of Radcliff that has narrow shoulders. These conditions contribute to a high critical rate factor (1.03) and high volume/service flow ratio (1 | Radcliff/Elizabethtown MPO | South | 39.2464 | 4.1991 | 14.6445 | 11.1611 | 2.7962 | 0 | 0 | 6.4455 | 39
Y | 4 | Elizabethtown-Radcliff MPO | IP20070170 |  |  |  | CONSTRUCT CURBS, GUTTERS & SIDEWALKS ALONG KY 144 IN VINE GROVE FROM KY 313 TO KY 1500 | Drainage Improvement | Hardin | 047-KY-0144 -000 | 1.134 | 2.791 | 1.657 | Maintenance Improvement | 10 |  | 0 |  | 800000 |  | 300000 |  | 600000 |  | 4400000 |  | 2019-01-08 08:40 | Improve drainage and pedestrian facilities along KY 144 in Vine Grove between KY 1500 and KY 313. | This section of KY 144 extends from KY 313 to KY 1500 (Knox Avenue), running directly through downtown Vine Grove. The pedestrian environment and the drainage system is currently inadequate. Construction and reconstruction of sidewalks and curb and gutter
Y | 4 | Elizabethtown-Radcliff MPO | IP20070172 |  |  |  | ADD CURB AND GUTTER TO IMPROVE DRAINAGE ALONG KY 222 IN GLENDALE FROM KY 1136 TO RAILROAD TRACKS | Drainage Improvement | Hardin | 047-KY-0222 -000 | 4.243 | 4.442 | 0.199 | Maintenance Improvement | 10 |  | 0 |  | 100000 |  | 250000 |  | 150000 |  | 450000 |  | 2019-01-08 08:40 | IMPROVE DRAINAGE ALONG KY 222 IN GLENDALE FROM KY 1136 TO RAILROAD TRACKS | KY 222 runs directly through "Historic" Glendale. This section of KY 222 is in the historic district and experiences drainage problems that affect local residences and businesses.
Y | 4 | Elizabethtown-Radcliff MPO | IP20070173 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 224 FROM HART C\L TO PLEASANT HILL-UPTON RD | Major Widening | Hardin | 047-KY-0224 -000 | 0 | 5.065 | 5.065 | Modernize Roadway-Rural | 26 |  | 500000 |  | 4000000 |  | 3500000 |  | 2000000 |  | 20000000 |  | 2019-01-07 09:39 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 224 FROM HART C\L TO PLEASANT HILL-UPTON RD | This project begins at the Hart County line (MP 0.000) and extends to Pleasant Hill Road (MP 5.065). KY 224 is a two-lane rural road that has narrow lanes (9') and no shoulders. The IRI along sections of KY 224 is as high as 201.40 indicating a potential
Y | 4 | Elizabethtown-Radcliff MPO | IP20070174 |  |  |  | EXTEND KY 434 FROM US 31W TO KY 361 | New Route | Hardin | 047-KY-0434 -000 | 0 | 0.025 | 0.025 | Construct Road in New Location | 0 | Y | 0 |  | 1200000 |  | 2100000 |  | 1500000 |  | 12000000 |  | 2019-01-07 09:41 | Address connectivity between US 31W and KY 361. | This project is to construct a new connector by extending KY 434 (near US 31W) west to the proposed E2RC. Regional connectivity will become an issue with the construction of the Elizabethtown to Radcliff Connector (E2RC) west of US 31W. US 31W currentl
Y | 4 | Elizabethtown-Radcliff MPO | IP20070175 |  |  |  | EXTENSION OF NEW GLENDALE ROAD FROM US 31W TO COMMERCE DRIVE IN ELIZABETHTOWN. | New Route | Hardin | 047-KY-1136 -000 | 10.653 | 10.655 | 0.002 | Construct Road in New Location | 0 |  | 300000 |  | 1300000 |  | 2750000 |  | 2200000 |  | 6600000 |  | 2019-01-07 09:42 | Improve connectivity between the south side of Elizabethtown and the east side of Elizabethtown. | KY 1136 is a two-lane rural road that connects US 31W south of the community of Glendale with US 31W in Elizabethtown. An extension to Commerce Drive in Elizabethtown will provide a connection with US 62 near Interstate 65. Commerce Drive is also a commer
Y | 4 | Elizabethtown-Radcliff MPO | IP20070176 |  |  |  | EXTENSION FROM KY 1868 S OF GLENDALE TO KY 220 AT KY 1600 N OF ELIZABETHTOWN | New Route | Hardin | 047-KY-1136 -000 | 2.768 | 3.942 | 1.174 | Construct Road in New Location | 0 |  | 1000000 |  | 20000000 |  | 20000000 |  | 20000000 |  | 57000000 |  | 2019-01-07 09:42 | Address connectivity on the west side of Hardin County from Glendale to the Rineyville area. | KY 1136 will play a major role in the event that development occurs on the Glendale Industrial Site. System connectivity is a major planning issue in this area of Hardin County. Improvements to the current KY 1136 and extension into northern Hardin County
Y | 4 | Elizabethtown-Radcliff MPO | IP20070177 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1600 FROM KY 1882 TO KY 144 AT FLAHERTY (mp 1.705 MEADE) | Reconstruction | Hardin | 047-KY-1600 -000 | 7.34 | 8.528 | 1.188 | Modernize Roadway-Rural | 26 |  | 0 |  | 1200000 |  | 2000000 |  | 1500000 |  | 11600000 |  | 2019-01-07 09:43 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1600 FROM KY 1882 TO KY 144 AT FLAHERTY (mp 1.705 MEADE) | This project extends from KY 1882 in Hardin County to KY 144 at Flaherty in Meade County. Safety and congestion along KY 1600 are key community concerns due to residential growth along the corridor. Vehicle crash analysis revealed high crash locations a
Y | 4 | Elizabethtown-Radcliff MPO | IP20070179 |  |  |  | CONSTRUCT EASTBOUND ON AND WESTBOUND OFF RAMPS ON THE BLUEGRASS PARKWAY AT KY 583. | New Interchange | Hardin | 047-BG-9002 -000 | 7.85 | 7.95 | 0.1 | Major Interchange Reconstruction | 32 |  | 0 |  | 500000 |  | 750000 |  | 450000 |  | 1900000 |  | 2019-01-07 09:54 | Address lack of eastbound on ramp and westbound off ramp at Bluegrass Parkway and KY 583. | This project would complete a diamond interchange on the Martha Layne Collins/ Bluegrass Parkway at KY 583. An agreement was made in the mid-90's with Hardin County, where they agreed to build these two ramps within 5 years of KYTC building the initial tw
Y | 4 | Barren River ADD | IP20070181 |  |  |  | IMPROVE CONNECTIVITY BETWEEN KY 88 AND US 31W AND I-65 TO IMPROVE SAFETY ON US 31W AND KY 88 IN MUNFORDVILLE. | New Route | Hart | 050-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 100000 |  | 1000000 |  | 1000000 |  | 400000 |  | 7000000 |  | 2019-01-07 09:55 | IMPROVE CONNECTIVITY BETWEEN KY 88 AND US 31W AND I-65 TO IMPROVE SAFETY ON US 31W AND KY 88 IN MUNFORDVILLE. | KY 88 provides direct access to Nolin Lake from Munfordville. Presently, motorists on I65 that wish to use KY88 must exit the inerstate at the US31W exit. Those motorists then follow US31W to the intersection with KY 88. This intersection is near the cour
Y | 4 | Barren River ADD | IP20070182 |  |  |  | WIDEN TO 3 LANES FROM GUTHRIE STREET IN HORSE CAVE TO SOUTH OF CAVERNA HIGH SCHOOL. EXCLUDES HES PROJECT. | Minor Widening | Hart | 050-US-0031W -000 | 0.05 | 2.875 | 2.825 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1200000 |  | 2200000 |  | 1500000 |  | 11500000 |  | 2019-01-07 09:57 | Address safety and congestion along US 31W in Horse Cave due to traffic stopping for vehicles to turn left. | US 31W between mile point .050 and mile point 2.875 in Hart County is a two lane facility. There is a high school, businesses, residences, and industrial plants located adajacent to the roadway. Presently, there are no turning lanes at the entrances to th
Y | 4 | Barren River ADD | IP20070183 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 88 FROM KY 479 IN GRAYSON COUNTY TO KY 728 IN HART COUNTY. SEE SECTION 3 IN MARCH 2004 PROGRAMMING STUDY. | Reconstruction | Hart | 050-KY-0088 -000 | 0 | 5.123 | 5.123 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3600000 |  | 2600000 |  | 20500000 |  | 2019-01-07 09:57 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 88 FROM KY 479 IN GRAYSON COUNTY TO KY 728 IN HART COUNTY. | KY 88 between the Grayson County Line and Munfordville is a narrow two lane facility with numerous horizontal and vertical curves. It provides direct access to Nolin Lake from Munfordville. There is a significant volume of farm machinery and vehicles tran
Y | 4 | Barren River ADD | IP20070184 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 88 FROM KY 728 TO JOHN LOGSDON ROAD. SEE SECTION 2 IN MARCH 2004 PROGRAMMING STUDY. | Reconstruction | Hart | 050-KY-0088 -000 | 5.123 | 10.714 | 5.591 | Modernize Roadway-Rural | 26 |  | 0 |  | 2200000 |  | 3900000 |  | 2800000 |  | 22400000 |  | 2019-01-07 09:58 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 88 FROM KY 728 TO JOHN LOGSDON ROAD. | KY 88 Between the Grayson County Line and Munfordville is a narrow two lane facility with numerous horizontal and verticle curves. It provides direct access to Nolin Lake from Munfordville. There is a significant volume of farm machinery and vehicles tran
Y | 4 | Barren River ADD | IP20070185 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1140 FROM US 31W NORTH OF MUNFORDVILLE TO MT. VERNON/ROCKY HILL RD. | Reconstruction | Hart | 050-KY-1140 -000 | 0 | 4.044 | 4.044 | Modernize Roadway-Rural | 26 |  | 0 |  | 1600000 |  | 2800000 |  | 2000000 |  | 16200000 |  | 2019-01-07 09:59 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 1140 FROM US 31W NORTH OF MUNFORDVILLE TO MT. VERNON/ROCKY HILL RD. | KY 1140 between US 31W and the MT. Vernon/Rocky Hill Road is a narrow two lane facility with numerous horizontal and vertical curves. There is also an at grade railroad crossing located on the road. The road serves as an access to the Roundstone Creek Tro
Y | 4 | Lincoln Trail ADD | IP20070186 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG US 31E FROM HODGENVILLE SQUARE TO THE NORTHERN INTERSECTION OF KY 470 AT WHITE CITY | Reconstruction | Larue | 062-US-0031E -000 | 10.093 | 14.78 | 4.687 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1900000 |  | 3500000 |  | 2300000 |  | 18700000 |  | 2019-01-07 09:59 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG US 31E FROM HODGENVILLE SQUARE TO THE NORTHERN INTERSECTION OF KY 470 AT WHITE CITY | This project begins at KY 210 (MP 10.093) and extends to KY 470 (MP14.510). US 31E is a rural minor arterial that connects several major points of interest such as the Abraham Lincoln Birthplace National Historic Site, the Abraham Lincoln Boyhood Nationa
Y | 4 | Lincoln Trail ADD | IP20070188 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 BETWEEN WHITE CITY AND HOWARDSTOWN FROM PLOUVIEW RD TO WHELAN RD. | Reconstruction | Larue | 062-KY-0084 -000 | 10.99 | 12.589 | 1.599 | Modernize Roadway-Rural | 26 |  | 250000 |  | 650000 |  | 1150000 |  | 1000000 |  | 6800000 |  | 2019-01-07 10:00 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 BETWEEN WHITE CITY AND HOWARDSTOWN FROM PLOUVIEW RD TO WHELAN RD. | This project extends from Plouvier Rd to Nelson County Line. KY 84 is a two-lane rural road with narrow shoulders and horizontal alignment deficiencies.
Y | 4 | Lincoln Trail ADD | IP20070189 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 49 FROM THE CASEY COUNTY LINE TO THE SOUTHERN INTERSECTION WITH KY 337 IN BRADFORDSVILLE. | Reconstruction | Marion | 078-KY-0049 -000 | 0 | 7.987 | 7.987 | Modernize Roadway-Rural | 26 |  | 500000 |  | 10000000 |  | 12000000 |  | 7000000 |  | 45000000 |  | 2019-01-07 10:01 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 49 FROM THE CASEY COUNTY LINE TO THE SOUTHERN INTERSECTION WITH KY 337 IN BRADFORDSVILLE. | The horizontal alignment is 3 indicating infrequent curves. It also has little to no shoulders.
Y | 4 | Lincoln Trail ADD | IP20070192 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 FROM KY 527 IN RAYWICK TO KY 426 WEST OF LEBANON. | Reconstruction | Marion | 078-KY-0084 -000 | 5.098 | 9.71 | 4.612 | Modernize Roadway-Rural | 26 |  | 250000 |  | 2000000 |  | 3200000 |  | 2300000 |  | 18400000 |  | 2019-01-07 10:04 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 FROM KY 527 IN RAYWICK TO KY 426 WEST OF LEBANON. | KY 84 connects the cities of Hodgenville in Larue Co. to Lebanon in Marion Co. Sections of this roadway have an horizontal alignment code of 3 and a vertical alignment code of 4 indicating infrequent curves and definite sight distance issues.
Y | 4 | Lincoln Trail ADD | IP20070193 |  |  |  | ADDRESS CONGESTION AND SAFETY ALONG US 62 IN BARDSTOWN FROM GUTHRIE DR TO KY 245 IN BARDSTOWN. | Reconstruction | Nelson | 090-US-0062 -000 | 15.262 | 15.919 | 0.657 | Modernize Roadway-Urban | 16 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 4000000 |  | 2019-01-07 10:05 | ADDRESS CONGESTION AND SAFETY ALONG US 62 IN BARDSTOWN FROM GUTHRIE DR TO KY 245 IN BARDSTOWN. | There is much congestion on this section of US 62 from Guthrie Drive to KY 245.
Y | 4 | Lincoln Trail ADD | IP20070194 | 4-396.10 |  | A | IMPROVE SAFETY, MOBILITY, AND GEOMETRICS ON US-150 FROM THE BLUEGRASS PARKWAY TO THE NELSON/WASHINGTON COUNTY LINE. (2016BOP)(18CCR) | RECONSTRUCTION(O) | Nelson | 090-US-0150 -000 | 1.952 | 7.653 | 5.701 | Modernize Roadway-Rural | 26 |  |  |  | 1200000 | 2020 | 4900000 |  | 2500000 |  | 25000000 |  | 2018-07-10 08:18 | ADDRESS SAFETY, MOBILITY AND GEOMETRIC DEFICIENCIES ALONG US 150 FROM THE BLUEGRASS PARKWAY (MILEPOINT 1.952) TO THE NELSON/WASHINGTON COUNTY LINE (MILEPOINT 7.653). | US 150 is the primary roadway from the Bluegrass Parkway to the City of Springfield located in Washington County. The horizontal and vertical alignment values are both a substandard 3 indicating infrequent curves and possible sight distance and speed iss | 4 | South | 69.5889 | 8.9668 | 11.7299 | 11.9964 | 1.8009 | 6.7773 | 4.455 | 8.8626 | 55 | 15
Y | 4 | Lincoln Trail ADD | IP20070197 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 55 FROM US 62 IN BLOOMFIELD TO KY 1066 IN SPENCER CO. SEE SECTION 3 IN JANUARY, 2001 SCOPING STUDY. | Reconstruction | Nelson | 090-KY-0055 -000 | 3.841 | 6.975 | 3.134 | Modernize Roadway-Rural | 26 |  | 250000 |  | 2750000 |  | 2750000 |  | 2200000 |  | 14850000 |  | 2019-01-07 10:07 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 55 FROM US 62 IN BLOOMFIELD TO KY 1066 IN SPENCER CO. | This project begins at US 62 in Bloomfield and extends to KY 1066 in Spencer County. KY 55 is a two-lane rural road that runs north-south through eastern Nelson county. Segments of this roadway have a horizontal alignment of 4 indicating infrequent curv
Y | 4 | Lincoln Trail ADD | IP20070198 |  |  |  | SPOT IMPROVEMENTS ALONG KY 605 FROM US 62 TO US 150. ESTIMATED TOTAL LENGTH: 2.0 MILES. | Spot Improvement | Nelson | 090-KY-0605 -000 | 3.608 | 10.575 | 6.967 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1000000 |  | 500000 |  | 7000000 |  | 2019-01-03 16:00 | Address safety and geometric deficiencies along KY 605 between US 150 and US 62. | This project extends from US 150 to US 62. KY 605 is a two-lane rural road with geometric deficiencies including narrow lanes and shoulders and horizontal alignment. Request was for spot improvements along this section. Assumed 2.0 miles of improvement
Y | 4 | Lake Cumberland ADD | IP20070200 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 70 FROM 0.2 MI E OF ROBERTS RD (NEAR ELK HORN BAPTIST CHURCH) TO NEAR KY 76 | Reconstruction | Taylor | 109-KY-0070 -000 | 3.1 | 4.1 | 1 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 900000 |  | 500000 |  | 3000000 |  | 2017-05-05 14:12 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 70 FROM 0.2 MI E OF ROBERTS RD (NEAR ELK HORN BAPTIST CHURCH) TO NEAR KY 76 | This project is to correct a series of horizontal and vertical curves from 0.2 mile east of Roberts Road (near Elk Horn Baptist Church) to near KY 76. Locals are very concerned about the safety of drivers in this area. Speed is also an issue. With a Crit | LAKE CUMBERLAND ADD | South | 40.9562 | 5.109 | 13.0806 | 7.34 | 2.7251 | 6.3981 | 0 | 6.3033 | 41
Y | 4 | Lake Cumberland ADD | IP20070201 |  |  |  | ADDRESS DEFICIENCIES ALONG KY 2222 AND KY 1799 FROM US 68 TO KY 658 TO IMPROVE ACCESS TO THE TAYLOR COUNTY AIRPORT. | Reconstruction | Taylor | 109-KY-2222 -000 | 0 | 0.518 | 0.518 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 700000 |  | 600000 |  | 4500000 |  | 2015-01-14 14:05 | ADDRESS DEFICIENCIES ALONG KY 2222 AND KY 1799 FROM US 68 TO KY 658 TO IMPROVE ACCESS TO THE TAYLOR COUNTY AIRPORT. | The problem with KY 2222/KY 1799 is that it is a narrow two lane roadway with little or no shoulders. Due to its proximity to the airport, stockyards, and industries, this road has higher than average volumes of truck traffic and cattle trailers. To handl
Y | 4 | Lake Cumberland ADD | IP20070202 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 3212 (OLD PITMAN RD) FROM KY 210 TO KY 527. | Minor Widening | Taylor | 109-KY-3212 -000 | 0 | 1.408 | 1.408 | Modernize Roadway-Rural | 26 |  | 0 |  | 850000 |  | 1000000 |  | 850000 |  | 6000000 |  | 2015-01-14 14:10 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 3212 (OLD PITMAN RD) FROM KY 210 TO KY 527. | KY 3212 is a semi-urban roadway with two 9 ft lanes, infrequent hills and curves, and minimal shouldering. There are several subdivision entrances along the roadway, with new ones developing. With new development, safety is becoming a concern along the ro
Y | 4 | Lincoln Trail ADD | IP20070203 |  |  |  | ADDRESS SAFETY ISSUES AT THE INTERSECTION OF US 150X AND KY 55 IN SPRINGFIELD. | Safety-Haz-Elm | Washington | 115-US-0150X -000 | 2 | 2.1 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 440000 |  | 550000 |  | 550000 |  | 1320000 |  | 2015-01-14 08:36 | ADDRESS SAFETY ISSUES AT THE INTERSECTION OF US 150X AND KY 55 IN SPRINGFIELD. | This project includes reconstruction of 1200' of KY 55. The intersection of KY 55 at US 150X can be difficult to negotiate safely and there have been numerous crashes at this location.
Y | 4 | Lincoln Trail ADD | IP20070204 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 EAST OF SPRINGFIELD FROM US 150X TO 0.3 MILES EAST OF THE BEECH FORK BRIDGE. | Reconstruction | Washington | 115-KY-0152 -000 | 7.981 | 12.5 | 4.519 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1400000 |  | 1400000 |  | 1000000 |  | 10800000 |  | 2019-01-07 10:08 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 EAST OF SPRINGFIELD FROM US 150X TO 0.3 MILES EAST OF THE BEECH FORK BRIDGE. | Several sections of KY 152 have a horizontal alignment of at least 3 indicating infrequent curves. Two sections have a vertical alignment rating of 4 indicating definite sight distance and speed issues. Narrow lane widths and shoulder widths are prevale
Y | 4 | Lincoln Trail ADD | IP20070205 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 FROM KELLY SHOP ROAD TO KY 438 (MAYES CREEK RD) WEST OF MACKVILLE. | Reconstruction | Washington | 115-KY-0152 -000 | 14.206 | 17.659 | 3.453 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 1100000 |  | 700000 |  | 9000000 |  | 2019-01-07 10:09 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 FROM KELLY SHOP ROAD TO KY 438 (MAYES CREEK RD) WEST OF MACKVILLE. | This roadway is a linkage between the City of Springfield and the City of Harrodsburg. This roadway a is two-lane highway with 9 feet wide lanes and almost no shoulders. The roadway has numerous horizontal curves.
Y | 4 | Lincoln Trail ADD | IP20070206 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 433 FROM KY 53 WEST OF WILLISBURG TO KY 555. | Reconstruction | Washington | 115-KY-0433 -000 | 6.311 | 7.339 | 1.028 | Modernize Roadway-Rural | 26 |  | 0 |  | 880000 |  | 1100000 |  | 440000 |  | 4400000 |  | 2017-05-05 14:17 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 433 FROM KY 53 WEST OF WILLISBURG TO KY 555. | This project extends from KY 53 to KY 555. KY 433 is a two-lane, rural road with narrow lanes and shoulders. The roadway also has some areas where the horizontal alignment is an issue. | LINCOLN TRAIL ADD | South | 15.2085 | 0.35071 | 3.3412 | 2.7014 | 4.9289 | 3.8863 | 0 | 0 | 15
Y | 4 | Lincoln Trail ADD | IP20080154 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 259 FROM TUG HOWARD RD TO KY 79. | Reconstruction | Breckinridge | 014-KY-0259 -000 | 0.127 | 7.901 | 7.774 | Modernize Roadway-Rural | 26 |  | 500000 |  | 3750000 |  | 5400000 |  | 3900000 |  | 32000000 |  | 2019-01-07 10:16 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 259 FROM TUG HOWARD RD TO KY 79. | THIS SECTION OF THE KY 259 CORRIDOR IS A NARROW, TWO-LANE RURAL ROAD THAT CARRIES A MODERATE AMOUNT OF TRAFFIC. SECTIONS OF THIS ROAD HAVE HORIZONTAL AND VERTICAL ALIGNMENT CODES OF 3 OR HIGHER INDICATING INFREQUENT CURVES AND SIGHT DISTANCE ISSUES.
Y | 4 | Lincoln Trail ADD | IP20080155 |  |  |  | ADDRESS SAFETY, DRAINAGE AND GEOMETRIC DEFICIENCIES ALONG KY 224 FROM US 62 IN CLARKSON TO THE WESTERN KY PARKWAY | Reconstruction | Grayson | 043-KY-0224 -000 | 0 | 0.804 | 0.804 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1500000 |  | 1250000 |  | 3750000 |  | 2017-05-04 14:02 | ADDRESS SAFETY, DRAINAGE AND GEOMETRIC DEFICIENCIES ALONG KY 224 FROM US 62 IN CLARKSON TO THE WESTERN KY PARKWAY | This section of KY 224 provides direct linkage from the WK Parkway to US 62 located in the City of Clarkson. This section is a two-lane roadway with a large amount of truck traffic. City of Clarkson officials have requested that this segment of road be | LINCOLN TRAIL ADD | South | 33.5746 | 8.6161 | 4.8341 | 4.3898 | 4.8341 | 6.3507 | 0 | 4.5498 | 34
Y | 4 | Lincoln Trail ADD | IP20080159 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 FROM THE NELSON COUNTY LINE TO KY 527 AT RAYWICK. | Reconstruction | Marion | 078-KY-0084 -000 | 0 | 5.098 | 5.098 | Modernize Roadway-Rural | 26 |  | 250000 |  | 2000000 |  | 3500000 |  | 2500000 |  | 20500000 |  | 2019-01-07 10:18 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 84 FROM THE NELSON COUNTY LINE TO KY 527 AT RAYWICK. | KY 84 connects the cities of Hodgenville in Larue Co. to Lebanon in Marion Co. The entire section has a vertical alignment code of 4 indicating definite sight distance issues.
Y | 4 | Lincoln Trail ADD | IP20080161 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ON KY 52 AT DEE HEAD ROAD. | Safety-Haz-Elm | Nelson | 090-KY-0052 -000 | 11.95 | 12.05 | 0.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 85000 |  | 220000 |  | 110000 |  | 850000 |  | 2019-01-07 10:19 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ON KY 52 AT DEE HEAD ROAD. | This project would address a sub-standard horizontal curve on KY 52 at Dee Head Road. There have been multiple injury accidents at this location. It is not possible for a truck to negotiate this curve without the rear trailer tires crossing the center l
Y | 4 | Lincoln Trail ADD | IP20080162 |  |  |  | HEARTLAND PARKWAY - UPGRADE KY 555 CORRIDOR FROM US 150X IN SPRINGFIELD TO THE BLUEGRASS PARKWAY. | Minor Widening | Washington | 115-KY-0555 -000 | 0 | 14.639 | 14.639 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 1000000 | 2021 | 500000 | 2021 | 500000 | 2022 | 15000000 | 2022 | 2019-03-11 16:14 | HEARTLAND PARKWAY - UPGRADE KY 555 CORRIDOR FROM US 150X IN SPRINGFIELD TO THE BLUEGRASS PARKWAY. | KY 555 is part of the Heartland Parkway which is the corridor from the Bluegrass Parkway to the Cumberland Parkway. This corridor is used by trucks and passing opportunities are limited and sometimes unsafe. The rest of this corridor has been improved, i
Y | 4 | Lincoln Trail ADD | IP20080163 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 THROUGH MACKVILLE FROM KY 438 TO THE MERCER COUNTY LINE. | Reconstruction | Washington | 115-KY-0152 -000 | 17.659 | 22.306 | 4.647 | Modernize Roadway-Rural | 26 |  | 250000 |  | 4000000 |  | 2500000 |  | 1500000 |  | 12000000 |  | 2019-01-07 10:20 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 152 THROUGH MACKVILLE FROM KY 438 TO THE MERCER COUNTY LINE. | KY 152 connects Springfield to Harrodsburg in Mercer Co. Sections of KY 152 have horizontal alignment ratings of 4 indicating frequent curves which require a driver to reduce speed to navigate safely. Narrow lane widths and minimal shoulder widths are p
Y | 4 | Lincoln Trail ADD | IP20080164 |  |  |  | ADDRESS GEOMETRIC DEFICIENCIES AND IMPROVE SAFETY ON KY 429 AT COWHOLE CURVE THROUGH THE ELIMINATION OF SIGHT DISTANCE ISSUES. | Reconstruction | Washington | 115-KY-0429 -000 | 2.1 | 2.5 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 440000 |  | 220000 |  | 2200000 |  | 2015-01-14 09:13 | ADDRESS GEOMETRIC DEFICIENCIES AND IMPROVE SAFETY ON KY 429 AT COWHOLE CURVE THROUGH THE ELIMINATION OF SIGHT DISTANCE ISSUES. | This segment of KY 429 is a narrow two lane road with little or no shoulders. Substandard vertical and horizontal alignments are present on this segment, locally known as Cowhole Curve. There is a creek on one side of the roadway and a high bank on the
Y | 4 | Lincoln Trail ADD | IP20080736 |  |  |  | CONSTRUCTION OF A CONNECTOR ROAD FROM KY 2154 VIA HENDRICKSON DRIVE TO KY 55, ALIGNING KY 2154 WITH THE LEBANON BYPASS. ESTIMATED TOTAL LENGTH: 1.1 MILES. | Bypass | Marion | 078-KY-0055 -000 | 1.614 | 1.866 | 0.252 | Construct Road in New Location | 0 |  | 0 |  | 700000 |  | 2000000 |  | 500000 |  | 5000000 |  | 2019-01-07 10:21 | Improve connectivity from the Lebanon Bypass to Hendrickson Drive and line up the northwest and northeast legs of the Bypass. | The Lebanon Bypass project (4-125.10) was constructed in 2008. This project will connect the Northern end of the Bypass to KY 2154, through Hendrickson Dr.
Y | 4 | Lincoln Trail ADD | IP20080737 |  |  |  | CONSTRUCT SOUTHEASTERN LEBANON BYPASS FROM INDUSTRIAL DRIVE TO US 68 AT KY 2154. ESTIMATED TOTAL LENGTH: 3.5 MILES. | Bypass | Marion | 078-US-0068 -000 | 9.364 | 12.322 | 2.958 | Construct Road in New Location | 0 |  | 0 |  | 1650000 |  | 6600000 |  | 1650000 |  | 17600000 |  | 2019-01-07 10:22 | Address congestion in Lebanon and improve connectivity from southern part of Lebanon to the eastern part of Lebanon for trucks and other traffic. | The Lebanon Bypass project (4-125.10) was constructed in 2008. This project will complete the Bypass around the city of Lebanon, and will include the reconstruction of Old Hickory Dr and a section of Sulphur Springs Rd.
Y | 4 | Lincoln Trail ADD | IP20080738 |  |  |  | ADDRESS COMMERCIAL TRAFFIC CONCERNS ALONG KY 49 FROM THE NEW INDUSTRIAL ROAD TO KY 2154 (LEBANON BYPASS) AND ALONG KY 2154 FROM KY 49 TO NORTH OF THE INDUSTRIAL ROAD OFF THE BYPASS. | Minor Widening | Marion | 078-KY-0049 -000 | 18.25 | 18.494 | 0.244 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 700000 |  | 500000 |  | 4000000 |  | 2019-01-07 10:24 | ADDRESS COMMERCIAL TRAFFIC CONCERNS ALONG KY 49 FROM THE NEW INDUSTRIAL ROAD TO KY 2154 (LEBANON BYPASS) AND ALONG KY 2154 FROM KY 49 TO NORTH OF THE INDUSTRIAL ROAD OFF THE BYPASS. | KY 49 is a narrow 2 lane road with little to no shoulders. Makers Mark will be putting a distribution center at the corner of KY 49 and KY 2154 which will increase truck traffic in the area. Trucks will have a hard time turning out of the new industrial
Y | 4 | Lincoln Trail ADD | IP20080739 |  |  |  | IMPROVE SYSTEM CONNECTIVITY AND DRAINAGE IN LEBANON BY EXTENDING MARTIN LUTHER KING, JR AVE. ALONG THE OLD RAILROAD BED FROM KY 55S (SPALDING AVE.) TO THE LEBANON BYPASS APPROX. 1200' SOUTH OF KY 49. | New Route | Marion | 078-CS-1101 -000 | 0 | 0.002 | 0.002 | Local Roadway Improvements | 3 |  | 0 |  | 850000 |  | 3000000 |  | 500000 |  | 10100000 |  | 2019-01-07 10:24 | IMPROVE SYSTEM CONNECTIVITY AND DRAINAGE IN LEBANON BY EXTENDING MARTIN LUTHER KING, JR AVE. ALONG THE OLD RAILROAD BED FROM KY 55S (SPALDING AVE.) TO THE LEBANON BYPASS APPROX. 1200' SOUTH OF KY 49. | The Lebanon Bypass project (4-125.10) was constructed in 2008. System connectivity within the City of Lebanon is very poor, which tends to create unsafe driving conditions in the downtown area.
Y | 4 | Elizabethtown-Radcliff MPO | IP20080742 |  |  |  | CONSTRUCT A NORTHWEST BYPASS AROUND GLENDALE FROM KY 222 TO KY 1136. SEE GLENDALE AREA TRANSPORTATION STUDY. | New Route | Hardin | 047-KY-0222 -000 | 3.239 | 4.243 | 1.004 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 500000 |  | 600000 |  | 2600000 |  | 2019-01-07 10:25 | Address capacity issues and congestion in the town of Glendale due to excess traffic traveling between KY 1136 and KY 222 northwest of town which will be created by the Glendale Industrial Site once it develops. | A 1,500 acre development site is located in the Glendale area. A study was conducted in 2008 to determine highway needs that may result from development on this site. This project will help move traffic to and from the development site and divert the traf
Y | 4 | Elizabethtown-Radcliff MPO | IP20080743 |  |  |  | INTERSECTION IMPROVEMENTS TO ADDRESS SAFETY AT KY 222/KY 1136 IN GLENDALE. SEE GLENDALE AREA TRANSPORTATION STUDY | Reconstruction | Hardin | 047-KY-0222 -000 | 4.2 | 4.3 | 0.1 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 150000 |  | 75000 |  | 550000 |  | 2019-01-07 10:26 | ADDRESS SAFETY AT THE KY 222/KY 1136 INTERSECTION IN GLENDALE. SEE GLENDALE AREA TRANSPORTATION STUDY | This project was identified in the Glendale Area Transportation Study as a needed improvement to enhance the movement of traffic through Glendale. The current intersection is a two-way stop on KY 1136 with through traffic on KY 222. This project could p
Y | 4 | Elizabethtown-Radcliff MPO | IP20080744 |  |  |  | CONSTRUCT A NORTHEAST BYPASS OF GLENDALE FROM KY 1136 TO KY 222. SEE GLENDALE AREA TRANSPORTATION STUDY. | New Route | Hardin | 047-KY-0222 -000 | 4.243 | 5.383 | 1.14 | Construct Road in New Location | 0 |  | 0 |  | 250000 |  | 500000 |  | 250000 |  | 2000000 |  | 2019-01-07 10:27 | Address capacity issues and congestion in the town of Glendale due to excess traffic traveling between KY 1136 and KY 222 northeast of town which will be created by the Glendale Industrial Site once it develops. | A 1,500 acre development site in located in the Glendale area. This project was identified in the Glendale Area Transportation Study. This proposed project was identified to improve traffic flow to and from the development site and to minimize traffic i
Y | 4 | Elizabethtown-Radcliff MPO | IP20080745 |  |  |  | ADD SHOULDERS AND TURN LANES TO US 31W BETWEEN KY 1136 AND KY 222 EAST OF GLENDALE. SEE GLENDALE AREA TRANSPORTATION STUDY. | Minor Widening | Hardin | 047-US-0031W -000 | 7.991 | 9.53 | 1.539 | Modernize Roadway-Rural | 26 |  | 0 |  | 275000 |  | 660000 |  | 550000 |  | 4400000 |  | 2019-01-07 10:27 | ADDRESS NARROW SHOULDERS AND LACK OF TURN LANES ALONG US 31W BETWEEN KY 1136 AND KY 222 EAST OF GLENDALE. SEE GLENDALE AREA TRANSPORTATION STUDY. | The proposed project was identified in the Glendale Area Transportation Study. The Glendale area has a 1,500 acre development site that is proposed for one major industry or other commercial entity. The study anticipates ancillary businesses to locate on
Y | 4 | Elizabethtown-Radcliff MPO | IP20080746 |  |  |  | ADDRESS CAPACITY AND SAFETY ALONG KY 1136, SOUTH OF GLENDALE FROM US 31W TO JAGGERS ROAD INCLUDING RECONSTRUCTION OR REPLACEMENT OF THE BRIDGE OVER I65. SEE 2008 GLENDALE AREA TRANSPORTATION STUDY. | Minor Widening | Hardin | 047-KY-1136 -000 | 0 | 1.321 | 1.321 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 660000 |  | 5200000 |  | 2019-01-07 10:43 | ADDRESS CAPACITY AND SAFETY ALONG KY 1136, SOUTH OF GLENDALE FROM US 31W TO JAGGERS ROAD INCLUDING RECONSTRUCTION OR REPLACEMENT OF THE BRIDGE OVER I65. SEE 2008 GLENDALE AREA TRANSPORTATION STUDY. | The Glendale area has a 1,500 acre development site that is designated for one major industry. KY 1136, south of Glendale, is likely to be one of the routes used to provide access to the site. Currently, KY 1136 is very narrow with no shoulders and has so
Y | 4 | Elizabethtown-Radcliff MPO | IP20080747 |  |  |  | ADDRESS CAPACITY AND SAFETY ALONG KY 1136 FROM THE PROPOSED PARTIAL GLENDALE BYPASS TO THE US 31W BYPASS IN ELIZABETHTOWN. SEE 2008 GLENDALE AREA TRANSPORTATION STUDY. | Major Widening | Hardin | 047-KY-1136 -000 | 4.25 | 9.937 | 5.687 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 4500000 |  | 2800000 |  | 15000000 |  | 2019-01-07 10:44 | ADDRESS CAPACITY AND SAFETY ALONG KY 1136 FROM THE PROPOSED PARTIAL GLENDALE BYPASS TO THE US 31W BYPASS IN ELIZABETHTOWN. SEE 2008 GLENDALE AREA TRANSPORTATION STUDY. | KY 1136 is currently a narrow two-lane roadway with little or no shoulders along most of the route. It is expected that travel along this section of KY 1136 will increase when an industry locates on the Glendale development site. This section of KY 1136
Y | 4 | Elizabethtown-Radcliff MPO | IP20080748 |  |  |  | ADDRESS SAFETY AND CAPACITY ALONG KY 222 FROM THE PROPOSED PARTIAL GLENDALE BYPASS TO THE KY 222/I65 INTERCHANGE PROJECT LIMITS (4-20.00). SEE 2008 GLENDALE AREA TRANSPORTATION STUDY | Major Widening | Hardin | 047-KY-0222 -000 | 4.45 | 6.459 | 2.009 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 600000 |  | 300000 |  | 1200000 |  | 2019-01-07 10:48 | ADDRESS SAFETY AND CAPACITY ALONG KY 222 FROM THE PROPOSED PARTIAL GLENDALE BYPASS TO THE KY 222/I65 INTERCHANGE PROJECT LIMITS (4-20.00). SEE 2008 GLENDALE AREA TRANSPORTATION STUDY | Potential development on the Glendale site will bring increase traffic along KY 222. The main entrance to the site is expected to be on this section of KY 222. This section of KY 222 currently has narrow lanes with little or no shoulders.
Y | 4 | Elizabethtown-Radcliff MPO | IP20080749 |  |  |  | CONSTRUCT A NEW CONNECTOR FROM EXISTING JAGGERS ROAD TO KY 222 EAST OF GLENDALE. | New Route | Hardin | 047-KY-0222 -000 | 4.4 | 5.4 | 1 | Local Roadway Improvements | 3 |  | 0 |  | 400000 |  | 300000 |  | 250000 |  | 1900000 |  | 2019-01-07 10:48 | Address connectivity issues due to the Glendale Development Site between Jaggers Road and KY 222 east of Glendale | This project will provide a new Jaggers Road connection to KY 222. The current roadway will be closed off since the land will be part of the Glendale Development Site.
Y | 4 | Elizabethtown-Radcliff MPO | IP20090006 |  |  |  | CONSTRUCT A NEW APPROACH TO BOONE ROAD FROM KY 447 AT W.A. JENKINS ROAD. | New Route | Hardin | 047-CR-1529 -000 | 0 | 0.2 | 0.2 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 100000 |  | 100000 |  | 1000000 |  | 2019-01-07 10:49 | Address safety and connectivity between US 31W and Patriot Parkway and at the intersection of South Wilson Road and Boone Road. | With Patriot Parkway constructed, a new approach to Boone Road from W. A. Jenkins Road would enhance connectivity between US 31W and Patriot Parkway. Also, traffic along South Wilson Road creates a safety hazard at its current intersection with Boone Road
Y | 4 | Elizabethtown-Radcliff MPO | IP20090008 |  |  |  | RECONSTRUCT THE INTERSECTION OF KY 1357 (ST. JOHN ROAD) AND CECILIA ROAD WEST OF ELIZABETHTOWN TO INCREASE SIGHT DISTANCE AND IMPROVE SAFETY. | Safety-Haz-Elm | Hardin | 047-KY-1357 -000 | 13 | 13.1 | 0.1 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 250000 |  | 125000 |  | 500000 |  | 2019-01-07 10:50 | Address safety and geometrics at the intersection of KY 1357 and Cecilia Road. | Sight distance is inadequate at this intersection. The intersection requires reconstruction to improve sight distance and safety.
Y | 4 | Elizabethtown-Radcliff MPO | IP20090009 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 62 EAST OF ELIZABETHTOWN FROM UPPER COLESBURG ROAD TO STOVALL ROAD. | Reconstruction | Hardin | 047-US-0062 -000 | 23.351 | 25.499 | 2.148 | Modernize Roadway-Rural | 26 |  | 200000 |  | 1500000 |  | 1750000 |  | 1100000 |  | 10000000 |  | 2019-01-07 10:50 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 62 EAST OF ELIZABETHTOWN FROM UPPER COLESBURG ROAD TO STOVALL ROAD. | This section of US 62 is currently two-lanes with limited shoulders. This area of US 62 has experience growth in residential development and an increase in traffic. A reconstruction to widen lanes and shoulders would enhance the safety of the roadway.
Y | 4 | Elizabethtown-Radcliff MPO | IP20090010 |  |  |  | INTERSECTION IMPROVEMENTS AT KY 1904 (BACON CREEK ROAD) AND CECILIA SMITH MILL ROAD JUST NORTH OF THE BRIDGE OVER WK PARKWAY TO INCREASE SIGHT DISTANCE AND IMPROVE SAFETY. | Safety-Haz-Elm | Hardin | 047-KY-1904 -000 | 2.5 | 2.55 | 0.05 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 125000 |  | 125000 |  | 1000000 |  | 2017-05-05 08:59 | ADDRESS SAFETY AT THE INTERSECTION OF KY 1904 (BACON CREEK ROAD) AND CECILIA SMITH MILL ROAD JUST NORTH OF THE BRIDGE OVER WK PARKWAY | This intersection poses some unique problems. Cecilia Smith Mill Road connects with KY 1904 (Bacon Creek Road) very close to the WK Parkway bridge and an odd angle. This affects sight distance and makes for a potential safety problem. | Radcliff/Elizabethtown MPO | South | 5.9242 | 1.7062 | 1.9905 | 0 | 2.2275 | 0 | 0 | 0 | 6
Y | 4 | Elizabethtown-Radcliff MPO | IP20090011 |  |  |  | REALIGNMENT OF SOUTH WILSON ROAD IN RADCLIFF TO CREATE A NEW INTERSECTION WITH THE NORTH WILSON ROAD REALIGNMENT AT WEST LINCOLN TRAIL BLVD | New Route | Hardin | 047-CS-2440 -000 | 4.915 | 5.154 | 0.239 | Improve Intersection | 26 |  | 0 |  | 600000 |  | 2400000 |  | 1250000 |  | 2500000 |  | 2017-05-05 10:07 | Address congestion on US 31W and connectivity issues for alternate routes to US 31W. | North Wilson Road is proposed to be realigned from its current ending point to create a new connection on West Lincoln Trail Blvd. Consequently, the southern section of Wilson Road need to be realigned to create a new Wilson Road intersection on West Lin | Radcliff/Elizabethtown MPO | South | 21.6351 | 4.5972 | 13.7915 | 1.9194 | 1.327 | 0 | 0 | 0 | 22
Y | 4 | Lake Cumberland ADD | IP20090012 |  |  |  | WIDEN KY 658 IN CAMPBELLSVILLE TO 3 LANES WITH CURB AND GUTTER FROM US 68 TO KY 3518. | Major Widening | Taylor | 109-KY-0658 -000 | 0 | 0.665 | 0.665 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 350000 |  | 750000 |  | 675000 |  | 2500000 |  | 2015-01-14 13:53 | Address congestion and safety along KY 658 from US 68 to KY 3518 in Campbellsville. | Currently, KY 658 has narrow lanes with little to no shoulders along with high traffic volumes. This project would widen KY 658 from 2 lanes to 3 and add curb and gutter. The Campbellsville Small Urban Area Study, completed in December 2008 recommended t
Y | 4 | Lake Cumberland ADD | IP20090013 | 4-443 |  | A | IMPROVE SAFETY, ACCESS, GEOMETRICS AND DRAINAGE ON KY-70 IN CAMPBELLSVILLE FROM US-68 TO COUNTRY VIEW COURT (CS-1305) | RECONSTRUCTION(O) | Taylor | 109-KY-0070 -000 | 0 | 1.367 | 1.367 | Modernize Roadway-Rural | 26 |  |  |  | 700000 | 2024 | [6 empty] | 2018-07-10 08:17 | Improve safety, access, geometrics and drainage on KY 70 in Campbellsville from US 68 to Country View Court | KY 70 in Campbellsville is a high accident corridor and is heavily congested. There are numerous access points to residences and business along this section with no turn lanes. | LAKE CUMBERLAND ADD | South | 70.981 | 8.9194 | 12.7251 | 12.3697 | 3.7678 | 7.7251 | 3.128 | 7.346 | 56 |  | 15
Y | 4 | Lake Cumberland ADD | IP20090014 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 527 BETWEEN WEDGEWOOD DRIVE AND KY 3212. | Reconstruction | Taylor | 109-KY-0527 -000 | 1.475 | 1.872 | 0.397 | Modernize Roadway-Rural | 26 |  | 0 |  | 120000 |  | 120000 |  | 80000 |  | 1000000 |  | 2015-01-14 13:48 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 527 BETWEEN WEDGEWOOD DRIVE AND KY 3212. | Currently, a high crash area exists along KY 527 from Wedgewood Drive to KY 3212 due to vertical and horizontal curvature deficiencies This project will correct the geometric deficiencies. The Campbellsville Small Urban Area Study, completed in December 2
Y | 4 | Lake Cumberland ADD | IP20090019 |  |  |  | CONSTRUCT A NEW ROUTE FROM KY 55 TO THE GREEN RIVER STATE PARK. | New Route | Taylor | 109-KY-1061 -000 | 1.445 | 2.931 | 1.486 | Construct Road in New Location | 0 |  | 250000 |  | 1500000 |  | 1500000 |  | 1000000 |  | 7000000 |  | 2015-01-14 10:43 | Address lack of safe direct route from KY 55 to the Green River State Park. | KY 1061, a narrow, rural roadway with 9 ft lanes, little or no shouldering, and frequent curves, is the only access route to the Green River State Park. This road is frequented by larger boat-trailer combinations which can not safely navigate the narrow r
Y | 4 | Lake Cumberland ADD | IP20090020 |  |  |  | CONSTRUCT A NEW CONNECTOR ROUTE FROM KY 61 TO KY 417 SOUTHEAST OF GREENSBURG TO IMPROVE CONNECTIVITY AND SAFETY BY PROVIDING A NEW ROUTE TO SCHOOLS AND HOSPITAL. PROJECT WAS SEGMENTED FROM 8-128.11 SEE ALSO 3-203.00 FOR PLANNING STUDY RECOMMENDATION | New Route | Green | 044-US-0068 -000 | 11.954 | 13.385 | 1.431 | Construct Road in New Location | 0 |  | 0 |  | 1300000 |  | 1200000 |  | 850000 |  | 6700000 |  | 2015-01-12 13:53 | Address safety and connectivity to schools and hospital. | This project would begin south of Greensburg along KY 61 and extend east and north to connect to KY 417. Currently, there is a serious highway interconnectivity problem in the City of Greensburg. All traffic passing through town, or moving from point t
Y | 4 | Elizabethtown-Radcliff MPO | IP20100003 |  |  |  | EXTEND KNOX BOULEVARD IN RADCLIFF FROM ITS CURRENT TERMINUS AT US 31W TO KY 361 (BULLION BLVD). | New Route | Hardin | 047-CS-2405 -000 | 0 | 0.557 | 0.557 | Local Roadway Improvements | 3 | Y | 0 |  | 750000 |  | 3500000 |  | 2000000 |  | 7800000 |  | 2019-01-07 10:56 | Improve connectivity between Knox Boulevard and Bullion Boulevard (KY 361). | Extensive growth is occurring at Fort Knox due to Base Realignment. Connectivity needs to be enhanced to help alleviate AM and PM traffic conditions in the Radcliff/Fort Knox area. This project will enhance connectivity by extending Knox Blvd. to KY 361
Y | 4 | Elizabethtown-Radcliff MPO | IP20100006 |  |  |  | EXTEND KY 144 (VINE STREET) FROM ITS TERMINUS AT US 31W IN RADCLIFF, EAST TO THE PROPOSED EAST LINCOLN TRAIL EXTENSION TO CONNECT WITH THE PROPOSED FORT KNOX ACCESS ROAD. | New Route | Hardin | 047-KY-0144 -000 | 4.83 | 4.85 | 0.02 | Construct Road in New Location | 0 | Y | 0 |  | 350000 |  | 550000 |  | 200000 |  | 4000000 |  | 2019-01-07 10:58 | Improve connectivity from KY 144 to East Lincoln Trail Blvd. | The expansion at Fort Knox is causing stress on the transportation system surrounding the military reservation. Enhancing the connectivity of the system is essential to improve traffic flow and safety. This project will enhance connectivity by extending K
Y | 4 | Elizabethtown-Radcliff MPO | IP20100007 |  |  |  | CONSTRUCT A TRUCK PARKING FACILITY FOR OVERNIGHT PARKING OF SEMI TRACTOR TRAILERS (LOCATION TO BE DETERMINED) | Safety-Haz-Elm | Hardin | 047-WK-9001 -000 | 119.649 | 136.796 | 17.147 | Other Improvement Types | 0 | Y | 0 |  | 500000 |  | 100000 |  | 500000 |  | 5000000 |  | 2010-12-10 11:29 | Address lack of facilities for truck drivers along the WK Parkway to safely pull over to rest. | This project was identified by Hardin County Water District #2. Trucks are currently parking on the WK Parkway ramp at KY 84 (White Mills). A sinkhole exists next to this ramp. This sinkhole percolates directly into the water source for the water distri
Y | 4 | Elizabethtown-Radcliff MPO | IP20100008 |  |  |  | RECONSTRUCT THE INTERSECTION OF KY 86 (HARDINSBURG ROAD) AND SOUTH BLACK BRANCH ROAD WEST OF CECILIA. | Safety-Haz-Elm | Hardin | 047-KY-0086 -000 | 14.4 | 14.45 | 0.05 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 75000 |  | 75000 |  | 300000 |  | 2019-01-07 11:53 | Address safety at the intersection of KY 86 and South Black Branch Road. | The angle of this intersection presents problems for motorists entering KY 86 from South Black Branch Road. To improve the safety at this location, the intersection needs to be reconstructed.
Y | 4 | Lake Cumberland ADD | IP20100056 |  |  |  | WIDEN THE SHOULDERS ALONG KY 527 IN CAMPBELLSVILLE FROM US 68 TO KY 3350. | Minor Widening | Taylor | 109-KY-0527 -000 | 0 | 1.124 | 1.124 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 100000 |  | 1200000 |  | 1000000 |  | 2015-01-14 13:45 | Address lack of shoulders, lane width, and geometrics along KY 527 from US 68 to the Bypass (KY 3350). | Currently, KY 527 from KY 3350 to US 68 exhibits narrow to no shoulders, utility poles at the road's edge, and in some places deep ditches, resulting in dangerous conditions to motorists and pedestrians. This project will widen the shoulders along KY 527
Y | 4 | Lake Cumberland ADD | IP20100059 |  |  |  | EXTEND KY 3350 (CAMPBELLSVILLE BYPASS) FROM KY 289 TO US 68 ON THE EAST SIDE OF CAMPBELLSVILLE. | New Route | Taylor | 109-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 250000 |  | 1250000 |  | 1250000 |  | 1000000 |  | 7000000 |  | 2015-01-14 14:19 | Address lack of connection from the east side of Campbellsville to the north side of Campbellsville on KY 210. | This project would extend KY 3350 (called Campbellsville Bypass by locals) from KY 289 to US 68. KY 3350 is used as a northern bypass of Campbellsville. However, it remains an incomplete bypass in that it does not connect up to US 68. Traffic on the east
Y | 4 | Lake Cumberland ADD | IP20110087 |  |  |  | IMPROVE SAFETY BY ADDRESSING FLOODING ISSUES ALONG KY 61 AT THE CANEY FORK BRIDGE JUST NORTH OF THE ADAIR COUNTY LINE. | Safety-Haz-Elm | Green | 044-KY-0061 -000 | 2 | 2.4 | 0.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 700000 |  | 250000 |  | 4000000 |  | 2015-01-12 14:04 | IMPROVE SAFETY BY ADDRESSING FLOODING ISSUES ALONG KY 61 AT THE CANEY FORK BRIDGE JUST NORTH OF THE ADAIR COUNTY LINE. | The Caney Fork Bridge has a history of flooding when rainfall is heavy with reports of the bridge being submerged 3' under water. This presents a major safety hazard with the possibility of the bridge washing out or vehicles being swept downstream. This
Y | 4 | Lake Cumberland ADD | IP20110089 |  |  |  | IMPROVE SIGHT DISTANCE AT THE INTERSECTION OF KY 61/KY 565 NORTH OF GRESHAM. | Safety-Haz-Elm | Green | 044-KY-0061 -000 | 5 | 5.5 | 0.5 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 200000 |  | 100000 |  | 1500000 |  | 2015-01-12 14:22 | Address safety at the intersection of KY 565 and KY 61. | Currently KY 565 intersects KY 61 at an angle and in a curve. On the northeast corner along KY 61 there is an embankment in the curve which limits sight distance for vehicles pulling from KY 565 onto KY 61 creating a safety hazard.
Y | 4 | Lincoln Trail ADD | IP20110146 |  |  |  | ADDRESS SAFETY AND MOBILITY ON US 60 FROM KY 2202 TO EAST OF SIXTH STREET IN IRVINGTON. | Minor Widening | Breckinridge | 014-US-0060 -000 | 29.559 | 30 | 0.441 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 300000 |  | 700000 |  | 400000 |  | 1500000 |  | 2019-01-07 11:55 | Improve safety and congestion along US 60 due to traffic stopping to turn left. | US 60 is a major route through Irvington in Breckinridge County. Development in this area has increased which has increased the traffic. US 60 is a 2 lane route and with the lack of turn lanes congestion has increased causing delays and a safety hazard.
Y | 4 | Lincoln Trail ADD | IP20110149 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 259 FROM BEAR CREEK ROAD (MP 9.217) TO NORTHERN INTERSECTION OF BLOOMINGTON ROAD (MP 11.761) SOUTH OF LEITCHFIELD | Reconstruction | Grayson | 043-KY-0259 -000 | 9.217 | 11.761 | 2.544 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 1800000 |  | 1300000 |  | 10500000 |  | 2017-05-04 14:04 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 259 FROM BEAR CREEK ROAD (MP 9.217) TO NORTHERN INTERSECTION OF BLOOMINGTON ROAD (MP 11.761) SOUTH OF LEITCHFIELD | This section of KY 259 has had numerous accidents which is reflected in the CRF of 1.062. The adequacy rating is low at 55.30 due to the inadequate curves, grades, shoulder width, and lane widths. | LINCOLN TRAIL ADD | South | 38.3685 | 4.0853 | 10.7346 | 8.4775 | 3.2227 | 0 | 2.891 | 8.9573 | 38
Y | 4 | Lake Cumberland ADD | IP20110164 |  |  |  | IMPROVE ACCESS, SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 289 IN CAMPBELLSVILLE FROM NORTH SHORE DRIVE TO KY 3350 (CAMPBELLSVILLE BYPASS) | Reconstruction | Taylor | 109-KY-0289 -000 | 1.168 | 1.9 | 0.732 | Modernize Roadway-Rural | 26 |  | 0 |  | 375000 |  | 675000 |  | 750000 |  | 3000000 |  | 2015-01-14 13:31 | IMPROVE ACCESS, SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 289 IN CAMPBELLSVILLE FROM NORTH SHORE DRIVE TO KY 3350 (CAMPBELLSVILLE BYPASS) | KY 289 is a heavily traveled 2 lane route which provides access to schools, the city park, and the regional hospital. There are numerous accidents along this stretch as indicated by the high CRF.
Y | 4 | Lincoln Trail ADD | IP20120063 |  |  |  | CONSTRUCT A LEFT TURN LANE ON US 68 AT KY 1404 NEAR THE MARION COUNTY HIGH SCHOOL. | Minor Widening | Marion | 078-US-0068 -000 | 12.97 | 13.254 | 0.284 | Improve Intersection | 26 |  | 0 |  | 110000 |  | 165000 |  | 110000 |  | 660000 |  | 2019-01-07 14:04 | Address safety and mobility for school traffic along US 68 at KY 1404. | US 68 is a heavily travelled 2-lane route between Lebanon and Danville. Numerous left turns are made onto KY 1404 by vehicles that are travelling eastbound and want to access Marion County High School including school buses. This causes a backup during
Y | 4 | Barren River ADD | IP20120064 |  |  |  | PRELIMINARY DESIGN TO ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 88 FROM KY 728 IN CUB RUN TO LOGSDON VALLEY ROAD. DESIGN OF OVERALL CORRIDOR. | Reconstruction | Hart | 050-KY-0088 -000 | 5.123 | 15.225 | 10.102 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 | 2021 | 0 |  | 0 |  | 0 |  | 2019-02-22 09:37 | PRELIMINARY DESIGN TO ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 88 FROM KY 728 IN CUB RUN TO LOGSDON VALLEY ROAD. | KY 88 BETWEEN THE GRAYSON COUNTY LINE AND MUNFORDVILLE IS A NARROW TWO LANE FACILITY WITH NUMBEROUS HORIZONTAL AND VERTICAL CURVES. IT PROVIDES DIRECT ACCESS TO NOLIN LAKE FROM MUNFORDVILLE. THERE IS A SIGNIFICANT VOLUME OF FARM MACHINERY AND VEHICLES T
Y | 4 | Elizabethtown-Radcliff MPO | IP20120068 |  |  |  | IMPROVE THE INTERSECTION OF US 31W AND KY 84 AT SONORA TO INCREASE SAFETY | Reconstruction | Hardin | 047-US-0031W -000 | 4.1 | 4.3 | 0.2 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 500000 |  | 500000 |  | 1500000 |  | 2017-05-04 14:47 | Address safety at the intersection of KY 84 and US 31W in Sonora | There have been numerous accidents and fatalities at the intersection of KY 84 and US 31W. | 4 | South | 29.8436 | 3.9905 | 12.4408 | 7.7488 | 1.8246 | 0 | 0 | 3.8389 | 30
Y | 4 | Lincoln Trail ADD | IP20130041 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM THE OHIO COUNTY LINE TO EDWARD CEMETERY ROAD. | Reconstruction | Grayson | 043-KY-0054 -000 | 0 | 3.978 | 3.978 | Modernize Roadway-Rural | 26 |  | 0 |  | 1600000 |  | 2800000 |  | 2000000 |  | 15900000 |  | 2019-01-07 14:08 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM THE OHIO COUNTY LINE TO EDWARD CEMETERY ROAD. | KY 54 has narrow lanes and no shoulders. Some accidents in this area involve vehicles hitting mirrors as they pass and also vehicles dropping off the pavement then over correcting. There are numerous slides along the road and sharp curves.
Y | 4 | Lincoln Trail ADD | IP20130042 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM EDWARD CEMETERY ROAD TO KY 79 AT SHORT CREEK. | Reconstruction | Grayson | 043-KY-0054 -000 | 3.978 | 7.621 | 3.643 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2500000 |  | 1800000 |  | 14600000 |  | 2019-01-07 14:10 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM EDWARD CEMETERY ROAD TO KY 79 AT SHORT CREEK. | KY 54 has narrow lanes and no shoulders. This creates a safety problem which includes vehicles dropping off the pavement and then over correcting.
Y | 4 | Lincoln Trail ADD | IP20130043 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM KY 79 AT SHORT CREEK TO THE EASTERN INTERSECTION OF KY 631. | Reconstruction | Grayson | 043-KY-0054 -000 | 7.621 | 11.632 | 4.011 | Modernize Roadway-Rural | 26 |  | 0 |  | 1600000 |  | 2800000 |  | 2000000 |  | 16000000 |  | 2019-01-07 14:09 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM KY 79 AT SHORT CREEK TO THE EASTERN INTERSECTION OF KY 631. | KY 54 is a narrow 2 lane road with no shoulders. KY 54 is commonly used to travel between Leitchfield and Owensboro and to get to Rough River Dam State Park. There are numerous crashes along this stretch of road and many can be attributed to the roadway
Y | 4 | Lincoln Trail ADD | IP20130044 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISUES ALONG KY 54 FROM THE EASTERN INTERSECTION OF KY 631 TO KY 2193 WEST OF LEITCHFIELD. | Reconstruction | Grayson | 043-KY-0054 -000 | 11.632 | 14.816 | 3.184 | Modernize Roadway-Rural | 26 |  | 0 |  | 1300000 |  | 2200000 |  | 1600000 |  | 12700000 |  | 2019-01-07 14:10 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISUES ALONG KY 54 FROM THE EASTERN INTERSECTION OF KY 631 TO KY 2193 WEST OF LEITCHFIELD. | KY 54 is a narrow 2 lane road with no shoulders. KY 54 is commonly used to travel between Leitchfield and Owensboro and to get to Rough River Dam State Park. Some of the accidents along this road can be attributed to the narrow roadway width.
Y | 4 | Lincoln Trail ADD | IP20130045 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM KY 2193 TO US 62 AT THE SQUARE IN LEITCHFIELD. | Reconstruction | Grayson | 043-KY-0054 -000 | 14.816 | 18.466 | 3.65 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 3700000 |  | 1800000 |  | 14800000 |  | 2019-01-07 14:10 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG KY 54 FROM KY 2193 TO US 62 AT THE SQUARE IN LEITCHFIELD. | KY 54 in this area has had numerous accidents, especially within the Leitchfield Corporate limits approaching the square. Many of these accidents are cross traffic not seeing on coming traffic and pulling in front of vehicles on traveling on KY 54.
Y | 4 | Lincoln Trail ADD | IP20130080 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 261 FROM THE NORTHERN INTERSECTION WITH KY 477 AT WEBSTER NORTH TO MP 25.200 | Spot Improvement | Breckinridge | 014-KY-0261 -000 | 24.653 | 25.2 | 0.547 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 380000 |  | 300000 |  | 1750000 |  | 2019-01-08 08:20 | Improve safety by removing back to back vertical curves | In this area, KY 261 has back to back vertical curves which are considered "thrill hills". Vehicles can become airborn when hitting these hills at a high rate of speed causing a safety hazard.
Y | 4 | Elizabethtown-Radcliff MPO | IP20130136 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG OLD EKRON ROAD BETWEEN KY 448 AND KY 1051. | Minor Widening | Meade | 082-CR-1002 -000 | 0 | 1.15 | 1.15 | Local Roadway Improvements | 3 |  | 0 |  | 575000 |  | 1150000 |  | 1150000 |  | 4600000 |  | 2019-01-08 08:20 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG OLD EKRON ROAD BETWEEN KY 448 AND KY 1051. | Old Ekron Road is a local road that connects Ekron to Brandenburg. The section to the north of KY 1051 is very urban with numerous government and commercial businesses along the route. The roadway is curvy with limited shoulders. Numerous accidents have o
Y | 4 | Elizabethtown-Radcliff MPO | IP20130137 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG OLD EKRON ROAD BETWEEN KY 1051 AND KY 1736. | Minor Widening | Meade | 082-CR-1002 -000 | 1.15 | 3.8 | 2.65 | Local Roadway Improvements | 3 |  | 0 |  | 800000 |  | 1860000 |  | 1060000 |  | 6360000 |  | 2019-01-08 08:21 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG OLD EKRON ROAD BETWEEN KY 1051 AND KY 1736. | Old Ekron Road is a local road that connects Ekron to Brandenburg. The section to the south of KY 1051 is very rural with narrow lanes and limited shoulders with some sharp horizontal curves. Numerous accidents have occurred along this corridor mostly rel
Y | 4 | Lincoln Trail ADD | IP20130138 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES, AND MAINTENANCE ISSUES ALONG KY 52 FROM THE NORTHERN INTERSECTION OF KY 49 TO BURKES SPRING ROAD. | Reconstruction | Marion | 078-KY-0052 -000 | 4.685 | 6.829 | 2.144 | Modernize Roadway-Rural | 26 |  | 0 |  | 850000 |  | 2000000 |  | 1100000 |  | 8500000 |  | 2019-01-08 08:21 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES, AND MAINTENANCE ISSUES ALONG KY 52 FROM THE NORTHERN INTERSECTION OF KY 49 TO BURKES SPRING ROAD. | KY 52 is a narrow, curvy road with little to no shoulders. This route is used by the numerous visitors to Makers Mark Distillery on Burkes Spring Road. Makers Mark also uses this route for their trucks creating a hazard. Makers Mark intends to increase
Y | 4 | Lincoln Trail ADD | IP20130139 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES, AND MAINTENANCE ISSUES ALONG KY 52 FROM BURKES SPRING ROAD TO THE SOUTHERN INTERSECTION OF KY 49. | Reconstruction | Marion | 078-KY-0052 -000 | 6.829 | 9.097 | 2.268 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 2100000 |  | 1200000 |  | 9000000 |  | 2019-01-08 08:22 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES, AND MAINTENANCE ISSUES ALONG KY 52 FROM BURKES SPRING ROAD TO THE SOUTHERN INTERSECTION OF KY 49. | KY 52 is a narrow, curvy road with little to no shoulders. This route is used by the numerous visitors to Makers Mark Distillery on Burkes Spring Road. Makers Mark also uses this route for their trucks creating a hazard. Makers Mark intends to increase
Y | 4 | Lake Cumberland ADD | IP20130150 |  |  |  | ADDRESS GEOMETRIC DEFICIENCIES ON KY 323 FROM OSCAR MILBY LANE TO DIXIE CREEK ROAD WEST OF SUMMERSVILLE AT GABE | Reconstruction | Green | 044-KY-0323 -000 | 6.044 | 7.393 | 1.349 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 300000 |  | 250000 |  | 2000000 |  | 2015-01-12 14:35 | ADDRESS GEOMETRIC DEFICIENCIES ON KY 323 FROM OSCAR MILBY LANE TO DIXIE CREEK ROAD WEST OF SUMMERSVILLE AT GABE | KY 323 is narrow with little to no shoulders and has multiple horizontal and vertical curves.
Y | 4 | Elizabethtown-Radcliff MPO | IP20140011 |  |  |  | Widen the shoulders along KY 313 from the KY 361/KY 1500 intersection in Hardin County to US 60 in Meade County. The Hardin County Milepoints are from 14.534 to 15.238 and the Meade County Milepoints are from 0.000 to 7.125. | Safety-Haz-Elm | Meade | 082-KY-0313 -000 | 0 | 7.125 | 7.125 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2017-05-05 08:32 | Address shoulder width and lack of refuge for impaired vehicles outside of the driving lanes. | Currently KY 313 has 4' dga shoulders and there is no where for broken down vehicles to get off the road safely. | Radcliff/Elizabethtown MPO | South | 22.0415 | 7.7346 | 3.4834 | 2.7903 | 0 | 0 | 3.91 | 4.1232 | 22
Y | 4 | Lincoln Trail ADD | IP20140024 |  |  |  | DRAINAGE IMPROVEMENTS ALONG KY 337 IN BRADFORDSVILLE BETWEEN THE EASTERN INTERSECTION WITH KY 49 AND 8TH STREET. | Drainage Improvement | Marion | 078-KY-0337 -000 | 4.265 | 4.42 | 0.155 | Maintenance Improvement | 10 |  | 0 |  | 50000 |  | 50000 |  | 75000 |  | 350000 |  | 2019-01-08 08:39 | Address Drainage issues along KY 337 in Bradfordsville. | During a heavy rain event, the water can back up onto some of the properties along KY 337 and on some occasions will reach the first trailer in the trailer park.
Y | 4 | Barren River ADD | IP20140047 |  |  |  | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY 728 FROM KY 88 TO KY 2786 | Reconstruction | Hart | 050-KY-0728 -000 | 4.044 | 8.1 | 4.056 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2800000 |  | 2000000 |  | 23500000 |  | 2019-01-08 08:23 | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY 728 FROM KY 88 TO KY 2786 | KY 728 is a narrow route with little to no shoulders and numerous horizontal and vertical curves. This route is utilized by recreational vehicles pulling boats and horse trails from I-65 to Mammoth Cave and Nolin Lake. The lack of shoulders and geometric
Y | 4 | Barren River ADD | IP20140048 |  |  |  | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY 728 FROM KY 2786 TO KY 1140 | Reconstruction | Hart | 050-KY-0728 -000 | 8.1 | 12.19 | 4.09 | Modernize Roadway-Rural | 26 |  | 0 |  | 1800000 |  | 2800000 |  | 2100000 |  | 21900000 |  | 2019-01-08 08:24 | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY 728 FROM KY 2786 TO KY 1140 | KY 728 is a narrow route with little to no shoulders and numerous horizontal and vertical curves. This route is utilized by recreational vehicles pulling boats and horse trails from I-65 to Mammoth Cave and Nolin Lake. The lack of shoulders and geometric
Y | 4 | Barren River ADD | IP20140049 |  |  |  | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY 728 FROM KY 1140 TO US 31W | Reconstruction | Hart | 050-KY-0728 -000 | 12.19 | 17.373 | 5.183 | Modernize Roadway-Rural | 26 |  | 0 |  | 2100000 |  | 3600000 |  | 2600000 |  | 29000000 |  | 2019-01-08 08:24 | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY 728 FROM KY 1140 TO US 31W | KY 728 is a narrow route with little to no shoulders and numerous horizontal and vertical curves. This route is utilized by recreational vehicles pulling boats and horse trails from I-65 to Mammoth Cave and Nolin Lake. The lack of shoulders and geometric
Y | 4 | Lincoln Trail ADD | IP20150040 |  |  |  | SOUTHWEST CONNECTOR FROM US 31E SOUTH OF BARDSTOWN TO US 62 WEST OF BARDSTOWN TO CONNECT WITH THE PROPOSED WESTERN BARDSTOWN CONNECTOR. | New Route | Nelson | 090-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 1500000 |  | 1000000 |  | 600000 |  | 7610000 |  | 2019-03-12 09:16 | Address congestion and safety in downtown Bardstown and connectivity on the west side of Bardstown. | Downtown Bardstown is heavily congested with many accidents along with truck traffic. There is no north/south route on the west side of Bardstown.
Y | 4 | Lincoln Trail ADD | IP20150041 | 4-396.20 / 4-8958 |  | A | ADDRESS SAFETY, MOBILITY, AND GEOMETRIC ISSUES ALONG US 150 IN WASHINGTON COUNTY FROM 400 FEET WEST OF OLD FREDERICKTOWN-BARDSTOWN ROAD (KY 1872) TO 0.7 MILES EAST OF GRUNDY HOME ROAD (CR 1337). (16CCN)(18CCN)(SAME AS 4-396.20) | SAFETY(P) | Washington | 115-US-0150 -000 | 0.426 | 2.5 | 2.074 | Modernize Roadway-Rural | 26 |  |  |  | 500000 | 2019 | 500000 | 2020 | 750000 | 2021 | 8000000 | 2022 | 2018-07-10 08:18 | Improve safety, mobility, and geometrics along US 150 from west of Old Frederickstown-Bardstown Road (KY 1872) through Grundy Home curve to Mayfield Lane | US 150 is the primary roadway from the Bluegrass Parkway to the City of Springfield located in Washington County. Along this section of US 150 there are three substandard vertical curves indicating possible sight distance and speed differential issues. Th | LINCOLN TRAIL ADD | South | 78.404 | 7.9716 | 10.6635 | 6.878 | 1.7773 | 8.3886 | 4.2417 | 8.4834 | 48 | 15 | 15
Y | 4 | Lincoln Trail ADD | IP20150047 |  |  |  | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 61 FROM NEAR SOUTH FORK RD (KY 1906)(MP 0.876) AT MT. SHERMON TO THE SOUTHERN INTERSECTION OF SOUTH L AND N TPKE (KY 470)(MP 5.152). | Minor Widening | Larue | 062-KY-0061 -000 | 0.876 | 5.152 | 4.276 | Modernize Roadway-Rural | 26 |  | 0 |  | 1300000 |  | 3200000 |  | 2100000 |  | 12000000 |  | 2017-05-05 10:11 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 61 FROM NEAR SOUTH FORK RD (KY 1906)(MP 0.876) AT MT. SHERMON TO THE SOUTHERN INTERSECTION OF SOUTH L AND N TPKE (KY 470)(MP 5.152). | This segment of KY 61 is located just south of the City of Hodgenville between KY 1906 and KY 470. This section of KY 61 is a narrow two-lane roadway with little or no shoulders.
Y | 4 | Lincoln Trail ADD | IP20150048 |  |  |  | MINOR WIDENING AND SPOT IMPROVEMENTS ALONG KY 61 FROM NEAR SOUTH L AND N TPKE(KY 470)(MP 5.152) TO THE INTERSECTION OF LINCOLN FARM RD (US 31E)(MP 8.031). | Minor Widening | Larue | 062-KY-0061 -000 | 5.152 | 8.031 | 2.879 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2200000 |  | 1400000 |  | 8000000 |  | 2017-05-05 10:16 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 61 FROM NEAR SOUTH L AND N TPKE(KY 470)(MP 5.152) TO THE INTERSECTION OF LINCOLN FARM RD (US 31E)(MP 8.031). | This segment of KY 61 is located just south of the City of Hodgenville between KY 470 and US 31E. This section of KY 61 is a narrow two-lane roadway with little or no shoulders.
Y | 4 | Lake Cumberland ADD | IP20150055 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM THE METCALFE COUNTY LINE TO THE INTERSECTION OF KY 218 SOUTH OF GREENSBURG. (SEE METCALFE CO. LISTING FOR CONTINUATION TO EDMONTON). | Minor Widening | Green | 044-US-0068 -000 | 0 | 6.099 | 6.099 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2500000 |  | 1900000 |  | 12000000 |  | 2018-10-18 14:27 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM THE METCALFE COUNTY LINE TO THE INTERSECTION OF KY 218 SOUTH OF GREENSBURG. | This project begins at the Metcalfe County line (MP 0.000) and extends to KY 218 (MP 6.099). US 68 is Green County's major East-West corridor. Segments of this roadway have several curves and elevation changes with no passing lanes. Safety is also an issu
Y | 4 | Lincoln Trail ADD | IP20150156 | 4-8802 |  | A | SPOT IMPROVEMENTS ON KY-49 (MP 20.900 TO MP 21.830) AS PER THE KY-49 PLANNING STUDY. (14CCN)(18CCN) | SPOT IMPROVEMENTS(O) | Marion | 078-KY-0049 -000 | 20.823 | 21.837 | 1.014 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 160000 | 2020 | 670000 | 2021 | 3450000 | 2023 | 2018-07-10 08:18 | Address safety and geometrics along KY 49. | KY 49 has little to no shoulders with many horizontal and vertical curves. | LINCOLN TRAIL ADD | South | 26.1682 | 3.1943 | 8.5308 | 6.1493 | 3.3649 | 0 | 0 | 4.9289 | 26
Y | 4 | Lake Cumberland ADD | IP20150252 | 4-8853 |  | A | SPOT IMPROVEMENTS & IMPROVE EXISTING ALIGNMENT ON KY 88 FROM 0.20 MILES WEST OF AKIN NARROWS OF PITMAN RD (MP 8.996) TO KY 61 (MP 11.232). (14CCN)(16CCR)(18CCN) | SPOT IMPROVEMENTS(O) | Green | 044-KY-0088 -000 | 8.996 | 11.232 | 2.236 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2021 | 2900000 | 2022 | 980000 | 2023 | 2580000 | 2024 | 2018-07-10 08:18 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ON KY 88 FROM 0.2 MILES WEST OF AKIN NARROWS OF PITMAN ROAD TO KY 61. (MP 8.996-MP 11.232) | The problem with KY 88 is that it is a narrow 2 lane road with 10’ lanes and 2’ earthen shoulders with moderate to severe curves and rolling hills. The roadway has a functional classification ranking in the 49 percentile from MP 0.00 to MP 11.23. However
Y | 4 | Lake Cumberland ADD | IP20150337 | 4-398 |  | A | CONSTRUCT NEW CONNECTOR FROM VAUGHN CURVE ON US-68 BYPASS EAST OF GREENSBURG CROSSING KY-61 AND KY-417 AND CONNECTING WITH KY-3535 NORTH OF GREENSBURG.(SEE ITEM #8-8711)(12CCN)(14CCR)(16CCR)(18CCN) | NEW ROUTE(O) | Green | 044-US-0068 -000 | 10.775 | 14.287 | 3.512 | Construct Road in New Location | 0 |  |  |  | 1000000 | 2021 | 3200000 | 2023 | 2000000 | 2024 | 16000000 |  | 2018-07-10 08:18 | Address congestion and truck traffic through downtown Greensburg. | US 68 through Greensburg is congested and the only route for trucks along with the only bridge crossing over the Green River in the area. | 4 | South | 28.7168 | 4.2085 | 0 | 12.5652 | 3.8863 | 8.0569 | 0 | 0 | 29
Y | 4 | Elizabethtown-Radcliff MPO | IP20150360 | 4-8705 | 401783 | A | RECONSTRUCT KY 79 FROM KY 144 TO KY 1051. (12CCN)(14CCR)(18CCN) | RECONSTRUCTION(O) | Meade | 082-KY-0079 -000 | 4.411 | 8.237 | 3.826 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1000000 |  | 2000000 | 2021 | 10000000 | 2023 | 2018-07-10 08:18 | Address safety, geometrics, and mobility along KY 79 from KY 144 in Midway to KY 313 (previously KY 1051) in Brandenburg. | KY 79 is currently a narrow, 2 lane route with little to no shoulders. Many large trucks use this route to travel from US 60 in Breckinridge County to Brandenburg. | Radcliff/Elizabethtown MPO | South | 56.827 | 3.8294 | 9.8815 | 9.7038 | 2.654 | 5.0711 | 3.1043 | 7.5829 | 42 |  | 15
Y | 4 | Lincoln Trail ADD | IP20150384 | 4-8809 |  | A | NEW ROUTE BETWEEN US 62 AND KY 245 WEST OF BARDSTOWN. (16CCR)(18CCN) | NEW ROUTE(O) | Nelson | 090-US-0031E -000 | 12.2 | 16.7 | 4.5 | Construct Road in New Location | 0 |  | 0 |  | 1500000 | 2020 | 3500000 | 2025 | 1500000 | 2025 | 12000000 | 2025 | 2018-07-10 08:18 | Address congestion and safety in downtown Bardstown and connectivity on the west side of Bardstown | Downtown Bardstown is heavily congested with many accidents along with truck traffic. There is no north/south route on the west side of Bardstown. | LINCOLN TRAIL ADD | South | 40.4479 | 7.7346 | 3.4123 | 14.6801 | 2.7962 | 7.4882 | 4.3365 | 0 | 40
Y | 4 | Lincoln Trail ADD | IP20150408 | 4-396 |  | A | IMPROVE US-150 FROM SPRINGFIELD TO BARDSTOWN. | RECONSTRUCTION(O) | Nelson | 090-US-0150 -000 | 2.102 | 7.653 | 5.551 | Transportation Studies | 0 |  |  |  | 0 | 2020 | [6 empty] | 2018-09-05 09:36 | Address safety, geometrics, and mobility along US 150 between Bardstown and Springfield. | US 150 is heavily traveled with both passenger cars and trucks. It is a 2-lane route with multiple accidents and fatalities. | LINCOLN TRAIL ADD | South | 27.1434 | 8.8436 | 0 | 12.1386 | 1.7299 | 0 | 4.4313 | 0 | 27
Y | 4 | Lake Cumberland ADD | IP20150417 | 4-8712 |  | A | IMPROVE SAFETY AND MOBILITY ON KY-61 FROM PITMAN CREEK BRIDGE TO DOC WARD RD (CR 1314). (12CCN)(14CCR)(16CCR) | MAJOR WIDENING(O) | Green | 044-KY-0061 -000 | 11.113 | 14.093 | 2.98 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 2000000 | 2022 | 2750000 | 2023 | 6000000 | 2024 | 2018-07-10 08:18 | Address the turning movements of trucks at the KY 323 intersection and improve the safety, mobility and connectivity between Summersville and Greensburg | KY 61 connects the community of Summersville to the city of Greensburg to the south. THis roadway has narrow lanes and minimal shoulder widths. Trucks can't make the turn at KY 323 without swinging into opposite lane. A truck climbing lane may be warrante | 4 | South | 70.1848 | 2.7204 | 9.1706 | 6.0427 | 4.0758 | 7.1564 | 3.0095 | 8.0095 | 40 | 15 | 15
Y | 4 | Elizabethtown-Radcliff MPO | IP20150432 | 4-8702 |  | A | RECONSTRUCT KY 79 FROM KY 428 TO KY 144.(12CCN)(14CCR)(18CCN) | RECONSTRUCTION(O) | Meade | 082-KY-0079 -000 | 1.263 | 4.411 | 3.148 | Modernize Roadway-Rural | 26 |  | 1040000 |  | 0 | 2021 | 2000000 | 2023 | 2600000 | 2024 | 4800000 | 2024 | 2018-07-10 08:18 | Address safety, geometrics, and mobility along KY 79 from KY 428 to KY 144 in Midway. | KY 79 is currently a narrow, 2 lane route with little to no shoulders. Many large trucks use this route to travel from US 60 in Breckinridge County to Brandenburg. | 4 | South | 36.2121 | 3.4218 | 8.4597 | 6.487 | 3.5782 | 4.5498 | 2.8436 | 6.872 | 36
Y | 4 | Elizabethtown-Radcliff MPO | IP20150448 | 4-153.01 |  | A | KY 251 IMPROVEMENTS FROM KY 3005 TO KY 434. | PHASE I DESIGN(O) | Hardin | 047-KY-0251 -000 | 2.866 | 6.288 | 3.422 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 4200000 | 2019 | 8700000 | 2021 | 2019-01-11 08:23 | Address safety and geometric deficiencies along KY 251 between KY 3005 and KY 434 | KY 251 has narrow lanes with little to no shoulders along with multiple horizontal and vertical curves. There have been numerous accidents along this route. | Radcliff/Elizabethtown MPO | South | 65.6043 | 5.5924 | 10.3791 | 9.846 | 1.8246 | 0 | 0 | 7.9621 | 36 | 15 | 15
Y | 4 | Lincoln Trail ADD | IP20150473 | 4-8904 |  | A | MINOR WIDENING OF KY 992 BETWEEN ROCK QUARRY AND US 60. (16CCN) (18CCN) | MINOR WIDENING(O) | Breckinridge | 014-KY-0992 -000 | 11.5 | 13.822 | 2.322 | Modernize Roadway-Rural | 26 | [9 empty] | 580000 | 2021 |  | Improve safety along KY 992 for trucks going to and coming from the quarry. | THIS SECTION OF ROADWAY CARRIES SEVERAL TRUCKS PER DAY FROM WHITE STONE ROCK QUARRY AND MAGO CONTRACTING ASPHALT PLANT. THE GOAL IS TO PROVIDE WIDER LANES AND SHOULDERS TO IMPROVE SAFETY ALONG THIS CORRIDOR. | LINCOLN TRAIL ADD | South | 19.173 | 0.46445 | 13.7204 | 3.6611 | 1.327 | 0 | 0 | 0 | 19
Y | 4 | Lincoln Trail ADD | IP20160068 | 4-8909 |  | I | CONNECTOR IMPROVEMENTS HODGENVILLE TO I-65. (16CCN) (18CCN)(PROJECT DONE UNDER ITEM NO. 4-8911) | SPOT IMPROVEMENTS(O) | Larue | 062-KY-0222 -000 | 0 | 5.84 | 5.84 | Modernize Roadway-Rural | 26 |  |  |  | 2500000 | 2019 | 2200000 | 2019 | 2000000 | 2020 | 32000000 | 2020 | 2018-11-15 10:42 | Improve access from Hodgenville to I-65 at Glendale | Currently the only route between Glendale and Hodgenville is KY 222 which is very narrow and has many deficient horizontal and vertical curves. | LINCOLN TRAIL ADD | South | 16.4571 | 0.11374 | 3.5545 | 2.9147 | 4.8341 | 0 | 0 | 5.04 | 16
Y | 4 | Lincoln Trail ADD | IP20160070 | 4-8917 |  | A | HEARTLAND PARKWAY: MARION/TAYLOR LINE TO LEBANON BYPASS.(16CCN)(18CCN) | MAJOR WIDENING(O) | Marion | 078-US-0068 -000 | 0 | 9.364 | 9.364 | Modernize & Widen Roadway-Rural | 26 | Y |  |  | 0 | 2021 | 500000 | 2023 | 900000 | 2024 | 10000000 | 2024 | 2018-07-10 08:18 | Address safety and mobility along US 68 from the Taylor County line to the Lebanon Bypass. | US 68 is part of the Heartland Parkway. It is a 2-lane route with no passing lanes. | LINCOLN TRAIL ADD | South | 66.0083 | 6.4645 | 12.7962 | 12.3164 | 0.47393 | 5.9242 | 3.8863 | 9.1469 | 51 |  | 15
Y | 4 | Lincoln Trail ADD | IP20160072 | 4-8954 |  | A | EXTEND THE WILLIAM THOMASON BYWAY (KY 3155) FROM THE SOUTHERN INTERSECTION AT KY 259 WESTERLY TO KY 54. (16CCN)(18CCN) | NEW ROUTE(O) | Grayson | 043-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 0 | 2019 | 2500000 | 2021 | 1500000 | 2021 | 18500000 | 2022 | 2019-01-16 13:41 | Address congestion, safety, and mobility on KY 259 in Leitchfield | KY 259 is congested, has many accidents, and multiple trucks per day driving through downtown Leitchfield. | LINCOLN TRAIL ADD | South | 62.2725 | 9.2512 | 3.1991 | 9.4194 | 2.1564 | 8.2464 | 0 | 0 | 32 | 15 | 15
Y | 4 | Elizabethtown-Radcliff MPO | IP20170082 |  |  |  | RECONSTRUCT INTERSECTION OF US 31W AT PEAR ORCHARD ROAD NW AND VETERANS WAY | Reconstruction | Hardin | 047-CS-1297 -000 | 0.932 | 1.032 | 0.1 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 500000 |  | 500000 |  | 2000000 |  | 2017-05-04 10:43 | Address safety at the intersection of Pear Orchard NW and US 31W. | Pear Orchard Road is currently utilized as an alternative route to the east of US 31W. It also serves a large residential area in Elizabethtown. This project will improve the intersection with US 31W and also Veterans Way on the west side of US 31W. | Radcliff/Elizabethtown MPO | South | 12.5118 | 3.0332 | 4.1943 | 3.0569 | 2.2275 | 0 | 0 | 0 | 12
Y | 4 | Lincoln Trail ADD | IP20180024 |  |  |  | Address safety, congestion, and mobility at the eastern intersection of US 68 and KY 2154 and along US 68 and KY 2154. improve the intersection of US 68/KY 2154 and along US 68 from entrance to TG Kentucky to the previous widening and along KY 2154/Corpo | Minor Widening | Marion | 078-US-0068 -000 | 12.2 | 12.8 | 0.6 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 500000 | 2021 | 1000000 | 2022 | 1500000 | 2022 | 6000000 | 2023 | 2018-12-05 15:43 | Address safety, congestion, and mobility at the eastern intersection of US 68 and KY 2154 and along US 68 and KY 2154 | This area is congested daily due to the industrial park, schools, and shopping center. There is another school being constructed along KY 2154 which will add to the congestion. There have been numerous accidents at the intersection throughout the years.
Y | 4 | Lincoln Trail ADD | IP20180030 | 4-80050 |  | A | CONSTRUCT A ROUNDABOUT AT THE INTERSECTION OF US-31E AND US-62. (NELSON COUNTY FISCAL COURT WILL DO DESIGN AND BUILD ROUNDABOUT)(18CCN) | CONGESTION MITIGTN(O) | Nelson | 090-US-0031E -000 | 13.9 | 14 | 0.1 | Improve Intersection | 26 | [9 empty] | 1500000 | 2020 |  | Address congestion, safety, mobility at the intersection of US 31E and US 62 in Bardstown | The US 31E/US62 intersection is gets congested and it's difficult to turn left in either direction. There have also been numerous accidents along with increases in traffic. | General Assembly | South | 45.3019 | 8.6038 | 15 | 12.8774 | 1.3208 | 0 | 4.1509 | 3.3491 | 45
Y | 4 | Lake Cumberland ADD | IP20180045 |  |  |  | Extend KY 3535 from its current terminus to the Heartland Parkway (KY 55) near KY 1701 in Taylor County | New Route | Green | 044-PF-9999 - | [17 empty] | Improve connectivity from the Green County Industrial Park to the Heartland Parkway south of Campbellsville. | Currently there is no defined trucking route from Greensburg to the Cumberland Parkway. A connection to the Heartland Parkway, which is on the National Truck Network would provide a safe route for truck traffic and improve economic development in Green C
Y | 4 | Lake Cumberland ADD | IP20180053 |  |  |  | Planning Study to improve access from Greensburg to I-65 | Reconstruction | Green | 044-KY-0088 -000 | 0 | 11.232 | 11.232 | Transportation Studies | 0 |  | 1000000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2018-09-24 08:34 | Study the east/west routes to determine the corridor used to access I-65 from Greensburg and identify improvements needed to increase safety and mobility. | The main east/west corridor used to access I-65 from Green County is KY 88 which has an abundance of horizontal and vertical curves, narrow lanes, little to no shoulders, and has had many crashes and fatalities. Once vehicles cross into Hart County, there
Y | 4 | Lake Cumberland ADD | IP20180071 |  |  |  | Reconstruct US 68 to a 2+1 from KY 61 in Green County to Davis Road in Taylor County. | Minor Widening | Green | 044-US-0068 -000 | 14.287 | 18.411 | 4.124 | Auxiliary Lanes or Operation Improvements | 11 |  | 0 |  | 500000 |  | 50000 |  | 350000 |  | 8000000 |  | 2018-09-25 10:40 | Address safety and passing opportunities along US 68 from KY 61 at Greensburg to Davis Road in Taylor County. | US 68 between Greensburg and Campbellsville is heavily traveled with a lot of accidents. Due to oncoming traffic there are limited places to safely pass and accidents have occurred due to people taking chances with passing.
Y | 4 | Elizabethtown-Radcliff MPO | IP20190034 |  |  |  | Transportation Study for connectivity along the east side of Elizabethtown. | Transportation Study | Hardin | 047-KY-3005 -000 | 8.829 | 10.582 | 1.753 | [14 empty] | Transportation Study for connectivity along the east side of Elizabethtown. | The City of Elizabethtown is growing rapidly on the east side with multiple new businesses which has created congestion and accidents along KY 3005 (Ring Road) and US 62 near the interchange with I-65 (Exit 94).
Y | 4 | Lincoln Trail ADD | IP20190055 |  |  |  | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND DRAINAGE ALONG US 62 FROM SCHOOLHOUSE ROAD TO THE PROPOSED LEITCHFIELD WESTERN BYPASS. | Minor Widening | Grayson | 043-US-0062 -000 | 17.909 | 19.85 | 1.941 | [14 empty] | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND DRAINAGE ALONG US 62 FROM SCHOOLHOUSE ROAD TO THE PROPOSED LEITCHFIELD WESTERN BYPASS. | US 62 is the main route to get to the multiple schools on Schoolhouse Road. The lanes are narrow with little to no shoulders along with some drainage issues.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20000014 |  |  |  | New interchange and connector road from KY 1447 to US 42 with interchange on I-71 near Jefferson/Oldham County border. The connector road would accomodate all modes, including bicyclists and pedestrians. | New Interchange | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 410000 |  | 1780000 |  | 920000 |  | 360000 |  | 20520000 |  | 2011-02-07 15:32 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | I-71 at the Oldham County/Jefferson County line is located in an area that is seeing development and additional development in the area is planned. Currently congestion is approaching high levels. Because of additional planned development in this area an
Y | 5 | Bluegrass ADD | IP20040016 | 5-551 |  | A | IMPROVE SAFETY, TRUCK MOBILITY, AND REDUCE CONGESTION ALONG I-64 FROM DIRECTLY EAST OF US-127 TO US-60 SOUTH OF FRANKFORT. | MAJOR WIDENING(O) | Franklin | 037-I -0064 -000 | 53.11 | 57.86 | 4.75 | Add Lane to Full Control Facility | 25 | Y |  |  | 4300000 | 2022 | [6 empty] | 2018-07-10 08:17 | The purpose of this project is to address the safety and travel time reliability along I-64 between US 127 and US 60. | The I-64 route serves as major connector linking Louisville, Frankfort and Lexington. The Critical Rate Factor for this section of I-64 analyzed from 2012-2016 is 1.499. The 2017 ADT is 46,591 with a truck percentage of 11%. I-64 through Kentucky is the m | BLUEGRASS ADD | Statewide | 63.8461 | 16.4229 | 8.1057 | 10.8205 | 1.8062 | 7.0925 | 6.5639 | 13.0344
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20050006 |  |  |  | Improve safety and reduce congestion on KY 245 at KY 3219 (Chapeze Lane). | Spot Improvement | Bullitt | 015-KY-0245 -000 | 5.2 | 5.5 | 0.3 | Improve Intersection | 26 |  | 0 |  | 81100 |  | 46400 |  | 46400 |  | 231600 |  | 2011-02-14 10:13 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | KY 245 is a rural minor arterial connecting I-65 and Bardstown through southern Bullitt County. This section has primarily low density residential development with an ADT of 11,000 on two 12’lanes. While this segment has a high composite rating of 83.5,
Y | 5 | Bluegrass ADD | IP20060241 |  |  |  | Improve safety and reduce congestion on US 460 from the end of the 4 lane section just east of Equine Way to the intersection with Redding Road. | Reconstruction | Franklin | 037-US-0460 -000 | 1.29 | 3.331 | 2.041 | Modernize Roadway-Urban | 16 |  | 250000 |  | 2630000 |  | 2700000 |  | 2000000 |  | 22000000 |  | 2018-11-30 10:56 | To improve safety and reduce congestion through addressing poor road curvature and geometry on US 460 from the end of the 4 lane section just east of Equine Way to the intersection with Redding Road. | The project corridor begins at the end of the existing 4 lane portion of US 460 and extends east 1.697 miles to Redding Road in Franklin County. A segment beginning at MP 2.500 is rated 4 for Horizontal Alignment indicating uncomfortable and unsafe curves
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080001 |  |  |  | Transportation System Management & Transportation Demand Management activities on US 31E (Bardstown Road) between Douglass Boulevard & Hikes Lane. Transportation System Management (TSM) projects are intended to improve the operation capacity of existing r | Congestion Management | Jefferson | 056-US-0031E -000 | 10.971 | 13.58 | 2.609 | Other Improvement Types | 0 | Y | 200000 |  | 1740000 |  | 3920000 |  | 4080000 |  | 15660000 |  | 2018-12-27 16:15 | The purpose of this project is to: 1) Improve operation capacity of the existing roadway and transit, 2) Reduce the number of vehicles on the roadway through offering other options, such as bicycle, pedestrian, and transit amenities/services and/or throug | US 31E (Bardstown Road) from Douglass Boulevard to Hikes Lane (MP 10.971 to MP 13.580) is located in central Jefferson County within the Urban Area boundary (former City of Louisville). The surrounding land uses are residential and commercial, and are de
Y | 5 | Bluegrass ADD | IP20080165 |  |  |  | Improve safety and level of service on I-64 from US 60 in Frankfort to the Woodford County line. | Major Widening | Franklin | 037-I -0064 -000 | 57.86 | 59.431 | 1.571 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 1400000 |  | 1100000 |  | 1000000 |  | 13700000 |  | 2018-11-29 12:33 | To address and improve safety and level of service on I-64 from US 60 in Frankfort to the Woodford County line. | Route serves as major connector linking Louisville, Frankfort and Lexington. High Critical Rate Factor of indicates serious safety issues along the corridor. I-64 through Kentucky is the major east/west interstate and a major freight corridor contributin
Y | 5 | Bluegrass ADD | IP20080166 |  |  |  | ADDRESS LEVEL OF SERVICE AND SAFETY ISSUES AT EXIT 58 (US 60) ON I-64 IN FRANKFORT | Reconstruction | Franklin | 037-I -0064 -000 | 57.688 | 58.187 | 0.499 | Major Interchange Reconstruction | 32 | Y | 0 |  | 850000 |  | 715000 |  | 690000 |  | 7000000 |  | 2018-11-29 12:02 | To address and remedy poor level of service and safety issues at exit 58 (US 60) on I-64 in Frankfort. | South of interchange crossroad the southbound LOS is F in the afternoon. South of interchange crossroad the northbound LOS is F in the morning and afternoon. North of interchange crossroad southbound LOS is F in the afternoon. North of interchange crossr
Y | 5 | Bluegrass ADD | IP20080167 |  |  |  | Improve safety and traffic flow on US 60 (Versailles Road) from US 460 to I-64 in Frankfort. | Major Widening | Franklin | 037-US-0060 -000 | 10.667 | 13.308 | 2.641 | Modernize Roadway-Urban | 16 | Y | 180000 |  | 1800000 |  | 3720000 |  | 660000 |  | 11580000 |  | 2018-11-30 10:42 | To improve safety and traffic flow on US 60 (Versailles Road) from US 460 to I-64 in Frankfort. | High ADT on US 60 from US 460 to I-64 in Frankfort, CRF indicates serious safety issues on segment. Existing and proposed commercial development on a large tract on west side of US 60 north of I-64, and large number of access points have combined to decre
Y | 5 | Bluegrass ADD | IP20080168 |  |  |  | Improve safety and address geometric deficiencies at the intersection of US 60 and KY 151. | Spot Improvement | Franklin | 037-US-0060 -000 | 0.4 | 0.6 | 0.2 | Improve Intersection | 26 |  | 0 |  | 115000 |  | 57000 |  | 23000 |  | 1150000 |  | 2015-07-07 14:58 | To improve safety and address geometric deficiencies at the intersection of US 60 and KY 151. For more information, see Six Year Plan item 5-97.50. | Route is a commuter corridor between Frankfort and Shelbyville that also serves as an alternative to I-64. When I-64 is shut down, US 60 is the only connection between Louisville and Frankfort. Vertical Alignment of 3 indicates infrequent grades and vert
Y | 5 | Bluegrass ADD | IP20080169 |  |  |  | Address level of service, congestion and safety on US 127 in Frankfort from I-64 to US 60. | Major Widening | Franklin | 037-US-0127 -000 | 4.42 | 6.1 | 1.68 | Modernize Roadway-Rural | 26 | Y | 470000 | 2025 | 2000000 |  | 5500000 |  | 3400000 |  | 13100000 |  | 2018-11-27 15:39 | To address level of service, congestion and safety concerns on US 127 in Frankfort from I-64 to US 60. | Significant CRF indicates numerous safety issues on US 127 in Frankfort from I-64 to US 60. Congestion and capacity concerns as future ADT is expected to be higher than current projections as new development west of the corridor such as new Bridgeport Ele
Y | 5 | Bluegrass ADD | IP20080170 |  |  |  | Address congestion, safety and level of service on US 127/ US 421 (Wilkinson Blvd.) in Frankfort from the West Frankfort / Capital Plaza Connector to US 60. | Major Widening | Franklin | 037-US-0127 -000 | 8.943 | 10.884 | 1.941 | Modernize Roadway-Rural | 26 | Y | 410000 |  | 2400000 |  | 4300000 |  | 4100000 |  | 17600000 |  | 2018-11-28 08:37 | To address congestion, safety and level of service issues on US 127/ US 421 (Wilkinson Blvd.) in Frankfort from the West Frankfort/Capital Plaza Connector to US 60. | ADT is high on this segment of Wilkinson Blvd. that serves numerous state office buildings, Buffalo Trace Distillery, Capital Plaza Tower, and Capital Plaza Complex/Convention Center. The 2000 Frankfort Transportation Study projects a LOS "F" by 2020.
Y | 5 | Bluegrass ADD | IP20080171 |  |  |  | Improve safety and LOS at the intersection of Wilkinson Blvd. and Mero Street in Frankfort. | Spot Improvement | Franklin | 037-US-0127 -000 | 8.93 | 9.03 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 490000 |  | 490000 |  | 3040000 |  | 860000 |  | 2011-02-14 11:02 | To address safety and level of service concerns at the intersection of Wilkinson Blvd. and Mero Street in Frankfort through spot improvements. | No continuous right turn lane at the intersection of Wilkinson Blvd. and Mero Street in Frankfort decreases intersection level of service, especially during peak hours, as route has a high ADT. One car can block the intersection creating additional conges
Y | 5 | Bluegrass ADD | IP20080172 |  |  |  | Improve safety and address geometric deficiencies at the intersection of US 127 and KY 1262/Steele Branch Road north of Frankfort. | Spot Improvement | Franklin | 037-US-0127 -000 | 15.6 | 15.9 | 0.3 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 80000 |  | 1250000 |  | 2013-05-16 07:59 | To add safety improvements and address geometric deficiencies at the intersection of US 127 and KY 1262/Steele Branch Road north of Frankfort. | No turn lanes are located on US 127 and Steel Branch Road in northern Franklin County. US 127 is a high-speed facility on the National Truck Network and NHS with trucks accounting for a significant segment of the ADT. Horizontal Alignment of 3 indicates i
Y | 5 | Bluegrass ADD | IP20080173 |  |  |  | Address safety at the intersection of US 127 and KY 2919 (Indian Gap Road) in Franklin County. | Spot Improvement | Franklin | 037-US-0127 -000 | 18.7 | 18.95 | 0.25 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 130000 |  | 130000 |  | 130000 |  | 490000 |  | 2018-11-28 15:14 | To address safety at the intersection of US 127 and KY 2919 (Indian Gap Road) in Franklin County, as there are no turn lanes through this section, resulting in congestion and safety hazards. | No turn lanes are located on US 127 and Indian Gap Road in northern Franklin County. US 127 is a high speed facility on the National Truck Network with trucks accounting for significant amount of the current ADT. Safety and congestion, especially during p
Y | 5 | Bluegrass ADD | IP20080174 |  |  |  | Address safety at the intersection of US 127 and Swallowfield Road in Franklin County. | Spot Improvement | Franklin | 037-US-0127 -000 | 20 | 20.2 | 0.2 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 150000 |  | 160000 |  | 60000 |  | 530000 |  | 2018-11-28 15:27 | To address safety at the intersection of US 127 and Swallowfield Road in Franklin County, as there are currently no turn lanes in this area. | No turn lanes are located on US 127 and Swallowfield Road. Steep grade increases safety problems on southbound US 127 at the intersection. US 127 is a high speed facility on the National Truck Network. Safety and congestion, especially during peak hours
Y | 5 | Bluegrass ADD | IP20080175 |  |  |  | Improve safety and level of service on US 421 (Bald Knob Hill) from the end of existing improvements approx. 0.9 miles north of US 127 to KY 12 in Franklin County. | Major Widening | Franklin | 037-US-0421 -000 | 5.39 | 11.132 | 5.742 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 7000000 |  | 7000000 |  | 37000000 |  | 2018-11-29 14:28 | To improve both safety and level of service on US 421 (Bald Knob Hill) from the end of existing improvements approx. 0.9 miles north of US 127 to KY 12 in Franklin County. | High CRF indicates safety problems along this segment of US 421 from approximately 0.9 miles north of US 127 to KY 12 in Franklin County. There is significant truck traffic on this two lane road. Vertical Alignment of 4 indicates significant sight distanc | BLUEGRASS ADD | North | 36.9223 | 1.6185 | 6.2308 | 9.2885 | 4.9538 | 5.7231 | 0 | 9.1077 | 37
Y | 5 | Bluegrass ADD | IP20080176 |  |  |  | IMPROVE SAFETY AND LEVEL OF SERVICE ON US-421 FROM KY 12 TO KY 561 IN FRANKLIN COUNTY | Major Widening | Franklin | 037-US-0421 -000 | 11.132 | 16.947 | 5.815 | Modernize Roadway-Rural | 26 |  | 350000 |  | 4600000 |  | 9700000 |  | 4700000 |  | 45200000 |  | 2011-02-02 15:17 | To improve both safety and level of service through widening the road on US-421 from KY 12 to KY 561 in Franklin County. | US 421 in the principal route from New Castle to Frankfort. The segment from KY 12 north of Frankfort to KY 561 has numerous safety issues as indicated narrow lanes and no shoulders present, along with a troublesome CRF. Substandard geometrics are indicat
Y | 5 | Bluegrass ADD | IP20080177 |  |  |  | Improve safety and address geometric deficiencies along US 460 from Redding Road in Franklin County to 0.2 miles east of KY 3378 (Pea Ridge Road) in Scott County. | Major Widening | Franklin | 037-US-0460 -000 | 3.331 | 6.114 | 2.783 | Modernize Roadway-Rural | 26 |  | 0 |  | 2200000 |  | 4510000 |  | 2200000 |  | 17110000 |  | 2015-06-25 14:59 | To improve safety and address geometric deficiencies along US 460 from Redding Road in Franklin County to 0.2 miles east of KY 3378 (Pea Ridge Road) in Scott County. Currently, substandard curves and poor roadway geometry are common along this route. | A segment of the route is in the very low Percentile, indicating that similar roads are in better condition US. 460 is the principal connector between Georgetown and Frankfort. Horizontal Alignment is 4 and Vertical Alignment is 3 and 4 indicating numerou
Y | 5 | Bluegrass ADD | IP20080178 |  |  |  | Improve safety and address geometric deficiencies along KY 1005 (Devils Hollow Road) from Pea Ridge Road to US 127 west of Frankfort. | Reconstruction | Franklin | 037-KY-1005 -000 | 6.508 | 7.45 | 0.942 | Modernize Roadway-Urban | 16 |  | 0 |  | 1050000 |  | 1780000 |  | 1260000 |  | 6400000 |  | 2018-11-29 12:17 | To improve safety and address geometric deficiencies along KY 1005 (Devils Hollow Road) from Pea Ridge Road to US 127 west of Frankfort. | Safety is the primary reason for this project due to the proximity of Westridge Elementary School. With narrow 3' shoulders, lanes and geometric concerns present, school buses have difficulty when they meet. CRF indicates safety issues. Also, a 400+ home
Y | 5 | Bluegrass ADD | IP20080179 |  |  |  | Improve safety and level of service on Evergreen Road (KY 1665) from US 127 to US 60 in Franklin County. | Reconstruction | Franklin | 037-KY-1665 -000 | 0.127 | 3.892 | 3.765 | Modernize Roadway-Rural | 26 |  | 180000 |  | 820000 |  | 2200000 |  | 1200000 |  | 8200000 |  | 2018-11-29 12:27 | To improve both safety and level of service on Evergreen Road (KY 1665) from US 127 to US 60 in Franklin County. | Evergreen Road (KY 1665) is a Rural Minor Collector that is becoming increasingly crowded as ADT has increased on this road used as an access route to I-64 and US 60 in Frankfort. High Critical Rate factor confirms safety problems present.
Y | 5 | Bluegrass ADD | IP20080180 |  |  |  | Improve safety and level of service on KY 2261 (Holmes Street) from KY 420 (High Street) to US 127 in Frankfort. | Reconstruction | Franklin | 037-KY-2261 -000 | 0.162 | 1.832 | 1.67 | Modernize Roadway-Rural | 26 |  | 140000 |  | 820000 |  | 2000000 |  | 1100000 |  | 6300000 |  | 2018-11-28 10:26 | To improve both safety and level of service on KY 2261 (Holmes Street) from KY 420 (High Street) to US 127 in Frankfort. | Holmes Street (KY 2261) from High Street (KY 420) to US 127 is a main route for state employees entering Frankfort from US 127 to Mero Street and the Capital Plaza Tower area. Currently peak hour congestion is occuring and with the increased ADT, more co
Y | 5 | KIPDA ADD | IP20080181 |  |  |  | Improve access to I-71 at KY 55 from Campbellsburg to the south in Henry County and Trimble County/Carroll County to the north. | New Interchange | Henry | 052-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 |  | 250000 |  | 2100000 |  | 2000000 |  | 1300000 |  | 35000000 |  | 2019-02-21 14:05 | Improve access to I-71 at KY 55 from Campbellsburg to the south in Henry County to Trimble County/Carroll County to the north. | This project is needed to improve system connectivity In Henry County, Trimble County, and Carroll County on I-71 from Campbellsburg to the south in Henry County to Trimble County/Carroll County to the north. Currently, the nearest access to I-71 is at | KIPDA ADD | North | 24.1846 | 8.4308 | 0 | 0 | 1 | 9.9692 | 4.7846 | 0 | 24
Y | 5 | KIPDA ADD | IP20080182 |  |  |  | Improve safety and geometrics on US 421 from Raisor Lane in Henry County to KY 561 (Gest Road) in Franklin County. | Minor Widening | Henry | 052-US-0421 -000 | 0 | 5.481 | 5.481 | Modernize Roadway-Rural | 26 |  | 350000 |  | 5300000 |  | 11200000 |  | 4700000 |  | 52100000 |  | 2011-02-03 10:02 | Improve safety and geometrics on US 421 from Raisor Lane in Henry County to KY 561 (Gest Road) in Franklin County. | This project is needed because US 421 between Raisor Lane in Henry County and KY 561 (Gest Road) in Franklin County has roadway deficiencies including narrow lanes, no shoulders, and substandard geometrics which creates potential safety concerns. The sub
Y | 5 | KIPDA ADD | IP20080183 |  |  |  | Improve safety and geometrics on US 421 from the proposed New Castle bypass (just north of KY 202) to KY 55. | Reconstruction | Henry | 052-US-0421 -000 | 15.27 | 21.713 | 6.443 | Modernize Roadway-Rural | 26 |  | 260000 |  | 2600000 |  | 6500000 |  | 2600000 |  | 25200000 |  | 2018-12-04 11:46 | Improve safety and geometrics on US 421 from the proposed New Castle bypass (just north of KY 202) to KY 55. | This project is needed because of substandard geometrics including substandard horizontal and vertical curves which creates potential safety concerns on US 421 from the proposed New Castle bypass (just north of KY 202) to KY 55.
Y | 5 | KIPDA ADD | IP20080184 |  |  |  | Improve safety and address roadway deficiencies on KY 55 from US 421 to I-71 north of Campbellsburg. | Reconstruction | Henry | 052-KY-0055 -000 | 4.49 | 7.259 | 2.769 | Modernize Roadway-Rural | 26 |  | 130000 |  | 1100000 |  | 2700000 |  | 1300000 |  | 15100000 |  | 2018-12-03 12:08 | Improve safety and address roadway deficiencies on KY 55 from US 421 to I-71 north of Campbellsburg. | This project is needed because of roadway deficiencies including substandard curves, sight distance, and minimal shoulders on KY 55 from US 421 to I-71 north of Campbellsburg. This project would also improve access to the Henry County Commerce Park.
Y | 5 | KIPDA ADD | IP20080185 |  |  |  | Improve safety and address roadway deficiencies on KY 55 from just north of Cobb Road (past the curve) to US 421 north of Eminence. | Minor Widening | Henry | 052-KY-0055 -000 | 2.21 | 4.49 | 2.28 | Modernize Roadway-Rural | 26 |  | 260000 |  | 1300000 |  | 2000000 |  | 1700000 |  | 10100000 |  | 2018-11-30 14:49 | Improve safety and address roadway deficiencies on KY 55 from just north of Cobb Road (past the curve) to US 421 north of Eminence. | This project is needed because KY 55 north of Eminence has roadway deficiencies including narrow lane widths and minimal to no shoulders present creating safety hazards from just north of Cobb Road to US 421.
Y | 5 | KIPDA ADD | IP20080186 |  |  |  | Improve safety and address geometric deficiencies on KY 153 from KY 146 to US 42 (from Sligo to south of the I-71/KY 153 interchange). | Reconstruction | Henry | 052-KY-0153 -000 | 5.521 | 8.509 | 2.988 | Transportation Studies | 0 |  | 135000 |  | 1470000 |  | 3150000 |  | 1365000 |  | 15855000 |  | 2015-06-25 13:23 | Improve safety and address geometric deficiencies on KY 153 from KY 146 to US 42 (from Sligo to south of the I-71/KY 153 interchange). | This project is needed to address substandard curves, narrow shoulders, and improve the safety on KY 153 from KY 146 to US 42 (from Sligo to south of the I-71/KY 153 interchange. This project also provides direct access to two Pilot Travel Centers off th
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080187 | 5-553 |  | A | IMPROVEMENTS WITHIN THE I-64 CORRIDOR FROM THE KENNEDY INTERCHANGE TO I-264 (WATTERSON EXPRESSWAY) ADDRESSING SAFETY AND CONGESTION ISSUES. THE IMPROVEMENTS MAY INCLUDE BUT ARE NOT LIMITED TO: CONSIDERATION OF ALTERNATIVE TRANSPORTATION MODES, DEPLOYMENT | CONGESTION MITIGTN(O) | Jefferson | 056-I -0064 -000 | 6.581 | 12.275 | 5.694 | Add Lane to Full Control Facility | 25 | Y | 250000 | 2019 | 2550000 | 2022 | [6 empty] | 2018-07-10 08:17 | Improve safety and reduce congestion within the I-64 corridor from the Kennedy interchange to I-264 (Watterson Expressway). | This project is needed because the capacity of I-64 between the Kennedy interchange and I-264 (Watterson Expressway) is inadequate to meet current and future traffic volumes, resulting in congestion and reduced mobility. This section of I-64 also has spo | Louisville MPO | Statewide | 81.2549 | 18.7665 | 18.4141 | 14.587 | 8.8987 | 0 | 6.2996 | 14.289
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080188 |  |  |  | I-65/1st Street/Liberty Street Transportation System Management/Transportation Demand Management operational improvements southbound on ramp and intersection. | Congestion Management | Jefferson | 056-I -0065 -000 | 135.4 | 135.6 | 0.2 | Innovative Interchange | 40 | Y | 0 |  | 53000 |  | 26000 |  | 12000 |  | 591000 |  | 2017-05-01 15:13 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | I-65 from MP 135.907 to MP 136.007 is located in northern Jefferson County in downtown Louisville. This area is densely developed with commercial, office and hospital/medical uses. Any improvements would be best attempted with existing right-of-way to le | Louisville MPO | North | 50.2719 | 9.2738 | 14.7692 | 11.4923 | 3.8923 | 0 | 4.7692 | 6.075 | 50
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080190 |  |  |  | Improve safety and reduce congestion of the I-265 northbound to I-71 southbound movement at the I-71/I-265 (Gene Snyder Freeway) interchange. | Reconstruction | Jefferson | 056-I -0071 -000 | 7.5 | 9.8 | 2.3 | Innovative Interchange | 40 | Y | 0 |  | 4000000 |  | 100000 |  | 3200000 |  | 40720000 |  | 2017-03-14 13:35 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | I-71 interchange at I-265 (MP 9.063 to MP 9.163) is located in north eastern Jefferson County. The land uses in this area are low to medium density residential. The adequacy rating data point to crash issues and congestion. At this time, this segment is e
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080191 | 5-554 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON I-265 FROM I-65 TO US-31E. | MAJOR WIDENING(O) | Jefferson | 056-I -0265 -000 | 10.25 | 17.3 | 7.05 | Add Lane to Full Control Facility | 25 | Y | 1000000 | 2021 | 3000000 | 2023 | [6 empty] | 2018-07-10 08:17 | Improve safety and reduce congestion on I-265 (Gene Snyder Freeway) from I-65 to US 31E (Bardstown Road). | This project is needed because of deficient ramps, inadequate capacity, and higher than average crash rates on I-265 (Gene Snyder Freeway) from I-65 to US 31E (Bardstown Road). As cited in the I-265 Study of January 2015 the projected 2020 LOS along this | 5 | Statewide | 72.1642 | 18.6256 | 13.7445 | 14.1244 | 4.4053 | 0 | 6.4317 | 14.8327
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080192 |  |  |  | Provide connectivity and improved mobility on I-265 at Rehl Road. The Rehl Road portion would include consideration for enhanced safety for bicyclists and pedestrians. | New Interchange | Jefferson | 056-I -0265 -000 | 24 | 24.6 | 0.6 | Construct Road in New Location | 0 | Y | 470000 |  | 2780000 |  | 1390000 |  | 580000 |  | 31360000 |  | 2011-02-08 09:58 | The planning-level purpose for the project is to accommodate the safe and efficient movement of traffic to and from the future development and the interstate network. | Numerous development activities have occurred in the study area including the amassing of land into large (over 200-acre) tracts; the rezoning of these tracts from residential to more intensive industrial uses; and the installation of sanitary sewers. Alt
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080193 |  |  |  | Transportation System Management improvements on US 31W from KY 841 to KY 44 in southern Jefferson County; to include the consideration of access management, bicycle, and continuous pedestrian facilities. | Congestion Management | Jefferson | 056-US-0031W -000 | 1.948 | 7.5 | 5.552 | Modernize Roadway-Urban | 16 | Y | 50000 |  | 1000000 |  | 300000 |  | 300000 |  | 6500000 |  | 2019-01-04 09:26 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | While Dixie Highway is one of the busiest and most important transportation corridors in the region, it is also frequently congested (LOS E, F found at multiple intersections), has very high total and fatal crash rates, and passed through several low and
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080194 |  |  |  | Improve safety and reduce congestion on US 42 (Brownsboro Road) from I-264 (Henry Watterson Expressway) to Seminary Drive. Project will evaluate one additional travel lane in each direction and consider accommodations for bicyclists and pedestrians. | Major Widening | Jefferson | 056-US-0042 -000 | 5.779 | 6.795 | 1.016 | Other Improvement Types | 0 | Y | 0 |  | 970000 |  | 1230000 |  | 1020000 |  | 7250000 |  | 2019-01-04 10:13 | The purpose of the project is to limit the congestion and delay on US 42 and increase safety of I-264, while minimizing the right-of-way impacts to the community. | The existing I-264/US 42 Interchange area does not have adequate capacity or storage to accommodate the current left-turn and through-traffic volumes during the peak hours. Commuters often sit through green phases at signalized intersections due to queues | Louisville MPO | North | 25.5338 | 8.6031 | 0 | 12.0231 | 1.5231 | 0 | 3.3846 | 0 | 26
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080195 |  |  |  | Align US 60 (Frankfort Avenue) intersection of Stilz Avenue and Hillcrest Avenue. | Safety-Haz-Elm | Jefferson | 056-US-0060 -000 | 1.91 | 2.01 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 240000 |  | 82000 |  | 35000 |  | 1740000 |  | 2011-02-08 10:18 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | US 60 from MP 1.910 to MP 2.010 is located in north central Jefferson County. This area is densely developed with commercial and residential uses, and runs parallel to an active rail line. These adequacy data suggest rough pavement conditions and crash is
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080196 |  |  |  | Improve safety and reduce congestion on US 60 from I-264 to KY 1747. Project design will evaluate one added travel lane in each direction and consider bicycle and pedestrian facilities. | Major Widening | Jefferson | 056-US-0060 -000 | 5.529 | 7.857 | 2.328 | Other Improvement Types | 0 | Y | 240000 |  | 1970000 |  | 1050000 |  | 470000 |  | 23160000 |  | 2011-02-08 10:50 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | US 60 from MP 5.529 to MP 7.857 is located in eastern central Jefferson County. This area is developed with primarily commercial uses abutting the corridor and residential uses either abutting the corridor or located directly behind the commercial. Thes
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080197 |  |  |  | Improve safety and reduce congestion on US 60 from KY 1747 to Old Shelbyville Road (CS 3596). Project will evaluate the addition of one travel lane in each direction and will consider accommodations for bicyclists, pedestrians, and transit users. | Major Widening | Jefferson | 056-US-0060 -000 | 7.857 | 11.1 | 3.243 | Other Improvement Types | 0 | Y | 0 |  | 3500000 |  | 6245000 |  | 10408000 |  | 34730000 |  | 2019-02-15 12:04 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | US 60 from MP 7.857 to MP 11.100 is located in eastern central Jefferson County. This area is developed with primarily commercial uses directly abutting the corridor and residential uses either abutting the corridor or located directly behind the commerc | Louisville MPO | North | 34.6815 | 8.8431 | 5.2615 | 14.3308 | 1.5231 | 0 | 4.7231 | 0 | 35
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080198 |  |  |  | Improve safety and reduce congestion on US 60 from Rockcrest Way (CS 3157) to Notting Hill Blvd (CS 1224J) at the Jefferson/Shelby County line. Project design will evaluate 3-lane widening with a continuous two-way center turn lane and other lower impact | Minor Widening | Jefferson | 056-US-0060 -000 | 15.114 | 17.375 | 2.261 | Install Two-way Left Turn Lane | 28 |  | 120000 |  | 350000 |  | 240000 |  | 120000 |  | 4060000 |  | 2011-02-08 11:19 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | The Critical Rate for this section of US 60 is 0.53 from years 2012 to 2016. This area is developing with primarily residential uses with commerical nodes. Additional development in this area is expected. US 60 is a regionally significant route linking L
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080200 |  |  |  | Improve safety and reduce congestion on KY 146 from Nelson Miller Parkway (CR1019C) to Reamers Road (CR1004D). To include consideration for bicycle and pedestrian facilities. Project will consider improvements to the I-265/KY 146 Interchange and the addit | Major Widening | Jefferson | 056-KY-0146 -000 | 6.964 | 8.251 | 1.287 | Major Widening-Urban Streets | 25 |  | 0 |  | 1500000 |  | 500000 |  | 500000 |  | 12000000 |  | 2019-02-19 13:25 | The purpose of this project is to improve safety and reduce congestion on KY 146 from Nelson Miller Parkway (CR1019C) to Reamers Road (CR1004D). To include consideration for bicycle and pedestrian facilities. | The Critical Rate Factor (CRF) for this segment of KY 146 is 3.79 for the years 2012 to 2016. The KY State Data Center Report indicates a current employment annual growth rate of 2.9% and a population annual growth rate of 0.70%. This route connects I-265 | Louisville MPO | North | 44.6654 | 5.1692 | 9.4154 | 11.0654 | 0 | 9.4154 | 3.6308 | 5.9692 | 45
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080201 |  |  |  | Improve safety and reduce congestion on KY 155 from Watterson Trail to I-265. Project design will evaluate 3-lane widening with two-way center turn lane and consider bicycle and pedestrian facilities. | Major Widening | Jefferson | 056-KY-0155 -000 | 6.3 | 9.35 | 3.05 | Major Widening-Urban Streets | 25 | Y | 0 |  | 1800000 |  | 2000000 |  | 2500000 |  | 18000000 |  | 2019-02-08 11:50 | Improve safety and reduce congestion on KY 155 from Watterson Trail to I-265, including consideration of bicycle and pedestrian accommodations. Project will consider widening from 2 to 5 lanes (5th lane will be a center turn lane) with sidewalks from | The Critical Rate Factor (CRF) for the longest segment of KY 155 (MP 6.9 to MP 9.1) from 2012 to 2016 is 1.72. The KY State Data Center Report indicates a current average Population Annual Growth Rate of 1.47% for this area. The development in the area is | Louisville MPO | North | 46.8538 | 6.6769 | 6.7385 | 13.2231 | 0 | 9.1077 | 3.6923 | 7.4154 | 47
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080202 | 5-8908 |  | A | WIDEN TAYLORSVILLE ROAD TO 3 LANES FROM I-265 TO KY-148. (18CCN) | MINOR WIDENING(O) | Jefferson | 056-KY-0155 -000 | 4.4 | 5.75 | 1.35 | Install Two-way Left Turn Lane | 28 |  | 920000 | 2019 | 1500000 | 2020 | 1000000 | 2022 | 500000 | 2022 | 15930000 | 2023 | 2018-07-10 08:18 | Improve safety, mobility for all modes, and provide better access along KY 155 from KY 148 to I-265 near Pope Lick Park. | The Critical Rate Factor for this section of KY 155 is 1.192 for the years 2012 to 2016. The KIPDA MPO TAZ data shows a 1.6% projected future population and employment growth in the project area. Commuters use this route to get to and from Shelby and Spen | 5 | North | 83.9308 | 8.3692 | 11.9538 | 10.5923 | 2.0923 | 9.4462 | 3.6615 | 7.8154 | 54 | 15 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080203 |  |  |  | Improve safety and reduce congestion on KY 155 from Hikes Lane/Browns Lane to KY 1747 (Hurstbourne Parkway). To include bicycle and pedestrian facilities . | Major Widening | Jefferson | 056-KY-0155 -000 | 11.395 | 13.314 | 1.919 | Major Widening-Urban Streets | 25 | Y | 0 |  | 1200000 |  | 750000 |  | 1500000 |  | 12000000 |  | 2019-01-18 12:19 | The purpose of this project is to improve safety and reduce congestion on KY 155 from Hikes Lane/Browns Lane to KY 1747 (Hurstbourne Parkway) including the bicycle and pedestrian modes. | The Critical Rate Factor (CRF) for this segment of KY 155 ranges from 1.36 to 2.15 for the years 2012 to 2016. The KY State Data Center Report indicates a current average Population Annual Growth Rate of 0.45%. Land uses vary from single and multi-family | Louisville MPO | North | 24.7715 | 7.5138 | 0 | 12.7038 | 0 | 0 | 4.5538 | 0 | 25
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080205 |  |  |  | Improve safety and reduce congestion on KY 864 (Fegenbush Lane) from KY 864 (Beulah Church Road) to KY 1747 (Fern Valley Road/South Hurstbourne Pkwy). Project design will evaluate 3-lane widening with two-way center turn lane and consider accommodations f | Minor Widening | Jefferson | 056-KY-0864 -000 | 4.25 | 6.596 | 2.346 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1280000 |  | 700000 |  | 240000 |  | 13660000 |  | 2011-02-08 14:40 | The purpose of this project is to improve safety and reduce congestion on KY 864 (Fegenbush Lane) from KY 864 (Beulah Church Road) to KY 1747 (Fern Valley Road/South Hurstbourne Pkwy). | The Critical Rate Factor (CRF) for the longest section of this KY 864 segment (MP 4.391 to MP 6.596) is 1.68 using 2012 to 2016 data. This route connects I-265 and KY 1747 (Hurstbourne Parkway)
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080207 |  |  |  | Reconstruct KY 864 (Cedar Creek Road) from Mt. Washington Road to Cooper Chapel Road & reconstruct KY 864 (Cooper Chapel Road) from Cedar Creek Road to Beulah Church Road. Project design will evaluate 3-lane widening with two-way center turn lane and cons | Minor Widening | Jefferson | 056-KY-0864 -000 | 0 | 1.818 | 1.818 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 350000 |  | 240000 |  | 120000 |  | 4060000 |  | 2011-02-08 15:28 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | The Beulah Church Road (KY 864) corridor is a rapidly developing section of Louisville with increasing traffic demand. KY 864 is classified as an urban collector and has many access points. It carries traffic from growing residential suburbs to the Gene S
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080209 |  |  |  | Improve safety and reduce congestion along KY 907 (Valley Station Road/3rd Street Road) from US 31W (Dixie Highway) to KY 1865 (New Cut Road). Project will evaluate 3-lane widening and consider bicycle and pedestrian facilities. | Minor Widening | Jefferson | 056-KY-0907 -000 | 0 | 6.31 | 6.31 | Modernize Roadway-Urban | 16 |  | 0 |  | 3800000 |  | 31550000 |  | 31550000 |  | 37860000 |  | 2019-01-09 10:04 | The purpose of this project is to: 1) Improve safety for vehicular, bicycle, and pedestrian traffic, 2) Improve bicycle and pedestrian network and TARC access points, 3) Improve Drainage, 4) Reduce congestion, 5) Improve signage and 6) Focus on low cost s | Major issues are deep drainage ditches, substandard shoulders, limited sidewalks, and a lack of adequate lane capacity. There are no bicycle facilities. Average Daily Traffic (ADT) ranges from 5,760 to 22,100 Vehicles per Day (VPD), while the percentage o
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080210 |  |  |  | Improve safety and reduce congestion at the KY 1065 and KY 61 intersection. Project will consider adding a right turn lane on westbound KY 1065 (Outer Loop) at KY 61 (Preston Highway). | Spot Improvement | Jefferson | 056-KY-1065 -000 | 6.055 | 6.155 | 0.1 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 1275000 |  | 100000 |  | 500000 |  | 2017-05-15 15:04 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | There is currently insufficient right turn capacity on westbound Outer Loop approaching KY 61. The intersection has had a total of 98 crashes between 5/1/2011 and 4/30/2016, including 44 injuries and one fatality. The highest crash types are angle (44) an | Louisville MPO | North | 39.8154 | 4.2154 | 14.3077 | 12.3692 | 0 | 0 | 4.2462 | 4.6769 | 40
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080211 |  |  |  | Improve safety and reduce congestion on KY 1065 (Outer Loop) from I-65 to KY 2052 (Shepherdsville Road). Project will evaluate the addition of one travel lane in each direction and consider accommodations for bicyclists and pedestrians. | Major Widening | Jefferson | 056-KY-1065 -000 | 4.93 | 7.655 | 2.725 | Modernize Roadway-Urban | 16 |  | 0 |  | 2180000 |  | 3270000 |  | 2730000 |  | 27250000 |  | 2019-01-11 15:21 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | KY 1065 from MP 4.930 to MP 7.655 (from I-65 to KY 2052) is located in southcentral Jefferson County. Surrounding land use is primarily medium density commercial with some residential uses. These adequacy rating data suggest high crash potential, rough pa | Louisville MPO | North | 29.7531 | 5.4954 | 5.3077 | 14.4577 | 0 | 0 | 4.4923 | 0 | 30
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080212 |  |  |  | Improve safety, access, and mobility for all modes along KY 1065 (Outer Loop) from KY 907 (3rd Street Road) to KY 1865 (New Cut Road). Project will consider 3-lane widening and accommodations for bicyclists and pedestrians. | Minor Widening | Jefferson | 056-KY-1065 -000 | 0 | 1.069 | 1.069 | Modernize Roadway-Urban | 16 |  | 250000 |  | 2300000 |  | 400000 |  | 4900000 |  | 18620000 |  | 2019-01-14 07:56 | The purpose of this project is to improve safety, targeting major intersections (New Cut Road), and improve mobility for travelers. | Safety is the primary concern along the corridor. The New Cut Road and National Turnpike intersections are identified as numbers one and nine, respectively, on the region's 2011 Top 40 High Crash Intersections list supplied by the KIPDA MPO. Records show | 5 | North | 75.1015 | 6.3631 | 12.7846 | 13.3385 | 1.5231 | 0 | 3.2462 | 7.8462 | 45 | 15 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080213 |  |  |  | Improve safety and reduce congestion on KY 1065 (Beulah Church Road) from KY 864 (Fegenbush Lane) to US 31E (Bardstown Road). Project will evaluate 3-lane widening or other lower impact solutions and consider accommodations for bicyclists and pedestrians. | Minor Widening | Jefferson | 056-KY-1065 -000 | 10.009 | 11.858 | 1.849 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1300000 |  | 930000 |  | 1480000 |  | 12950000 |  | 2017-05-04 16:19 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 1065 from MP 10.009 to MP 11.858 (from KY 864 to US 31E) is located in south eastern Jefferson County. Surrounding land use is primarily medium density residential with some commercial. Data suggest less-than-optimum pavement condition and that congest | Louisville MPO | North | 50.3062 | 6.3754 | 11.8154 | 11.6538 | 3.4462 | 7.9692 | 0 | 9.0462 | 50
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080214 |  |  |  | Improve safety and reduce congestion on KY 1447 (Westport Road) from Murphy Lane to KY 146. Project design will evaluate 3-lane widening with two-way center turn lane and consider bicycle and pedestrian facilities. | Minor Widening | Jefferson | 056-KY-1447 -000 | 7.5 | 9.242 | 1.742 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 470000 |  | 240000 |  | 120000 |  | 4640000 |  | 2011-02-10 10:25 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | KY 1447 from MP 7.641 to MP 8.141 is located in eastern Jefferson County. This area is undergoing development currently: residential, commercial, and industrial. This area also contains a Ford auto plant with a large number of employees as well as freight
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080215 |  |  |  | Relocate & reconstruct KY 1531 (Johnson Road) as a 2 lane road (no additional lanes) with improved geometry from US 60 (Shelbyville Road) to Aiken Road. Project will consider bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-KY-1531 -000 | 9.1 | 11.9 | 2.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 930000 |  | 470000 |  | 240000 |  | 10190000 |  | 2011-02-10 10:36 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 1531 from MP 9.000 to MP 11.682 is located in eastern Jefferson County. Adequacy rating data for this segment are not complete, and are only provided in terms of ADT and IRI. Upon physical inspection of the area, it is undergoing residential developme
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080216 |  |  |  | Implement peak period parking restrictions on KY 1703 (Baxter Avenue) from Castlewood Avenue to Highland Avenue. | Congestion Management | Jefferson | 056-KY-1703 -000 | 4.876 | 5.682 | 0.806 | Other Improvement Types | 0 |  | 0 |  | 5800 |  | 5800 |  | 3500 |  | 57900 |  | 2011-02-10 10:41 | The purpose of this project is to improve: 1) Traffic flow on roadways during peak travel hours, and 2) Air quality. | KY 1703 from MP 4.876 to MP 5.682 (Castlewood to Highland Avenue) is located in north central Jefferson County in what is know as the Highlands area. Abutting land uses are primarily medium to high density residential. Both residential and commercial use
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080217 |  |  |  | Improve safety and reduce congestion on KY 1747 (Hurstbourne Parkway) from US 31E (Bardstown Road) to KY 155 (Taylorsville Road). Project will evaluate the addition of one additional travel lane in each direction and other lower impact alternatives. Proj | Major Widening | Jefferson | 056-KY-1747 -000 | 7.4 | 11.1 | 3.7 | Modernize Roadway-Urban | 16 | Y | 0 |  | 2000000 |  | 1500000 |  | 1500000 |  | 20000000 |  | 2019-01-14 16:27 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 1747 from MP 0.000 to MP 3.540 is located in eastern Jefferson County. This area is experiencing growth at this time and additional development is planned. Residential and commercial uses are prominent in this area, with commercial and multi-family re | Louisville MPO | North | 45.2823 | 7.3477 | 4.7077 | 14.2269 | 0 | 0 | 4 | 0 | 30 |  | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080219 |  |  |  | Improve safety, mobility for all modes, and address geometric deficiencies along KY 1819 (Billtown Road) from I-265 (Gene Snyder Freeway) to Ruckriegel Parkway/Billtown Road (in and near Jeffersontown). Project will evaluate 3-lane widening and consider | Minor Widening | Jefferson | 056-KY-1819 -000 | 5.3 | 8.9 | 3.6 | Install Two-way Left Turn Lane | 28 |  | 240000 |  | 2090000 |  | 1160000 |  | 470000 |  | 23160000 |  | 2019-01-14 16:03 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | The corridor has limited right-of-way and narrow shoulders that are under three feet. Historic traffic volumes have shown strong growth along Billtown Road with traffic volumes expected to increase by 7.5% per year along the length of Billtown Road; with
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080221 |  |  |  | Improve safety and reduce congestion on KY 1931 (Manslick Road) from KY 1931 (St. Andrews Church Road) to I-264 (Henry Watterson Expressway). Project will evaluate 3-lane widening and consider accommodations for bicyclists and pedestrians. | Major Widening | Jefferson | 056-KY-1931 -000 | 5.477 | 7.702 | 2.225 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 1557500 |  | 6323450 |  | 11559000 |  | 10270000 |  | 2019-01-17 09:30 | The purpose of the proposed KY 1931 project is to improve safety and local traffic operations along this route between Dixie Highway and I-264. Other project goals include accommodating bicyclists and pedestrians, improving emergency response time, minimi | The need is expressed through above average crash rates, substandard geometric features, and congested traffic operations. Existing traffic volumes range from 11,100 to 18,200 vehicles per day, with the heavier volumes in the middle section between Palatk | Louisville MPO | North | 51.7992 | 8.7877 | 9.9692 | 13.2577 | 0 | 8.9538 | 2.9231 | 7.9077 | 52
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080222 |  |  |  | Transportation System Management improvements on KY 1932 (Breckenridge Lane) from KY 1447 (Westport Road) to Kresge Way. | Congestion Management | Jefferson | 056-KY-1932 -000 | 4.25 | 5.555 | 1.305 | Access Consolidation | 25 |  | 0 |  | 82000 |  | 58000 |  | 35000 |  | 869000 |  | 2019-01-17 10:16 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 1932 from MP 4.250 to MP 5.555 is located in central eastern Jefferson County in the City of St. Matthews. This area is medium to high density commercial and residential. The Baptist East Hospital complex sits at the southern end of this segment with
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080224 |  |  |  | Reconstruct KY 2845 (Manslick Road) from KY 61 to KY 864 (Beulah Church Road). Project will evaluate 3-lane widening with two-way center turn lane and consider accommodations for bicyclists and pedestrians. | Minor Widening | Jefferson | 056-KY-2845 -000 | 0 | 3.776 | 3.776 | Install Two-way Left Turn Lane | 28 |  | 120000 |  | 1390000 |  | 700000 |  | 350000 |  | 13900000 |  | 2011-02-10 14:29 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 2845 from MP 0.00 to MP 3.776 is located in southern Jefferson County. Surrounding land uses are primarily medium density residential with some commercial nodes. Data suggest this segment has crash issues, and a very rough pavement condition. Current
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080225 |  |  |  | Reconstruct Briscoe Lane as a 2 lane road (no additional lanes) from Vaughn Mill Road to Smyrna Parkway. Includes consideration of bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-CR-1013G -000 | 0.915 | 1.858 | 0.943 | Modernize Roadway-Urban | 16 |  | 0 |  | 120000 |  | 120000 |  | 120000 |  | 1160000 |  | 2019-01-17 13:31 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | CR 1013G (Briscoe Lane) is located in southern Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. Briscoe Lane, as is, does not meet current design standards (no shoulders, sub-standard lane widths,
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080226 |  |  |  | Reconstruct East Pages Lane as a 2 lane (no additional lanes) road with several improvements to intersections from US 31W (Dixie Highway) to KY 907 (3rd Street Road). Includes consideration of bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-CR-1013L -000 | 0 | 1.299 | 1.299 | Modernize Roadway-Urban | 16 |  | 0 |  | 900000 |  | 500000 |  | 300000 |  | 8100000 |  | 2019-01-17 13:34 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | CR 1013L (East Pages Lane) is located in western Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. The roadway, as is, does not meet current design standards, which is an isue in terms of safety and | Louisville MPO | North | 20.3715 | 8.7446 | 0 | 7.2115 | 4.4154 | 0 | 0 | 0 | 20
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080227 |  |  |  | Extend & widen Ellingsworth Lane from KY 913 (Blankenbaker Parkway) to Urton Lane. Project design will evaluate 3 lane road with two-way center turn lane and consider bicycle and pedestrian facilities. | New Route | Jefferson | 056-CR-1030H -000 | 0 | 0.607 | 0.607 | Modernize Roadway-Urban | 16 |  | 0 |  | 350000 |  | 240000 |  | 120000 |  | 3710000 |  | 2019-01-23 09:58 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | Ellingsworth Lane connects KY 913 and Tucker Station Road through heavy, residential development. With the proposed reconstruction of Urton Lane (KIPDA # 474) and Tucker Station (KIPDA # 472) Roads, an extension of Ellingsworth Lane would connect Urton L
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080228 |  |  |  | Reconstruct Fairground Road from US 31E to KY 1819. Project design will evaluate a 2 lane road (no added lanes), left-turn lanes at US 31E, Billtown Road, possibly other intersections, and radius improvements at three 90-degree curves and consider bike an | Reconstruction | Jefferson | 056-CR-1011H -000 | 0 | 1.953 | 1.953 | Modernize Roadway-Urban | 16 |  | 0 |  | 700000 |  | 350000 |  | 240000 |  | 6950000 |  | 2019-01-23 10:07 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | Fairground Road is a collector serving a residentially developed area. Although the length of Fairground Road is only two miles, it has significant number of local street intersections. Three of these have abnormally high volumes of traffic and actually
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080229 |  |  |  | Upgrade Fairmount Road from US 31E (Bardstown Road) to Broad Run Road. Project design will evaluate 2 lane road (no added lanes) and consider bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-CR-1004N -000 | 2.524 | 4.114 | 1.59 | Construct Road in New Location | 0 |  | 0 |  | 1100000 |  | 600000 |  | 300000 |  | 12100000 |  | 2018-12-21 14:47 | The purpose of this project is restore the linkage between two severed sections of Fairmount Road in Southeastern Jefferson County. | This project would put back a bridge across Floyds Fork creek that was removed decades ago because of poor condition and low ADT. At the time, the cost of replacing the bridge was determined to be greater than the benefit of replacing it. The current | Louisville MPO | North | 6.1708 | 0.14769 | 0 | 1.2231 | 4.8 | 0 | 0 | 0 | 6
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080230 |  |  |  | Improve safety and reduce congestion on Mud Lane from KY 1450 (Blue Lick Road) to Antle Drive. Project design will evaluate 2 lane road (no added lanes) and consider bicycle and pedestrian facilities. | Minor Widening | Jefferson | 056-CR-1003M -000 | 0 | 2.048 | 2.048 | Modernize Roadway-Urban | 16 |  | 0 |  | 580000 |  | 350000 |  | 120000 |  | 5790000 |  | 2019-01-23 15:25 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | As planned development occurs along KY 1450 (Blue Lick Road), Mud Lane will increasingly serve as a much needed outlet for traffic. Mud Lane is also a high accident corridor which will worsen as traffic volumes increase. This project will reduce traffic
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080231 |  |  |  | Improve safety and reduce congestion on Phillips Lane from KY 61 (Preston Highway) to KY 1631 (Crittenden Drive). Includes consideration of bicycle and pedestrian facilities. | Major Widening | Jefferson | 056-CS-1024G -000 | 0 | 1.277 | 1.277 | Modernize Roadway-Urban | 16 |  | 131000 |  | 1042000 |  | 1072000 |  | 1563000 |  | 7501000 |  | 2019-01-23 15:29 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | Phillips Lane connect KY 61 (Preston Highway) and KY 1631 (Crittenden Drive) just south of the Kentucky Fair and Exposition property. Phillips Lane has experience growth recently from the hospitality industry - many new hotels have been added along this
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080232 |  |  |  | Reconstruct Rehl Road from KY 913 (Blankenbaker Parkway) to S. Pope Lick Road. Project design will evaluate 2 lane road (no added lanes) and consider bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-CR-1006H -000 | 0 | 2.255 | 2.255 | Modernize Roadway-Urban | 16 |  | 0 |  | 930000 |  | 470000 |  | 240000 |  | 10420000 |  | 2019-01-23 15:33 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | Rehl Road is an east-west corridor that intersects with Blankenbaker Lane on the west and South Pope Lick Road and English Station Road on the east. At its junction with I-265(Gene Snyder Fwy.), a new interchange is being proposed. Additional development
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080233 |  |  |  | Improve safety and reduce congestion on Shepherdsville Road from KY 2845 (Manslick Road) to Applegate Lane. Project design will evaluate 2 lane road (no added lanes) and consider bicycle and pedestrian facilities. | Minor Widening | Jefferson | 056-CR-1008G -000 | 0.307 | 1.513 | 1.206 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 600000 |  | 400000 |  | 200000 |  | 7000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 2052 is located in southern Jefferson County. This area is in the process of developing with additional development planned in the future. The current roadway does not meet current design standards.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080234 |  |  |  | Reconstruct Tucker Station Road from Rehl Road to Ellingsworth Lane. Project design will evaluate 2 lane road (no added lanes) and consider intersection improvements (S. Pope Lick, Rehl Road & Ellingsworth Lane) and bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-CR-1001H -000 | 1.079 | 3.54 | 2.461 | Modernize Roadway-Urban | 16 |  | 0 |  | 930000 |  | 470000 |  | 240000 |  | 10420000 |  | 2019-01-24 13:55 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | Tucker Station Road is a narrow 2 lane collector extending from U. S. 60 to KY 155 (Taylorsville Road). It is the only non-interstate route which crosses I-64 between Blankenbaker and English Station roads. With planned development in the Urton Lane corr
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080235 |  |  |  | Reconstruct Arnoldtown Road from KY 1931 to KY 907. Project design will evaluate 2 lane road (no added lanes) with turning lanes at high volume intersections including Windsor Lakes, Windsor Forest, Mountain Brook & Hardwood Forest and consider bicycle an | Reconstruction | Jefferson | 056-CR-1003F -000 | 0 | 2.317 | 2.317 | Modernize Roadway-Urban | 16 |  | 0 |  | 1750000 |  | 400000 |  | 150000 |  | 11000000 |  | 2019-01-25 08:37 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | The Arnoldtown Road corridor between KY 1931 (St. Andrews Church Road) and KY 907 (Third Street Road) is located in southwestern Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. The roadway, as is,
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080236 |  |  |  | Reconstruct Cooper Chapel Road from Smyrna Parkway to KY 864. Project design will evaluate 2 lane road with left turn lanes at major intersections (Smyrna Parkway, Pennsylvania Run Road, KY 864, Beulah Church Road) and consider bicycle and pedestrian faci | Reconstruction | Jefferson | 056-CR-1002M -000 | 1.847 | 3.564 | 1.717 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 580000 |  | 350000 |  | 120000 |  | 5790000 |  | 2019-01-24 13:59 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The area south of I-265 (Gene Snyder Freeway) between KY 61 (Preston Highway) and US 31E (Bardstown Road) is experiencing rapid growth with the development of many new residential subdivisions. Cooper Chapel Road is a heavily traveled collector road servi
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080237 |  |  |  | Reconstruct Watterson Trail South from KY 1747 (Hurstbourne Parkway) to Glaser Lane. Project design will include 2 lane road (no added lanes) and consider bicycle and pedestrian facilities. | Minor Widening | Jefferson | 056-CR-1005H -000 | 1.5 | 2.815 | 1.315 | Install Two-way Left Turn Lane | 28 |  | 240000 |  | 2320000 |  | 1160000 |  | 470000 |  | 25470000 |  | 2019-01-24 14:03 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | CR 1005R (Watterson Trail South) is located in southeastern Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. The roadway, as is, does not meet current design standards. This segment serves a connec
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080238 |  |  |  | Extend Enterprise Drive from KY 1020 (National Turnpike) to KY 1631 (Fern Valley Road). Project design will evaluate a 4 lane road and consider bicycle and pedestrian facilities. | New Route | Jefferson | 056-CS-1122F -000 | 0 | 0.843 | 0.843 | Construct Road in New Location | 0 |  | 580000 |  | 3480000 |  | 2320000 |  | 2320000 |  | 40520000 |  | 2019-01-24 14:09 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | CS 1122F (Enterprise Drive) is located in central Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. Surrounding land uses are primarily industrial and/or warehouse, with some connection to United Pa
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080239 | 5-80003 |  | A | EXTEND PLANTSIDE DRIVE FROM REHL ROAD TO TAYLORSVILLE ROAD(18CCN) | NEW ROUTE(O) | Jefferson | 056-CS-1001H -000 | 3.139 | 4.17 | 1.031 | Other Improvement Types | 0 |  |  |  | 750000 | 2020 | [6 empty] | 2018-07-10 08:18 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | CS 1001H (Plantside Drive) is located in eastern Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. The roadway, as it currently exists, serves as local access to Bluegrass Industrial Park. . This n
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080240 |  |  |  | Improve safety and reduce congestion on Grade Lane from KY 1065 (Outer Loop) to KY 1631 (Fern Valley Road). Project design will evaluate 3-lane widening with two-way center turn lane and consider bicycle and pedestrian facilities. | Major Widening | Jefferson | 056-CR-1001G -000 | 2.106 | 4.058 | 1.952 | Modernize Roadway-Urban | 16 |  | 120000 |  | 1200000 |  | 700000 |  | 300000 |  | 13500000 |  | 2019-01-24 14:15 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | CR 1001G (Grade Lane) is located in central Jefferson County in close proximity to the Louisville International Airport. Adequacy rating information is not available as this is not a state-maintained roadway. The roadway, as is, does not meet current de | Louisville MPO | North | 25.9623 | 5.9815 | 4.6154 | 10.0269 | 2.0769 | 0 | 3.2615 | 0 | 26
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080242 |  |  |  | Extend and reconstruct Blowing Tree Boulevard from KY 155 (Taylorsville Road) to Bunsen Parkway. Project design will evaluate 3 lane road with two-way center turn lane and consider bicycle and pedestrian facilities. | New Route | Jefferson | 056-KY-1747 -010 | 11.056 | 11.457 | 0.401 | Construct Road in New Location | 0 |  | 0 |  | 500000 |  | 450000 |  | 580000 |  | 3000000 |  | 2019-02-06 11:50 | This project has six transportation goals which consist of: 1) system linkage, 2) transportation demand from the MPO or regional planning, 3) travel speed improvements, 4) improved access to public facilities, 5) improving modal connections, and 6) a redu | Traffic impact analysis demonstrates a relief of traffic congestion in the short term after the completion of the connector route and prior to full development of the Oxmoor Farms property. By 2035, however, as the Oxmoor Farms property develops, traffic | Louisville MPO | North | 6.5369 | 0.16 | 0 | 2.5615 | 3.8154 | 0 | 0 | 0 | 6
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080243 |  |  |  | Align Hikes Lane intersections of Furman Boulevard & Klondike Lane. | Safety-Haz-Elm | Jefferson | 056-CR-1002G -000 | 2.22 | 2.309 | 0.089 | Modernize Roadway-Urban | 16 |  | 0 |  | 240000 |  | 350000 |  | 120000 |  | 2670000 |  | 2019-02-01 10:07 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | CR 1002G (Hikes Lane) is located in central Jefferson County. Adequacy rating information is not available as this is not a state-maintained roadway. The intersection of Hikes Lane, Furman Boulevard, and Klondike Lane is offset, causing potential safety
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080244 | 5-80005 |  | A | IMPROVE THE INTERCHANGE OF I 71 AND KY 329. (18CCN) | SAFETY(P) | Oldham | 093-I -0071 -000 | 14 | 15 | 1 | Interchange Safety Improvements | 35 | Y |  |  | 280000 | 2019 | [6 empty] | 2019-03-08 13:14 | Improve safety and reduce congestion at the I-71/KY 329 interchange. | This project is needed because of a high amount of crashes and limited sight distance that exists at the I-71 ramps at KY 329. Additionally, the capacity of KY 329 is inadequate to handle current traffic volumes during peak hours.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080246 |  |  |  | Improve traffic flow, minimize congestion, and address safety issues on US 42 between Ridgemoor Drive and KY 1694 (Gum Street). Includes consideration of a three lane widening and bike/ped accommodations. | Minor Widening | Oldham | 093-US-0042 -000 | 0.942 | 6.034 | 5.092 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 820000 |  | 470000 |  | 240000 |  | 9300000 |  | 2011-02-03 14:44 | The purpose of the project is to improve traffic flow, minimize congestion, and address safety issues on US 42 between Ridgemoor Drive and KY 1694 (Gum Street). | This project is needed because or current and projected capacity issues and roadway deficiencies on US 42 between Ridgemoor Drive and KY 1694 (Gum Street). Local commuters use this route daily to travel to and from Jefferson County. There are five schoo
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080247 |  |  |  | Improve traffic flow, minimize congestion, and address safety issues on US 42 between KY 1694 (Gum Street) and KY 53. Includes consideration of a three lane widening and bike/ped accommodations. | Reconstruction | Oldham | 093-US-0042 -000 | 6.034 | 13.024 | 6.99 | Install Two-way Left Turn Lane | 28 |  | 240000 |  | 1600000 |  | 820000 |  | 350000 |  | 17400000 |  | 2011-02-03 14:54 | Improve traffic flow, minimize congestion, and address safety issues on US 42 between KY 1694 (Gum Street) and KY 53. | This project is needed because of substandard geometrics including substandard vertical curves which creates potential safety concerns on US 42 between KY 1694 (Gum Street) and KY 53. Continued development in this area along this corridor will contribute
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080249 |  |  |  | Improve safety and traffic flow at the intersection of KY 22 and KY 53. | Safety-Haz-Elm | Oldham | 093-KY-0022 -000 | 11.351 | 11.551 | 0.2 | Improve Intersection | 26 |  | 0 |  | 2400 |  | 2400 |  | 1200 |  | 29000 |  | 2018-12-18 15:06 | The purpose of this project is to improve safety and traffic flow at the intersection of KY 22 and KY 53. | This project is needed because KY 22 is currently a through street while northbound KY 53 traffic is stop-controlled even though KY 53 has a higher functional classification and carries more traffic than KY 22.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080250 |  |  |  | Improve safety and reduce congestion on KY 53 from I-71 to Zhale Smith Road. Includes consideration of a five lane widening and bike/ped accommodations. | Major Widening | Oldham | 093-KY-0053 -000 | 5.685 | 6.268 | 0.583 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 1600000 |  | 820000 |  | 350000 |  | 17400000 |  | 2018-12-19 14:45 | The purpose of this project is to improve safety and reduce congestion on KY 53 from I-71 to Zhale Smith Road. | This project is needed because there are a high amount of crashes and continued development in this area and south along KY 53 is anticipated, adding to future potential congestion issues on KY 53 from I-71 to Zhale Smith Road.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080251 |  |  |  | Improve safety and reduce congestion on KY 146 (LaGrange Road) from KY 329B (KY 329 Bypass) to KY 393. Includes consideration of a four lane widening and bike/ped accommodations. | Major Widening | Oldham | 093-KY-0146 -000 | 2.642 | 7.673 | 5.031 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 240000 |  | 1600000 |  | 820000 |  | 350000 |  | 17500000 |  | 2011-02-03 15:55 | The purpose of this project is to improve safety and reduce congestion on KY 146 (LaGrange Road) from KY 329B (KY 329 Bypass) to KY 393. | This project is needed because there there are sections of KY 146 from KY 329B (KY 329 Bypass) to KY 393 that has inadequate capacity and is frequently congested during peak hours. With planned development in Oldham County, this area is expected to grow
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080252 |  |  |  | Reduce congestion, improve access, and provide better mobility for all modes along KY 146 from the Oldham/Jefferson County line to Pryor Avenue in Crestwood. Project design will consider reconstructing KY 146 as a 2 lane road (no additional lanes) from | Reconstruction | Oldham | 093-KY-0146 -000 | 0 | 2.021 | 2.021 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1500000 |  | 500000 |  | 500000 |  | 12000000 |  | 2015-02-13 09:06 | The purpose of this project is to reduce congestion, improve access, and provide better mobility for all modes along KY 146 from the Oldham/Jefferson County line to Pryor Avenue in Crestwood. | This project is needed because KY 146 from the Oldham/Jefferson County line to Pryor Avenue in Pewee Valley experiences a high level of congestion and has potential crash issues. With the additional population expected in Oldham County in this area, and
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080253 |  |  |  | Improve safety, reduce congestion, and provide better mobility for all modes along KY 329 from the Oldham/Jefferson County line to I-71. | Reconstruction | Oldham | 093-KY-0329 -000 | 0 | 6.894 | 6.894 | Modernize Roadway-Rural | 26 |  | 350000 |  | 2500000 |  | 1300000 |  | 580000 |  | 29000000 |  | 2011-02-03 16:04 | The purpose of this project is to improve safety, reduce congestion, and provide better mobility for all modes along KY 329 from the Oldham/Jefferson County line to I-71. | This project is needed because there are high crash segments on KY 329 from the Oldham/Jefferson County line to I-71. There is a need, with current and planned development in the area, to increase capacity and improve safety for motorists along this rout
Y | 5 | KIPDA ADD | IP20080255 |  |  |  | Address safety issues, traffic congestion, access control, and sight distance along KY 53 from KY55 north of Shelbyville to the Oldham County Line. | Reconstruction | Shelby | 106-KY-0053 -000 | 9.765 | 19.609 | 9.844 | Modernize Roadway-Rural | 26 |  | 218000 |  | 3780000 |  | 8186000 |  | 3418000 |  | 45445000 |  | 2018-11-30 13:47 | Address safety issues and traffic congestion on KY 53. | Route serves as major connector linking LaGrange and Shelbyville and provides direct access to multiple schools. Higher than average reported crashes indicate potential safety concerns. Current congestion, along with high projected ADT indicate future cap
Y | 5 | KIPDA ADD | IP20080256 |  |  |  | Address access management and safety issues along KY 55X from KY 43 to the Entrance of the Shelbyville Bypass (KY 55). | Major Widening | Shelby | 106-KY-0055X -000 | 1.354 | 2.076 | 0.722 | Major Widening-Rural Mutilane | 34 |  | 250000 |  | 2090000 |  | 200000 |  | 816000 |  | 16020000 |  | 2018-12-03 09:51 | Address access management and safety issues along the roadway of KY 55X from KY 43 to the Entrance of the Shelbyville Bypass (KY 55). | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all user types. Higher than average reported crashes indicate potential safety concerns. Current congestion, along with high
Y | 5 | KIPDA ADD | IP20080257 |  |  |  | Address safety issues, substandard curves, and sight distance along KY 395 from I-64 to US 60. | Major Widening | Shelby | 106-KY-0395 -000 | 9 | 10.284 | 1.284 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 670000 |  | 1594000 |  | 911000 |  | 5360000 |  | 2018-12-03 08:59 | The purpose of this project is to address safety issues, reduce congestion, and improve mobility on KY 395 from I-64 to US 60. | This project would seek to improve freight and commercial mobility between I-64 and US 60. There are substandard curves and low or no shoulders along the roadway of KY 395. The KY 395 corridor has narrow lanes.
Y | 5 | KIPDA ADD | IP20080258 |  |  |  | Address safety issues, substandard curves, low shoulders, narrow lanes, and sight distance to upgrade the safety of the KY 55 corridor from Taylorsville (MP 6.52) to KY 2239 (2.92). | Reconstruction | Spencer | 108-KY-0055 -000 | 2.922 | 6.518 | 3.596 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3400000 |  | 600000 |  | 12750000 |  | 2013-05-16 08:32 | The purpose of this project is to improve access on KY 55 from KY 44 to KY 2239. | There are substandard curves and low or no shoulders along the roadway of KY 55. According to the KY 55 Scoping Study most accident crashes happened at KY 55/KY 44 in downtown Taylorsville.
Y | 5 | KIPDA ADD | IP20080259 |  |  |  | Address safety issues, substandard curves, low shoulders, narrow lanes, and sight distance to upgrade the safety of the KY 55 corridor from KY 2239 to KY 1066. | Reconstruction | Spencer | 108-KY-0055 -000 | 0.316 | 2.922 | 2.606 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 4000000 |  | 2000000 |  | 11750000 |  | 2013-05-16 11:15 | Address safety issues, substandard curves, low shoulders, narrow lanes, and sight distance to upgrade the safety of the KY 55 corridor from KY 2239 to KY 1066. | This project would seek to improve freight, commercial and recreational mobility between the Bluegrass Parkway and city of Taylorsville. There are substandard curves and low or no shoulders along the roadway of KY 55. The KY 55 corridor has narrow lanes
Y | 5 | KIPDA ADD | IP20080260 |  |  |  | Improve safety and reduce congestion on KY 55 from the KY1633/KY155 intersection to the intersection with KY 44. | Major Widening | Spencer | 108-KY-0055 -000 | 6.518 | 11.27 | 4.752 | Modernize Roadway-Rural | 26 |  | 200000 |  | 1690000 |  | 5120000 |  | 2490000 |  | 18870000 |  | 2015-02-13 12:58 | Improve safety and reduce congestion on KY 55 from the KY1633/KY155 intersection to the intersection with KY 44. | The following needs have been identified for this project: 1. Improve the safety of the road. 2. Provide adequate transportation linkage between the Cities of Taylorsville and Louisville. 3. Provide better freight mobility between Bluegrass Parkway
Y | 5 | KIPDA ADD | IP20080261 |  |  |  | Improve safety and address geometric deficiencies along KY 55 from KY 155/KY 1633 to the Spencer/Shelby County Line. | Major Widening | Spencer | 108-KY-0055 -000 | 11.27 | 13.566 | 2.296 | Modernize Roadway-Rural | 26 |  | 250000 |  | 830000 |  | 1800000 |  | 1050000 |  | 10700000 |  | 2018-12-02 12:36 | The purpose statement of this project is to expand KY 55 beginning at the intersection of KY 55/KY 155 (MP 11.27) and ending at (MP 13.566) in Spencer County | This project would seek to improve freight, commercial and recreational mobility between Shelbyville and Taylorsville. There are horizontal curves and low or no shoulders along the roadway of KY 55. The KY 55 corridor has narrow lanes.
Y | 5 | KIPDA ADD | IP20080262 | 5-8954 |  | A | CONSTRUCT A 2+1 ROAD ON KY 55/155 (TAYLORSVILLE ROAD) IN SPENCER COUNTY AND KY 155 (TAYLORSVILLE LAKE ROAD) IN JEFFERSON COUNTY BY ADDING A CONTINUOUS THIRD LANE THAT SERVES AS AN ALTERNATING PASSING LANE.(16CCN)(18CCN) | RECONSTRUCTION(O) | Spencer | 108-KY-0155 -000 | 0 | 4.247 | 4.247 | Modernize Roadway-Rural | 26 |  |  |  | 4750000 | 2024 | 30000 | 2025 | 760000 | 2025 | 13700000 | 2025 | 2019-03-08 10:58 | CONSTRUCT A 2+1 ROAD ON KY 55/155 (TAYLORSVILLE ROAD) IN SPENCER COUNTY AND KY 155 (TAYLORSVILLE LAKE ROAD) IN JEFFERSON COUNTY BY ADDING A CONTINUOUS THIRD LANE THAT SERVES AS AN ALTERNATING PASSING LANE. | This project would seek to improve freight access and interregional mobility between the City of Taylorsville, the Bluegrass Parkway (Central Kentucky) and City of Louisville. The current 2-lane roadway has limited capacity and ADT is projected to incre | KIPDA ADD | North | 59.6215 | 6.9292 | 10.8923 | 6.8769 | 0 | 8.6462 | 3.0923 | 8.1846 | 45 |  | 15
Y | 5 | KIPDA ADD | IP20080263 |  |  |  | Improve safety and address geometric deficiencies along KY 1169 from KY 55 to Meadowlake Drive. | Major Widening | Spencer | 108-KY-1169 -000 | 4.96 | 7.14 | 2.18 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3220000 |  | 1600000 |  | 5000000 |  | 2013-05-16 08:26 | Improve safety and address geometric deficiencies along KY 1169 from KY 55 to Meadowlake Drive. | Route is an unimproved two lane country road with deficient roadway geometrics not meeting current design standards resulting in higher than average crash rates. Issues include insufficient lane and shoulder widths, deficient vertical and horizontal curv | KIPDA ADD | North | 28.2692 | 2.5538 | 9.6462 | 5.7462 | 4.3846 | 5.9385 | 0 | 0 | 28
Y | 5 | KIPDA ADD | IP20080264 |  |  |  | Address safety issues and geometric issues on KY 1169 from KY 1060 to just west of the KY 1169/KY 55 intersection. | Major Widening | Spencer | 108-KY-1169 -000 | 0 | 4.96 | 4.96 | Modernize Roadway-Rural | 26 |  | 0 |  | 410000 |  | 2730000 |  | 3190000 |  | 3540000 |  | 2011-02-04 11:38 | Address safety issues and geometric issues on KY 1169 from KY 1060 to just west of the KY 1169/KY 55 intersection. | Route is an unimproved two lane country road with deficient roadway geometrics not meeting current design standards resulting in higher than average crash rates. Issues include insufficient lane and shoulder widths, substandard bridges, deficient vertica | KIPDA ADD | North | 28.4296 | 1.4585 | 6.1846 | 3.1269 | 4.8769 | 5.5077 | 0 | 7.275 | 28
Y | 5 | KIPDA ADD | IP20080266 |  |  |  | Improve safety and address geometric deficiencies along US 421 from US 42 to the Ohio River Bridge (from Bedford to Milton). | Reconstruction | Trimble | 112-US-0421 -000 | 6.704 | 18.773 | 12.069 | Modernize Roadway-Rural | 26 |  | 400000 |  | 4750000 |  | 8890000 |  | 3900000 |  | 45600000 |  | 2018-12-04 12:18 | The purpose of this project is to rebuild US 421 from Bedford to Ohio River bridge to address safety issues. | The current roadway alignment has narrow lanes and shoulders. The most frequent crash type in the project area was a vehicle running off the road. Other issues with the existing route are the curves and grades that do not meet current guidelines or provid
Y | 5 | KIPDA ADD | IP20080268 |  |  |  | Improve safety, truck mobility, and address geometric deficiencies along KY 36 from US 421 to 250 feet east of School Hollow Road in Milton. | Reconstruction | Trimble | 112-KY-0036 -000 | 0 | 0.25 | 0.25 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 250000 |  | 1875000 |  | 2017-04-20 09:14 | Improve safety, truck mobility, and address geometric deficiencies along KY 36 from US 421 to 250 feet east of School Hollow Road in Milton. | The Intersection of KY 36/US 421 in downtown Milton cannot be negotiated by trucks because of insufficient truck turning radius geometry causing safety and travel delay issues. Currently, KY 36 cannot be listed as on the NTN or KHFN freight networks beca | KIPDA ADD | North | 22.7454 | 1.5262 | 4.3385 | 1.5115 | 4.2 | 7.2615 | 0 | 3.9077 | 23
Y | 5 | KIPDA ADD | IP20080269 |  |  |  | Address safety issues, sight distance, a substandard curve to upgrade the roadway of KY 754. | Reconstruction | Trimble | 112-KY-0754 -000 | 1.42 | 1.62 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 325000 |  | 130000 |  | 70000 |  | 725000 |  | 2013-05-16 08:24 | The purpose of this project is to rebuild curves on KY 754 to address safety issues and sight distance issues. | This section of KY 754 provides direct access to two major industrial traffic generators in Trimble County. There is 18% of truck traffic that travels daily on this section of KY 754. Route is an unimproved two lane country road not suited for heavt tru | KIPDA ADD | North | 13.9077 | 1.3538 | 2.5846 | 0 | 4.3385 | 5.6308 | 0 | 0 | 14
Y | 5 | KIPDA ADD | IP20080270 |  |  |  | Address safety issues, sight distance, substandard curves to upgrade the safety of the roadway on KY 1226. | Spot Improvement | Trimble | 112-KY-1226 -000 | 2.41 | 2.61 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 130000 |  | 70000 |  | 750000 |  | 2013-05-16 08:34 | The purpose of this project is to address spot safety improvements on KY 1226. | This section of KY 1226 provides mobility to Carroll County. Route is an unimproved two lane country road with deficient roadway geometrics not meeting current roadway design standards resulting in higher than average crash rates. Issues include insuffi
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110073 |  |  |  | Improve Safety & Connectivity and Reduce Congestion along Shelbyville Road (US 60), Hurstbourne Lane (KY 1747), Interstate I 64 and Taylorsville Road (KY 155) in the vicinity of Oxmoor Farms. Project will consider a Bunsen Boulevard/Christian Way con | New Route | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 0 |  | 2250000 |  | 560000 |  | 370000 |  | 20260000 |  | 2019-02-04 12:08 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | This segment is being proposed in eastern Jefferson County in close proximity to US 60, I-64, and KY 1747. The segment is being proposed for what is currently the Bullitt Farm property, south of Oxmoor mall. There is a lack of connectivity in this area | Louisville MPO | North | 36.7438 | 8.2092 | 0 | 14.5962 | 0 | 9.5077 | 4.4308 | 0 | 37
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110074 |  |  |  | Improve Safety and Connectivity and Reduce Congestion along Shelbyville Road (US 60), Hurstbourne Lane (KY 1747), Interstate I 64 and Taylorsville Road (KY 155) in the vicinity of Oxmoor Farms. Project will consider a Bowling Boulvard/Christian Way c | New Route | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 0 |  | 2000000 |  | 860000 |  | 890000 |  | 20000000 |  | 2019-02-14 13:58 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice from Bowling Blvd. to Christian Way. | This segment is being proposed in eastern Jefferson County in close proximity to US 60, I-64, I-264, and KY 1747. The segment is being proposed for what is currently the Bullitt Farm property, south of Oxmoor mall. There is a lack of connectivity in th | Louisville MPO | North | 37.3785 | 8.3323 | 0 | 14.7231 | 0 | 9.5077 | 4.8154 | 0 | 37
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110076 |  |  |  | Extend Cedar Creek Road connector from south & west of Johnson School Road to KY 864 (Beulah Church Road). Project design will evaluate 2 lane road and consider bicycle and pedestrian facilities. | New Route | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 310000 |  | 155000 |  | 65000 |  | 3600000 |  | 2019-01-28 15:16 | The purpose of this project is to improve connectivity between Johnson School Road and KY 864 (Beulah Church Road). | KY 61 is expanding with commercial development at the intersection with Cedar Creek Road, drawing residents and commecial uses to the surrounding area. Current surrounding land uses are primarily medium and low density residential.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110077 |  |  |  | Reconstruct South English Station Road (CR-1002J) from Poplar Lane (CR-1025H) to Christian Academy. Project design will evaluate 2 lane road (no added lanes) and consider bicycle and pedestrian facilities. | Reconstruction | Jefferson | 056-CR-1002J -000 | 2.95 | 3.9 | 0.95 | Modernize Roadway-Urban | 16 |  | 0 |  | 150000 |  | 80000 |  | 30000 |  | 1800000 |  | 2019-01-30 13:42 | The purpose of this project is to improve safety on South English Station Road (CR-1002J) from Poplar Lane (CR-1025H) to Christian Academy including consideration for connectivity of additional bicycle and pedestrian facilities. | This segment of South English Station Road is not current with modern geometric design standards including minimal to no shoulders existing along this route. The current Population Annual Growth Rate for the area ranges from 1.6% to 2.6%, and the current
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110078 |  |  |  | Transportation System Management/Transportation Demand Management, aesthetic improvements at medical center on South Floyd Street (CS-1003F) from East Broadway (US-150) to Jefferson Street (CS-1014B). | Congestion Management | Jefferson | 056-CS-1003F -000 | 0.2 | 0.8 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 6200 |  | 3200 |  | 1200 |  | 75000 |  | 2011-02-28 12:42 | The purpose of this project is to improve the operational capacity and transit on South Floyd Street (CS-1003F) from East Broadway (US-150) to Jefferson Street (CS-1014B). | The need for this project is to reduce the current congestion along the route.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110081 |  |  |  | Realign Kentucky Street (CS 1005) to connect to Garland Avenue to avoid crossing the P&L railroad. | Relocation | Jefferson | 056-CS-1005F -000 | 2.539 | 2.817 | 0.278 | Modernize Roadway-Urban | 16 |  | 0 |  | 60000 |  | 30000 |  | 20000 |  | 660000 |  | 2019-02-07 14:50 | The purpose of this project is to improve safety at Kentucky Street (CS 1005) to connect to Garland Avenue to avoid crossing the P&L railroad. | There are 10 to 12 tracks that you have to cross at the railyard on Kentucky street. It poses a safety issue. This is an industrial area and tractor trailers avoid this intersection as much as possible. By closing off the RR crossing and realigning Ken | Louisville MPO | North | 30.3585 | 6.0738 | 14.3538 | 7.3615 | 2.5692 | 0 | 0 | 0 | 30
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110082 |  |  |  | Reconstruct the I-64/(Hurstbourne Parkway) interchange. | Reconstruction | Jefferson | 056-PF-9999 - |  |  |  | Innovative Interchange | 40 | Y | 0 |  | 3500000 |  | 1000000 |  | 2500000 |  | 37000000 |  | 2019-02-06 14:10 | The purpose of this project is to improve safety and operational performance at the at the I-64/KY1747 (Hurstbourne Parkway) interchange . | This interchange was ranked 11 out of the 20 "Top Ranked Crash Interstate Interchanges" in 2015 by the KIPDA MPO Interchange Crash Analysis. The Critical Rate Factor (CRF) thru the interchange (MP 15.018 to MP 17.177) was 2.14 from 2012 to 1016. The cur
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110083 |  |  |  | Improve safety and reduce congestion Watterson Trail (CS 1073H) from Old Taylorsville Road to Grand Avenue with consideration for bicycle and pedestrian facilities. | Minor Widening | Jefferson | 056-CS-1073H -000 | 0.352 | 0.642 | 0.29 | Other Improvement Types | 0 |  | 0 |  | 43000 |  | 22000 |  | 9000 |  | 500000 |  | 2011-02-28 14:27 | The purpose of this project is to improve safety and reduce congestion Watterson Trail (CS 1073H) from Old Taylorsville Road to Grand Avenue. | This area is the "gateway" from the Bluegrass Business Park to the City of Jeffersontown to the south. At this time, this area is heavily congested because of the lack of carrying capacity of the roadway. Additional industry is planned in the business p
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110085 |  |  |  | Improve safety and traffic flow at the intersection of KY 53 (North/South First Avenue) and KY 146 (East/West Jefferson Street) in LaGrange. | Safety-Haz-Elm | Oldham | 093-KY-0053 -000 | 7.005 | 7.105 | 0.1 | Improve Intersection | 26 |  | 0 |  | 83000 |  | 42000 |  | 18000 |  | 950000 |  | 2011-02-28 15:16 | The purpose of this project is to improve safety and traffic flow at the intersection of KY 53 (North/South First Avenue) and KY 146 (East/West Jefferson Street) in LaGrange. | This project is needed because safety is a concern at the intersection of KY 53 (North/South First Avenue) and KY 146 (East/West Jefferson Street) in LaGrange; speed and volumes are both factors.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110104 |  |  |  | KY 907 at James Hill Road intersection curve improvements - long term horizontal and vertical curve reconstruction. | Spot Improvement | Jefferson | 056-KY-0907 -000 | 2.8 | 3 | 0.2 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 100000 |  | 100000 |  | 1200000 |  | 2019-02-11 09:52 | The purpose of this project is to reduce congestion and improve safety in the long term on the KY 907 (Third Street) and James Hill Road intersection. | The roadway network in this area was established many years ago with few major improvements other than some widening and resurfacing. Consequently, some major issues are deep drainage ditches, substandard shoulders, limited sidewalks, and a lack of adequa
Y | 5 | Bluegrass ADD | IP20110207 |  |  |  | Improve safety, access, and reduce congestion at the intersection of US 60 and Brighton Park Boulevard/Laralan Avenue in Frankfort. | Spot Improvement | Franklin | 037-US-0060 -000 | 11.375 | 11.659 | 0.284 | Improve Intersection | 26 | Y | 0 |  | 200000 |  | 100000 |  | 50000 |  | 1500000 |  | 2018-11-30 09:55 | Improve safety access and reduce congestion at the intersection of US60 and Brighton Park Boulevard/Laralan Avenue in Frankfort. | High Critical Rate Factor, high IRI and significant ADT indicate safety issues at this location.
Y | 5 | Bluegrass ADD | IP20110208 |  |  |  | Improve safety and access at the US 127/KY 420 intersection in Frankfort. | Spot Improvement | Franklin | 037-US-0127 -000 | 3.591 | 3.791 | 0.2 | Improve Intersection | 26 | Y | 0 |  | 500000 |  | 300000 |  | 300000 |  | 4000000 |  | 2011-11-18 13:38 | Improve safety and access at the US 127/KY 420 intersection in Frankfort. | Critical Rate Factor, congestion and high ADT, including large truck volume, and pavement issues indicate safety problems at this intersection.
Y | 5 | KIPDA ADD | IP20110217 |  |  |  | Improve safety and reduce congestion on I-71 from KY 153 to US 421. | Major Widening | Henry | 052-I -0071 -000 | 28 | 34 | 6 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 4000000 |  | 1500000 |  | 600000 |  | 48000000 |  | 2015-04-02 14:15 | Improve safety and reduce congestion on I-71 from KY 153 to US 421. | This project is needed because of a higher than average crash rate compared to similar roadway segments and a large amount of truck traffic on I-71 from KY 153 to US 421. The critical crash rate factor (CCRF) in this section of I-71 is 0.959 as cited in t
Y | 5 | KIPDA ADD | IP20110218 |  |  |  | Improve safety and access along KY 55 from KY 1899 (Mulberry Pike) to KY 22 in Eminence. | Minor Widening | Henry | 052-KY-0055 -000 | 0.737 | 1.4 | 0.663 | Modernize Roadway-Rural | 26 |  | 0 |  | 190000 |  | 260000 |  | 420000 |  | 1260000 |  | 2015-07-08 13:51 | The purpose of this project is to reduce crashes, improve corridor access and safety on KY 55 from KY 1899 (Mulberry Pike) to KY 22 in Eminence. | This project is needed because narrow lane widths, inadequate drainage, and numerous entrances/driveways exist on KY 55 from KY 1899 (Mulberry Pike) to KY 22 in Eminence creating safety hazards.
Y | 5 | KIPDA ADD | IP20110219 |  |  |  | Improve safety and access on KY 22 from KY 55 (Main Street) to KY 1359 (Hillspring Road). | Minor Widening | Henry | 052-KY-0022 -000 | 7.42 | 8.995 | 1.575 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 200000 |  | 150000 |  | 3000000 |  | 2011-11-18 13:30 | Improve safety and access on KY 22 from KY 55 (Main Street) to KY 1359 (Hillspring Road). | This project is needed to address substandard curves, roadway deficiencies, and the intersection of KY 22/KY 55 on KY 22 from KY 55 (Main Street) to KY 1359 (Hillspring Road) in Eminence.
Y | 5 | KIPDA ADD | IP20110224 |  |  |  | Improve safety and access at the KY53/KY 322 intersection. | Reconstruction | Shelby | 106-KY-0053 -000 | 16.178 | 16.278 | 0.1 | Improve Intersection | 26 |  | 0 |  | 420000 |  | 160000 |  | 105000 |  | 2625000 |  | 2015-07-07 15:36 | Address safety issues and sight distance at the intersection of KY 53 and KY 322. | Intersection joins two unimproved two-lane country roads having deficient roadway geometrics and not meeting current roadway design standards. Issues at the intersection include severely skewed tee intersection, no turn lanes, insufficient lane and shoul
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20120002 |  |  |  | Extend Urton Lane from north of I-64 to Seatonville Road. Includes consideration of facilities for all modes (pedestrian, bicycle, SOV, and transit). | New Route | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y | 0 |  | 4000000 |  | 3000000 |  | 2500000 |  | 52000000 |  | 2019-02-11 11:14 | The purpose of this project is to improve access and increase connectivity on Urton Lane from north of I-64 to Seatonville Road. | The Urton Lane Extension is essential in providing a connection to the existing arterials and away from local/subdivision streets away from local/subdivision streets from the existing, new and proposed developments. The forecasted 2020 Average Daily Traff
Y | 5 | Bluegrass ADD | IP20120030 |  |  |  | Improve safety and access along US 60 from the I-64 ramp to KY 1681 (Duncan Road) south of Frankfort. | Minor Widening | Franklin | 037-US-0060 -000 | 13.4 | 13.599 | 0.199 | Auxiliary Lanes or Operation Improvements | 11 | Y | 0 |  | 300000 |  | 340000 |  | 450000 |  | 2000000 |  | 2018-11-30 10:05 | Improve safety and access along US 60 from the I-64 ramp to KY 1681 (Duncan Road) south of Frankfort. | Create an additional lane on US 60 from the I-64 / US 60 interchange to Duncan Road in Frankfort. Project was completed that created a slip ramp with a right turn lane from the I-64 EB to US 60 SB ramp (right turn lane onto KY 1681 Duncan Road). There is
Y | 5 | KIPDA ADD | IP20130004 |  |  |  | Improve safety and reduce congestion on I-71 from US 421 to the Henry County/Trimble County line. | Major Widening | Henry | 052-I -0071 -000 | 34 | 38.086 | 4.086 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 4000000 |  | 1000000 |  | 500000 |  | 41000000 |  | 2015-03-04 11:10 | Improve safety and reduce congestion on I-71 from US 421 to the Henry County/Trimble County line. | This project is needed because of a higher than average crash rate compared to similar roadway segments and a large amount of truck traffic on I-71 from US 421 to the Henry County/Trimble County line. The percent of fatal crashes in this section of I-71
Y | 5 | KIPDA ADD | IP20130005 |  |  |  | Improve safety and geometrics on KY 561 (Gest Road) from KY 573 (Woods Pike) to KY 389 (Harpers Ferry Road). | Minor Widening | Henry | 052-KY-0561 -000 | 1.183 | 2.995 | 1.812 | Modernize Roadway-Rural | 26 |  | 0 |  | 410000 |  | 460000 |  | 730000 |  | 2720000 |  | 2019-02-21 14:51 | Improve safety and geometrics on KY 561 (Gest Road) from KY 573 (Woods Pike) to KY 389 (Harpers Ferry Road). | This project is needed because KY 561 (Gest Road) has narrow lanes and needs to address geometric deficiencies along the roadway from KY 573 (Woods Pike) to KY 389 (Harpers Ferry Road).
Y | 5 | KIPDA ADD | IP20130006 |  |  |  | Improve safety and reduce congestion on I-71 from the Henry/Trimble County line to the Trimble/Carroll County line. | Major Widening | Trimble | 112-I -0071 -000 | 38.086 | 38.808 | 0.722 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 700000 |  | 100000 |  | 100000 |  | 7200000 |  | 2015-03-06 11:25 | Improve safety and reduce congestion on I-71 from the Henry/Trimble County line to the Trimble/Carroll County line. | This section of I-71 does not meet current design standards. Deficiencies cited in the I-71 Corridor Study (March 2014)include shoulder width, clear zone, and maximum grades equal to the 4% maximum grade recommended in the AASHTO "A Policy on Design Stand
Y | 5 | KIPDA ADD | IP20130007 |  |  |  | Improve connectivity from KY53 at the Old Seven Mile Pike intersection to US60/Rocket Lane intersection. | New Route | Shelby | 106-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 1660000 |  | 2000000 |  | 1400000 |  | 13690000 |  | 2017-03-21 15:07 | Improve connectivity from the newly aligned intersection of the newly constructed KY 53 and Old Mt. Eden Road (CR1200) to just west of the US 60/Rocket Lane (KY 1871) intersection. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity, 3) Improve access to major traffic generators along the roadways of US 60 and KY 1871 and 4) Reduce congestion at the KY 53 US 60 inter | KIPDA ADD | North | 27.2877 | 8.08 | 0 | 9.2538 | 1.5231 | 8.4308 | 0 | 0 | 27
Y | 5 | KIPDA ADD | IP20130035 | 5-8955 |  | A | IMPROVE SAFETY AND ADDRESS GEOMETRIC DEFICIENCIES ALONG KY-44 NEAR DUTCHMAN CREEK ROAD. (16CCN) | SAFETY(P) | Spencer | 108-KY-0044 -000 | 0.28 | 0.44 | 0.16 | Improve Intersection | 26 |  |  |  | 270000 | 2022 | 230000 | 2025 | 210000 | 2025 | 1270000 | 2025 | 2019-03-08 11:11 | Improve safety and address geometric deficiencies along KY 44 near Dutchman Creek Road. | Spot location has safety and sight distance issues resulting from a deficient horizontal curve, skewed intersection and a narrow bridge not wide enough to support intersection turn lanes. Deficiencies are identified in 5-396 2012 corridor study. | 5 | North | 48.9477 | 2.8246 | 13.3846 | 8.0769 | 4.0154 | 0 | 2.1077 | 3.5385 | 34 |  | 15
Y | 5 | KIPDA ADD | IP20130038 | 5-80004 |  | A | FOUR RIGHT TURNING LANES AT THE INTERSECTION OF KY 55X AND KY 43 AND TWO LEFT TURNING LANES FROM KY 55X ONTO KY 43.(18CCN) | SAFETY(P) | Shelby | 106-KY-0055X -000 | 1.097 | 1.419 | 0.322 | Improve Intersection | 26 |  |  |  | 150000 | 2019 | 22000 | 2019 | 22000 | 2019 | 500000 | 2020 | 2018-07-10 08:18 | Improve safety and mobility of vehicles at the intersection of KY 55X and KY 43 northeast of Shelbyville. | The following needs have been identified at the intersection of KY 55X and KY 43 in Shelbyville.: 1) Improve Roadway Safety. 2) Reduce Intersection Congestion. 3) Increase Capacity for all vehicle types. | KIPDA ADD | North | 28.9246 | 4.3323 | 13.9385 | 2.5154 | 0 | 0 | 3.4308 | 4.7077 | 29
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130128 |  |  |  | Improve safety and reduce congestion at the I-71/KY 53 (North/South First Avenue) interchange. Includes consideration of an additional two-way left turn lane and bike/ped accommodations. | Reconstruction | Oldham | 093-I -0071 -000 | 21.328 | 22.328 | 1 | Interchange Safety Improvements | 35 | Y | 0 |  | 1000000 |  | 500000 |  | 800000 |  | 7500000 |  | 2018-12-20 11:01 | The purpose of this project is to improve safety and reduce congestion at the I-71/KY 53 (North/South First Avenue) interchange. | This project is needed because the current I-71/KY 53 (North/South First Avenue) interchange is inadequate to meet current and future capacity demands. This interchange operates at a low level of service and fails in the AM and PM peaks. | 5 | North | 40.7377 | 9.0646 | 8.8615 | 9.3346 | 1.1231 | 0 | 4.8462 | 7.5077 | 41
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130129 |  |  |  | Improve safety and reduce congestion on KY 44 between the I-65 interchange and the KY 61 intersection. Consider access management, pedestrian facilities and grade separated rail crossing. | Congestion Management | Bullitt | 015-KY-0044 -000 | 12.215 | 12.94 | 0.725 | Access Consolidation | 25 |  | 0 |  | 600000 |  | 4000000 |  | 1000000 |  | 5945000 |  | 2017-05-04 15:17 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | Louisville MPO | North | 42.2092 | 5.6615 | 13.5231 | 12.9231 | 0 | 0 | 3.8615 | 6.24 | 42
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130130 |  |  |  | Reduce congestion and improve safety along I-264 from I-64 to the KY 3082 (Bank Street) interchange. Project design will evaluate the addition of one travel lane in each direction. | Congestion Management | Jefferson | 056-I -0264 -000 | 0 | 0.333 | 0.333 | Major Interchange Reconstruction | 32 | Y | 0 |  | 1750000 |  | 200000 |  | 300000 |  | 7000000 |  | 2019-02-07 15:14 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | The Purpose of the I-264 and I-64 interchange widening and reconstruction is to address the capacity deficiencies and operational issues that currently characterize the existing corridor and provide increased efficiency and safety for the traveling public
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130131 |  |  |  | Improve safety and and address geometric deficiencies at the intersection of KY 1450 and KY 1526 east of the I-65/KY 1526 interchange. | Safety-Haz-Elm | Bullitt | 015-KY-1450 -000 | 1.795 | 1.995 | 0.2 | Improve Intersection | 26 |  | 0 |  | 1000000 |  | 400000 |  | 300000 |  | 5000000 |  | 2013-09-17 14:20 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified at the KY 1450 and KY 1526 intersection as a result of significant commercial and residential growth in the Brooks, KY area: 1) Improve Capacity, 2) Provide an improved highway that meets current safety design stan
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130132 |  |  |  | Improve safety, access, and address geometric deficiencies along KY 362 from the Oldham/Shelby County line to KY 146 (in and south of Pewee Valley). Includes consideration of a 3 lane widening with a two way left turn lane and bike/ped accommodations. | Safety-Haz-Elm | Oldham | 093-KY-0362 -000 | 0.975 | 3.039 | 2.064 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1365000 |  | 1000000 |  | 420000 |  | 7350000 |  | 2018-12-20 11:14 | The purpose of this project is to improve safety, access, and address geometric deficiencies along KY 362 from the Oldham/Shelby County line to KY 146 (in and south of Pewee Valley). | This project is needed because of a high crash rate, substandard curves, lane widths, and shoulders along KY 362 from the Oldham/Shelby County line to KY 146 (in and south of Pewee Valley). A new corridor (Old Henry Road) will eventually tie into this se
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130133 |  |  |  | Improve safety, access, and address geometric deficiencies along KY 1408 (Floydsburg Road) from Old Floydsburg Road to KY 146 (in and near Crestwood). Includes consideration of a three lane widening with a two way left turn lane. | Safety-Haz-Elm | Oldham | 093-KY-1408 -000 | 2.036 | 3.132 | 1.096 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 300000 |  | 500000 |  | 3500000 |  | 2013-09-17 14:30 | The purpose of this project is to improve safety, access, and address geometric deficiencies along KY 1408 (Floydsburg Road) from Old Floydsburg Road to KY 146 (in and near Pewee Valley). | This project is needed because of a high crash rate, substandard grades, curves, lane widths, and shoulders along KY 1408 (Floydsburg Road) from Old Floydsburg Road to KY 146 (in and near Pewee Valley).
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130134 |  |  |  | Reduce congestion and improve safety on KY 2049 (Crums Lane) from I-264 underpass to US 31W. Includes consideration of pedestrian facilities, consider bike lane, provide access management and safety improvements from I-264 underpass to US 31W. | Congestion Management | Jefferson | 056-KY-2049 -000 | 0.516 | 1.72 | 1.204 | Install Two-way Left Turn Lane | 28 |  | 200000 |  | 750000 |  | 1000000 |  | 1200000 |  | 6020000 |  | 2017-05-04 16:28 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | Route is an unimproved two lane local urban arterial road with deficient roadway geometrics not meeting current roadway design standards resulting in higher than average crash rates. Issues include insufficient lane and shoulder widths, deficient vertica | Louisville MPO | North | 53.5692 | 5.6615 | 12.8769 | 11.7231 | 3.5846 | 8.7077 | 2.6462 | 8.3692 | 54
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130135 | 5-555 |  | A | REDUCE CONGESTION AND IMPROVE SAFETY ALONG KY-1747 (HURSTBOURNE PARKWAY) FROM STONY BROOK DRIVE TO I-64. | CONGESTION MITIGTN(O) | Jefferson | 056-KY-1747 -000 | 10.5 | 11.995 | 1.495 | Modernize Roadway-Urban | 16 | Y | 250000 | 2019 | [9 empty] | Reduce congestion and improve safety along KY 1747 (Hurstbourne Parkway) from Stony Brook Drive to I-64. | The Critical Rate Factor (CRF) for this section from 2012 to 2016 ranges from 3.18 to 5.01. | 5 | North | 81.1046 | 8.6892 | 14.8615 | 14.7692 | 0 | 0 | 4.4462 | 8.3385 | 51 | 15 | 15
Y | 5 | KIPDA ADD | IP20130144 |  |  |  | Address geometric deficiencies along KY 44 near Breashers Creek Road in Taylorsville. | Reconstruction | Spencer | 108-KY-0044 -000 | 10.217 | 10.315 | 0.098 | Maintenance Improvement | 10 |  | 0 |  | 45000 |  | 32000 |  | 21000 |  | 275000 |  | 2015-07-07 15:12 | Address geometric deficiencies along KY 44 near Breashers Creek Road in Taylorsville. | Rehabilitate bridge approaches (10800045R & 10800045L) over Brashears Creek. The approaches were built on shale material which has settled. | 5 | North | 2.3385 | 1.6923 | 0 | 0.64615 | 0 | 0 | 0 | 0 | 2
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130146 |  |  |  | Improve safety and address geometric deficiencies along KY 44 near Old Pitts Point Road (in and west of Shepherdsville).(ID#015B00020N) | Safety-Haz-Elm | Bullitt | 015-KY-0044 -000 | 10 | 10.25 | 0.25 | Modernize Roadway-Urban | 16 |  | 0 |  | 800000 |  | 1710000 |  | 590000 |  | 5000000 |  | 2019-02-17 11:13 | Improve safety and address geometric deficiencies along KY 44 near Old Pitts Point Road (in and west of Shepherdsville). | Rehabilitate bridge and approaches on ID#015B00020N on KY 44 over Bullitt Lick Creek in Bullitt County in order to maintain the bridge for safety. Bridge was originally constructed in 1938, and approaches, due to erosion from the creek, need to be recons | 5 | North | 27.46 | 3.7969 | 4.1538 | 2.0077 | 2.5692 | 7.5692 | 2.3231 | 5.04 | 28
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20140002 |  |  |  | Reduce congestion, improve safety, and provide mobility for all users along KY 1932 (Breckenridge Lane) from Hikes Lane to Kresge Way (Hikes Point to DuPont). Project design will evaluate addition of one travel lane in each direction and consider bicycle, | Congestion Management | Jefferson | 056-KY-1932 -000 | 2.695 | 4.25 | 1.555 | Modernize Roadway-Urban | 16 |  | 250000 |  | 2500000 |  | 1000000 |  | 1000000 |  | 22000000 |  | 2019-02-06 13:16 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | Route is an unimproved two lane local urban arterial road with deficient roadway geometrics not meeting current roadway design standards resulting in higher than average crash rates. Issues include insufficient lane and shoulder widths, deficient vertica
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20140033 |  |  |  | Reduce congestion and improve safety along KY 2050 (Herr Lane) from KY 1447 (Westport Road) to KY 22 (Brownsboro Road). Project will evaluate 3-lane widening and consider accommodations for bicyclists and pedestrians. | Minor Widening | Jefferson | 056-KY-2050 -000 | 1.03 | 2.18 | 1.15 | Modernize Roadway-Urban | 16 |  | 200000 |  | 440000 |  | 690000 |  | 920000 |  | 3030000 |  | 2019-02-07 11:17 | The purpose of this project is to reduce congestion and improve safety along KY 2050 (Herr Lane) from KY 1447 (Westport Road) to KY 22 (Brownsboro Road). | The Herr Lane project corridor is a two-lane, 1.15 mile-long, high-traffic section of road in an area of eastern Jefferson County that is almost totally developed. Average daily traffic (ADT) volumes on Herr Lane range from 11,300 to 13,800 vehicles per d | 5 | North | 41.3046 | 8.5662 | 11.3538 | 9.6923 | 1.5231 | 0 | 2.6923 | 7.4769 | 41
Y | 5 | KIPDA ADD | IP20140038 | 5-2035.40 / 5-2035.41 |  | A | WIDEN I-64 TO 6 LANES FROM KY-395 TO KY-151. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) | MAJOR WIDENING(O) | Shelby | 106-I -0064 -000 | 43.332 | 46.303 | 2.971 | Add Lane to Full Control Facility | 25 | Y |  |  |  |  | 200000 | 2021 | 200000 | 2021 | 98000000 | 2023 | 2018-07-10 08:18 | WIDEN I-64 TO 6 LANES FROM KY-395 TO KY-151. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) Shelby MP 43.330 to MP 46.303 Franklin MP 46.303 to MP 47.000 5-2035.40 | This route serves as a major connector linking Louisville, Frankfort, and Lexington. The V/SF rating indicates and increasing capacity problems. The truck percentage shows the importance of this east and west interstate to freight movement. Address cur | 5 | Statewide | 57.9234 | 14.2907 | 7.489 | 9.3502 | 1.8062 | 7.9295 | 5.9471 | 11.1106
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150031 | 5-556 |  | I | IMPROVE SAFETY AND REDUCE CONGESTION ON I-71 FROM ZORN AVE TO I-264. (SEE ITEM NO. 5-557) | MAJOR WIDENING(O) | Jefferson | 056-I -0071 -000 | 2 | 5 | 3 | Add Lane to Full Control Facility | 25 | Y |  |  | 2000000 | 2023 | [6 empty] | 2018-07-10 08:17 | Improve safety and reduce congestion on I-71 from Zorn Ave to I-264 (Watterson Expressway). | This project is needed because of a higher than average injury crash rate, inadequate current and future capacity, and roadway deficiencies on I-71 from Zorn Avenue to I-264 (Watterson Expressway). The percent of injury crashes cited in the March 2014 I- | 5 | Statewide | 69.0973 | 17.9736 | 13.3921 | 10.7874 | 9.1189 | 2.2247 | 3.8767 | 11.724
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150032 | 5-557 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON I-71 FROM ZORN AVENUE TO I-265. | MAJOR WIDENING(O) | Jefferson | 056-I -0071 -000 | 1.724 | 9 | 7.276 | Add Lane to Full Control Facility | 25 | Y | 2000000 | 2019 | 0 | 2022 | [6 empty] | 2019-01-08 10:30 | Improve safety and reduce congestion on I-71 from I-264 (Watterson Expressway) to I-265 (Gene Snyder Freeway). | This project is needed because of inadequate current and future capacity and roadway deficiencies on I-71 from I-264 (Watterson Expressway) to I-265 (Gene Snyder Freeway). The critical crash rate factor (CCRF) in this segment of I-71 is 0.950 as cited in | 5 | Statewide | 78.8753 | 18.2731 | 13.5683 | 13.2654 | 9.1189 | 2.4449 | 9.0308 | 13.1738
Y | 5 | KIPDA ADD | IP20150049 |  |  |  | Address safety and geometric issues on KY 574 just east of US 421 in Campbellsburg to Turner Station | Spot Improvement | Henry | 052-KY-0574 -000 | 0.5 | 3.4 | 2.9 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 1260000 |  | 400000 |  | 2600000 |  | 2015-03-24 14:45 | Address safety and geometric issues on KY 574 just east of US 421 in Campbellsburg to Turner Station. | This project is needed because of substandard geometrics of three curves on KY 574 between Campbellsburg and Turner Station. These substandard curves create potential safety hazards.
Y | 5 | KIPDA ADD | IP20150050 |  |  |  | Address safety and corridor improvements on KY 36 just east of School Hollow Road to Carroll County Line. | Reconstruction | Trimble | 112-KY-0036 -000 | 0.25 | 2.2 | 1.95 | Modernize Roadway-Rural | 26 |  | 0 |  | 790000 |  | 490000 |  | 780000 |  | 3930000 |  | 2015-07-08 10:38 | Address safety and corridor improvements on KY 36 just east of School Hollow Road to Carroll County Line. | The need is to bring geometric roadway deficiencies up to current design standards. | KIPDA ADD | North | 29.9046 | 1.4585 | 9.1846 | 4.0615 | 1.4769 | 6.8923 | 0 | 6.8308 | 30
Y | 5 | KIPDA ADD | IP20150051 | 5-552 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON I-71 FROM KY-53 TO KY-153. | MAJOR WIDENING(O) | Henry | 052-I -0071 -000 | 24.727 | 28 | 3.273 | Add Lane to Full Control Facility | 25 | Y |  |  | 5600000 | 2023 | [6 empty] | 2018-07-10 08:17 | Improve safety and reduce congestion on I-71 from KY 53 in Oldham County to KY 153 in Henry County. | This project is needed because of a higher than average crash rate compared to similar roadway segments and a large amount of truck traffic on I-71 from KY 53 in Oldham County to KY 153 in Henry County. The percent of injury crashes along this section of | KIPDA ADD | Statewide | 59.4748 | 15.6476 | 5.9031 | 7.12 | 1.8062 | 7.0705 | 8.2379 | 13.6896
Y | 5 | KIPDA ADD | IP20150052 |  |  |  | Address safety and geometric issues on KY 44 at Junction KY 1251 to curve after Hunter's Trace Road. | Spot Improvement | Spencer | 108-KY-0044 -000 | 5.6 | 6.2 | 0.6 | Modernize Roadway-Rural | 26 |  | 0 |  | 420000 |  | 180000 |  | 300000 |  | 1950000 |  | 2017-03-22 09:52 | Address safety and geometric issues on KY 44 at Junction KY 1251 to curve after Hunter's Trace Road. This will provide an adequate transportation system between the Cities of Mt. Washington and Taylorsville for schools, commuters, emergency services, and | The need for this segment of KY 44 includes sharp curves, inadequate sight distance, and poor intersection geometry. | KIPDA ADD | North | 32.7892 | 3.2185 | 12 | 3.9923 | 4.8154 | 0 | 2.5231 | 6.24 | 33
Y | 5 | KIPDA ADD | IP20150054 |  |  |  | Improve safety at the intersection of KY 155 and KY 3192/Hochstrasser Road. | Spot Improvement | Spencer | 108-KY-0155 -000 | 2.4 | 2.6 | 0.2 | Improve Intersection | 26 |  | 0 |  | 230000 |  | 50000 |  | 120000 |  | 1050000 |  | 2015-07-07 15:14 | Improve safety at the intersection of KY 55 and KY 3192/Hochstrasser Road. | Reduce crashes at the intersection of KY 55 and KY 3192/Hochstrasser Road. | KIPDA ADD | North | 31.0308 | 6.9292 | 12.5538 | 3.4154 | 0 | 0 | 3.0923 | 5.04 | 31
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150080 | 5-558 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON I-265 FROM US-31E (BARDSTOWN RD) TO KY-155 (TAYLORSVILLE RD). | MAJOR WIDENING(O) | Jefferson | 056-I -0265 -000 | 17.3 | 23.1 | 5.8 | Add Lane to Full Control Facility | 25 | Y |  |  | 7500000 | 2023 | [6 empty] | 2018-07-10 08:17 | Improve safety and reduce congestion on I-265 (Gene Snyder Freeway) from US 31E (Bardstown Rd) to KY 155 (Taylorsville Road). | This project is needed because of deficient ramps and inadequate capacity on I-265 (Gene Snyder Freeway) from US 31E (Bardstown Road) to KY 155 (Taylorsville Road). The I-265 Study completed in January of 2015 cites an existing LOS D along this section i | 5 | Statewide | 66.927 | 19.1189 | 11.1013 | 11.0683 | 4.4053 | 0 | 6.9163 | 14.3169
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150095 |  |  |  | Improve safety and reduce congestion on I-265 from KY 155 (Taylorsville Rd) to KY 3084 (Old Henry Rd). | Major Widening | Jefferson | 056-I -0265 -000 | 23.1 | 28.78 | 5.68 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 7000000 |  | 2030000 |  | 2000000 |  | 70000000 |  | 2019-02-07 10:15 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | According to the I-265 Study from January of 2015 the projected 2020 AM and PM peak LOS is E and F along this section. The same study projects a 2040 LOS E and majority F in this segment. The rear end crash rate along part of this section exceeds the aver
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150099 |  |  |  | Improve safety and reduce congestion on I-265 from KY 3084 (Old Henry Rd) to KY 1447 (Westport Rd). | Major Widening | Jefferson | 056-I -0265 -000 | 28.78 | 32.5 | 3.72 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 4500000 |  | 1500000 |  | 400000 |  | 45000000 |  | 2019-02-07 10:50 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | According to the I-265 Study from January of 2015 this segment has a projected 2040 LOS F in the AM and PM peaks. Within the vicinity of the study area of I-265 (I-65 to the new east end bridge) or along the mainline there are over 40 projects identified
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150116 |  |  |  | Improve safety and reduce congestion on I-265 from KY 1447 (Westport Rd) to I-71. | Major Widening | Jefferson | 056-I -0265 -000 | 32.5 | 34.727 | 2.227 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 2500000 |  | 780000 |  | 250000 |  | 25000000 |  | 2019-02-07 10:53 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | The I-265 Study completed in January of 2015 cites an existing LOS D along a portion of this section with a 2040 projected minimum LOS E and F in the AM and PM peaks. The projected 2040 V/C Ratio from the study ranges from 0.844 to 1.395. The Crash Rate a
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150139 | 5-80000 |  | A | EASTWOOD FISHERSVILLE CONNECTOR TO I-64 (18CCN) | NEW INTERCHANGE(O) | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 750000 | 2018 | [9 empty] | Reduce congestion and improve connectivity to I-64 in eastern Jefferson County between I-265 (Gene Snyder Freeway) in Jefferson County to KY 1848 (Buck Creek Road) in Shelby County. | This project is needed because in light of existing and anticipated growth, local and regional access via the interstate system and local roadway network is needed due to their being a distance of 9 miles between access to I-64 from I-265 (Gene Snyder Fre | 5 | North | 33.9446 | 8.7446 | 4.4769 | 5.5846 | 1 | 9.5077 | 4.6308 | 0 | 34
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150154 | 5-347.51 |  | A | NEW TURN LANES IN FRONT OF BULLITT EAST HIGH SCHOOL. (BREAKOUT FROM 347.50) (18CCN) | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 23.6 | 23.7 | 0.1 | Modernize Roadway-Rural | 26 |  |  |  | 520000 | 2019 | 120000 | 2020 | 590000 | 2021 | 680000 | 2022 | 2019-03-07 16:47 | Improve capacity, relieve congestion, and improve safety along KY 44 from US 31E (Bardstown Road) to Parkland Trace/Winning Colors Drive. | This project is needed because of existing delays especially during AM peak periods near the KY 44/US 31E intersection and Bullitt East High School/Old Mill Elementary School and a high crash rate from US 31E (Bardstown Road) to Parkland Trace/Winning Col | 5 | North | 62.98 | 5.4338 | 12.2769 | 10.2231 | 2.5692 | 8.0615 | 3.2 | 6.2154 | 48 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150157 | 5-80053 / 5-80053.10 / 5-8703 |  | A | RESURFACE, STREETSCAPE, PEDESTRIAN BUMP-OUTS AND OTHER TRAFFIC IMPROVEMENTS ON EAST MARKET STREET FROM BAXTER TO BROOK STREET, BETWEEN NUCLEUS UL URBAN RESEARCH PARK AND HOME OF THE INNOCENTS.(12CCN) | BIKE/PED FACIL(O) | Jefferson | 056-US-0031E -001 | 16.635 | 17.669 | 1.034 | Bike and Pedestrian Improvements | 13 | Y |  |  | 0 | [5 empty] | 18800000 | 2017 | 2013-03-14 15:50 | Enhance the streetscape aesthetics of the corridor and improve the travel experience, accessibility, and safety for non-vehicular modes of travel on US 31E (East Market Street) from First Street to Johnson Street. | This project is needed to increase traffic and pedestrian/biking safety along US 31E (East Market Street) from First Street to Johnson Street. This project is in an urban location with numerous pedestrians/cyclists, bus usage, and on-street parking. All | Louisville MPO | North | 38.1377 | 3.2185 | 0 | 11.7808 | 4.4154 | 0 | 3.7231 | 0 | 23 |  | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150201 | 5-150.50 |  | A | SECTION 5 - FROM US-31EX TO US-31E BYPASS. (2008BOPC). | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 22.8 | 23.25 | 0.45 | Major Widening-Urban Streets | 25 |  |  |  | 0 | 2019 | 1550000 | 2024 | 550000 | 2024 | 2460000 | 2025 | 2018-07-10 08:18 | The purpose of the KY 44 project is to reduce congestion, improve safety and provide for better emergency vehicle access. | The 3/2012 DES (5-150.01 in Attachments) for the KY 44 corridor cited a CRF of 2.3 for this segment and projected a 2030 V/C of 1.73 and a LOS of F in the No-Build Alternative. This project would provide improved connectivity between the cities of Mt. Was | 5 | North | 83.61 | 9.4523 | 13.8 | 11.4808 | 0 | 9.4769 | 4.2308 | 5.1692 | 54 | 15 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150213 | 5-8810 |  | A | THREE LANE WIDENING ALONG KY-1931 FROM THE DOSS HIGH SCHOOL ENTRANCE TO PALATKA ROAD, INCLUDING INTERSECTION IMPROVEMENTS WITH PALATKA ROAD AND TURN LANES. (14CCN) | MINOR WIDENING(O) | Jefferson | 056-KY-1931 -000 | 4.65 | 5.52 | 0.87 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 2630000 | 2022 | 4160000 | 2022 | 3900000 | 2025 | 2018-09-21 10:02 | Improve safety and local traffic operations along KY 1931 (Saint Andrews Church Road) between Doss High School/Trunnell Elementary and KY 1142 (Palatka Road). | This project is needed because KY 1931 (Saint Andrews Church Road) between Doss High School/Trunnell Elementary and KY 1142 (Palatka Road) experiences frequent congestion during peak hours and needs significant improvements in safety and local traffic ope | 5 | North | 62.7077 | 7.4462 | 11.5385 | 8.3077 | 2.5692 | 9.2308 | 3.1385 | 5.4769 | 48 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150272 |  |  |  | IMPROVE MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(SAME AS 5-8612.00) | Minor Widening | Jefferson | 056-KY-2053 -000 | 1.501 | 2.688 | 1.187 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 400000 |  | 1500000 |  | 1300000 |  | 8200000 |  | 2017-02-16 08:11 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | KIPDA ADD | IP20150368 | 5-8822 |  | A | SCOPING/PLANNING STUDY FOR KY-389 IN HENRY COUNTY FROM KY-202 (DRENNON ROAD) NORTH TO HENRY COUNTY/CARROLL COUNTY LINE. (14CCN) | SCOPING STUDY(O) | Henry | 052-KY-0389 -000 | 13.16 | 21.791 | 8.631 | Transportation Studies | 0 |  | 250000 |  | 500000 | 2025 | 500000 | 2025 | 250000 | 2025 | 2000000 | 2025 | 2018-07-10 08:18 | Improve connectivity on KY 389 from KY 202 (Drennon Road) to the Henry County/Carroll County line. | This project is needed because the road slope on KY 389 from KY 202 (Drennon Road) to the Henry County/Carroll County line needs stabilized (slope failures due to erosion). Geotechnical investigations are needed to establish corrective approach and cost | KIPDA ADD | North | 7.94 | 0.20923 | 0 | 4.3615 | 3.3692 | 0 | 0 | 0 | 8
Y | 5 | Bluegrass ADD | IP20150402 | 5-2035.70 |  | A | WIDEN I-64 TO 6 LANES FROM KY-151 TO WEST OF THE KY-420 BRIDGE. (2004BOPC)(DESIGN FUNDED UNDER 5-2035.40)(16CCN) | MAJOR WIDENING(O) | Franklin | 037-I -0064 -000 | 47.7 | 53.75 | 6.05 | Add Lane to Full Control Facility | 25 | Y |  |  |  |  | 120000 | 2022 | 120000 | 2022 | 61000000 | 2024 | 2018-07-10 08:18 | Improve safety, truck mobility, and reduce congestion on I-64 from the KY 151 interchange (MP 47.70) to directly east of US 127 (MP 53.75). | Route serves as major connector linking Louisville, Frankfort and Lexington. High CRF indicates serious safety concerns. Congestion, along with high current and projected ADT (along with high current truck percentage) indicate future capacity problems. I- | 5 | Statewide | 64.5817 | 14.2555 | 9.8678 | 10.6883 | 1.8062 | 9.163 | 5.6828 | 13.118
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150414 | 5-8852 |  | A | DESIGN FOR IMPROVING KY-53 FROM ZHALE SMITH ROAD TO KY-22 (TOTAL 3.2 MILES). (14CCN)(18CCN) | DESIGN ENGINEERING(O) | Oldham | 093-KY-0053 -000 | 3.068 | 5.685 | 2.617 | Modernize & Widen Roadway-Rural | 26 |  |  |  | 2000000 | 2021 | 1700000 | 2025 | 700000 | 2025 | 35000000 | 2025 | 2018-07-10 08:18 | The purpose of this project is to improve safety and reduce congestion on KY 53 from Zhale Smith Road to KY 22. | This project is needed because continued development in this area and south along KY 53 from Zhale Smith Road to KY 22 will contribute to congestion issues in the future. This route is also highly traveled by local commuters to gain access to I-71 to the
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150415 |  |  |  | IMPROVEMENTS TO MT. WASHINGTON ROAD. (04CCN)(06CCR) | Minor Widening | Jefferson | 056-KY-2053 -000 | 0 | 2.688 | 2.688 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 0 |  | 4100000 |  | 3020000 |  | 9500000 |  | 2017-02-16 08:10 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | KIPDA ADD | IP20150477 |  |  |  | The purpose of this project is to address safety and improve traffic flow for operations improvements on KY 55 at Old Brunerstown Road. This project is to include a right turn lane on KY 55 that may include a traffic signalization. | Spot Improvement | Shelby | 106-KY-0055 -000 | 6.6 | 6.7 | 0.1 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 50000 |  | 100000 |  | 830000 |  | 2016-01-21 13:13 | The purpose of this project is to address safety and improve traffic flow for operations improvements on KY 55 at Old Brunerstown Road. This project will consider a right turn lane on KY 55 that may include a traffic signalization. | The following needs have been identified at the intersection of KY 55 and Old Brunerstown Road in Shelbyville: 1) Improve Roadway Safety. 2) Reduce Intersection Congestion. 3) Increase Capacity for all vehicle types. 4) Improve Freight Movement. | KIPDA ADD | North | 27.66 | 5.1446 | 9.9231 | 4.5462 | 0 | 0 | 4.4769 | 3.5692 | 28
Y | 5 | KIPDA ADD | IP20150478 |  |  |  | Address safety and improve traffic flow with consideration for adding a right turn lane southbound on KY 55 and US 60 intersection in Shelbyville. | Spot Improvement | Shelby | 106-KY-0055 -000 | 7.8 | 8 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 100000 |  | 160000 |  | 670000 |  | 2016-01-21 14:03 | Address safety and improve traffic flow with consideration for adding a right turn lane southbound on KY 55 and US 60 intersection in Shelbyville. | The following needs have been identified at the intersection of KY 55 and US 60 in Shelbyville: 1) Improve Roadway Safety. 2) Reduce Intersection Congestion. 3) Increase Capacity for all vehicle types. 4) Improve Freight Movement. | KIPDA ADD | North | 37.8692 | 3.8154 | 14.5385 | 11.2385 | 0 | 0 | 4.1231 | 4.1538 | 38
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160017 | 5-559 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-65/I-264 (WATTERSON EXPRESSWAY) INTERCHANGE. | RECONSTRUCTION(O) | Jefferson | 056-I -0065 -000 | 129.289 | 131.587 | 2.298 | Major Interchange Reconstruction | 32 | Y | 0 | 2019 | 3250000 | 2021 | [6 empty] | 2019-03-07 13:23 | Improve safety and reduce congestion at the I-65/I-264 (Watterson Expressway) interchange. | The I-65/I-264 interchange was ranked as the number one highest crash interchange in the KIPDA MPA area for Kentucky (Bullitt, Jefferson, and Oldham Counties). This analysis was based upon crash data for the years of 2009-2011. In that time period there | 5 | Statewide | 73.5047 | 19.7181 | 12.1586 | 14.2731 | 4.4053 | 0 | 9.4273 | 13.5223
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160018 |  |  |  | Improve safety, reduce congestion, and improve multi-modal transportation options along KY 61 from Commerce Crossings Dr (BMP 1.395) to Briden Avenue (EMP 8.400) including the I-264 (Watterson Expressway) and I-265 (Gene Snyder Freeway) interchanges. | Reconstruction | Jefferson | 056-KY-0061 -000 | 1.395 | 8.4 | 7.005 | Upgrade to Grade Separation | 40 |  | 400000 |  | 2000000 |  | 2000000 |  | 2000000 |  | 20000000 |  | 2019-01-02 13:56 | Improve safety, reduce congestion, and improve multi-modal transportation options along KY 61 from Commerce Crossings Dr. to Briden Avenue including the I-264 (Watterson Expressway) and I-265 (Gene Snyder Freeway) interchanges. | The KY 61 corridor from Commerce Crossings Drive to Briden Avenue had four roadway segments ranked in the top 41 of the highest roadway crash segments in the KIPDA MPO area for Kentucky (Bullitt, Jefferson, and Oldham Counties). This analysis was based u | 5 | North | 75.7992 | 7.0338 | 14.7231 | 14.8731 | 0 | 9.5077 | 4.6615 | 10 | 61 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160019 | 5-560 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-65/I-265 (GENE SNYDER FREEWAY) INTERCHANGE. | RECONSTRUCTION(O) | Jefferson | 056-I -0065 -000 | 124.7 | 125.7 | 1 | Innovative Interchange | 40 | Y | 400000 | 2021 | [9 empty] | The Purpose of the I-65/I-265 interchange project is to reduce congestion and improve safety. | The 2015 I-265 Programming Study has projected the I-265 westbound to I-65 northbound diverge as operating at a level of service (LOS) of F in both the AM and PM peaks in the year 2020. The study also identifies the I-65 to I-265 eastbound merge as opera | 5 | Statewide | 64.2539 | 17.0925 | 8.2819 | 12.2081 | 4.4053 | 0 | 9.6916 | 12.5743
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160046 | 5-804 |  | A | RECONSTRUCT/WIDEN I-264 (WATTERSON EXPRESSWAY) FROM WESTPORT ROAD (KY-1447) TO I-71, INCLUDING THE US-42 INTERCHANGE AS A SPUI.(PROJECT INCLUDES 5-594) (12CCR)(14CCR) | RECONSTRUCTION(O) | Jefferson | 056-I -0264 -000 | 20.9 | 22.6 | 1.7 | Innovative Interchange | 40 | Y |  |  | 3000000 |  | 5280000 | 2021 | 1270000 | 2021 | 53070000 | 2024 | 2019-02-25 13:15 | The purpose of the project is to improve system operation by reducing delays and congestion along Interstate 264 (Watterson Expressway) and the interchange at US 42. By reducing congestion and delay within the project limits the safety on US 42 and I-264 | The existing I-264/US 42 interchange does not have adequate capacity or storage to accommodate the left turn and through traffic volumes during the AM and PM peak hours. Commuters are experiencing long delays. These long delays are causing long queue le | 5 | Statewide | 60.6999 | 15.5419 | 6.9604 | 12.076 | 4.4053 | 6.2775 | 4.5374 | 10.9015
Y | 5 | KIPDA ADD | IP20160124 |  |  |  | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 44 FROM THE BULLIT/SPENCER COUNTY LINE (MP 0.00) TO OAK TREE WAY (MP 7.542). (2016BOP) | Safety-Haz-Elm | Spencer | 108-KY-0044 -000 | 0 | 7.542 | 7.542 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 14:00
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160192 | 5-483.10 |  | A | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY-329 (MP 14.1) TO KY-393 (MP 18.0). (16CCN) | MAJOR WIDENING(O) | Oldham | 093-I -0071 -000 | 14.1 | 18 | 3.9 | Add Lane to Full Control Facility | 25 | Y |  |  | 3500000 | 2019 | 1900000 | 2022 | 1700000 | 2022 | 34000000 | 2024 | 2018-07-10 08:18 | The Purpose of the I-71 widening and reconstruction is to address the capacity deficiencies and operational issues that currently characterize the existing corridor and provide increased efficiency and safety for the traveling public. It will serve throug | The Needs being addressed by the proposed I-71 project are based on the following facts: • Increasing traffic volumes have resulted in traffic congestion and poor traffic flow characteristics. In 2009, the Average Daily Traffic was near 56,600 vehicles | Central Office | Statewide | 72.1945 | 16.9339 | 11.2775 | 10.5396 | 4.4053 | 7.467 | 7.533 | 14.0381
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160193 | 5-483.20 |  | A | WIDEN I-71 FROM FOUR TO SIX LANES FROM KY-393 (MP 18.0) TO KY-53 (MP 22.4). (16CCN) | MAJOR WIDENING(O) | Oldham | 093-I -0071 -000 | 18 | 22.4 | 4.4 | Add Lane to Full Control Facility | 25 | Y |  |  | 11000000 | 2023 | 4600000 | 2025 | 2000000 | 2025 | 80000000 | 2025 | 2018-07-10 08:18 | The Purpose of the I-71 widening and reconstruction is to address the capacity deficiencies and operational issues that currently characterize the existing corridor and provide increased efficiency and safety for the traveling public. It will serve throug | The Needs being addressed by the proposed I-71 project are based on the following facts: • Increasing traffic volumes have resulted in traffic congestion and poor traffic flow characteristics. In 2009, the Average Daily Traffic was approximately 56,600 | Central Office | Statewide | 71.1775 | 15.6476 | 10.0441 | 10.3414 | 4.4053 | 7.6211 | 8.8987 | 14.2193
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160194 |  |  |  | DESIGN AND CONSTRUCT A NEW NORTH/SOUTH PARK ACCESS ROAD AND TRAIL ON THE EAST SIDE OF THE LAKE TRAVERSING THE QUAIL CHASE GOLF COURSE FROM MOUNT WASHINGTON ROAD TO THE END OF SECTION 1. (2014BOP) | New Route | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 7005000 |  | 2016-12-15 11:16 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160205 |  |  |  | RECONSTRUCT KY-44 AT BOGARD/LLOYD LANE. (06CCN) (10CCR)(12CCR)(16CCR) | Safety-Haz-Elm | Bullitt | 015-KY-0044 -000 | 18.38 | 18.8 | 0.42 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 1280000 |  | 2016-12-15 10:57 | The purpose of this project is to improve: 1) Safety, 2) Reliability, and 3) Mobility. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160216 |  |  |  | Improve safety and reduce congestion on KY 61 at Plaza Park Boulevard. | Safety-Haz-Elm | Bullitt | 015-KY-0061 -000 | 1.8 | 2.2 | 0.4 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 220000 |  | 2017-03-14 11:25 | The purpose of this project is to improve: 1) Safety, 2) Reliability, and 3) Mobility. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160219 |  |  |  | ACCESS MANAGEMENT PROJECT TO RELOCATE LOVE'S ACCESS ROAD ON KY 480 IN BULLITT COUNTY TO ADDRESS CONGESTION SAFETY PROBLEMS (2014BOP FROM 5-391.20). | Safety-Haz-Elm | Bullitt | 015-KY-0480 -000 | 1.1 | 1.455 | 0.355 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-11-01 12:38 | The purpose of this project is to improve: 1) Safety, 2) Reliability, and 3) Mobility. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160276 | 5-367.20 | 2020-07-15 | A | EXTENSION OF OLD HENRY ROAD EAST TO ASH AVENUE (KY362). (12CCR)(18CCN) | NEW ROUTE(O) | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 1990000 |  | 18900000 | 2021 | 2019-03-01 13:58 | The purpose of this project is to provide improved access to the I-265/Old Henry Road (KY 3084) interchange for vehicles traveling from Oldham County, Shelby County, and far eastern Jefferson County. | This project is needed because vehicles are using a residential street, Village Green Boulevard, to access Old Henry Road and the interchange. Roadway deficiencies include 10' lanes, 1' shoulders, and substandard geometrics. | 5 | North | 41.9292 | 6.9908 | 0 | 6.3231 | 1.5231 | 8.8 | 3.2923 | 0 | 27 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160278 |  |  |  | CONSTRUCT A NEW EXTENSION ROAD FROM SOUTH FOURTH STREET TO WARNOCK AS PER AGREEMENT WITH THE UNIVERSITY OF LOUISVILLE FOUNDATION AND KYTC.(12CCN) | New Route | Jefferson | 056-US-0060A -000 | 3.409 | 3.848 | 0.439 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-11-17 13:36 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170047 |  |  |  | Improve safety and reduce congestion at the I-71/I-264 (Watterson Expressway) interchange. | Reconstruction | Jefferson | 056-I -0071 -000 | 4 | 6.2 | 2.2 | Transportation Studies | 0 | Y | 250000 |  | 5000000 |  | 2000000 |  | 2000000 |  | 60000000 |  | 2017-03-13 14:58 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170048 |  |  |  | IMPROVEMENTS TO INTERSTATE LIGHTING AT THE I-65/I-264 INTERCHANGE MP 129.8 TO MP 131.3. | Safety-Haz-Elm | Jefferson | 056-I -0065 -000 | 129.8 | 131.3 | 1.5 | Maintenance Improvement | 10 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 1382714 |  | 2019-02-05 13:48 | The purpose of this project is to improve: 1) Safety | The following needs have been identified for this project: 1) Improve Roadway Safety 2) rehabilitation of KYTC assets. | 5 | North | 30.3792 | 9.9754 | 0 | 14.3423 | 1.1231 | 0 | 4.9385 | 0 | 30
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170049 |  |  |  | IMPROVEMENTS TO INTERSTATE LIGHTING AT THE I-65/I-265 INTERCHANGE MP 124.5 TO MP 125.5. | Safety-Haz-Elm | Jefferson | 056-I -0065 -000 | 124.5 | 125.5 | 1 | Maintenance Improvement | 10 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 712922 |  | 2019-02-05 14:00 | The purpose of this project is to improve: 1) Safety. | The following needs have been identified for this project: 1) Improve Roadway Safety 2) rehabilitation of KYTC assets. | 5 | North | 26.5969 | 9.1508 | 0 | 11.3538 | 1.1231 | 0 | 4.9692 | 0 | 27
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170064 | 5-550 |  | A | WIDEN I-65 FROM 6 TO 8 LANES FROM KY-61 (PRESTON HIGHWAY) IN LEBANON JUNCTION TO I-265 (GENE SNYDER FREEWAY) | MAJOR WIDENING(O) | Bullitt | 015-I -0065 -000 | 104.788 | 123.18 | 18.392 | Add Lane to Full Control Facility | 25 | Y | 0 | 2020 | 7470000 | 2022 | [6 empty] | 2018-07-10 08:17 | Reduce congestion and improve mobility on I-65 from KY 61 (Preston Highway) in Lebanon Junction (Bullitt County) to I-265 (Gene Snyder Freeway) in Jefferson County. | This project is needed because the capacity of of I-65 from KY 61 (Preston Highway) in Lebanon Junction (Bullitt County) to I-265 (Gene Snyder Freeway) in Jefferson County is inadequate to meet current and future traffic volumes, resulting in congestion | Louisville MPO | Statewide | 79.7192 | 17.4449 | 12.3348 | 13.5297 | 1.8062 | 10 | 9.6035 | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170065 |  |  |  | Reconstruct and widen US 31 E from 2 to 5 lanes in Bullitt County beginning with the widening of the Salt River Bridge to 4 lanes to the existing 5 lane section at KY 44 in Mount Washington (District 5 section) | Reconstruction | Bullitt | 015-US-0031E -000 | 0.236 | 3.538 | 3.302 | Modernize Roadway-Rural | 26 |  | 0 |  | 2270000 |  | 100000 |  | 1110000 |  | 15600000 |  | 2017-05-04 15:13 | The purpose of this project is to substantially increase system capacity and traffic service with consideration of improved roadway geometry and additional travel lanes between project termini. | The portion of US 31E does not meet current design criteria for a roadway carrying the existing traffic volume or posted speed limit. Horizontal and vertical curves impede sight distance and the shoulder and ditch widths allow no margin of error for the t | Louisville MPO | North | 41.6369 | 5.76 | 6.8769 | 8.0769 | 1.4462 | 7.8462 | 2.8308 | 8.8 | 42
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170066 |  |  |  | Reconstruct KY 44 from US 31 W (Dixie Highway) to KY 61 (Preston Highway)in Shepherdsville. Project design will consider 3 lane section with two way left turn lane. | Reconstruction | Bullitt | 015-KY-0044 -000 | 0 | 12.215 | 12.215 | Modernize Roadway-Rural | 26 |  | 0 |  | 9600000 |  | 8550000 |  | 6100000 |  | 81000000 |  | 2017-05-04 15:22 | Reconstruct KY 44 from US 31 W (Dixie Highway) to KY 61 (Preston Highway) in Shepherdsville | Route is an unimproved two lane country road with deficient roadway geometrics not meeting current roadway design standards resulting in higher than average crash rates. Issues include insufficient lane and shoulder widths, deficient vertical and horizon | Louisville MPO | North | 48.1631 | 3.8708 | 10.8462 | 12.9692 | 4.1692 | 6.4923 | 0 | 9.8154 | 48
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170067 |  |  |  | Extend 12th Street from Hill Street to Industry Road | New Route | Jefferson | 056-CS-1034F -000 | 1.783 | 1.881 | 0.098 | Local Roadway Improvements | 3 |  | 0 |  | 700000 |  | 875000 |  | 1400000 |  | 6900000 |  | 2017-05-15 15:34 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | Louisville MPO | North | 8.1985 | 0.16 | 0 | 6.5308 | 1.5077 | 0 | 0 | 0 | 8
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170069 |  |  |  | Extend Cardinal Boulevard to the west of 4th Street, across the railroad tracks at grade to connect to Davies Avenue and 7th Street | New Route | Jefferson | 056-CS-1477F -000 | 0 | 0.357 | 0.357 | Construct Road in New Location | 0 |  | 0 |  | 1520000 |  | 760000 |  | 760000 |  | 7600000 |  | 2017-05-04 15:40 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | Louisville MPO | North | 27.6708 | 3.3477 | 2.2154 | 11.6308 | 2.5692 | 7.9077 | 0 | 0 | 28
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170070 |  |  |  | Address congestion and safety issues in the vicinity of the Breckenridge Lane (KY 1932) and Dutchmans Lane Intersection. Project will consider lane additions to Breckenridge Lane south of Dutchmans Lane; Dutchmans Parkway Lane west of Breckenridge lane; D | Reconstruction | Jefferson | 056-KY-1932 -000 | 3.7 | 3.9 | 0.2 | Improve Intersection | 26 |  | 0 |  | 330000 |  | 300000 |  | 400000 |  | 2250000 |  | 2017-05-04 15:45 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | Louisville MPO | North | 58.2215 | 7.2369 | 13.8923 | 13.0615 | 0 | 0 | 4.4154 | 4.6154 | 43 |  | 15
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170071 |  |  |  | Reconstruct the intersection of Hill Street and 7th Street to provide left turn lanes. | Reconstruction | Jefferson | 056-CS-1011F -000 | 0.558 | 0.758 | 0.2 | Improve Intersection | 26 |  | 0 |  | 480000 |  | 240000 |  | 240000 |  | 2400000 |  | 2017-05-04 15:54 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | Louisville MPO | North | 42.8554 | 9.1323 | 14.4923 | 12.5538 | 2.5692 | 0 | 4.1077 | 0 | 43
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170073 |  |  |  | Reconstruct Ferndale Road as a 2 lane road (no additional lanes) | Reconstruction | Jefferson | 056-CR-1021H -000 | 0.119 | 1.358 | 1.239 | Modernize Roadway-Rural | 26 |  | 0 |  | 450000 |  | 300000 |  | 600000 |  | 3000000 |  | 2017-05-04 15:51 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | Louisville MPO | North | 26.2508 | 4.72 | 7.4769 | 3.9462 | 3.7692 | 6.3385 | 0 | 0 | 26
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170092 |  |  |  | Improve safety, reduce congestion, and improve modal options on 4th Street between the Park Hill Industrial Corridor and I-65 and I-264. | Reconstruction | Jefferson | 056-CS-1001F -000 | 2.977 | 3.587 | 0.61 | Local Roadway Improvements | 3 |  | 0 |  | 500000 |  | 856243 |  | 721400 |  | 2821217 |  | 2017-07-06 14:33 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors. | The following needs have been identified for this project: 1) Improve Capacity, 2) Provide an improved highway that meets current safety design standards, 3) Enhance network connections, 4) Serve recent and planned growth.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170096 | 5-80003 |  | A | EXTEND PLANTSIDE DRIVE FROM REHL ROAD TO TAYLORSVILLE ROAD(18CCN) | NEW ROUTE(O) | Jefferson | 056-KY-0155 -000 | 6.279 | 8.247 | 1.968 | Construct Road in New Location | 0 | Y |  |  | 750000 | 2020 | [6 empty] | 2018-07-10 08:18 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Mobility within designated freight corridors by extending existing Plantside Drive to connect with Taylorsville Road. This p | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | General Assembly | North | 31.7057 | 8.6972 | 0 | 8.4977 | 2.2171 | 8.8991 | 3.3945 | 0 | 32
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20180008 |  |  |  | Third Street Road (KY 907) -James Hill Road Interim Curve Improvement. Short Term Drainage, Signage and Pavement Marking Improvements. | Spot Improvement | Jefferson | 056-KY-0907 -000 | 2.8 | 3 | 0.2 | Maintenance Improvement | 10 |  | 0 |  | 30000 |  | 30000 |  | 30000 |  | 175000 |  | 2019-01-31 10:29 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types, 3) correct limited sight distances, 4) correct insufficient drainage.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20180043 | 5-80001 |  | A | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD.(18CCN) | MAJOR WIDENING(O) | Jefferson | 056-US-0060 -000 | 11.093 | 11.684 | 0.591 | Major Widening-Urban Streets | 25 | Y |  |  | 1260000 | 2019 | 550000 | 2021 | 720000 | 2022 | 1500000 | 2023 | 2018-07-10 08:18 | WIDEN US-60 TO 6 LANES FROM OLD SHELBYVILLE RD. TO NORTH ENGLISH STATION RD. (SPP) | The following needs have been identified for this project: 1) Improve Capacity, 2) Provide an improved highway that meets current safety design standards, 3) Enhance network connections, 4) Serve recent and planned growth.
Y | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20180044 |  |  |  | IMPROVE THE INTERCHANGE OF I-71 AND KY 329 | Spot Improvement | Oldham | 093-KY-0329 -000 | 6.89 | 6.994 | 0.104 | Innovative Interchange | 40 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-12-06 09:43 | The purpose of this project is to improve: 1) Safety, 2) Reliability, and 3) Mobility. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types. | General Assembly | North | 24.2783 | 9.0031 | 3.5321 | 2.5688 | 1.5291 | 0 | 3.3945 | 4.2508 | 24
Y | 5 | KIPDA ADD | IP20190078 |  |  |  | Improve safety and reduce congestion at the I-65/ KY-1526 (Brooks Hill Road - John Harper Highway) interchange including improvements to KY-1526 from KY-1020 (Coral Ridge Road) to KY-1450 (Blue Lick Road). I-65 MP 121.20 to MP 122.00. | Reconstruction | Bullitt | 015-I -0065 -000 | 121.2 | 122 | 0.8
Y | 5 | KIPDA ADD | IP20190080 |  |  |  | Reconstruct KY 22 at Avenue of the Woods and Chatsworth Lane. MP 1.16 to MP 1.30. | Spot Improvement | Jefferson | 056-KY-0022 -000 | 1.16 | 1.3 | 0.14
Y | 5 | KIPDA ADD | IP20190081 |  |  |  | Reconstruct intersection of KY 22 at Barbour Lane. MP 1.94 to MP 2.34. | Spot Improvement | Jefferson | 056-KY-0022 -000 | 1.94 | 2.34 | 0.4
Y | 5 | KIPDA ADD | IP20190082 |  |  |  | Reconstruct KY 22/KY 146 from Pryor Avenue to KY 329B - 3 lane section with center turn lane. From MP 3.500 to MP 3.929. | Reconstruction | Oldham | 093-KY-0022 -000 | 3.5 | 3.929 | 0.429 | Improve Railroad Crossing | 55 |  | 0 |  | 1000000 |  | 4200000 |  | 2500000 |  | 8800000 |  | 2019-03-13 16:49 | Reconstruct KY 22/KY 146 from Pryor Avenue to KY 329B - 3 lane section with center turn lane. From MP 3.500 to MP 3.929. | Improve capacity, provide an improved highway that meets current safety design standards, enhance network connections, implement a long term regional priority and serve recent and planned growth. Complete build out of parent project 5-304.00.
Y | 5 | KIPDA ADD | IP20190083 |  |  |  | Section 2 - Chimney Rock Drive to CE Smith Road. MP 15.1 to MP 17.5. | Reconstruction | Bullitt | 015-KY-0044 -000 | 15.1 | 17.5 | 2.4
Y | 5 | KIPDA ADD | IP20190085 |  |  |  | Section 3 - CE Smith Road to Armstrong Lane. MP 17.5 to MP 21.0. | Reconstruction | Bullitt | 015-KY-0044 -000 | 17.5 | 21 | 3.5
Y | 5 | KIPDA ADD | IP20190087 |  |  |  | Improve capacity, relieve congestion, and improve safety along KY 44 from KY 1319 (Kings Church Road) to the Spencer County Line. MP 25.278 to MP 26.286. | Reconstruction | Bullitt | 015-KY-0044 -000 | 25.278 | 26.286 | 1.008
Y | 5 | KIPDA ADD | IP20190089 |  |  |  | Improve safety and reduce congestion on KY 61 from KY 44 in Shepherdville to KY 245. Project will evaluate widening from 2 to 4 travel lanes and consider other lower impact alternatives. Design will also consider accommodations for bicyclists, pedestria | Reconstruction | Bullitt | 015-KY-0061 -000 | 9.42 | 14.5 | 5.08
Y | 5 | KIPDA ADD | IP20190090 |  |  |  | Improve safety and reduce congestion on KY 61 from KY 245 to Plaza Park Blvd in Lebanon Junction. Project will evaluate widening from 2 to 4 travel lanes and consider other lower impact alternatives. Design will also consider accommodations for bicyclis | Reconstruction | Bullitt | 015-KY-0061 -000 | 1.97 | 9.42 | 7.45
Y | 5 | KIPDA ADD | IP20190116 |  |  |  | Install auto gates at Norfolk Southern Railroad crossing (CS-1023F). MP 1.95 to MP 1.97. 28TH STREET | Safety-Haz-Elm | Jefferson | 056-CS-1023F -000 | 1.95 | 1.97 | 0.02
Y | 5 | KIPDA ADD | IP20190117 |  |  |  | Install auto gates at Norfolk Southern Railroad crossing (CS-1184F). MP 0.35 to MP 0.37. CATALPA STREET | Safety-Haz-Elm | Jefferson | 056-CS-1184F -000 | 0.35 | 0.37 | 0.02
Y | 5 | KIPDA ADD | IP20190118 |  |  |  | Install auto gates at Norfolk Southern Railroad crossing (CS-1012F). MP 1.36 to MP 1.39. HALE AVE. | Safety-Haz-Elm | Jefferson | 056-CS-1012F -000 | 1.36 | 1.39 | 0.03
Y | 5 | KIPDA ADD | IP20190119 |  |  |  | Construct a railroad safety crossing, improve lighting, erect signals, and roadway crossings between Cardinal Boulevard (CS-1477F) MP 0.00 to MP 0.02 and Hill Street (CS-1016F). | Safety-Haz-Elm | Jefferson | 056-CS-1477F -000 | 0 | 0.02 | 0.02
Y | 5 | KIPDA ADD | IP20190131 | 5-80006 |  | A | CONSTRUCT NEW INTERCHANGE ON KY-841 AT THE RENAISSANCE SOUTH BUSINESS PARK(18CCN) | SPOT IMPROVEMENTS(O) | Jefferson | 056-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 | [9 empty] | 14070000 | 2021 |  | Relieve negative congestion and safety impacts to the existing transportation infrastructure surrounding the Renaissance South Business Park by improving access and upgrading facilities to current design and safety standards. Supplement future success of | Congestion and freight delays along Outer Loop, I-65 and Gene Snyder freeway in the vicinity of and accessing Louisville International Airport, Ford's Louisville Assembly Plant and Renaissance South Business Park (UPS). Limited freight access to Renaissa
Y | 5 | KIPDA ADD | IP20190132 |  |  |  | Improve intersection, signalize and correct sight distance problem at KY 1065 (Beulah Church Road) and Fern Creek Road. MP 11.30 to MP 11.50 | Spot Improvement | Jefferson | 056-KY-1065 -000 | 11.3 | 11.5 | 0.2
Y | 5 | KIPDA ADD | IP20190135 |  |  |  | Improve safety, access, and mobility for all modes along KY 1065 (Outer Loop) from KY 1865 (New Cut Road) to KY 1020 (National Turnpike). Project will consider 5-lane widening and accommodations for bicyclists and pedestrians. MP 1.00 to MP 2.53. | Major Widening | Jefferson | 056-KY-1065 -000 | 1 | 2.53 | 1.53
Y | 5 | KIPDA ADD | IP20190136 |  |  |  | Improve safety, access, and mobility for all modes along KY 1142 (Palatka Road) from KY 1931 (Saint Andrews Church Road) to KY 907 (3rd Street Road). Project will consider 3-lane widening with two-way center turn lane and accommodations for bicyclists and | Minor Widening | Jefferson | 056-KY-1142 -000 | 0 | 1.736 | 1.736
Y | 5 | KIPDA ADD | IP20190137 |  |  |  | Reduce congestion and improve safety on Westport Road at the Herr Lane and Washburn Road intersections. MP 1.965 to MP 2.574. | Spot Improvement | Jefferson | 056-KY-1447 -000 | 1.965 | 2.574 | 0.609
Y | 5 | KIPDA ADD | IP20190139 |  |  |  | BULLITT COUNTY SECTION - Implementation of a truck parking information management system using existing ITS technology on I-65 to help truckers more quickly and reliably identify accurate and up-to-date information about the availability of safe truck par | Congestion Management | Bullitt | 015-I -0065 -000 | 103.308 | 123.18 | 19.872
Y | 5 | KIPDA ADD | IP20190140 |  |  |  | JEFFERSON COUNTY SECTION - Implementation of a truck parking information management system using existing ITS technology on I-65 to help truckers more quickly and reliably identify accurate and up-to-date information about the availability of safe truck p | Congestion Management | Jefferson | 056-I -0065 -000 | 123.18 | 137.318 | 14.138
Y | 5 | KIPDA ADD | IP20190141 |  |  |  | Clean and paint the US 31 (George Rogers Clark) Bridge over the Ohio River between Louisville and Jeffersonville. (This structure is 100% owned and maintained by Kentucky.) MP 0.000 to MP 1.222 5-110.00 | Reconstruction | Jefferson | 056-US-0031 -000 | 0 | 1.222 | 1.222
Y | 5 | Bluegrass ADD | IP20190142 | 5-2035.40 / 5-2035.41 |  | A | WIDEN I-64 TO 6 LANES FROM KY-395 TO KY-151. (2004BOPC)(DESIGN FUNDING COVERS 5-2035.70 SECTION ALSO) | MAJOR WIDENING(O) | Franklin | 037-I -0064 -000 | 46.303 | 47.7 | 1.397 | [7 empty] | 200000 | 2021 | 200000 | 2021 | 98000000 | 2023 | 2018-07-10 08:18
Y | 5 | Bluegrass ADD | IP20190143 |  |  |  | Improve safety and level of service on US 421 (Bald Knob Hill) from the end of existing improvements approx. 0.9 miles north of US 127 to KY 12 in Franklin County. MP 5.39 to MP 7.30 5-374.00 | Reconstruction | Franklin | 037-US-0421 -000 | 5.39 | 7.3 | 1.91 | Modernize Roadway-Rural | 26 |  | 0 |  | 680000 |  | 2440000 |  | 1350000 |  | 13620000 |  | 2019-03-13 11:14 | Improve safety and level of service on US 421 (Bald Knob Hill) from the end of existing improvements approx. 0.9 miles north of US 127 to KY 12 in Franklin County. MP 5.39 to MP 7.30 5-374.00 | The need established for this project was to address safety concerns and geometric deficiencies for the purpose of reducing crashes along this corridor. Any improvements should also enhance interregional mobility and economic development with US-421 bei
Y | 5 | Bluegrass ADD | IP20190167 |  |  |  | Interim improvements to address capacity and safety at the I-64/US-60 Interchange. Project will evaluate additional left turn lane storage in both directions for vehicles entering I-64 from US-60. | Minor Widening | Franklin | 037-US-0060 -000 | 13.2 | 13.45 | 0.25 | Improve Intersection | 26 |  | 0 |  | 84000 |  | 30000 |  | 750000 |  | 840000 |  | 2019-03-13 16:25 | Interim improvements to address capacity and safety at the I-64/US-60 Interchange. Project will evaluate additional left turn lane storage in both directions for vehicles entering I-64 from US-60. | Address high left turn volumes accessing I64 leads to queue spillbacks that disrupt movements at adjacent signalized intersections. 129 crashes in three years. 2 high CCRF segments and 4 high CCRF spots.
Y | 5 | KIPDA ADD | IP20190174 | 5-80002 |  | A | NEW INTERCHANGE ON I-64E EAST OF THE GENE SNYDER FREEWAY(18CCN) | NEW INTERCHANGE(O) | Jefferson | 056-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 |  | 650000 | 2021 | [9 empty] | NEW INTERCHANGE ON I-64E EAST OF THE GENE SNYDER FREEWAY(18CCN) 5-80002.00 | Project Goals and Issues The Project Team developed the following project goals: 1) Congestion Mitigation 2) Connectivity of the Road and Interstate Network 3) Future Planning 4) Safety Improvements 5) Environmental Preservation 6) Proactive and Jo
Y | 6 | Northern Kentucky ADD | IP20000017 |  |  |  | Improve travel reliability by addressing safety and geometric deficiencies along KY 20 from Petersburg to Taylor Creek. | Relocation | Boone | 008-KY-0020 -000 | 6.606 | 7.563 | 0.957 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 1300000 |  | 500000 |  | 8000000 |  | 2015-02-21 21:11 |  | improves safety and traffic flow
Y | 6 | Northern Kentucky ADD | IP20000018 |  |  |  | Improve safety and mobility along KY 20 (Petersburg Road) from Graves Road to KY 237 (North Bend Road). | Major Widening | Boone | 008-KY-0020 -000 | 14.525 | 16.62 | 2.095 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 2000000 |  | 1000000 |  | 16800000 |  | 2017-02-09 09:00 |  | improves safety | 6 | North | 58.9415 | 3.7723 | 9.7385 | 9.0462 | 3.1846 | 6.7385 | 2.2615 | 9.2 | 44 | 15
Y | 6 | Northern Kentucky ADD | IP20000019 |  |  |  | Improve safety and reduce congestion along US 27 from KY 9 (AA Highway) to Murnan Road; include multi-modes. | Major Widening | Campbell | 019-US-0027 -000 | 13.573 | 14.912 | 1.339 | Other Improvement Types | 0 | Y | 0 |  | 750000 |  | 5000000 |  | 750000 |  | 11000000 |  | 2010-02-25 16:51 |  | relieve congestion and improve traffic flow
Y | 6 | Northern Kentucky ADD | IP20000020 |  |  |  | RECONSTRUCT US 27 from Cannon Ridge to Highland Ave | Reconstruction | Campbell | 019-US-0027 -000 | 19.25 | 20 | 0.75 | Other Improvement Types | 0 | Y | 0 |  | 250000 |  | 500000 |  | 250000 |  | 3500000 |  | 2016-04-07 11:09 |  | improve safety
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20000021 |  |  |  | Improve safety & mobility, and address geometric deficiencies along KY 915 from KY 9 (AA Hwy.) to KY 2924. | Reconstruction | Campbell | 019-KY-0915 -000 | 5.982 | 9.286 | 3.304 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 5000000 |  | 2000000 |  | 25000000 |  | 2015-02-14 13:17 | TBD | Safety improvements needed to support growth of large residential subdivisions. KY 915 has sharp curves and little or no shoulders. Roadway improvements would increase safety and mobility. | 6 | North | 35.2285 | 0.91692 | 7.0154 | 7.7885 | 4.3077 | 5.4462 | 0 | 9.7538 | 35
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20000023 |  |  |  | Improve safety along US 25 (Dixie Hwy) from the Grant County line to the Boone County line. | Minor Widening | Kenton | 059-US-0025 -000 | 0 | 4.978 | 4.978 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 8000000 |  | 3000000 |  | 25000000 |  | 2017-05-05 13:38 | TBD | U.S. 25 (Boone to Grant county lines). Reconstruct and widen to create 3-lanes. Include purchase of right of way for future trail. This was a low priority recommendation in the Kenton County Transportation Plan (OKI, June 2014). per email correspodence | Cincinnati/Northern Kentucky MPO | North | 33.1092 | 3.5323 | 9.2769 | 8.9308 | 2.5385 | 0 | 0 | 8.8308 | 33
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20000024 |  |  |  | Improve Safety and reduce congestion along KY 16 (Taylor Mill Rd) from KY 2047 (Senour Rd) to KY 536 (Harris Pike); include multi-modal needs. | Major Widening | Kenton | 059-KY-0016 -000 | 5.537 | 9.269 | 3.732 | Modernize Roadway-Rural | 26 |  | 0 |  | 4500000 |  | 8000000 |  | 2000000 |  | 30000000 |  | 2017-05-04 11:16 | TBD | Improve multi-modal transportation options, mobility and north/south connectivity. Continue improvements on recently reconstructed KY 16. Traffic data shows a mixture of AM and PM peak congestion along a short segment with multiple, closely-set inters | Cincinnati/Northern Kentucky MPO | North | 64.68 | 6.4492 | 8.7231 | 11.1692 | 3.2923 | 7.6 | 2.6615 | 9.7846 | 50 | 15
Y | 6 | Buffalo Trace ADD | IP20000025 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 617 (Piqua-Kentontown Rd) from US 62 TO KY 1476 (Thomas Pike). | Minor Widening | Robertson | 101-KY-0617 -000 | 0 | 1.032 | 1.032 | Other Improvement Types | 0 |  | 0 |  | 1250000 |  | 1000000 |  | 750000 |  | 7000000 |  | 2014-02-25 10:05 | The project addresses the goal of safety and efficiently moving goods and services through the BTADD region. | KY 617 is narrow and windy. Geometric deficiencies need to be corrected to improve safety.
Y | 6 | Northern Kentucky ADD | IP20040017 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 42 from the western city limit of Ghent to the Gallatin County line. | Minor Widening | Carroll | 021-US-0042 -000 | 13.2 | 16.5 | 3.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3000000 |  | 2000000 |  | 24000000 |  | 2015-02-06 15:29 | Improve safety and mobility and address geometric deficiencies along US 42 from the western city limit of Ghent to the Gallatin County line. Continuation of 6-8002.10 (Widen US 42 from Four Mile Road to west Ghent city limit). | There is 5 billion dollars worth of investment in the US-42 corridor in Carroll county and it could expand. Roads are the single most important issue to local businesses. 5000 jobs are available to local residents. 2 plants are currently looking to loc | 6 | North | 68.8385 | 4.8308 | 5.7231 | 6.6692 | 1.5231 | 6.7692 | 3.9385 | 9.3846 | 39 | 15 | 15
Y | 6 | Bluegrass ADD | IP20050007 |  |  |  | RECONSTRUCTION FROM SCOTT C\L TO KY 1842 AT CONNERSVILLE | Reconstruction | Harrison | 049-KY-0032 -000 | 0 | 2.821 | 2.821 | Other Improvement Types | 0 |  | 0 |  | 3500000 |  | 1500000 |  | 750000 |  | 18000000 |  | 2010-02-25 16:51 | The reconstruction from Scott C\L to KY 1842 at Connersville due to known safety concerns. | Safety issues are the concern for this corridor. Narrow 9' lanes with little or no shoulder leave no room for error. High CRF indicates serious safety concerns. KY 32 connects Harrison County to Sadieville in Scott County, thereby providing alternate I-75
Y | 6 | Northern Kentucky ADD | IP20050008 |  |  |  | RECONSTRUCTION FROM KY 159 TO KY 539 IN BRACKEN CO. | Reconstruction | Pendleton | 096-KY-0022 -000 | 11.696 | 19.237 | 7.541 | Modernize Roadway-Rural | 26 |  | 0 |  | 7000000 |  | 4000000 |  | 3000000 |  | 62000000 |  | 2014-05-02 15:33 | RECONSTRUCTION FROM KY 159 TO KY 539 IN BRACKEN CO BY BRINGING THE ROAD UP TO CURRENT GEOMETRIC STANDARDS | The purpose of this project is increase connectivity of the center of Pendleton county to the west and Bracken County. CRF (1.31)may be high and IRI (144) may be high.
Y | 6 | Northern Kentucky ADD | IP20050040 |  |  |  | Construct and extend from KY-36 south to Cherry Grove Cross Rd (Eibeck Ln) in Williamstown. | New Route | Grant | 041-KY-2943 -000 | 0 | 0.563 | 0.563 | Construct Road in New Location | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 750000 |  | 6000000 |  | 2014-05-02 12:54 | Construct and extend from KY-36 south to Cherry Grove Cross Rd (Eibeck Ln) in Williamstown. | To promote the safe and efficient movement of people, goods, and services throughout Northern Kentucky
Y | 6 | Northern Kentucky ADD | IP20050041 |  |  |  | Provide connectivity and improved mobility from KY 36 to KY 1560 (Barnes Road) west of I-75. | New Route | Grant | 041-I -0075 -000 | 154.8 | 155.8 | 1 | Construct Road in New Location | 0 | Y | 0 |  | 1500000 |  | 3000000 |  | 500000 |  | 9000000 |  | 2015-02-05 10:17 | Provide connectivity and improved mobility from KY 36 to KY 1560 (Barnes Road) west of I-75. | Growth is anticipated with the proposed construction of a theme park. The new route would assist with traffic management by providing local access to (2) I-75 interchanges. Further, it could provide additional economic growth opportunities for ancilliar
Y | 6 | Northern Kentucky ADD | IP20050042 |  |  |  | New route from US-27 to Ky-539 near the Licking River Fork Bridge in Bracken County | New Route | Pendleton | 096-US-0027 -000 | 6.9 | 10.285 | 3.385 | Construct Road in New Location | 0 |  | 0 |  | 6000000 |  | 4000000 |  | 2500000 |  | 62000000 |  | 2011-02-28 11:59
Y | 6 | Buffalo Trace ADD | IP20070207 |  |  |  | Major Widening from KY 1109 in Bracken County to KY 159 in Pendleton County | Major Widening | Bracken | 012-KY-0009 -000 | 13.59 | 19.857 | 6.267 | Other Improvement Types | 0 | Y | 0 |  | 7000000 |  | 3500000 |  | 1500000 |  | 56000000 |  | 2010-10-26 11:17 | Improve safety and mobility | The purpose of this project is increase ease of travel and possible widen a major thouroughfare in Bracken County. This is a major road and better connectivity will benefit all surrounding counties. This route is highly traveled by semi-truck and passen
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20070209 |  |  |  | Address safety and mobility along KY 1072 (Highland Pike/Kyles Lane) from KY 17 (Madison Pike) to Interstate 71/75 northbound on and off ramps. | Reconstruction | Kenton | 059-KY-1072 -000 | 0.731 | 2.58 | 1.849 | Modernize Roadway-Rural | 26 |  | 0 |  | 840000 |  | 7200000 |  | 1000000 |  | 5600000 |  | 2017-06-27 08:57 | TBD | Improve safety and congestion along KY 1072 (Highland Pike/Kyles Lane) from KY 17 to I-75. | Cincinnati/Northern Kentucky MPO | North | 44.6646 | 5.8338 | 14.9538 | 12.8769 | 0 | 0 | 4.0154 | 6.9846 | 45
Y | 6 | Northern Kentucky ADD | IP20070210 |  |  |  | AA HIGHWAY - MAJOR WIDENING TO 4 LANES FROM KY 154 IN PENDLETONKY @*@*O CO. TO 4 LANE SECTION IN CAMPBELL CO. SEE ALTERNATE 3, PRIORITY SECTION 2 IN SEPTEMBER 2002 KY 9 WIDENING STUDY. | Major Widening | Pendleton | 096-KY-0009 -000 | 2.833 | 4.339 | 1.506 | Modernize Roadway-Rural | 26 | Y | 0 |  | 2250000 |  | 2000000 |  | 750000 |  | 15000000 |  | 2016-08-24 13:41 | MAJOR WIDENING OF KY 9 TO 4 LANES FROM KY 154 IN PENDLETONKY @*@*O CO. TO 4 LANE SECTION IN CAMPBELL CO. TO PROVIDE ADDITION THROUGH CAPACITY | The purpose of this project is increase ease of travel and possible widen a major thouroughfare in Pendleton County. This is a major road and better connectivity will benefit all surrounding counties.
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20080271 |  |  |  | Improve safety and reduce congestion along US 42 from KY 237 to KY 842 | Major Widening | Boone | 008-US-0042 -000 | 12.602 | 13.502 | 0.9 | Other Improvement Types | 0 | Y | 0 |  | 2000000 |  | 8000000 |  | 1500000 |  | 20000000 |  | 2010-10-26 10:33 | TBD | The roadway has extreme congestion and significant growth is expected along and south of this corridor. ADT in the area reaches a maximum of 34,900 vpd on four, 12' lanes with 2' shoulders. A composite rating of 31.05 indicates that nearly 95.91% of th
Y | 6 | Northern Kentucky ADD | IP20080273 | 6-444 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-236 (DONALDSON ROAD) FROM KY-842 (HOUSTON ROAD) TO KY-3076 (MINEOLA PIKE). (18CCR)(DESIGN INCLUDES ITEM # 6-445) | MAJOR WIDENING(O) | Boone | 008-KY-0236 -000 | 0 | 1.594 | 1.594 | Modernize Roadway-Rural | 26 |  | 2000000 | 2019 | 0 | 2020 | 6000000 | 2023 | 500000 | 2025 | 18000000 | 2025 | 2019-01-29 08:36 |  | This portion of KY236 from Cherry Tree lane (Kenton County line) to KY3076 (Mineola Pike) is a two lane road which provides local access to the Cincinnati International Airport, business parks, residences and a high school. Poor pavement conditions (IRI | 6 | North | 80.1323 | 5.5323 | 12.9692 | 10.9385 | 1.5231 | 8.5538 | 4.0308 | 6.5846 | 50 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20080274 |  |  |  | Inactive | Major Widening | Boone | 008-KY-0842 -000 | 4.9 | 5.2 | 0.3 | Improve Intersection | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 1000000 |  | 5000000 |  | 2017-04-26 14:32 |  | The intersection of KY 18 and KY 842 experiences long delays and congestion contributing to a high accident rate (CRF=1.93). This is among the busiest intersections in Northern Kentucky with nearly 7000 vehices during the peak hour. During the PM peak h | Cincinnati/Northern Kentucky MPO | North | 38.3085 | 8.2277 | 11.5846 | 9.3115 | 0 | 0 | 3.9231 | 5.2615 | 38
Y | 6 | Northern Kentucky ADD | IP20080275 |  |  |  | Improve safety & mobility, and address geometric deficiencies along KY 3060 (Frogtown Rd.) from US 42 to US 25 (Dixie Hwy); include multi-modes. | Major Widening | Boone | 008-KY-3060 -000 | 0 | 2.726 | 2.726 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 10000000 |  | 2000000 |  | 20000000 |  | 2017-06-02 14:05 |  | ADT in the area reaches a maximum of 6,052 vpd on two, 10' lanes with 3' shoulders. A composite rating as low as 43 indicates that nearly 72% of the statewide urban collectors are rated better. An IRI as high as 128 is contributing to a condition index | 6 | North | 65.3254 | 8.6831 | 8.4923 | 10.5346 | 3.6615 | 6.9846 | 3.0769 | 8.8923 | 50 | 15
Y | 6 | Northern Kentucky ADD | IP20080276 | 6-445 |  | A | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON KY-3076 (MINEOLA PIKE) FROM KY-236 TO I-275. (18CCR)(DESIGN CONDUCTED UNDER ITEM 3 6-444) | MAJOR WIDENING(O) | Boone | 008-KY-3076 -000 | 0 | 1.05 | 1.05 | Modernize Roadway-Rural | 26 |  |  |  | 1500000 | 2019 | 5000000 | 2022 | 750000 | 2023 | 15000000 | 2025 | 2019-01-29 08:38 |  | This route is anticipated to need upgrades due to the growth of industry in the areas around CVG. (DHL, Wayfair and Amazon) This route provides a direct access from CVG to I-275. | 6 | North | 66.7846 | 3.3846 | 6.0462 | 7.9385 | 1.5231 | 6.9538 | 3.0615 | 7.8769 | 37 | 15 | 15
Y | 6 | Buffalo Trace ADD | IP20080277 |  |  |  | Address the issue of congestion on KY 9 in Bracken County from KY 19 to KY 1109 by widening to four lanes | Major Widening | Bracken | 012-KY-0009 -000 | 5.546 | 13.59 | 8.044 | Other Improvement Types | 0 | Y | 0 |  | 8000000 |  | 3500000 |  | 1500000 |  | 80000000 |  | 2010-10-26 11:15 | Improve safety and mobility | The problem associated with KY9 is the congestion. KY9 in Bracken County is a major thoroughfare for people and goods and services to and from Northern KY at I-275. KY9 is on the NHS and Truck network. Ins widening study sponsored by the Cabinet, this
Y | 6 | Buffalo Trace ADD | IP20080279 |  |  |  | Improvements to KY 10 from Brooksville to Germantown to address the safety issue as well as the geometric deficiencies along the roadway | Relocation | Bracken | 012-KY-0010 -000 | 14.298 | 20.67 | 6.372 | Other Improvement Types | 0 |  | 0 |  | 6000000 |  | 4000000 |  | 2000000 |  | 38000000 |  | 2010-02-25 16:51 | Improve safety and mobility | This is a road with curves in agricultural areas of the counties with many points of potential sight distance problems with intersections and farm equipment. The route has high CRF and needs to be evaluated. There is a study for the reconstruction or re
Y | 6 | Buffalo Trace ADD | IP20080280 |  |  |  | Realign several large curves in succession on KY 10 from MP 16.51 to 17.20 to address safety concerns and sight distance issues. (Spot Improvement B from 2004 Programming Study) | Spot Improvement | Bracken | 012-KY-0010 -000 | 16.4 | 17.1 | 0.7 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 750000 |  | 500000 |  | 4000000 |  | 2010-02-25 16:51 | To improve safety and mobility | Upon the completion of the May 2004 Programming Study, (Six-Year Plan Item No. 06-8100.00/09-8103.00) recommendations were made by QK4. The project team developed project goals for the study that included 1) Improve safety by reducing the number of crash
Y | 6 | Buffalo Trace ADD | IP20080281 |  |  |  | Realign 90-degree curve from MP 17.5 to 19.0 on KY 10. (Spot Improvement C from 2004 Programming Study) | Spot Improvement | Bracken | 012-KY-0010 -000 | 17.5 | 19 | 1.5 | Other Improvement Types | 0 |  | 0 |  | 320000 |  | 130000 |  | 60000 |  | 5480000 |  | 2014-02-03 15:51 | To improve safety and mobility | Spot Improvement C from the 2004 Programming Study by QK4. Realign 90-degree curve and high crash spot location from approx MP 17.50 (1,640 feet east of Doyle Road) to MP 19.09 (1,300 feet west of Hillsdale Road), approx 1.32 miles. Total cost estimate
Y | 6 | Buffalo Trace ADD | IP20080282 |  |  |  | Improvements to the intersection of KY 10 and KY 19 to address sight distance problems | Reconstruction | Bracken | 012-KY-0010 -000 | 10.3 | 10.5 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 250000 |  | 75000 |  | 750000 |  | 2010-02-25 16:51 | To improve safety and mobility. | There is an obvious problem with sight distance at the intersection of KY 10 and KY 19 at Powerville. The sight problem is caused by trees and a curve. The CRF is at 2.32 which is more than double the rate of concern. No truck percentages were availabl
Y | 6 | Buffalo Trace ADD | IP20080283 |  |  |  | Reconstruct KY 19 from Locust Creek to KY 875 (Mount Zion Road) to address line of sight and curves | Reconstruction | Bracken | 012-KY-0019 -000 | 10.678 | 12.2 | 1.522 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 750000 |  | 400000 |  | 8000000 |  | 2014-02-05 15:29 | To improve safety and mobility | KY 19 provides a connection to the new "Pie Jett Highway" section of KY 19 that was newly constructed. The route improvements would allow for continuing with the previous improvements that would connect into Brooksville, the County seat. There is line o
Y | 6 | Buffalo Trace ADD | IP20080284 |  |  |  | Improvements to the intersection of KY 435 and KY 2370 near Augusta to address safety and sight distance concerns | Reconstruction | Bracken | 012-KY-0435 -000 | 6.46 | 6.66 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 500000 |  | 100000 |  | 750000 |  | 2010-02-25 16:51 | To improve safety and mobility. | There are no detailed statistics available for the Rural Minor Collector route, but the photos will represent the project as an alignment not square with the connecting route of KY 2370 near Augusta. The traffic count is not high, but the angle at which
Y | 6 | Buffalo Trace ADD | IP20080285 |  |  |  | Improve KY 539 from the Robertson C/L to KY 19 at Milford to address safety concerns on a narrow roadway | Minor Widening | Bracken | 012-KY-0539 -000 | 0 | 3.204 | 3.204 | Other Improvement Types | 0 |  | 0 |  | 2700000 |  | 1500000 |  | 800000 |  | 27000000 |  | 2014-02-06 12:51 | To improve safety and mobility | The route is very narrow with 8' lanes and narrow or no shoulders. The traffic volume is low, but the route has significant safety deficiencies. Much of the route is along a hillside and guardrails are not in place at this time. There are no statistics
Y | 6 | Buffalo Trace ADD | IP20080286 |  |  |  | Improve KY 1019 from KY 10 to KY 9 to current standards | Reconstruction | Bracken | 012-KY-1019 -000 | 0 | 2.696 | 2.696 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 1400000 |  | 1000000 |  | 15000000 |  | 2014-02-06 15:07 | To improve safety and mobility | There are no statistics available for this route, but the photos represent this problem well. The majority of this route is one sharp curve after another. The pavement condition is not very good throughout the route either. This route needs a full reco
Y | 6 | Buffalo Trace ADD | IP20080288 |  |  |  | Improvements to KY 1159 by addressing the problem by adding a truck climbing lane | Reconstruction | Bracken | 012-KY-1159 -000 | 3.715 | 4.3 | 0.585 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 750000 |  | 250000 |  | 5000000 |  | 2010-02-25 16:51 | To improve safety and mobility | KY 1159 from the KY 9 intersection needs a truck climbing lane toward Brooksville. The route has a high CRF and needs improvement. The truck traffic is only 7%, but this affects many deliveries and automobiles with the slope.
Y | 6 | Northern Kentucky ADD | IP20080289 | 6-81 |  | A | REDUCE CONGESTION ALONG THE I-471 CORRIDOR FROM US-27 TO OHIO STATE LINE. | MAJOR WIDENING(O) | Campbell | 019-I -0471 -000 | 0 | 5 | 5 | Add Lane to Full Control Facility | 25 | Y | 4500000 | 2024 | [10 empty] | In 2012, ADT at the northern end of this project area near the Daniel Carter Beard Bridge was 119,849 vpd (with 12,212 trucks) on a maximum of six, 12' foot lanes with 10' shoulders. In 2013, ADT towards the southern end of this project area near the I-27 | Cincinnati/Northern Kentucky MPO | Statewide | 77.0355 | 18.185 | 5.1982 | 14.5374 | 7.2247 | 9.9559 | 8.37 | 13.5641
Y | 6 | Northern Kentucky ADD | IP20080292 |  |  |  | Improve safety, mobility and reliability along US 27 from KY 1892 to KY 1120, include multi-modes. | Reconstruction | Campbell | 019-US-0027 -000 | 21.209 | 21.463 | 0.254 | Modernize Roadway-Rural | 26 | Y | 0 |  | 2000000 |  | 1000000 |  | 2000000 |  | 15000000 |  | 2017-04-26 12:22 |  | This segment of KY 27 from KY 1892 (Carothers Rd) to KY 1120 (11th Street) in City of Newport includes very poor pavement condition (IRI=182) and a very high accident rate (CRF=6). Changes in vertical alignment as well as a RR overpass, contribute to th | Cincinnati/Northern Kentucky MPO | North | 45.9192 | 5.9385 | 7.7077 | 9.2885 | 4 | 9.0154 | 4.8615 | 5.1077 | 46
Y | 6 | Northern Kentucky ADD | IP20080293 |  |  |  | Improve safety & mobility, and address geometric deficiencies, slope stabilization and multi-modes along KY 6335 from Tower Hill Rd to KY 445 (River Rd.). | Reconstruction | Campbell | 019-KY-6335 -000 | 1.767 | 4.636 | 2.869 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 2000000 |  | 2000000 |  | 45000000 |  | 2016-04-07 10:57 |  | ADT in the area reaches a maximum of 1,729 vpd on two, 10' lanes with 1' shoulders. A composite rating of 34 indicates that nearly 94.57% of the statewide urban minor arterials are rated better. An IRI as high as 168 is contributing to a condition index
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20080294 |  |  |  | Improve safety, reduce congestion, increase multi-modal mobility for KY 8 from Riviera Drive Bellevue to Walnut Street in Dayton. Possible reversible lane option. | Reconstruction | Campbell | 019-KY-0008X -000 | 0.814 | 1.603 | 0.789 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 5000000 |  | 1000000 |  | 2500000 |  | 2010-02-25 16:51 | TBD | Improve travel safety, improve accessibility and mobility options for people and goods, enhance the integration and connectivity of the transportation system and support economic vitality. ADT in the area reaches a maximum of 31,374 vpd on two, 12' lan
Y | 6 | Northern Kentucky ADD | IP20080295 | 6-448 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION AT THE I-275 INTERCHANGE WITH KY-9 (AA HWY.) | CONGESTION MITIGTN(O) | Campbell | 019-KY-0009 -000 | 17.525 | 17.978 | 0.453 | Innovative Interchange | 40 | Y | 700000 | 2021 | [10 empty] | The I-275/KY 9 interchange needs to be reconstructed to improve the operational efficiency and increase safety. High volumes and poor pavement conditions conditions contribute to an intersection that operates at LOS F during peak hours. A major widenin | 6 | North | 35.4031 | 7.6185 | 4.8923 | 12.8769 | 0 | 0 | 4.6 | 5.4154 | 35
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20080296 |  |  |  | Improve mobility along KY 547 from KY 9 (AA Highway) to KY 10; include multi-modes. | Reconstruction | Campbell | 019-KY-0547 -000 | 0 | 1.75 | 1.75 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2500000 |  | 1000000 |  | 15500000 |  | 2017-02-20 15:24 | TBD | ADT in this area is 3004 vpd on a maximum of two, 9' foot lanes with 3' shoulders. A composite rating as low as 66.5 indicates that nearly 46.79% of the statewide urban principle arterials are rated better. An IRI as high as 121 is contributing to a con
Y | 6 | Northern Kentucky ADD | IP20080297 |  |  |  | Reconstruct Pooles Creek #1 (KY 1998) from AA Highway to US 27. | Reconstruction | Campbell | 019-KY-1998 -000 | 0 | 1.738 | 1.738 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 4000000 |  | 1750000 |  | 25000000 |  | 2017-02-14 11:24 |  | ADT in this area is 4000 vpd on a maximum of two, 10' foot lanes with 1' shoulders. A composite rating as low as 37 indicates that nearly 6.52% of the statewide urban principle arterials are rated better. An IRI as high as 245 is contributing to a condi
Y | 6 | Northern Kentucky ADD | IP20080298 |  |  |  | NEW INTERCHANGE AT KY 47 NEAR GALLATIN C\L | New Interchange | Carroll | 021-I -0071 -000 | 53.3 | 53.433 | 0.133 | Construct Road in New Location | 0 | Y | 5000000 |  | 3000000 |  | 4500000 |  | 1500000 |  | 26000000 |  | 2014-04-21 15:15 | NEW INTERCHANGE AT KY 47 NEAR GALLATIN C\L | Carroll and Gallatin counties could benefit greatly from a new interstate interchange near KY-47. There would be all the usual benefit of a county gaining more access to an interstate for commercial reasons. However, there are over 8 billion dollars wort
Y | 6 | Northern Kentucky ADD | IP20080299 |  |  |  | RECONSTRUCTION FROM Kentucky River Bridge TO KY 320 IN CARROLLTON CRF , IRI and v/sf may all be high. This section of road is a main transit route and has a potentially narrow bridge for truckers from US-42 traveling to KY-36 and into Indiana. | Reconstruction | Carroll | 021-US-0042 -000 | 6 | 6.8 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1500000 |  | 1500000 |  | 6000000 |  | 2014-04-21 14:41 | Modernize US 42 in Carrollton to help with local and heavy truck traffic leading to the bridge over the Kentucky River | CRF , IRI and v/sf may all be high. This section of road is a main transit route and has a potentially narrow bridge for truckers from US-42 traveling to KY-36 and into Indiana.
Y | 6 | Northern Kentucky ADD | IP20080300 |  |  |  | Improve drainage and mobility along US 42 from Donna Drive to the Kentucky River Bridge in Prestonville; include multi-modes. | Reconstruction | Carroll | 021-US-0042 -000 | 5.3 | 5.7 | 0.4 | Maintenance Improvement | 10 |  | 0 |  | 300000 |  | 300000 |  | 600000 |  | 2000000 |  | 2015-02-06 13:18 | Modernize roadway to Improve drainage and pedestrian safety and mobility along US 42 from Donna Drive to the Kentucky River Bridge in Prestonville. | CRF may be really high, IRI might be high. There has been a long standing water issue on this segment of road the the country has tried to address multiple times, but seems to be reoccurring. The site may be benefited by a complete overhaul on the area. | NORTHERN KENTUCKY ADD | North | 14.49 | 6.0246 | 0 | 4.05 | 1.5231 | 0 | 2.8923 | 0 | 14
Y | 6 | Northern Kentucky ADD | IP20080301 |  |  |  | RECONSTRUCTION FROM MILTON TO US 42 AT CARROLLTON to increase safety, ease travel and reduce travel times on ky-36 Industry uses this Ky-36. It runs along the Ohio River. It connects I-71 to Markland Dam and is a major thoroughfare to get to Casinos | Reconstruction | Carroll | 021-KY-0036 -000 | 0 | 8.132 | 8.132 | Modernize Roadway-Rural | 26 |  | 0 |  | 8000000 |  | 8500000 |  | 4000000 |  | 70000000 |  | 2010-02-25 16:51 | RECONSTRUCTION of KY 36 FROM MILTON TO US 42 AT CARROLLTON to increase safety, ease travel and reduce travel times by bringing deficiencies up to modern standards. | Industry uses this Ky-36. It runs along the Ohio River. It connects I-71 to Markland Dam and is a major thoroughfare to get to Casinos in Indiana. Trucks travel it to go from industry to interstate. It may be a curvy road that could benefit from strai
Y | 6 | Northern Kentucky ADD | IP20080302 |  |  |  | Improve safety and mobility and address geometric deficiencies at the intersection of KY 36 & KY 1492 (Locust Road). | Safety-Haz-Elm | Carroll | 021-KY-0036 -000 | 5.1 | 5.4 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 300000 |  | 200000 |  | 3000000 |  | 2015-02-06 13:29 | Improve safety and mobility and address geometric deficiencies at the intersection of KY 36 & KY 1492 (Locust Road). | he intersection of KY-1492 @ KY-36 is a steep intersection with fast moving traffic on KY-36. It may be difficult to turn off of KY-36 and merge onto KY-36 with the steep grade.
Y | 6 | Northern Kentucky ADD | IP20080303 |  |  |  | Improve safety, mobility, and geometric deficiencies on KY 36 from KY 227 to 0.1 mile east of Four Mile Road. | Spot Improvement | Carroll | 021-KY-0036 -000 | 8.998 | 13 | 4.002 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3500000 |  | 2000000 |  | 22000000 |  | 2018-12-20 13:55 | Improve safety and mobility and correct geometric deficiencies on KY 36 from KY 227 to 0.1 mile east of Four Mile Road. | RI and CRF may be high. The Judge Executive and local residents are concerned about the high amount of truck traffic. Road may be curvy and narrow for truck traffic. | NORTHERN KENTUCKY ADD | North | 17.9331 | 0.83692 | 6.0923 | 6.3577 | 4.6462 | 0 | 0 | 0 | 18
Y | 6 | Northern Kentucky ADD | IP20080304 |  |  |  | Reconstruct KY 47 from KY 184 to US 42 This road may be narrow and does get some truck traffic. | Relocation | Carroll | 021-KY-0047 -000 | 2.038 | 9.539 | 7.501 | Modernize Roadway-Rural | 26 |  | 0 |  | 8000000 |  | 3000000 |  | 1500000 |  | 60000000 |  | 2014-04-21 15:03 | Increase safety, ease of travel, and travel times on KY-47 in Carroll County by bringing deficiencies up to modern standards | This road may be narrow and does get some truck traffic.
Y | 6 | Northern Kentucky ADD | IP20080305 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 55 from KY 389 to US 42. | Minor Widening | Carroll | 021-KY-0055 -000 | 5.767 | 8.262 | 2.495 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2500000 |  | 1500000 |  | 18000000 |  | 2015-02-06 15:13 | Improve safety and mobility and address geometric deficiencies along KY 55 from KY 389 to US 42. | The IRI and CRF seem to be getting high. This section of road is the major artery of travel for Trimble/Carroll traffic. It is also a major artery when I-71 is closed or backed up.
Y | 6 | Northern Kentucky ADD | IP20080306 |  |  |  | RECONSTRUCTION FROM TRIMBLE C\L TO KY 389 IRI may be getting high. This section of road is the major artery of travel for Trimble/Carroll traffic. It is also a major artery when I-71 is closed or backed up. | Reconstruction | Carroll | 021-KY-0055 -000 | 0 | 5.767 | 5.767 | Modernize Roadway-Rural | 26 |  | 0 |  | 4500000 |  | 4500000 |  | 3000000 |  | 50000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on KY-55 from the Trimble County line to KY 389 | RI may be getting high. This section of road is the major artery of travel for Trimble/Carroll traffic. It is also a major artery when I-71 is closed or backed up.
Y | 6 | Northern Kentucky ADD | IP20080307 |  |  |  | RECONSTRUCTION FROM I-71 TO KY 36. KY-227 may have a high CRF. This road is the major exit in the county and gets most of the traffic. All the industry along the river (5 billion dollars worth of investment) accesses the interstate through KY-227. I | Reconstruction | Carroll | 021-KY-0227 -000 | 4.254 | 6.816 | 2.562 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 750000 |  | 1500000 |  | 18000000 |  | 2010-02-25 16:51 | RECONSTRUCTION of KY 227 FROM I-71 TO KY 36 by widening lanes and shoulders up to modern standards. | KY-227 may have a high CRF. This road is the major exit in the county and gets most of the traffic. All the industry along the river (5 billion dollars worth of investment) accesses the interstate through KY-227. It is the major retail center for the c
Y | 6 | Northern Kentucky ADD | IP20080308 |  |  |  | Improve safety along KY 389 from I 71 to KY 55. | Spot Improvement | Carroll | 021-KY-0389 -000 | 4.3 | 7.239 | 2.939 | Modernize Roadway-Rural | 26 |  | 0 |  | 3300000 |  | 3000000 |  | 700000 |  | 17300000 |  | 2018-12-20 14:00 | Reconstruct KY 389 from I 71 TO KY 55 to improve mobility and safety by bringing geometric deficiencies up to modern standards | KY 389 does not meet current design standards. There are no shoulders and narrow lanes. Side roads come in at bad angles creating hazardous conditions. | NORTHERN KENTUCKY ADD | North | 26.7962 | 0.61538 | 4.2923 | 4.9038 | 3.9385 | 5.4154 | 0 | 7.6308 | 27
Y | 6 | Northern Kentucky ADD | IP20080309 |  |  |  | Improve safety and address geometric deficiencies at the intersection of KY 389 and Greens Bottom Road. | Spot Improvement | Carroll | 021-KY-0389 -000 | 4.75 | 4.95 | 0.2 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 200000 |  | 200000 |  | 1000000 |  | 2018-12-20 14:03 | Improve safety and mobility and address geometric deficiencies at the intersection of KY 389 and Greens Bottom Road. | Intersection of KY 389 and Greenbottom Rd does not meet current design standards. There are no shoulders, narrow lanes, inadequate sight distances, bad grades and a confusing Y configuration creating hazardous conditions. | NORTHERN KENTUCKY ADD | North | 11.2369 | 0.62154 | 2.9077 | 0.78462 | 3.2 | 0 | 0 | 3.7231 | 11
Y | 6 | Northern Kentucky ADD | IP20080310 |  |  |  | Improve drainage and pedestrian safety and mobility along KY 467 from Old US 227 South Road to Jackson Ridge Road in Worthville. | Drainage Improvement | Carroll | 021-KY-0467 -000 | 0.322 | 0.702 | 0.38 | Maintenance Improvement | 10 |  | 0 |  | 300000 |  | 100000 |  | 500000 |  | 2000000 |  | 2014-04-21 15:42 | modernize roadway to improve drainage and pedestrian safety and mobility along KY 467 from Old US 227 South Road to Jackson Ridge Road in Worthville. | Worthville may need curb and gutter to keep water out of the streets.
Y | 6 | Northern Kentucky ADD | IP20080311 |  |  |  | RECONSTRUCTION FROM KY 227 TO KY 36 | Reconstruction | Carroll | 021-KY-1112 -000 | 0 | 4.28 | 4.28 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 2500000 |  | 1500000 |  | 28000000 |  | 2010-02-25 16:51 | RECONSTRUCTION OF KY 1112 FROM KY 227 TO KY 36 TO BRING GEOMETRIC DEFICIENCIES UP TO MODERN STANDARDS | KY 1112 does not meet current design standards. This project is needed to minimize safety concerns and provide better access to KY 36, KY 227 and the interstate.
Y | 6 | Northern Kentucky ADD | IP20080312 |  |  |  | CONSTRUCT NEW INTERCHANGE AT KY 562 | New Interchange | Gallatin | 039-I -0071 -000 | 66.1 | 66.5 | 0.4 | Construct Road in New Location | 0 | Y | 0 |  | 2500000 |  | 2000000 |  | 1000000 |  | 25000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on I-71 by constructing a new interchange on I 71 at KY 562 | here are major industries located and locating in northern Gallatin County. This exit would give the industry a much closer and easier access to I-71. This would alleviate truck traffic from US-42 and downtown Warsaw. This exit will also upen up access
Y | 6 | Northern Kentucky ADD | IP20080313 |  |  |  | Reconstruct I-71 with additional lanes from Little Sugar Road Overpass to the Boone County Line | Major Widening | Gallatin | 039-I -0071 -000 | 65.5 | 69.89 | 4.39 | Modernize Roadway-Rural | 26 | Y | 0 |  | 3500000 |  | 250000 |  | 250000 |  | 65000000 |  | 2010-02-25 16:51 | Improve travel safety, improve accessibility and mobility options for people and goods, enhance the integration and connectivity of the transportation system and support economic vitality. | nticipated growth in southern Boone County and northern Galllatin County will push growth into this area requiring increased capacity for I-71, along with the need for a pavement rehabilitation for this cooridor. This project would also expand the ITS sy
Y | 6 | Northern Kentucky ADD | IP20080314 |  |  |  | Reconstruct I-71 from the end of the 6-lane typical section to Little Sugar Road Overpass | Major Widening | Gallatin | 039-I -0071 -000 | 59.9 | 65.5 | 5.6 | Modernize Roadway-Rural | 26 | Y | 0 |  | 4000000 |  | 500000 |  | 500000 |  | 55000000 |  | 2010-02-25 16:51 | Improve travel safety, improve accessibility and mobility options for people and goods, enhance the integration and connectivity of the transportation system and support economic vitality. | Anticipated growth in northern Galllatin County will push growth into this area requiring increased capacity for I-71, along with the need for a pavement rehabilitation for this cooridor.
Y | 6 | Northern Kentucky ADD | IP20080315 |  |  |  | Reconstruct US-42 from the intersection of US 127 east of Warsaw to the Boone County Line. | Reconstruction | Gallatin | 039-US-0042 -000 | 11.878 | 16.97 | 5.092 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 5000000 |  | 1000000 |  | 50000000 |  | 2010-02-25 16:51 | Modernize road standards to fix prone areas of landslides by reconstructing US-42 from the intersection of US 127 east of Warsaw to the Boone County Line. | is stretch of road is extremely prone to the hill slipping and effecting US-42, which creates multiple delays and road closure as well as repaving. Reconstruction may be cheaper in the long run for everyone.
Y | 6 | Northern Kentucky ADD | IP20080316 |  |  |  | Upgrade US-42 from KY 35, through Warsaw, to Middleton Road | Minor Widening | Gallatin | 039-US-0042 -000 | 6.832 | 8.888 | 2.056 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2000000 |  | 2500000 |  | 15000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on US-42 from KY 35, through Warsaw, to Middleton Road | This section of US-42 carries major truck traffic. Upgrading the system might aid in keeping the roadways safe for all people traveling the roadway.
Y | 6 | Northern Kentucky ADD | IP20080317 |  |  |  | Improve safety and reliability on US 42 from Middleton Road to US 127. (Alternate 2B 1999 Location Study Report) | Reconstruction | Gallatin | 039-US-0042 -000 | 8.888 | 11.878 | 2.99 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 2500000 |  | 500000 |  | 29000000 |  | 2015-02-17 15:09 | Improve safety and reliability on US 42 from Middleton Road to US 127. (Alternate 2B 1999 Location Study Report) by bringing geometric deficiencies up to modern standards. | This stretch of road is extremely prone to the hill slipping and effecting US-42, which creates multiple delays and road closure as well as repaving. Reconstruction may be cheaper in the long run. | NORTHERN KENTUCKY ADD | North | 26.4146 | 3.8954 | 5.0769 | 3.9808 | 2.3538 | 0 | 2.1538 | 8.9538 | 26
Y | 6 | Northern Kentucky ADD | IP20080319 |  |  |  | Reconstruct US-127 from Owen County line to KY16 (Fairground); include multi-modes. | Reconstruction | Gallatin | 039-US-0127 -000 | 0 | 1.3 | 1.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 1400000 |  | 1500000 |  | 700000 |  | 13000000 |  | 2014-07-29 14:42 | Reconstruct US-127 from Owen County line to KY 16 by bringing deficiencies up to modern standards | This section of US-127 has no shoulders, narrow lanes, and an at grade railroad crossing. KY 476 has offset intersections to US 127. This route provides access to I-71 and other means for Gallatin & Owen residents to reach employers.
Y | 6 | Northern Kentucky ADD | IP20080320 |  |  |  | Reconstruction from KY 16 to I-71 | Reconstruction | Gallatin | 039-US-0127 -000 | 1.125 | 2.568 | 1.443 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2000000 |  | 700000 |  | 14300000 |  | 2014-07-29 14:49 | Improve connectivity I 71 and improve safety by reconstructing US 127 from KY 16 to I-71 | This section of US-127 has a narrow lanes and no shoulders. It provides access to I-71 a means to Gallatin/Owen Cos. to reach employers.
Y | 6 | Northern Kentucky ADD | IP20080321 |  |  |  | Reconstruction from I-71 to US 42. | Reconstruction | Gallatin | 039-US-0127 -000 | 2.589 | 6.037 | 3.448 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 2000000 |  | 3500000 |  | 25000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on US-127 by bringing deficiencies up to modern standards. | This section of US-127 links I-71 US-42 and KY-35 together. It is used by vehicles from all three roads to travel to any of te other two. This road may need upgraded as this rural county gains more development
Y | 6 | Northern Kentucky ADD | IP20080322 |  |  |  | Reconstruction from Carroll C/L to KY-35 | Reconstruction | Gallatin | 039-KY-0467 -000 | 0 | 2.165 | 2.165 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 2500000 |  | 2000000 |  | 15500000 |  | 2010-10-26 15:28 | Reconstruction of KY 467 from Carroll C/L to KY-35 by bringing geometric deficiencies up to modern standards. | The road has a high IRI. The road may be too narrow to promote the safe and efficient movement of people, goods, and services. Consider aligning KY 467 to eliminate offset intersections at KY 35.
Y | 6 | Northern Kentucky ADD | IP20080323 |  |  |  | RECONSTRUCTION FROM KY 35 TO US 127 | Reconstruction | Gallatin | 039-KY-0467 -000 | 2.165 | 7.666 | 5.501 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 3500000 |  | 4000000 |  | 44000000 |  | 2010-10-26 15:32 | RECONSTRUCTION OF KY 467 FROM KY 35 TO US 127 TO ADDRESS THE VERY HIGH CRF FOR SAFE CONNECTION WITH MAIN NORTH SOUTH ARTERY. | This stretch of road has a high CRF, and a high IRI. There is a crossing under the RR tracks at the same point a creek passes under the road. It is in Flood Plain Zone A - prone to frequent flooding. There are NO guardrails and at least a 5 foot fall t
Y | 6 | Northern Kentucky ADD | IP20080324 |  |  |  | Improve safety and mobility and address geometric deficiencies on KY 467 from US 127 to the Grant County line. | Minor Widening | Gallatin | 039-KY-0467 -000 | 7.666 | 9.994 | 2.328 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 1500000 |  | 16500000 |  | 2014-07-25 12:57 | Improve safety to KY 467 by widening and modernizing deficiencies in Gallatin County | This road is narrow and has no shoulders. It is be hard to pass and may be dangerous for travelers that are not familiar with traveling this road. KY 467 has an offset intersection at US 127. | NORTHERN KENTUCKY ADD | North | 20.9477 | 0.67077 | 4.7538 | 3.1385 | 4.2923 | 0 | 0 | 8.0923 | 21
Y | 6 | Northern Kentucky ADD | IP20080326 |  |  |  | Reconstruct US-25 from KY 36 East junction to KY 22 East junction in Williamstown. | Reconstruction | Grant | 041-US-0025 -000 | 8.994 | 11.365 | 2.371 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2000000 |  | 1500000 |  | 20000000 |  | 2014-05-01 14:58 | Modernize roadway for safety and ease of travel by Reconstructing US-25 from KY 36 East junction to KY 22 East junction in Williamstown. | US 25 has narrow lanes and deteriating sidewalks through Williamstown and Dry Ridge.
Y | 6 | Northern Kentucky ADD | IP20080327 |  |  |  | Reconstruct US-25 with bikeway from KY 22 in Williamstown to end of Dry Ridge Bypass in Dry Ridge. | Reconstruction | Grant | 041-US-0025 -000 | 11.365 | 15.987 | 4.622 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 1000000 |  | 500000 |  | 15000000 |  | 2014-05-01 15:42 | Modernizing the roadway for safety and added through capacity by Reconstructing US-25 with bikeway from KY 22 in Williamstown to end of Dry Ridge Bypass in Dry Ridge. | US-25 may benefit from increased shoulders. Adding a bike lane and increasing the shoulders may make it easier to travel the route by bike as well as increasing the safety of the road. There may be some safety problems because there is a high CRF. IRI
Y | 6 | Northern Kentucky ADD | IP20080328 |  |  |  | RECONSTRUCT WITH BIKEWAY FROM DRY RIDGE BYPASS TO KY 1994 IN SHERMAN | Reconstruction | Grant | 041-US-0025 -000 | 15.987 | 19.435 | 3.448 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 2000000 |  | 1500000 |  | 25000000 |  | 2010-02-25 16:51 | Modernize the roadway for easy of travel and safety by RECONSTRUCTING WITH BIKEWAY FROM DRY RIDGE BYPASS TO KY 1994 IN SHERMAN | This project is needed to increase capacity, reduce congestion,improve safety and provide a parallel route to the interstate. It will also eliminate at grade crossings.
Y | 6 | Northern Kentucky ADD | IP20080329 |  |  |  | Updating US-25 from KY 1994 to KY 491 north junction. | Reconstruction | Grant | 041-US-0025 -000 | 19.435 | 23.225 | 3.79 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 3000000 |  | 1500000 |  | 39000000 |  | 2010-02-25 16:51 | Updating US-25 from KY 1994 to KY 491 north junction by modernizing the roadway for ease of travel and safety. | This section of US-25 runs parallel to I-75, it is used in times of high traffic volume or if accidents occur on I-75. This section is NORTH of Williamstown connects To a more urbanized Kenton County.
Y | 6 | Northern Kentucky ADD | IP20080330 |  |  |  | Reconstruct US 25 from Scott County line to KY-36 | Reconstruction | Grant | 041-US-0025 -000 | 0 | 8.994 | 8.994 | Modernize Roadway-Rural | 26 |  | 0 |  | 9000000 |  | 7000000 |  | 3000000 |  | 90000000 |  | 2010-02-25 16:51 | Bring this section of roadway up to modern standards for safety and ease of travel by Reconstructing US 25 from Scott County line to KY-36 | The purpose of this project is to widen US-25 there are no shoulder on this route, narrow lanes and many land slides.
Y | 6 | Northern Kentucky ADD | IP20080331 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 22 from KY 1993 (Lawrenceville Road) to Baton Rouge Road. (Section A3 May 2004 Programming Study) | Minor Widening | Grant | 041-KY-0022 -000 | 0.63 | 6.671 | 6.041 | Modernize Roadway-Rural | 26 |  | 0 |  | 6000000 |  | 10000000 |  | 2000000 |  | 42000000 |  | 2015-06-26 10:39 | Improve safety and mobility and address geometric deficiencies along KY 22 from KY 1993 (Lawrenceville Road) to Baton Rouge Road. (Section A3 May 2004 Programming Study. | he KY-22 corridor is going to be the focus of regional efforts. KY 22 links Pendleton, Grant and Owen Counties. Since I-74 is not going to be constructed at present, there is a need to connect the three counties, mainly to give Pendleton and Owen counti | NORTHERN KENTUCKY ADD | North | 63.5546 | 1.0277 | 7.4308 | 11.2962 | 4.6308 | 0 | 0 | 9.1692 | 34 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20080332 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 22 from Baton Rouge Road to KY 467 (Warsaw Road). (Section A4 May 2004 Programming Study) | Spot Improvement | Grant | 041-KY-0022 -000 | 6.671 | 10.748 | 4.077 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 4000000 |  | 1000000 |  | 30000000 |  | 2015-02-05 11:15 | Improve safety and mobility and address geometric deficiencies along KY 22 from Baton Rouge Road to KY 467 (Warsaw Road). (Section A4 May 2004 Programming Study) | The KY-22 corridor is going to be the focus of regional efforts. KY22 links Pendleton, Grant and Owen Counties. Since I-74 is not going to be constructed at present, there is a need to connect the three counties, mainly to give Pendleton and Owen counti | NORTHERN KENTUCKY ADD | North | 63.0692 | 1.7538 | 7.8923 | 9.6231 | 4.7846 | 0 | 0 | 9.0154 | 33 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20080333 |  |  |  | Provide connectivity and improved mobility for KY 22 around NE Williamstown from US 25 at Baton Rouge Rd. to KY 489 (Fairview Rd.) (See 1988 DEA Study). | Relocation | Grant | 041-KY-0022 -000 | 11.761 | 13.413 | 1.652 | Construct Road in New Location | 0 |  | 0 |  | 3000000 |  | 4000000 |  | 1500000 |  | 21500000 |  | 2015-02-05 15:01 | Provide connectivity and improved mobility for KY 22 around NE Williamstown from US 25 at Baton Rouge Rd. to KY 489 (Fairview Rd.) (See 1988 DEA Study). | The KY 22 corridor is a focus of regional efforts. KY 22 links Pendleton, Grant and Owen Counties. Since I-74 is not going to be constructed at present, there is a need to connect the three counties, mainly to give Pendleton and Owen counties access to
Y | 6 | Northern Kentucky ADD | IP20080334 |  |  |  | Improve safety, mobility and connectivity and address geometric deficiences along KY 22 from KY 489 (Fairview Rd) to KY 1054. | Reconstruction | Grant | 041-KY-0022 -000 | 13.413 | 15.56 | 2.147 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 3000000 |  | 2000000 |  | 37000000 |  | 2015-01-12 13:19 | Improve safety, mobility and connectivity and address geometric deficiences along KY 22 from KY 489 (Fairview Rd) to KY 1054. | he purpose of this project is to relocate an intersection in order to improve the connectivity of the border region. The IRI and CRF suggest that there might be problems with this section of roadway.
Y | 6 | Northern Kentucky ADD | IP20080335 |  |  |  | RECONSTRUCT WITH BIKEWAY FROM OWEN C\L TO KY 22 AT FOUR CORNERS | Reconstruction | Grant | 041-KY-0036 -000 | 0 | 6.452 | 6.452 | Modernize Roadway-Rural | 26 |  | 0 |  | 5500000 |  | 3000000 |  | 1500000 |  | 55000000 |  | 2014-05-02 08:44 | RECONSTRUCT WITH BIKEWAY FROM OWEN C\L TO KY 22 AT FOUR CORNERS by bringing the road up to modern standards. | The purpose of this project is to widen KY-36 and allow for bicycle and pedestrian traffic to safely travel this route. This widening may increase walkability of communities, safety on roadways for cyclist and motor vehicles. Lanes being widened may ben
Y | 6 | Northern Kentucky ADD | IP20080336 |  |  |  | Reconstruct from Ky 22 at four corners to KY-1995 | Reconstruction | Grant | 041-KY-0036 -000 | 6.452 | 10.592 | 4.14 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 4500000 |  | 1000000 |  | 33000000 |  | 2010-02-25 16:51 | Reconstruct from Ky 22 at four corners to KY-1995 by bringing the road up to modern standards. | The purpose of this project is to widen KY-36 and allow for bicycle and pedestrian traffic to safely travel this route. This widening may increase walkability of communities, safety on roadways for cyclist and motor vehicles. Lanes being widened may ben
Y | 6 | Northern Kentucky ADD | IP20080337 |  |  |  | Reconstruct KY 467 from the Gallatin County line to Clarks Creek Road | Reconstruction | Grant | 041-KY-0467 -000 | 0 | 7.483 | 7.483 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 6000000 |  | 3500000 |  | 57000000 |  | 2010-02-25 16:51 | Reconstruct KY 467 from the Gallatin County line to Clarks Creek Road by bringing the road up to modern standards. | KY 467 is a roadway that connects rural Grant, Owen, Pendleton, and Gallatin counties. This section of road may be windy and narrow.
Y | 6 | Northern Kentucky ADD | IP20080338 |  |  |  | Reconstruct KY-467 from Clarks Creek Road to Osborne Road | Reconstruction | Grant | 041-KY-0467 -000 | 7.483 | 10.065 | 2.582 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1500000 |  | 500000 |  | 20000000 |  | 2010-02-25 16:51 | Reconstruct KY-467 from Clarks Creek Road to Osborne Road by bringing the road up to modern standards. | KY 467 is a roadway that connects rural Grant, Owen, Pendleton, and Gallatin counties. This section of road may be windy and narrow.
Y | 6 | Northern Kentucky ADD | IP20080339 |  |  |  | Reconstruct KY-467 from Osborne Lane to KY 22 | Reconstruction | Grant | 041-KY-0467 -000 | 10.065 | 11.704 | 1.639 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 1500000 |  | 750000 |  | 14000000 |  | 2010-02-25 16:51 | Reconstruct KY-467 from Osborne Lane to KY 22 by bringing the road up to modern standards | KY 467 is a roadway that connects rural Grant, Owen, Pendleton, and Gallatin counties. This section of road may be windy and narrow.
Y | 6 | Northern Kentucky ADD | IP20080340 |  |  |  | Reconstruct from US 25 to Pendleton County Line | Reconstruction | Grant | 041-KY-0467 -000 | 11.704 | 15.874 | 4.17 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 3000000 |  | 1500000 |  | 32000000 |  | 2014-05-02 10:55 | Bring KY 467 up to modern standards for safety and ease of travel for cars and pedestrians reconstructing from US 25 to Pendleton County Line. | he purpose of this project is to widen KY-467 which is a direct access to US-25 and allow for bicycle and pedestrian traffic to safely travel this route. This widening may increase walkability of communities, safety on roadways for cyclist and motor vehi
Y | 6 | Northern Kentucky ADD | IP20080341 |  |  |  | Reconstruct KY 491 from the Boone County Line through the I-75 Interchange to US 25 | Reconstruction | Grant | 041-KY-0491 -000 | 0 | 3.98 | 3.98 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 3000000 |  | 1500000 |  | 32000000 |  | 2014-05-02 11:02 | Reconstruct KY 491 from the Boone County Line through the I-75 Interchange to US 25 by upgrading deficiencies to modern standards for easy of travel | This section of road connects US-25 in Grant country to Kenton County
Y | 6 | Northern Kentucky ADD | IP20080342 |  |  |  | Reconstruct from US 25 to the Pendleton County line | Reconstruction | Grant | 041-KY-0491 -000 | 3.98 | 8.349 | 4.369 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 3000000 |  | 1500000 |  | 32000000 |  | 2014-05-02 11:06 | Reconstruct from US 25 to the Pendleton County line by upgrading deficiencies to modern standards for ease of travel | The purpose of this project is to widen Ky-491 which is a direct access to US-25 and allow for bicycle and pedestrian traffic to safely travel this route. This widening may increase walkability of communities, safety on roadways for cyclist and motor veh
Y | 6 | Northern Kentucky ADD | IP20080343 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 1994 (Sherman Mt Zion Rd) from I-75 to US 25 to accomodate new I-75 interchange.(6-112.10 in Highway Plan) | Major Widening | Grant | 041-KY-1994 -000 | 3.411 | 3.934 | 0.523 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 500000 |  | 6000000 |  | 2015-02-05 10:55 | Improve safety and mobility and address geometric deficiencies along KY 1994 (Sherman Mt Zion Rd) from I-75 to US 25 to accommodate new I-75 interchange.(6-112.10 in Highway Plan) | This reconstruction from I-75 to US 25 may promote the safe and effcient movement of people, good and services.
Y | 6 | Northern Kentucky ADD | IP20080344 |  |  |  | Improve drainage, pedestrian safety, and mobility along KY 2363 (Violet Rd) from KY 491 (Lebanon Rd) to Eads Rd. | Reconstruction | Grant | 041-KY-2363 -000 | 0 | 0.564 | 0.564 | Maintenance Improvement | 10 |  | 0 |  | 900000 |  | 700000 |  | 900000 |  | 6000000 |  | 2015-02-09 11:13 | Improve drainage and pedestrian safety and mobility along KY 2363 (Violet Rd) from KY 491 (Lebanon Rd) to Eads Rd. | Road may have drainage problems and may benefit from an upgrade to curb and gutter. Further, growth in the area would benefit from sidewalks. | NORTHERN KENTUCKY ADD | North | 8.2231 | 2.2154 | 0 | 2.8385 | 3.1692 | 0 | 0 | 0 | 8
Y | 6 | Bluegrass ADD | IP20080345 |  |  |  | Address safety and level of service on US 27 from the West Cynthiana Bypass to Two Lick Road/Lower Two Lick Road in Harrison County. | Reconstruction | Harrison | 049-US-0027 -000 | 6.736 | 10.538 | 3.802 | Other Improvement Types | 0 |  | 0 |  | 4500000 |  | 2500000 |  | 1000000 |  | 30000000 |  | 2014-03-06 15:18 | To address the safety and level of service issues on US 27 from the West Cynthiana Bypass to Two Lick Road/Lower Two Lick Road in Harrison County. | Route from the proposed West Cynthiana Bypass to Two Lick Road/Lower Two Lick Road has various safety concerns such as sight distance restrictions as indicated by Vertical Alignment rating of 3 and Horizontal Alignment rating of 3 indicates problem curves
Y | 6 | Bluegrass ADD | IP20080346 |  |  |  | Improve safety and level of service on US 27 from Two Lick Road/Lower Two Lick Road to Blackburn Road in Harrison County. | Reconstruction | Harrison | 049-US-0027 -000 | 10.538 | 15.275 | 4.737 | Other Improvement Types | 0 |  | 0 |  | 5500000 |  | 3400000 |  | 1500000 |  | 37000000 |  | 2014-03-06 15:53 | To improve both safety and level of service on US 27 from Two Lick Road/Lower Two Lick Road to Blackburn Road in Harrison County. | Route from Two Lick Road/Lower Two Lick Road to Blackburn Road has various safety concerns such as sight distance restrictions as indicated by Vertical Alignment rating of 3 and Horizontal Alignment rating of 3 indicates problem curves at the prevailing
Y | 6 | Bluegrass ADD | IP20080347 |  |  |  | Improve safety and level of service on US 27 from Blackburn Road in Harrison County to the Pendleton County line. | Reconstruction | Harrison | 049-US-0027 -000 | 15.275 | 19.545 | 4.27 | Other Improvement Types | 0 |  | 0 |  | 5200000 |  | 3000000 |  | 1500000 |  | 33000000 |  | 2014-03-06 16:01 | To improve safety and level of service on US 27 from Blackburn Road in Harrison County to the Pendleton County line. | US 27 from Blackburn Road in Harrison County to the Pendleton County line has various safety concerns such as sight distance restrictions as indicated by Vertical Alignment rating of 3 and Horizontal Alignment rating of 3 indicates problem curves at the p
Y | 6 | Bluegrass ADD | IP20080348 |  |  |  | Improve safety and congestion along US 62 (Oddville Ave) from Pine Street to KY 392 (Republican Pike) in Cynthiana. | Reconstruction | Harrison | 049-US-0062 -000 | 9.449 | 10.259 | 0.81 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 500000 |  | 5750000 |  | 2015-02-19 10:11 | To improve both safety and congestion along US 62 (Oddville Ave) from Pine Street to KY 392 (Republican Pike) in Cynthiana. | Current IRI notes possible pavement issues. The 20 year ADT projection on US 62 (Oddville Avenue) from Pine Street to KY 392 indicates that safety concerns will be enhanced from the current Critical Rate Factor that indicates safety issue. There are no tu | BLUEGRASS ADD | North | 32.0215 | 6.8738 | 7.9385 | 5.6077 | 3.2308 | 0 | 2.4308 | 5.94 | 32
Y | 6 | Bluegrass ADD | IP20080349 |  |  |  | Improve safety, freight mobility. and geometric deficiencies along KY 32 from Sea Biscuit Way to US 27 (Cynthiana Bypass). | Reconstruction | Harrison | 049-KY-0032 -000 | 8.05 | 8.303 | 0.253 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 500000 |  | 200000 |  | 2000000 |  | 2017-05-04 10:06 | To improve both safety and freight mobility and address geometric deficiencies along KY 32 from Sea Biscuit Way to US 27 (Cynthiana Bypass). | Road segments are in the low Percentile indicating that similar roads are in better condition. Horizontal Alignment of 3 indicates infrequent curves with design speeds less than the prevailing speed limit. CRF is extremely high noting safety problems. The | BLUEGRASS ADD | North | 20.9415 | 0.88 | 3.9231 | 2.7231 | 3.6615 | 5.5385 | 0 | 4.2154 | 21
Y | 6 | Bluegrass ADD | IP20080350 | 6-908 | 2017-08-28 | I | IMPROVE SAFETY ON KY-32 AT THE ENTRANCE TO HARRISON MEMORIAL HOSPITAL IN CYNTHIANA.(12CCR)(18CCN) | SAFETY(P) | Harrison | 049-KY-0032 -000 | 10.075 | 10.461 | 0.386 | Improve Intersection | 26 |  |  |  | 0 |  | 450000 |  | 0 |  | 0 | 2021 | 2018-07-10 08:18 | To improve safety on KY 32 at the entrance to Harrison Memorial Hospital in Cynthiana. | The high Critical Rate Factor indicates serious safety concerns on the segment on KY 32 in Cynthiana at the entrance to Harrison Memorial Hospital. Crash data indicates that the majority of collisions at the entrance to the hospital are angle collisions | 6 | North | 16.8331 | 1.9754 | 4.2 | 3.1962 | 2.5692 | 0 | 0 | 4.8923 | 17
Y | 6 | Bluegrass ADD | IP20080351 |  |  |  | Improve safety on KY 36 from approximately 200' west of the Mill Creek Bridge to approximately 200' east of the Mill Creek Bridge in Harrison Count. | Safety-Haz-Elm | Harrison | 049-KY-0036 -000 | 12.407 | 12.607 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 250000 |  | 100000 |  | 4100000 |  | 2014-03-07 13:06 | To improve safety on KY 36 from approximately 200' west of the Mill Creek Bridge to approximately 200' east of the Mill Creek Bridge in Harrison Count. | Adequacy Ratings indicate this segment of KY 36 has safety issues with a high Critical Rate Factor. The route serves as a major collector between northeastern Harrison County and Cynthiana as well as provide alternate access to I-75 at Williamstown.
Y | 6 | Bluegrass ADD | IP20080352 |  |  |  | Reconstruct KY 982 (Lair Road/Church Street) from the CSX RR crossing to KY 32 (Pike Street) | Major Widening | Harrison | 049-KY-0982 -000 | 4.57 | 6 | 1.43 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 1500000 |  | 500000 |  | 12000000 |  | 2014-03-07 14:29 | Reconstruction of KY 982 (Lair Road/Church Street) from the CSX RR crossing to KY 32 (Pike Street). | Safety concerns and issues on narrow 2, 9 feet wide lanes on corridor that serves 2 factories, Harrison County High School, Harrison County Middle School, Southside Elementry School, Vocational School and Community College particularly during peak hours.
Y | 6 | Bluegrass ADD | IP20080353 |  |  |  | Improve safety on KY 1842 in Harrison County between Hicks Pike and Grays Run Road. | Reconstruction | Harrison | 049-KY-1842 -000 | 2.635 | 3.16 | 0.525 | Other Improvement Types | 0 |  | 0 |  | 1250000 |  | 500000 |  | 150000 |  | 3000000 |  | 2010-02-25 16:51 | To improve safety on KY 1842 in Harrison County between Hicks Pike and Grays Run Road. | Safety concerns are the main issue as roadway has narrow lanes and little or no shoulders. Roadway flooding is a problem as local officials and residents note that rain runoffs on the road are occuring due to considerable development in the southwest part
Y | 6 | Northern Kentucky ADD | IP20080354 |  |  |  | Improve safety and reduce congestion along US 25 (Dixie Hwy) from KY 1017 (Turfway Rd) in Boone County to KY 236 (Commonwealth Ave). | Major Widening | Kenton | 059-US-0025 -000 | 4.978 | 6.076 | 1.098 | Other Improvement Types | 0 |  | 0 |  | 5000000 |  | 20000000 |  | 3000000 |  | 25000000 |  | 2015-02-16 13:02 |  | ADT in this area is 24,200 vpd on a maximum of four, 10' foot lanes with 0' shoulders. A composite rating as low as 29.85 indicates that nearly 96.94% of the statewide urban principle arterials are rated better. An IRI as high as 1.40 is contributing to
Y | 6 | Northern Kentucky ADD | IP20080357 | 6-80002 |  | A | RECONSTRUCT KY 236 (STEVENSON ROAD) FROM ALICE STREET TO JACQUELINE DRIVE.(18CCN) | RECONSTRUCTION(O) | Kenton | 059-KY-0236 -000 | 0 | 1.436 | 1.436 | Maintenance Improvement | 10 |  |  |  | 800000 | 2019 | 1000000 | 2020 | 1000000 | 2021 | 5300000 | 2022 | 2018-07-10 08:18 |  | The roadway does not meet current design standards. This project would address the deficient geometry, no shoulders, narrow lanes, restricted sight distance, and drainage problems. Project Description Narrative: Reconstruct Stevenson Road from KY 1303 | 6 | North | 27.3946 | 4.4062 | 8.7692 | 10.8346 | 3.3846 | 0 | 0 | 0 | 27
Y | 6 | Northern Kentucky ADD | IP20080358 |  |  |  | Reconstruct KY 536 to a 4 lane urban section from the Boone County Line to KY 17 (MP 0.0 to MP 4.5)(00CCR)(04CCN)(06CCR)(2006BOPC)(Phase I design shown under 6-162.00)(12CCR)(14CCR) | Major Widening | Kenton | 059-KY-0536 -000 | 0 | 4.5 | 4.5 | Arterial to Partial Control | 23 |  | 0 |  | 0 |  | 22050000 |  | 4160000 |  | 0 |  | 2016-12-09 14:23 |  | DT in this area is 8403 vpd on a maximum of two, 12' foot lanes with 4' shoulders. A composite rating of 78 indicates that 24.39% of the statewide urban principle arterials are rated better. An IRI as high as 106 is contributing to a condition index as lo
Y | 6 | Northern Kentucky ADD | IP20080359 |  |  |  | Provide connectivity, improve mobility, and reduce congestion along KY 536 from KY 17 to KY 16; include multi-modes. | Major Widening | Kenton | 059-KY-0536 -000 | 4.602 | 6.092 | 1.49 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 6500000 |  | 500000 |  | 7000000 |  | 2017-05-05 13:18 |  | Improve travel safety, accessibility and mobility options for people and goods; including multi-modes. Enhance the integration and connectivity of the transportation system and support economic vitality across Boone-Kenton-Campbell Counties. ADT in th | Cincinnati/Northern Kentucky MPO | North | 35.75 | 3.9692 | 5.4462 | 5.9654 | 4.4154 | 6.6769 | 2.5385 | 6.7385 | 36
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20080360 |  |  |  | Improve safety and provide connectivity along KY 536 from KY 16 (Taylor Mill Rd) to KY 177 (Decoursey Pike); including multi-modes. | Relocation | Kenton | 059-KY-0536 -000 | 6.092 | 10.249 | 4.157 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 4500000 |  | 3000000 |  | 26000000 |  | 2017-05-05 13:23 | TBD | Improve travel safety, accessibility and mobility options for people and goods; including multi-modes. Enhance the integration and connectivity of the transportation system and support economic vitality across Boone-Kenton-Campbell Counties. ADT in th | Cincinnati/Northern Kentucky MPO | North | 23.3192 | 1.4769 | 7.6154 | 9.5192 | 4.7077 | 0 | 0 | 0 | 23
Y | 6 | Northern Kentucky ADD | IP20080362 | 6-8916 |  | A | EXTEND HOUSTON ROAD TO CINEMA PROPERTY. (16CCN)(18CCN) | NEW ROUTE(O) | Kenton | 059-CS-3000 -000 | 0 | 0.31 | 0.31 | Construct Road in New Location | 0 |  |  |  | 0 | 2019 | 500000 |  | 300000 |  | 3500000 |  | 2016-09-22 |  | Hartman Road (KY 2978) extends about 1/3 miles from the Houston Road (KY 842) and Donaldson Road (KY 236) intersection to Erlanger Road. The facility serves the Erlanger Commercial Park, several other commercial businesses and provides access to the for
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20080363 |  |  |  | Improve safety & mobility, and geometric deficiencies at the intersections of KY 3187 (Kyles Lane) and Farrell Dr. and Mount Vernon; including multi-modal needs. | Safety-Haz-Elm | Kenton | 059-KY-3187 -000 | 0.7 | 0.828 | 0.128 | Improve Intersection | 26 |  | 0 |  | 600000 |  | 1500000 |  | 300000 |  | 3000000 |  | 2017-05-04 11:24 | TBD | Farrell Drive serves Ft. Wright Elem. School and multiple-various types of elderly housing. There is a large residential neighborhood on the south side of KY 3187. The intersection of Farrell/KY 3187 suffers from acute geometric lines of sight and steep | 6 | North | 17.9369 | 4.9292 | 3.7846 | 2.3308 | 3.2615 | 0 | 0 | 3.6308 | 18
Y | 6 | Northern Kentucky ADD | IP20080364 |  |  |  | Reconstruct US 127 from KY 35 to the Gallatin County Line | Reconstruction | Owen | 094-US-0127 -000 | 22.979 | 28.488 | 5.509 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 3000000 |  | 1000000 |  | 45000000 |  | 2014-04-02 11:22 | Bring US 127 up to modern geometric standards by Reconstructing US 127 from KY 35 to the Gallatin County Line | A potential problem lies in the fact the US-127 has wider lanes and larger shoulders from Frankfort north to the KY-35/US-127 split in northern Owen County. The road north of KY 35 is rough and the shoulders are almost non existant. This road gets heavy
Y | 6 | Northern Kentucky ADD | IP20080365 |  |  |  | Improve safety and mobility along KY 35 from US 127 to the Gallatin County line. | Spot Improvement | Owen | 094-KY-0035 -000 | 0 | 4.132 | 4.132 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2500000 |  | 1500000 |  | 25000000 |  | 2015-02-16 13:50 | Improve safety and mobility along KY 35 from US 127 to the Gallatin County line by bringing the road up to modern standards. | A potential problem lies in the fact the US-127 has wider lanes and larger shoulders from Frankfort north to the KY-35 /US-127 split in northern Owen County. KY-35 is the easiest route to I-71 and gets a majority of US-127 traffic. Ky-35 gets heavy f | NORTHERN KENTUCKY ADD | North | 25.0862 | 1.3477 | 5.3538 | 4.6615 | 2.9385 | 0 | 2.2 | 8.5846 | 25
Y | 6 | Northern Kentucky ADD | IP20080366 |  |  |  | RECONSTRUCTION FROM HARMONY RD TO KY 607 | Reconstruction | Owen | 094-KY-0227 -000 | 0.691 | 5.561 | 4.87 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3500000 |  | 1500000 |  | 40000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on KY-22 by RECONSTRUCTION FROM HARMONY RD TO KY 607 | The purpose of this project is create a more direct route to KY-22. The IRI suggest that there maybe a problem with pavement. Local citizens and local officials think that the road is too curvy.
Y | 6 | Northern Kentucky ADD | IP20080367 |  |  |  | RECONSTRUCTION FROM KY 607 TO KY 845 (north junction) | Reconstruction | Owen | 094-KY-0227 -000 | 5.561 | 8.892 | 3.331 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2000000 |  | 1500000 |  | 27000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on KY-22 by RECONSTRUCTION FROM KY 607 TO KY 845 (north junction) | The purpose of this project is create a more direct route to KY-22. The IRI suggest that there maybe a problem with pavement. Local citizens and local officials think that the road is too curvy.
Y | 6 | Northern Kentucky ADD | IP20080368 |  |  |  | RECONSTRUCTION FROM KY 845 TO KY 330 | Reconstruction | Owen | 094-KY-0227 -000 | 8.892 | 12.172 | 3.28 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2000000 |  | 1500000 |  | 27000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on KY-22 by RECONSTRUCTION FROM KY 845 TO KY 330 | The purpose of this project is create a more direct route to KY-22. The IRI suggest that there maybe a problem with pavement. Local citizens and local officials think that the road is too curvy.
Y | 6 | Northern Kentucky ADD | IP20080369 |  |  |  | RECONSTRUCTION FROM KY 330 TO KY 22 | Reconstruction | Owen | 094-KY-0227 -000 | 12.172 | 14.131 | 1.959 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 1500000 |  | 1000000 |  | 16000000 |  | 2010-02-25 16:51 | Increase safety, ease of travel, and travel times on KY-22 by RECONSTRUCTION FROM KY 330 TO KY 22 | The purpose of this project is create a more direct route to KY-22. The IRI suggest that there maybe a problem with pavement. Local citizens and local officials think that the road is too curvy.
Y | 6 | Northern Kentucky ADD | IP20080370 |  |  |  | RECONSTRUCTION FROM US 127 IN MONTEREY TO KY 22 IN GRATZ | Reconstruction | Owen | 094-KY-0355 -000 | 0 | 6.398 | 6.398 | Modernize Roadway-Rural | 26 |  | 250000 |  | 4000000 |  | 3000000 |  | 2000000 |  | 54000000 |  | 2010-02-25 16:51 | RECONSTRUCTION FROM US 127 IN MONTEREY TO KY 22 IN GRATZ TO CONNECT WESTERN OWEN COUNTY TO US 127 | KY-355 connects western Owen County and is a major conduit to US-127 for these residents
Y | 6 | Northern Kentucky ADD | IP20080371 |  |  |  | RECONSTRUCTION FROM KY 22 IN GRATZ TO KY 1982 NEAR PERRY PARK | Reconstruction | Owen | 094-KY-0355 -000 | 6.398 | 12.482 | 6.084 | Modernize Roadway-Rural | 26 |  | 250000 |  | 4500000 |  | 5000000 |  | 2000000 |  | 54000000 |  | 2010-02-25 16:51 | RECONSTRUCTION FROM KY 22 IN GRATZ TO KY 1982 NEAR PERRY PARK TO PROMOTE EASE OF TRAVEL. | KY-355 connects western Owen County and is a major conduit to US-127 for these residents
Y | 6 | Northern Kentucky ADD | IP20080372 |  |  |  | Reconstruct KY 355 from KY 1982 to Eagle Creek Resort Rd | Reconstruction | Owen | 094-KY-0355 -000 | 12.482 | 18.189 | 5.707 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 4000000 |  | 2000000 |  | 45000000 |  | 2010-02-25 16:51 | Reconstruct KY 355 from KY 1982 to Eagle Creek Resort Rd to promote the safe and efficient movement of people, goods, and services. | KY-355 connects western Owen County and is a major conduit to US-127 for these residents
Y | 6 | Northern Kentucky ADD | IP20080373 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 607 (Claxon Ridge Road) at hairpin turn at Sawridge Creek Road. | Reconstruction | Owen | 094-KY-0607 -000 | 3.8 | 4.6 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 500000 |  | 250000 |  | 3500000 |  | 2015-02-16 14:45 | Improve safety and mobility and address geometric deficiencies along KY 607 (Claxon Ridge Road) at hairpin turn at Sawridge Creek Road. | KY-607 is a narrow winding road in Owen County which has a hairpin turn in this road segment that needs improvement.
Y | 6 | Northern Kentucky ADD | IP20080374 |  |  |  | Reconstruct KY 1982 to current 2 lane standards from KY 355 to Hensley Road. | Reconstruction | Owen | 094-KY-1982 -000 | 0 | 4.88 | 4.88 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3000000 |  | 1000000 |  | 40000000 |  | 2014-04-02 14:05 | Reconstruct KY 1982 by bringing geometric deficiencies up to current 2 lane standards from KY 355 to Hensley Road. | KY 1982 does not meet current design standards. This project is needed to minimize safety concerns and provide better access to Carrollton and Perry Park Country Club
Y | 6 | Northern Kentucky ADD | IP20080375 |  |  |  | Reconstruct KY 1982 to current 2 lane standards from Hensley Road to KY 22. | Reconstruction | Owen | 094-KY-1982 -000 | 4.88 | 7.153 | 2.273 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 2000000 |  | 1000000 |  | 20000000 |  | 2010-02-25 16:51 | Reconstruct KY 1982 by bringing geometric deficiencies us to current 2 lane standards from Hensley Road to KY 22. | Ky 1982 does not meet current standards. This project is needed to minimize safety concerns and provide better access to Carrollton and Perry Park Country Club.
Y | 6 | Northern Kentucky ADD | IP20080376 |  |  |  | Improve safety and mobility US 27 from Bridge in Falmouth to KY 177 in Butler. | Spot Improvement | Pendleton | 096-US-0027 -000 | 8.2 | 17.151 | 8.951 | Modernize Roadway-Rural | 26 |  | 0 |  | 15000000 |  | 25000000 |  | 10000000 |  | 100000000 |  | 2014-05-02 15:41 | Updating US 127 to modern standards is crucial to promoting safe travel on this major corridor. | here are no 4 lane highways in the county. There is heavey truck traffic on US-27. There are three major trucking companies, one of which is Rumpke. Rumpke services as a landfill for the 12 surrounding KY counties and 8 Ohio counties. The county schoo
Y | 6 | Northern Kentucky ADD | IP20080377 |  |  |  | Improve safety and mobility along US 27 northbound from the Harrison County line to near KY 1053 (Rankin Mill Road). | Minor Widening | Pendleton | 096-US-0027 -000 | 0 | 0.8 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 500000 |  | 200000 |  | 5000000 |  | 2017-05-22 08:48 | Increase safety, ease of travel, and travel times on US-27 by constructing a truck climbing lane on US 27 northbound from the Harrison County line to near KY 1053 (Rankin Mill Road | Pendleton Counties three top employers are trucking companies that use US-27 to serve 11 surrounding KY counties and 7 Ohio Counties. This stretch of US-27 is used by all three companies as well as the citizens of Pendleton County. This stretch is also | NORTHERN KENTUCKY ADD | North | 18.2615 | 1.7538 | 5.6308 | 1.7538 | 1.5231 | 0 | 2.0923 | 5.5077 | 18
Y | 6 | Northern Kentucky ADD | IP20080378 |  |  |  | Address safety and level of service on US 27 from Harrison County line to KY 22. | Reconstruction | Pendleton | 096-US-0027 -000 | 0 | 6.9 | 6.9 | Modernize Roadway-Rural | 26 |  | 0 |  | 6000000 |  | 5000000 |  | 3000000 |  | 70000000 |  | 2010-02-25 16:51 |  | Adequacy Rating is 73.00 on US 27 from the county line with Harrison County to 6.9 miles into Pendleton. IRI may be high at 142. ADT is 3,830 by computer estimate. Route connects the county seats of Cynthiana and Falmouth and serves as an alternate to
Y | 6 | Northern Kentucky ADD | IP20080379 |  |  |  | RECONSTRUCT FROM KY 154 TO KY 2828 | Reconstruction | Pendleton | 096-KY-0008 -000 | 0.4 | 2.249 | 1.849 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 1000000 |  | 12000000 |  | 2010-02-25 16:51 | RECONSTRUCT KY 8 FROM KY 154 TO KY 2828 BY UPGRADING THE ROAD TO MODERN STANDARDS | The purpose of this project is increase connectivity and ease of travel in Pendleton County.
Y | 6 | Northern Kentucky ADD | IP20080380 |  |  |  | Improve safety and mobility at the intersection of KY 9 and KY 159 (New Hope Road). | Safety-Haz-Elm | Pendleton | 096-KY-0009 -000 | 0.27 | 0.37 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 300000 |  | 300000 |  | 100000 |  | 2500000 |  | 2015-02-13 13:07 | Improve safety and mobility at the intersection of KY 9 and KY 159 (New Hope Road). | Add left turn lane on KY 9 NB to KY 159 and right turn lane on KY 9 SB to KY 159.
Y | 6 | Northern Kentucky ADD | IP20080381 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 17 from US 27 to KY 1853 (Bryan Griffin Road). | Reconstruction | Pendleton | 096-KY-0017 -000 | 0 | 0.765 | 0.765 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 750000 |  | 1000000 |  | 7000000 |  | 2015-01-12 13:16 | Improve safety and mobility and address geometric deficiencies along KY 17 from US 27 to KY 1853 (Bryan Griffin Road). | Narrow curvy road exists for high volume truck traffic at Rumpke and Griffin Industries' state road access. Straightening the road and widening the roads may make the road more efficent, safer, and easier to travel
Y | 6 | Northern Kentucky ADD | IP20080382 |  |  |  | Reconstruct KY 17 from KY 1853 to KY 467. | Reconstruction | Pendleton | 096-KY-0017 -000 | 0.765 | 6.997 | 6.232 | Modernize Roadway-Rural | 26 |  | 0 |  | 5500000 |  | 3000000 |  | 2500000 |  | 55000000 |  | 2010-02-25 16:51 | Reconstruct KY 17 from KY 1853 to KY 467 by bringing the road up to current geometric standards. | The existing lanes along this section of KY 17 are narrow with sharp curves and steep grades making it unsage for the high volume of commercial verhicles that travel this road daily. This project is needed in order to reduce congistion and improve safety
Y | 6 | Northern Kentucky ADD | IP20080383 |  |  |  | Reconstruct KY 17 from KY 467 to the Kenton County Line. | Reconstruction | Pendleton | 096-KY-0017 -000 | 6.997 | 10.339 | 3.342 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 3000000 |  | 2000000 |  | 25000000 |  | 2010-02-25 16:51 | Reconstruct KY 17 from KY 467 to the Kenton County Line to bring the road up to current geometric standards. | The existing lanes along this section of KY 17 are narrow, with sharp curves and steep grades, making it unsafe for the high volume of commercial vehicles that travel this road daily. This project is needed in order to reduce congestion and improve safe
Y | 6 | Northern Kentucky ADD | IP20080384 |  |  |  | Improve safety, mobility, connectivity, and geometrics along KY 22 from KY 1054 to Turner Ridge Road. | Relocation | Pendleton | 096-KY-0022 -000 | 1.934 | 8.704 | 6.77 | Modernize Roadway-Rural | 26 |  | 0 |  | 7500000 |  | 7000000 |  | 3500000 |  | 50000000 |  | 2017-05-05 14:21 | Improve safety, mobility and connectivity and address geometric deficiencies along KY 22 from KY 1054 to Turner Ridge Road. | The KY-22 corridor is going to be the focus of our regional efforts. KY22 links Pendleton, Grant and Owen Counties. Since I-74 is not going to be constructed at present, we feel there is a need to connect the three counties, mainly to give Pendleton and | NORTHERN KENTUCKY ADD | North | 42.2762 | 0.23385 | 4.6615 | 7.5346 | 5 | 0 | 0 | 9.8462 | 27 |  | 15
Y | 6 | Northern Kentucky ADD | IP20080386 |  |  |  | RECONSTRUCTION FROM KY 10 AT PEACH GROVE TO KY 8 | Reconstruction | Pendleton | 096-KY-0154 -000 | 2.371 | 5.681 | 3.31 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 4000000 |  | 4000000 |  | 28000000 |  | 2010-02-25 16:51 | Bring KY 154 up to modern standards by RECONSTRUCTING FROM KY 10 AT PEACH GROVE TO KY 8 | The purpose of this project is increase connectivity of central Pendleton County to KY-8, which carries traffic from AA. AA is a major artery along the Ohio River from Cincinnati to Ashland. The Adequacy Rating data shown on this form reflects the cur
Y | 6 | Northern Kentucky ADD | IP20080387 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 159 from KY 22 to Kincaid Lake State Park. | Minor Widening | Pendleton | 096-KY-0159 -000 | 0 | 3.538 | 3.538 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2500000 |  | 2000000 |  | 28000000 |  | 2015-02-13 13:04 | Improve safety and mobility and address geometric deficiencies along KY 159 from KY 22 to Kincaid Lake State Park. | Road may be narrow, reconstruction to Kincaid state park may promote the safe and efficient movement of people, goods, and services throughout Pendleton County and help move boat traffic from AA to Lake Kincaid State Park. There is no Adequacy Rating
Y | 6 | Northern Kentucky ADD | IP20080388 |  |  |  | RECONSTRUCTION FROM KY 609 N OF KINCAID STATE PARK TO KY 10 AT MT. AUBURN | Reconstruction | Pendleton | 096-KY-0159 -000 | 3.869 | 10.54 | 6.671 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 3000000 |  | 1500000 |  | 47000000 |  | 2010-02-25 16:51 | Bring 159 up to modern standards to promote safe travel to Kincaid State Park. | Road may be narrow, reconstruction to Kincaid state park may promote the safe and efficient movement of people, goods, and services throughout Pendleton County and help improve boat traffic from AA to Lake Kincaid State Park There is no Adequacy Rating
Y | 6 | Northern Kentucky ADD | IP20080389 |  |  |  | Reconstruction from KY-159 to US-27 in Butler. | Reconstruction | Pendleton | 096-KY-0177 -000 | 0 | 4.012 | 4.012 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 3000000 |  | 1500000 |  | 32000000 |  | 2010-02-25 16:51 | Reconstruction from KY-159 to US-27 in Butler to increase connectivity and safety including heavy truck traffic. | The purpose of this project is increase connectivity to US-27, the major artery in Pendleton County. Truck traffic is apparent when driving the road, which may not be best suited for truck traffic. There is no Adequacy Rating data currently available
Y | 6 | Northern Kentucky ADD | IP20080390 |  |  |  | RECONSTRUCTION FROM US 27 IN BUTLER TO KENTON C\L | Reconstruction | Pendleton | 096-KY-0177 -000 | 4.012 | 9.578 | 5.566 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 4500000 |  | 4000000 |  | 53000000 |  | 2010-02-25 16:51 | RECONSTRUCTION FROM US 27 IN BUTLER TO KENTON C\L TO PROVIDE CONNECTIVITY TO KENTON COUNTY | The purpose of this project is to create better connectivity between the major artery (US-27) and Kenton County. The IRI may be high on this section of KY 177.
Y | 6 | Northern Kentucky ADD | IP20080392 |  |  |  | RECONSTRUCTION FROM GRANT C\L TO KY 1657 | Reconstruction | Pendleton | 096-KY-0467 -000 | 0 | 5.425 | 5.425 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3500000 |  | 3000000 |  | 40500000 |  | 2010-02-25 16:51 | RECONSTRUCTION FROM GRANT C\L TO KY 1657 | The purpose of this project is is to make the road more easily driveable, it may be more easily traveled if the road were straighter. There is no Adequacy Rating data available for the project milepoints. The data shown reflects the data for a compar
Y | 6 | Northern Kentucky ADD | IP20080393 |  |  |  | RECONSTRUCTION FROM KY 1657 TO KY 17 | Reconstruction | Pendleton | 096-KY-0467 -000 | 5.425 | 9.688 | 4.263 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2000000 |  | 1500000 |  | 33000000 |  | 2010-02-25 16:51 | RECONSTRUCTION FROM KY 1657 TO KY 17 | The purpose of this project is is to make the road more easily driveable, it may be more easily traveled if the road were straighter. The IRI may be high creating rough travel conditions. There is no Adequacy Rating data available for the project mil
Y | 6 | Northern Kentucky ADD | IP20080394 |  |  |  | RECONSTRUCTION FROM KY 17 TO KY 177 | Reconstruction | Pendleton | 096-KY-0467 -000 | 9.688 | 10.285 | 0.597 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 750000 |  | 500000 |  | 5000000 |  | 2010-02-25 16:51 | RECONSTRUCTION FROM KY 17 TO KY 177 | The purpose of this project is is to make the road more easily driveable, it may be more easily traveled if the road were straighter.
Y | 6 | Northern Kentucky ADD | IP20080395 |  |  |  | Reconstruct from KY-9 in Campbell County to KY-8 in Pendleton County | Reconstruction | Pendleton | 096-KY-2828 -000 | 0 | 0.466 | 0.466 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 500000 |  | 750000 |  | 6500000 |  | 2010-02-25 16:51 | Reconstruct from KY-9 in Campbell County to KY-8 in Pendleton County | The purpose of this project is is to increase connectivity between KY-8 and KY-9.
Y | 6 | Buffalo Trace ADD | IP20080396 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 from 0.2 miles east of KY 616 (Mt Pleasant Road) to the Mason County Line. | Reconstruction | Robertson | 101-US-0062 -000 | 12.469 | 15.438 | 2.969 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 3500000 |  | 1250000 |  | 25000000 |  | 2014-02-24 10:35 | Improve safety and mobility as well as address geometric deficiencies along US 62. | The problem with US62 from near Sardis into Mason County at KY1029 is the vertical alignment and curves along a residential and agricultural route. The ADT of 821 does not appear to that great, but when the population of Robertson County is only 2,266 th
Y | 6 | Northern Kentucky ADD | IP20080755 |  |  |  | Extend KY-1992 to Southfork Road. Approx 0.7 miles. | Reconstruction | Gallatin | 039-KY-1992 -000 | 5.9 | 5.982 | 0.082 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 200000 |  | 5000000 |  | 2014-05-01 11:21 | Extend KY-1992 to Southfork Road to provide additional through capacity. | Connecting KY 1992 Southfork Rd will promote easier connections for the development of a County Park adjacent to this roadway.
Y | 6 | Northern Kentucky ADD | IP20080756 |  |  |  | New construction on the east side of the RR from Dry Ridge By-Pass north to Case Ln. | New Route | Grant | 041-US-0025 -000 | 16.587 | 22.266 | 5.679 | Construct Road in New Location | 0 |  | 0 |  | 5500000 |  | 6000000 |  | 3500000 |  | 56000000 |  | 2011-02-28 11:34 | New construction on the east side of the RR from Dry Ridge By-Pass north to Case Ln. | This project is needed to increase capacity, reduce congestion,improve safety and provide a parallel route to the interstate.
Y | 6 | Buffalo Trace ADD | IP20090001 |  |  |  | Improve KY 19 from KY 2897 to KY 539 | Reconstruction | Bracken | 012-KY-0019 -000 | 0 | 1.9 | 1.9 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 1200000 |  | 500000 |  | 11000000 |  | 2014-02-05 15:49 | To improve safety and mobility | Additional ADT up to 3,615 on KY 10 and on KY19 of 1,491. This route has many issues ralated to narro shoulders with potential drop offs and needs evaluated for upgrading asphalt as shown in the photos as attached with the map. The route also has fixed
Y | 6 | Buffalo Trace ADD | IP20090002 |  |  |  | Reconstruct KY 19 from KY 539 to KY 165 | Reconstruction | Bracken | 012-KY-0019 -000 | 2.4 | 7.674 | 5.274 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 2000000 |  | 1000000 |  | 28800000 |  | 2011-07-26 08:20 | To improve safety and mobility | Additional ADT up to 3,615 on KY 10 and on KY 19 of 1,491. This route has many issues related to narrow shoulders with potential drop offs and needs evaluated for upgrading asphalt as shown in the photos as attachede with the map. The route also has fix
Y | 6 | Buffalo Trace ADD | IP20090003 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 19 (Powersville-Harrison Co Road) from KY 165 (Old Oakland Road) to KY 10 (Powersville-Willow Road). | Reconstruction | Bracken | 012-KY-0019 -000 | 7.674 | 8.553 | 0.879 | Modernize Roadway-Rural | 26 |  | 0 |  | 1400000 |  | 750000 |  | 500000 |  | 9000000 |  | 2017-03-23 07:53 | To improve safety and mobility | Additional ADT up to 3,615 on KY10 and on KY19 of 1,491. This route has many issues related to narrow shoulders with potential drop offs and needs evaluted for upgrading asphalt as shown in the photos as attached with the map. The route also has fixed o
Y | 6 | Bluegrass ADD | IP20090004 |  |  |  | IMPROVEMENTS TO KY-19 FROM US-62 IN HARRISON COUNTY TO KY-2897 IN BRACKEN COUNTY TO CORRECT SIGHT DISTANCE AND HORIZONTAL CURVE ISSUES. | Reconstruction | Harrison | 049-KY-0019 -000 | 0 | 2.862 | 2.862 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 4000000 |  | 1000000 |  | 21000000 |  | 2010-02-25 16:51 | To add improvements to KY-19 from US-62 in Harrison County to KY-2897 in Bracken County to correct sight distance and horizontal curve issues. | KY 19 from US 62 in Harrison County to KY 2879 is a narrow 2 lanes road with little shoulders. Route has sight distance and horizontal curve issues. High IRI indicates pavement problems present.
Y | 6 | Northern Kentucky ADD | IP20100044 |  |  |  | Improve connectivity and mobility from US 42 to KY 227 on the east side of Carrollton. | Bypass | Carroll | 021-US-0042 -000 | 0 | 3 | 3 | Construct Road in New Location | 0 |  | 0 |  | 3000000 |  | 4000000 |  | 1000000 |  | 25000000 |  | 2012-01-27 15:32 | Construction of By-Pass to Improve connectivity and mobility from US 42 to KY 227 on the east side of Carrollton due to congestion along US 42 | Congestion on US 42 in Carrollton is significant due to truck traffic . A bypass may create a better driving environment for all the drivers in Carroll County. Truck traffic would use this bypass to avoid a congested downtown area. The traffic count esti
Y | 6 | Northern Kentucky ADD | IP20100045 |  |  |  | Construct a new route from US-27 to KY-9. | New Route | Pendleton | 096-KY-0177 -000 | 0 | 4.012 | 4.012 | Construct Road in New Location | 0 |  | 0 |  | 9000000 |  | 4500000 |  | 3000000 |  | 60000000 |  | 2014-05-06 14:44 | Construct a new route from US-27 to KY-9 to increase access to KY 9. | County may need better access to KY-9. This would alleviate US-27 of some truck traffic. The increased access to KY-9 will provided a connection between major roads, where only windy roads connect KY-9 and US-27 presently.
Y | 6 | Buffalo Trace ADD | IP20100049 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 from the Harrison County line to KY 1504 (Central Ridge Road). | Minor Widening | Robertson | 101-US-0062 -000 | 0 | 0.702 | 0.702 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 550000 |  | 150000 |  | 5500000 |  | 2014-02-24 10:44 | Improve safety and mobility and address geometric deficiencies. | This segment of roadway has a good alignment but could use an upgrade of the cross section of the roadway. Wider lanes and improved shoulders would create a recovery zone for the traveling public.
Y | 6 | Buffalo Trace ADD | IP20100050 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 from KY 1504 (Central Ridge Road) to KY 617 (Piqua-Kentontown Road). | Minor Widening | Robertson | 101-US-0062 -000 | 0.702 | 5.026 | 4.324 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 3000000 |  | 1300000 |  | 35000000 |  | 2014-02-24 10:49 | Improve safety and mobility as well as address geometric deficiencies. | This segment of roadway has a good alignment but could use an upgrade of the cross sections of the roadway. Wider lanes and improved shoulders would create a recovery zone for the traveling public. US62 in Robertson County is a major route connecting Mt
Y | 6 | Buffalo Trace ADD | IP20100051 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 from KY 617 (Piqua-Kentontown Rd) to Willie Curtis Road. | Minor Widening | Robertson | 101-US-0062 -000 | 5.026 | 6.612 | 1.586 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 1500000 |  | 500000 |  | 12000000 |  | 2014-02-24 10:53 | Improve safety and mobility as well as geometric deficiencies. | US62 in Robertson County is classified as a State Secondary route and a Rural Major Collector. This route last went through major upgrades in the 1930's and since that time only routine maintenance is conducted. This segment of roadway does have some h
Y | 6 | Buffalo Trace ADD | IP20100052 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 from Willie Curtis Road to KY 1504 (Pinhook Road). | Minor Widening | Robertson | 101-US-0062 -000 | 6.612 | 9.449 | 2.837 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 2500000 |  | 1500000 |  | 21000000 |  | 2014-02-24 10:56 | Improve safety and mobility as well as address geometric deficiencies | US62 in Robertson County is classified as a State Secondary route and a Rural Major Collector. This route has no had any major upgrades since 1930's and has only seen routine maintenance conducted on it. This segment of roadway starting at MP 6.612 an
Y | 6 | Buffalo Trace ADD | IP20100053 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 from KY 539 (Pinhook Road) to KY 165 (Blue Lick Pike). | Minor Widening | Robertson | 101-US-0062 -000 | 9.449 | 10.257 | 0.808 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 500000 |  | 5500000 |  | 2014-02-24 11:00 | Improve safety and mobility as well as address geometric deficiencies. | This section starts into Mt. Olivet, lanes need to be widened with curb gutter and sidewalks. Lanes are very narrow.
Y | 6 | Buffalo Trace ADD | IP20110040 |  |  |  | Improve safety and mobility along KY 8 (Mary Ingles Highway) from KY 2228 (Foster Road) to milepoint 2.78. | Reconstruction | Bracken | 012-KY-0008 -000 | 1.19 | 2.78 | 1.59 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 1500000 |  | 1000000 |  | 25000000 |  | 2015-01-28 10:19 | To improve safety and mobility | KY 8 in Bracken County has some significant slide issues in certain locations. The topography is challenging in this location due to the hillside on one side and the railroad tracks and river on the other. Safety and mobility is a concern in this area.
Y | 6 | Buffalo Trace ADD | IP20110041 |  |  |  | Improve safety and mobility along KY 8 (Mary Ingles Highway) from Willow Creek Road to Snag Creek Road. | Minor Widening | Bracken | 012-KY-0008 -000 | 3.597 | 4.004 | 0.407 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 200000 |  | 100000 |  | 2050000 |  | 2014-02-03 09:43 | To improve safety and mobility | KY 8 in Bracken County experiences slide issues due to it's location next to a hillside on one side and railroad tracks and river on the other side. Safety and mobility are a concern in this area for motorist, cyclists and freight.
Y | 6 | Buffalo Trace ADD | IP20110042 |  |  |  | Improve safety and mobility along KY 8 (Mary Ingles Highway) from East Snag Road to Ruff Road. | Minor Widening | Bracken | 012-KY-0008 -000 | 4.263 | 6.859 | 2.596 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 2000000 |  | 1000000 |  | 20000000 |  | 2015-02-11 13:57 | Improve safety and mobility | KY 8 in Bracken County experiences slides due to its location between a hillside on one side and railroad tracks and a river on the other. Safety and mobitilty for motorist, cyclist, and freight is a concern.
Y | 6 | Buffalo Trace ADD | IP20110043 |  |  |  | Reconstruct KY8 from Locust Creek Road to Wrangling Run Rd. **Note: This PIF has been modified from its original scope and cost. It has been broken into two sections. See PIF 06 012 D0008 8.00 for more information. | Reconstruction | Bracken | 012-KY-0008 -000 | 7.165 | 9.666 | 2.501 | Other Improvement Types | 0 |  | 0 |  | 1600000 |  | 2000000 |  | 1200000 |  | 12710000 |  | 2014-02-03 09:45 | To improve safety and mobility | Reconstruct KY 8 from Locust Creek Road to Wrangling Run Rd
Y | 6 | Northern Kentucky ADD | IP20110063 |  |  |  | Improve safety and mobility and address geometric deficiencies at the intersections of KY 36 & Commanche Trail and KY 36 & Boone Road. | Safety-Haz-Elm | Carroll | 021-KY-0036 -000 | 9.479 | 10.445 | 0.966 | Improve Intersection | 26 |  | 0 |  | 400000 |  | 400000 |  | 200000 |  | 4000000 |  | 2015-06-26 15:08 | Improve safety and mobility and address geometric deficiencies at the intersections of KY 36 & Commanche Trail and KY 36 & Boone Road. | Bad sighlines exiting Comanche Ln and Boone Rd on to route 36. Safety issues. IRI and CRF may be high. The Judge Executive and local residents are concerned about the high amount of truck traffic. Road may be curvy and narrow for truck traffic.
Y | 6 | Bluegrass ADD | IP20110106 |  |  |  | Improve safety and mobility along KY 32 from the west intersection with KY 1842 to the east intersection with KY 1842 in Connersville. | Spot Improvement | Harrison | 049-KY-0032 -000 | 2.821 | 3.154 | 0.333 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 500000 |  | 100000 |  | 1250000 |  | 2011-07-12 11:15 | Improve safety and mobility. | There have been three reported crashes between 1-1-2015 and 11-1-18; two were property damage only crashes and one crash involved an injury.
Y | 6 | Bluegrass ADD | IP20110107 |  |  |  | Improve safety at the intersection of KY 32 and KY 3018 (Mill Creek Road). | Reconstruction | Harrison | 049-KY-0032 -000 | 4.7 | 5.4 | 0.7 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 500000 |  | 200000 |  | 5000000 |  | 2014-03-07 12:46 | Improve safety. | There is a tight curve along KY 32 near this intersection. Sight distance appears to be poor.
Y | 6 | Bluegrass ADD | IP20110108 |  |  |  | Improve safety along KY 36 from KY 1054 to KY 356 | Reconstruction | Harrison | 049-KY-0036 -000 | 10.769 | 15.297 | 4.528 | Other Improvement Types | 0 |  | 0 |  | 6000000 |  | 4000000 |  | 2000000 |  | 38000000 |  | 2014-03-07 13:22 | Improve safety. | KY 36 is a winding road with multiple locations where there is poor sight distance. There have been seventy-six crashes reported on this road between 1-1-15 and 11-1-18; fifty-four of the these crashes were only property damage and twenty-two involved an
Y | 6 | Bluegrass ADD | IP20110109 |  |  |  | Improve safety along KY 36 from Renaker Berry Road to KY 1054 | Reconstruction | Harrison | 049-KY-0036 -000 | 5.854 | 10.769 | 4.915 | Other Improvement Types | 0 |  | 0 |  | 6000000 |  | 4000000 |  | 2000000 |  | 38000000 |  | 2014-03-07 13:32 | Improve safety. | KY 36 is a winding road with multiple locations where there is poor sight distance. There have been thirty crashes reported on this road between 1-1-15 and 11-1-18; twenty-one of these crashes were only property damage and nine involved an injury.
Y | 6 | Bluegrass ADD | IP20110110 |  |  |  | Improve safety along KY 36 from KY 1032 to Renaker Berry Road | Reconstruction | Harrison | 049-KY-0036 -000 | 0.955 | 5.854 | 4.899 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 5000000 |  | 1000000 |  | 40000000 |  | 2012-01-27 15:36 | Improve safety. | KY 36 is a winding road with multiple locations where there is poor sight distance. There have been nine crashes reported on this road between 1-1-15 and 11-1-18; eight of the nine crashes were property damage and one involved an injury.
Y | 6 | Bluegrass ADD | IP20110111 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 62 (Oddville Pike) from KY 392 (Republican Pike) to Salem Pike. | Spot Improvement | Harrison | 049-US-0062 -000 | 10.259 | 11.7 | 1.441 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2500000 |  | 1000000 |  | 10000000 |  | 2017-03-21 09:59 | Improve safety and mobility and address geometric deficiencies along US 62 (Oddville Pike) from KY 392 (Republican Pike) to Salem Pike. | High critical rate factor, significant congestion and pavement issues are present on this segment of US 62. Truck traffic is a signifficant segment of the ADT on the road with narrow shoulders. | BLUEGRASS ADD | North | 26.4088 | 1.8954 | 7.8462 | 4.8692 | 2.4923 | 0 | 2.0308 | 7.275 | 26
Y | 6 | Bluegrass ADD | IP20110112 |  |  |  | Improve safety along US 62 from Salem Pike to KY 3003 | Reconstruction | Harrison | 049-US-0062 -000 | 11.9 | 15 | 3.1 | Other Improvement Types | 0 |  | 0 |  | 4000000 |  | 3000000 |  | 2000000 |  | 31000000 |  | 2018-11-09 08:57 | Improve safety. | This section of road is winding. There have been twenty-eight crashes reported on this section of road between 1-1-15 and 11-1-18; nineteen of these crashes only involved property damage and nine involved at least one injury.
Y | 6 | Bluegrass ADD | IP20110113 |  |  |  | Improve safety along US 62 from KY 3003 to Smalley Branch Rd. | Reconstruction | Harrison | 049-US-0062 -000 | 14.9 | 17.7 | 2.8 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 3000000 |  | 2000000 |  | 28000000 |  | 2018-11-09 09:03 | Improve safety. | This section of road is winding. There have been sixteen crashes reported on this section of road between 1-1-15 and 11-1-18; fourteen of these crashes only involved property damage and two involved at least one injury.
Y | 6 | Bluegrass ADD | IP20110114 |  |  |  | Improve safety along US 62 from Barlow Road to KY 19 | Reconstruction | Harrison | 049-US-0062 -000 | 20.145 | 22.051 | 1.906 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 1000000 |  | 500000 |  | 13000000 |  | 2014-03-07 14:03 | Improve safety. | There have been eleven crashes reported on this section of road between 1-1-15 and 11-1-18; ten of these crashes only involved property damage and one involved at least one injury.
Y | 6 | Bluegrass ADD | IP20110115 |  |  |  | Improve safety along KY 1284 from US 27 to Falmouth Sunrise Road | Reconstruction | Harrison | 049-KY-1284 -000 | 0 | 2.742 | 2.742 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 1000000 |  | 500000 |  | 17000000 |  | 2014-03-07 14:51 | Improve safety. | KY 1284 is a winding road with multiple locations where there is poor sight distance. There have been twelve crashes reported on this section of road between 1-1-15 and 11-1-18; ten of these crashes were only property damage and two involved an injury.
Y | 6 | Bluegrass ADD | IP20110116 |  |  |  | Improve safety along KY 1284 from Falmouth Sunrise Road to US 62 in Harrison County. | Reconstruction | Harrison | 049-KY-1284 -000 | 2.742 | 6.365 | 3.623 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 750000 |  | 500000 |  | 25000000 |  | 2011-07-14 11:52 | Improve safety. | KY 1284 is a winding road with multiple locations where there is poor sight distance. There have been ten crashes reported on this section of road between 1-1-15 and 11-1-18; nine crashes were property damage and one involved an injury.
Y | 6 | Buffalo Trace ADD | IP20110117 |  |  |  | Reconstruct KY 22 from the Pendleton County Line to KY 10 | Reconstruction | Bracken | 012-KY-0022 -000 | 0 | 4.387 | 4.387 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 500000 |  | 16000000 |  | 2017-03-23 08:24 | To improve safety and moility | Reconstruct KY 22 from the Pendleton County Line to KY 10
Y | 6 | Buffalo Trace ADD | IP20110121 |  |  |  | Improve safety & mobility, and address geometric deficiencies along KY 165 (Blue Lick Pike) from KY 1476 (Thomas Pike) to US 62. | Reconstruction | Robertson | 101-KY-0165 -000 | 6.908 | 9.543 | 2.635 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3000000 |  | 1000000 |  | 19000000 |  | 2015-02-15 12:05 | Improve safety and mobility as well as address geometric deficiencies along KY 165 | KY 165 is a windy narrow road with little to no shoulders that lead from Mount Olivet south to US 68. The road is in need of geometric improvements for safety reasons.
Y | 6 | Northern Kentucky ADD | IP20110122 |  |  |  | Improve safety and address geometric deficiencies along KY 18 from Caroline Williams Way to KY 338; include multi-modes. | Reconstruction | Boone | 008-KY-0018 -000 | 9.258 | 10.443 | 1.185 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 1000000 |  | 10000000 |  | 2013-08-06 09:14 |  | Improve safety and correct geometric deficiencies
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20110123 |  |  |  | Improve safety & mobility, and address geometric deficiencies along KY 338 (Richwood Rd. ) from Hicks Pike to Triple Crown Boulevard. | Major Widening | Boone | 008-KY-0338 -000 | 0.756 | 1.35 | 0.594 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1000000 |  | 500000 |  | 5000000 |  | 2015-02-16 16:18 | TBD | With growing population in Boone County the need for wider roads is becoming a priority for KY 338. | 6 | North | 37.4769 | 7.2 | 7.1538 | 4.6154 | 3.4923 | 8.6769 | 0 | 6.3385 | 38
Y | 6 | Northern Kentucky ADD | IP20110140 |  |  |  | Construct a new connections from Needham Lane to Hyde Road on east side of the Norfork Southern Railroad (2 miles) | New Route | Grant | 041-US-0025 -000 | 18.68 | 20.855 | 2.175 | Construct Road in New Location | 0 |  | 0 |  | 2000000 |  | 3000000 |  | 4000000 |  | 17500000 |  | 2011-08-09 11:06 | Construct a new connections from Needham Lane to Hyde Road on east side of the Norfork Southern Railroad (2 miles) | Improve safety and eliminate at grade railroad crossings
Y | 6 | Northern Kentucky ADD | IP20110141 |  |  |  | Improve safety, mobility, geometrics along KY 22 (Gratz Road) from KY 355 north to milepoint 2.3. | Spot Improvement | Owen | 094-KY-0022 -000 | 0.31 | 2.3 | 1.99 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 1500000 |  | 1000000 |  | 15000000 |  | 2015-06-26 14:44 | Improve safety and eliminate geometric deficiencies along KY 22 (Gratz Road) from KY 355 north to milepoint 2.3. | KY 22 is the main cross county highway in Owen County to access I-75. KY 22 in curvy and narrow and in need of geometric upgrades to improve safety and traffic flow. | NORTHERN KENTUCKY ADD | North | 21.5208 | 0.24 | 4.8 | 3.3577 | 4.4154 | 0 | 0 | 8.7077 | 22
Y | 6 | Northern Kentucky ADD | IP20110142 |  |  |  | Improve safety, mobility, and geometrics along KY 22 (Gratz Road) from Morgan Road to Hide Away Drive. | Spot Improvement | Owen | 094-KY-0022 -000 | 3.978 | 6.373 | 2.395 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 1750000 |  | 750000 |  | 19000000 |  | 2015-02-16 14:11 | Improve safety and mobility and address geometric deficiencies along KY 22 (Gratz Road) from Morgan Road to Hide Away Drive. | KY 22 is the main cross county highway in Owen County that accesses I-75. It is curvy and narrow and in need of geometric upgrades to improve safety and traffic flow. | NORTHERN KENTUCKY ADD | North | 19.9254 | 0.59077 | 4.3846 | 3.6115 | 4.2 | 0 | 0 | 7.1385 | 20
Y | 6 | Northern Kentucky ADD | IP20110143 |  |  |  | Improve safety, mobility, and geometrics along KY 22 (Gratz Road) from Hide Away Drive to KY 1670 (Davis Lake Road). | Spot Improvement | Owen | 094-KY-0022 -000 | 6.373 | 8.526 | 2.153 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 1500000 |  | 500000 |  | 17000000 |  | 2015-02-16 14:25 | Improve safety and mobility and address geometric deficiencies along KY 22 (Gratz Road) from Hide Away Drive to KY 1670 (Davis Lake Road). | KY 22 is the main cross county highway for Owen County to I-75. The road in narrow and curvy with little or no shoulders. Geometric improvements are needed to improve safety and traffic flow. | NORTHERN KENTUCKY ADD | North | 19.4538 | 1.0154 | 4.1077 | 3.3 | 4.0769 | 0 | 0 | 6.9538 | 20
Y | 6 | Northern Kentucky ADD | IP20110144 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 22 (Seminary Street) from KY 1670 (Davis Lake Road) to US 127 (Main Street). | Minor Widening | Owen | 094-KY-0022 -000 | 8.526 | 9.467 | 0.941 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 500000 |  | 500000 |  | 9000000 |  | 2011-08-09 15:53 | Improve safety and mobility and address geometric deficiencies along KY 22 (Seminary Street) from KY 1670 (Davis Lake Road) to US 127 (Main Street). | This is the last part of the KY 22 reconstruction into Owenton. KY 22 in the main cross county corridor for Owen County to I-75.
Y | 6 | Northern Kentucky ADD | IP20110231 |  |  |  | Construct a new connection on the east side of the Norfork Southern Railroad tracks from the Dry Ridge By Pass to Dry Ridge Road | New Route | Grant | 041-CR-1043 -000 | 0 | 0.592 | 0.592 | Construct Road in New Location | 0 |  | 0 |  | 1000000 |  | 500000 |  | 1000000 |  | 10000000 |  | 2017-02-10 13:18 | Construct a new connection on the east side of the Norfork Southern Railroad tracks from the Dry Ridge By Pass to Dry Ridge Road | Improve safety and eliminate at grade railroad crossings
Y | 6 | Bluegrass ADD | IP20120053 |  |  |  | Reconstruct US 62 from KY 353 to the new Cynthiana Bypass. | Reconstruction | Harrison | 049-US-0062 -000 | 5.6 | 9 | 3.4 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 1000000 |  | 250000 |  | 25000000 |  | 2013-05-06 14:22 | Reconstruct US 62 from KY 353 to the new Cynthiana Bypass. | Lack of adequate passing lanes has been identified.
Y | 6 | Bluegrass ADD | IP20130001 |  |  |  | Improve safety and mobility and address geometric deficiencies along US 27 from the Bourbon Co line to US 62 (Cynthiana Bypass Jct). | Minor Widening | Harrison | 049-US-0027 -000 | 0 | 4.135 | 4.135 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 5000000 |  | 3000000 |  | 32000000 |  | 2013-01-15 10:05 | Improve safety and mobility and address geometric deficiencies along US 27 from the Bourbon Co line to US 62 (Cynthiana Bypass Jct). | Update to current design standards.
Y | 6 | Northern Kentucky ADD | IP20130008 | 6-446 |  | A | PROVIDE EAST-WEST CONNECTIVITY AND IMPROVED MOBILITY FROM KY-237 (PLEASANT VALLEY ROAD) THRU KY-842 (HOPEFUL CHURCH ROAD) TO MALL ROAD/I-75 INTERCHANGE. (18CCR) | NEW ROUTE(O) | Boone | 008-US-0042 -000 | 12.508 | 13.489 | 0.981 | Construct Road in New Location | 0 | Y |  |  | 1500000 | 2020 | [6 empty] | 2018-07-10 08:17 |  | Additional east-west connectivity is needed to support continual growth of Boone County. This connectivity would provide much needed congestion relief and increased safety along US 42. Additional capacity to the 5-lane US 42 is challenging as R/W costs | Cincinnati/Northern Kentucky MPO | North | 75.9215 | 8.8677 | 7.6615 | 13.8231 | 1.3077 | 9.5077 | 4.7538 | 0 | 46 | 15 | 15
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20130009 |  |  |  | Improve mobility along KY 1072 (Kyles Lane) from Interstate 75 to Henry Clay Ave. | Minor Widening | Kenton | 059-KY-1072 -000 | 2.489 | 2.7 | 0.211 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 200000 |  | 200000 |  | 1000000 |  | 2013-05-03 10:23 | TBD | address congestion along this roadway segment Add one lane on KY 1072 from IR 75 to Henry Clay Ave - OKI 2040 Plan, 2012 Update (#707)
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20130010 |  |  |  | Provide connectivity and improve mobility between KY 177 (Decoursey Pike) and I-275. | New Route | Kenton | 059-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 250000 |  | 5000000 |  | 10000000 |  | 3000000 |  | 35000000 |  | 2019-02-20 10:06 | Provide connectivity and improve mobility between KY 177 (Decoursey Pike) and I-275. | This is a HIGH priority recommendation in the KCTP 6/14. Improve multi-modal transportation (freight truck and commuter traffic) mobility, connectivity and access from KY 177 to interstate I-275. •This recommendation is intended to improve east/west conn
Y | 6 | Northern Kentucky ADD | IP20130018 |  |  |  | Improve mobility and reduce congestion at the interchange of I-275 and KY 3076 (Mineola Pike). | Reconstruction | Boone | 008-I -0275 -000 | 1.7 | 2.4 | 0.7 | Other Improvement Types | 0 | Y | 0 |  | 1000000 |  | 100000 |  | 500000 |  | 8000000 |  | 2013-05-03 14:39 |  | Enhance traffic mobility and reduce congestion
Y | 6 | Northern Kentucky ADD | IP20130020 |  |  |  | Provide connectivity along KY 1501 (Hands Pike) from KY 16 to KY 177 (Decoursey Pike). | New Route | Kenton | 059-KY-1501 -000 | 0 | 0.002 | 0.002 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 200000 |  | 150000 |  | 10000000 |  | 2016-10-31 10:20 |  | Provide connectivity KY 1501 (Hands Pike) Extension on new alignment from KY 16 to KY 177 (Decoursey Pike)
Y | 6 | Northern Kentucky ADD | IP20130021 |  |  |  | Improve safety and reduce congestion along Hicks Pike (CR 1151) from US 42 to KY 338. | Minor Widening | Boone | 008-CR-1151 -000 | 0 | 2.51 | 2.51 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 9000000 |  | 750000 |  | 10000000 |  | 2013-08-05 15:23 |  | Hicks Rd is a winding narrow road with little to no shoulders. Improved east-west connectivity and safety is needed for this road.
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20130022 |  |  |  | Provide freight connectivity and improve mobility between Aero Parkway (KY 1017) to Limaburg Road. | New Route | Boone | 008-KY-0237 -000 | 6.269 | 7.921 | 1.652 | Construct Road in New Location | 0 | Y | 0 |  | 2000000 |  | 2000000 |  | 1000000 |  | 14000000 |  | 2017-04-26 14:46 | TBD | Enhance economic vitality, improve congestion and travel time. Improve access to CVG. | Cincinnati/Northern Kentucky MPO | North | 28.5923 | 5.3846 | 0 | 9.5769 | 0 | 9.3231 | 4.3077 | 0 | 29
Y | 6 | Northern Kentucky ADD | IP20130023 |  |  |  | Provide connectivity from the KY 14 (Mary Grubbs Hwy) intersection with US 25 (Dixie Hwy) to the KY 17/KY 16 intersection. | New Route | Boone | 008-KY-0016 -000 | 2.8 | 3.3 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 5000000 |  | 20000000 |  | 5000000 |  | 42000000 |  | 2013-05-06 15:13 |  | Improve economic vitality and connectivity Construct new alignment/facility from the new Mary Grubbs Highway railroad bridge eastward to KY 17 near the KY 17/KY 16 intersection.
Y | 6 | Northern Kentucky ADD | IP20130024 |  |  |  | Improve safety and reduce congestion along KY 824 from KY 1121 to US 27 | Reconstruction | Campbell | 019-KY-0824 -000 | 0 | 3.069 | 3.069 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 12000000 |  | 1000000 |  | 30000000 |  | 2013-05-06 15:48 |  | Improve safety and address congestion
Y | 6 | Northern Kentucky ADD | IP20130029 |  |  |  | Improve safety and mobility on US 42 from the Carroll County line to KY 1039. | Minor Widening | Gallatin | 039-US-0042 -000 | 0 | 3.325 | 3.325 | Modernize Roadway-Rural | 26 |  | 0 |  | 3500000 |  | 2000000 |  | 1500000 |  | 24000000 |  | 2013-08-14 11:09 | Improve safety and mobility by bringing US 42 up to modern standards to provide additional through standards from the Carroll County line to KY 1039. | This will be an extension of the US 42 project in Carroll Co. Many trucks travel this route and would increase flow and safety along US 42 to Rt 1039. | NORTHERN KENTUCKY ADD | North | 58.4038 | 2.9846 | 5.8615 | 6.7731 | 1.2923 | 0 | 2.3538 | 9.1385 | 28 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20130030 |  |  |  | Reconstruct KY 330 from KY 845 (north junction)to Canby Ln. | Reconstruction | Owen | 094-KY-0330 -000 | 5.375 | 10.164 | 4.789 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 3000000 |  | 1000000 |  | 40000000 |  | 2014-04-02 12:30 | Improve safety and mobility and address geometric deficiencies along KY 330 (Owenton Road) from KY 845 (north junction)to Canby Ln. | KY 330 in Owen County is a connector to I-75 near Corinth. The road is curvy and in need of geometric upgrades.
Y | 6 | Northern Kentucky ADD | IP20130031 |  |  |  | Reconstruct KY 845 from KY 330 to KY 22. | Reconstruction | Owen | 094-KY-0845 -000 | 11.326 | 13.951 | 2.625 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2000000 |  | 1000000 |  | 20000000 |  | 2014-04-02 13:35 | Bring KY 845 up to geometric standards by Reconstructing KY 845 from KY 330 to KY 22. | To connect the interior of Owen Co with I-75
Y | 6 | Northern Kentucky ADD | IP20130040 |  |  |  | Address safety and mobility on US 42 at the Gallatin Steel Administration building. | Safety-Haz-Elm | Gallatin | 039-US-0042 -000 | 0.7 | 1.1 | 0.4 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 500000 |  | 250000 |  | 2000000 |  | 2015-02-17 13:10 | Address safety and mobility on US 42 at the Gallatin Steel Administration building by adding much needed turn lanes. | US 42 in Gallatin County is a heavily traved truck route to access industry along the Ohio River. Turning lanes are needed at the Gallatin Steel Admnistration building to increase safety and improve traffic flow.
Y | 6 | Northern Kentucky ADD | IP20130053 |  |  |  | Address safety and mobility along KY 2373 (Bromley Crescent Springs Rd) from west intersection with Amsterdam Rd to Highwater Rd. | Major Widening | Kenton | 059-KY-2373 -000 | 4.13 | 4.988 | 0.858 | Other Improvement Types | 0 |  | 0 |  | 1440000 |  | 1060000 |  | 2120000 |  | 8140000 |  | 2014-06-16 14:56 |  | Reduce congestion and increase accessibility, mobility and multi-modal transportation options Multi-modal improvement to the Bromley Crescent Springs Rd corridor from west intersection with Amsterdam Rd to Highwater Road to address high existing traffic
Y | 6 | Northern Kentucky ADD | IP20130055 |  |  |  | Address safety along Edgewood Rd from US 25 (Dixie Hwy) to KY 1303 (Turkeyfoot Rd). | Reconstruction | Kenton | 059-CS-4115 -000 | 0 | 0.717 | 0.717 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 4000000 |  | 3000000 |  | 9000000 |  | 2013-05-31 14:53 |  | Increase safety and traffic flow Reconstruct Edgewood Rd from US 25 (Dixie Highway) to Turkeyfoot Rd.; includes sidewalks on both sides. This project was raised during the 2013 MPO UPL ranking process. Edgewood Rd is not functionally classified.
Y | 6 | Northern Kentucky ADD | IP20130056 |  |  |  | Address safety along CS 2215 (Sixth St) from Scott to Johnson streets. | Reconstruction | Kenton | 059-CS-2206 -000 | 0.276 | 0.515 | 0.239 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 100000 |  | 500000 |  | 1500000 |  | 2013-06-14 10:07 |  | Increase safety and traffic flow.
Y | 6 | Northern Kentucky ADD | IP20130057 |  |  |  | Address safety and geometric deficiencies along KY 14 (Rich Rd) from KY 17 to KY 177. | Reconstruction | Kenton | 059-KY-0014 -000 | 3.29 | 8.37 | 5.08 | Other Improvement Types | 0 |  | 0 |  | 7500000 |  | 14560000 |  | 5000000 |  | 50000000 |  | 2014-08-13 11:27 |  | Relieve congestion and improve safety. Reconstruct and widen. install guard rails as needed on KY 14 (Rich Rd) from KY 17 to KY 177. This is a LOW priority recommendation in the KCTP 6/14.
Y | 6 | Northern Kentucky ADD | IP20130058 |  |  |  | Provide connectivity and improve mobility from KY 3060 (Frogtown Road) to KY 536 (Mt. Zion Road). | New Route | Boone | 008-KY-3060 -000 | 0 | 2.726 | 2.726 | Construct Road in New Location | 0 |  | 75000 |  | 2925000 |  | 11000000 |  | 1200000 |  | 17500000 |  | 2015-02-16 15:55 |  | Growth in Boone County necessitates an increase to connectivity and mobility. A Frogtown Rd Connector Extension provides an north-south connection instead of local traffic using I-75. Proposed project begins at KY 3060 and Frogtown Rd Connector and go
Y | 6 | Northern Kentucky ADD | IP20130068 |  |  |  | Improve safety along KY 18 (Burlington Pike) from KY 20 (Belleview Rd) to Middle Creek Rd. | Spot Improvement | Boone | 008-KY-0018 -000 | 3.5 | 4.5 | 1 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1000000 |  | 990000 |  | 7000000 |  | 2013-05-31 16:25 |  | Safety
Y | 6 | Northern Kentucky ADD | IP20130081 |  |  |  | Improve existing grade separated railroad crossing over KY 467 to correct geometric deficiencies and raise road out of flood plain. | Safety-Haz-Elm | Gallatin | 039-KY-0467 -000 | 3.3 | 3.7 | 0.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 700000 |  | 200000 |  | 300000 |  | 4500000 |  | 2017-05-21 17:18 | Improve existing grade separated railroad crossing over KY 467 to correct geometric deficiencies and raise road out of flood plain. | Ex. KY 467 alignment has abrupt s-curve undernear of RR and KY 467 goes over Lost Creek, which is a tributary of nearbly Eagle Creek. This area per FEMA is in Flood Zone A. A family of 5 were killed when trying to navigate the RR underpass.
Y | 6 | Northern Kentucky ADD | IP20130082 | 6-79 |  | A | IMPROVE SAFETY, MOBILITY, OPERATIONS, AND GEOMETRICS AT THE JUNCTION OF I-75 AND I-275 AND THE SYSTEM-TO-SYSTEM RAMPS. | CONGESTION MITIGTN(O) | Boone | 008-I -0075 -000 | 182.2 | 183.312 | 1.112 | Innovative Interchange | 40 | Y |  |  | 0 | 2019 | [6 empty] | 2018-11-16 12:46 |  | I-75 NB lanes are typically congested from Exit 184 (KY 236) thru the I-275 junction towards Exit 186. The SB collector/distributor ramp from I-275 ramps to SB I-75 experiences heavy traffic and frequent backups during the evening rush hour. The num | 6 | Statewide | 70.3292 | 18.9427 | 9.4273 | 13.5793 | 4.4053 | 2.7313 | 9.8678 | 11.3755
Y | 6 | Northern Kentucky ADD | IP20130083 |  |  |  | Improve safety and mobility on US 27 at the KY 17 intersection. | Spot Improvement | Pendleton | 096-US-0027 -000 | 11.6 | 12 | 0.4 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 150000 |  | 2500000 |  | 2015-06-26 10:13 | Improve connectivty and safety in the region by adding turn lanes on US 27 at the KY 17 intersection to improve safety and mobility. | US 27 is a 2-lane, high speed, high volume facility with no left turn lane on northbound US 27 at KY 17. Through vehicles have to wait on left turning vehicles at this intersection. | NORTHERN KENTUCKY ADD | North | 44.2669 | 5.84 | 9.2308 | 4.9038 | 1.3538 | 0 | 3.5077 | 4.4308 | 29 |  | 15
Y | 6 | Northern Kentucky ADD | IP20130085 |  |  |  | Improve safety and mobility and address geometric deficiences along KY 330 (Owenton Rd) from KY 607 (New Columbus Rd) at the Owen Co. line to US 25 in Corinth. | Reconstruction | Grant | 041-KY-0330 -000 | 0 | 3.253 | 3.253 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3500000 |  | 1500000 |  | 28000000 |  | 2015-02-10 08:14 | Improve safety and mobility and address geometric deficiences along KY 330 (Owenton Rd) from KY 607 (New Columbus Rd) at the Owen Co. line to US 25 in Corinth. | Per Owen Co. Judge Executive Keith, KY 330 provides residential access for Owen County to Central KY (Lexington) where there are places of employment. KY 330 is narrow, windy and in poor condition.
Y | 6 | Northern Kentucky ADD | IP20130086 |  |  |  | Improve safety and mobility on US 27 at the KY 22 intersection. | Spot Improvement | Pendleton | 096-US-0027 -000 | 10 | 10.4 | 0.4 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 150000 |  | 2500000 |  | 2015-02-13 13:23 | Improve connectivty and safety in the region by adding turn lanes on US 27 at the KY 22 intersection to improve safety and mobility. | US 27 is a 2-lane, high volume & high speed facility with no left turn lane on northbound US 27 at KY 22. Through vehicles have to stop for left turning vehicles. | NORTHERN KENTUCKY ADD | North | 26.4762 | 5.8646 | 8.3538 | 2.9654 | 1.3538 | 0 | 3.5077 | 4.4308 | 26
Y | 6 | Northern Kentucky ADD | IP20130087 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 330 (Owenton Road) from Canby Lane to KY 607 (New Columbus Road). | Reconstruction | Owen | 094-KY-0330 -000 | 10.164 | 14.222 | 4.058 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 4000000 |  | 2000000 |  | 30000000 |  | 2015-02-16 15:06 | Improve safety and mobility and address geometric deficiencies along KY 330 (Owenton Road) from Canby Lane to KY 607 (New Columbus Road). | KY 330 in Owen County is a connector to I-75 near Corinth. The road is curvy and in need of geometric upgrades.
Y | 6 | Northern Kentucky ADD | IP20130113 |  |  |  | Reduce congestion and improve mobility along KY 2847 (Empire Drive) from KY 1829 (Industrial Road) to KY 3503 (Empire Connector); include multi-modes. | Major Widening | Boone | 008-KY-3503 -000 | 1.047 | 1.674 | 0.627 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 1000000 |  | 400000 |  | 6000000 |  | 2013-08-26 10:48 |  | KY 3503 is an industrial access road in Boone County. The pavement is in need of reconstruction due to the heavy trucks that frequent the road.
Y | 6 | Northern Kentucky ADD | IP20130114 |  |  |  | Reduce congestion and improve mobility along KY 2847 (Empire Drive) from KY 3503 (Empire Connector) to US 25 (Dixie Highway); include multi-modes. | Major Widening | Boone | 008-KY-2847 -000 | 0 | 0.726 | 0.726 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 1000000 |  | 600000 |  | 7000000 |  | 2013-08-26 10:57 |  | KY 2847 provides a direct access for trucks to US 25 from the Industrial Park. The road needs to be reconstructed and widened to three lanes accomodate the truck traffic.
Y | 6 | Northern Kentucky ADD | IP20130118 |  |  |  | Construct new interchange on I-71 at KY 455 in Gallatin County. | New Interchange | Gallatin | 039-I -0071 -000 | 59 | 60.9 | 1.9 | Construct Road in New Location | 0 | Y | 500000 |  | 6000000 |  | 1000000 |  | 500000 |  | 20000000 |  | 2014-05-01 10:07 | Increase safety, ease of travel, and travel times on I-71 by constructing a new interchange on I 71 at KY 455. | Industrial traffic located along US 42 & the Ohio River results in all tractor trailers accessing I-71 via KY 227 in Carrollton. An interstate access point located in Gallatin County would eliminate back-tracking approx. 17 miles. Also, many local r
Y | 6 | Northern Kentucky ADD | IP20130119 |  |  |  | Reconstruct Baton Rouge Rd (US 25X, CS 1051, KY 2940)from I-75 overpass to US 25 (Arnie Risen Blvd). (Length 0.5 miles.) | Reconstruction | Grant | 041-US-0025X -000 | 0.252 | 0.345 | 0.093 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 500000 |  | 250000 |  | 2000000 |  | 2013-08-26 14:02 | Reconstruct Baton Rouge Rd (US 25X, CS 1051, KY 2940)from I-75 overpass to US 25 (Arnie Risen Blvd). (Length 0.5 miles.) | Grant County recently constructed (~2010) a County Fairgrounds along Baton Rouge Road. The existing road is 2 narrow lanes and minimal shoulders.
Y | 6 | Bluegrass ADD | IP20130120 |  |  |  | Reconstruction of US 62 from Smalley Branch Rd to Barlow Road to correct geometric issues. | Reconstruction | Harrison | 049-US-0062 -000 | 21.264 | 22.051 | 0.787 | Other Improvement Types | 0 |  | 0 |  | 3000000 |  | 2000000 |  | 1000000 |  | 18000000 |  | 2014-03-07 14:16
Y | 6 | Bluegrass ADD | IP20130121 |  |  |  | Improve safety and mobility at the intersection of US 62 (Oddville Pike) at KY 1284 (Sunrise-Claysville Road). | Safety-Haz-Elm | Harrison | 049-US-0062 -000 | 21.289 | 21.489 | 0.2 | Improve Intersection | 26 |  | 0 |  | 150000 |  | 200000 |  | 50000 |  | 1000000 |  | 2015-06-26 14:06 |  | The intersection has sight distance deficiencies.
Y | 6 | Northern Kentucky ADD | IP20130122 |  |  |  | Address safety and mobility along KY 16 from KY 177 (Ritte's Corner) to KY 17 (Madison Ave). | Reconstruction | Kenton | 059-KY-0016 -000 | 14.873 | 15.844 | 0.971 | Other Improvement Types | 0 | Y | 0 |  | 700000 |  | 400000 |  | 500000 |  | 7000000 |  | 2013-08-26 15:08 |  | Increase mobility and safety. Reconstruction of pavement and drainage on KY 16 from KY 177 (Ritte's Corner) to KY 17 (Madison Ave).
Y | 6 | Northern Kentucky ADD | IP20130123 |  |  |  | Improve safety at the intersection of KY 17 and KY 3072 (Hempfling Rd). | Reconstruction | Kenton | 059-KY-0017 -000 | 6.9 | 7.3 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 100000 |  | 50000 |  | 500000 |  | 2013-08-26 15:17 |  | Improve safety and mobility. This is a LOW priority recommendation in the KCTP 6/14.
Y | 6 | Northern Kentucky ADD | IP20130124 |  |  |  | Reconstruct KY 3549 to eliminate sharp curves | Reconstruction | Owen | 094-KY-3549 -000 | 0.7 | 1.2 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 400000 |  | 100000 |  | 4000000 |  | 2014-04-02 14:13 | Increase safety and mobility by Reconstructing KY 3549 to eliminate sharp curves. | KY 3549 has a curvy stretch around Greenup Creek that needs to be straighten and widened to improve safety.
Y | 6 | Northern Kentucky ADD | IP20130125 |  |  |  | Reconstruction of KY 17 from MP 3.7 to 5.3 | Reconstruction | Pendleton | 096-KY-0017 -000 | 3.7 | 5.3 | 1.6 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 1500000 |  | 500000 |  | 12000000 |  | 2014-05-02 14:02 | Reconstruction of KY 17 from MP 3.7 to 5.3 to bring the road up to current geometric standards. | This section of KY 17 in Pendleton County is very curvy with little or no shoulders resulting in a dangerous road. Safety improvements need to be made.
Y | 6 | Buffalo Trace ADD | IP20130126 |  |  |  | Improve safety and mobility at the intersection of KY 1476 (Thomas Pike) and White Road. | Reconstruction | Robertson | 101-KY-1476 -000 | 1 | 1.2 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 50000 |  | 150000 |  | 50000 |  | 500000 |  | 2013-08-26 15:56 | To improve safety and mobility | The intersection of KY 1486 (Thomas Pike) and White Road is in a sharp curve and needs safety improvements.
Y | 6 | Buffalo Trace ADD | IP20130127 |  |  |  | Improve safety and mobility at the intersection of KY 617 (Piqua-Kentontown Rd) & KY 165 (Blue Lick Pike). | Reconstruction | Robertson | 101-KY-0617 -000 | 5.2 | 5.363 | 0.163 | Other Improvement Types | 0 |  | 0 |  | 50000 |  | 100000 |  | 100000 |  | 500000 |  | 2013-08-26 16:09 | To improve safety and mobility | Realignment to improve safety
Y | 6 | Bluegrass ADD | IP20130148 |  |  |  | KY 32 east of Cynthiana is a narrow winding rural highway with geometric deficiencies and narrow shoulders. This project would address spot improvements along this corridor to correct these deficiencies and narrow shoulder widths from Harrison Memorial Ho | Safety-Haz-Elm | Harrison | 049-KY-0032 -000 | 10.4 | 14.581 | 4.181 | Other Improvement Types | 0 |  | 0 |  | 4500000 |  | 3500000 |  | 3000000 |  | 30000000 |  | 2014-03-07 12:53 | KY 32 east of Cynthiana is a narrow winding rural highway with geometric deficiencies and narrow shoulders. This project would address spot improvements along this corridor to correct these deficiencies and narrow shoulder widths from Harrison Memorial Ho | Correct geometric deficiencies and narrow shoulder widths along KY 32 east of Cynthiana from Harrison Memorial Hospital to the Bourbon County line.
Y | 6 | Buffalo Trace ADD | IP20140001 |  |  |  | Improve safety and mobility along KY 10 (Powersville-Willow Road) from KY 22 (Willow-Neave Road) to KY 19 (Powersville-Harrsion Co Road). | Reconstruction | Bracken | 012-KY-0010 -000 | 7.728 | 10.38 | 2.652 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 2500000 |  | 750000 |  | 20000000 |  | 2017-03-23 07:56 | To improve safety and mobility | Widen and correct geometric deficiencies. | BUFFALO TRACE ADD | North | 22.4208 | 0.76308 | 5.0308 | 4.35 | 4.7077 | 0 | 0 | 7.5692 | 22
Y | 6 | Buffalo Trace ADD | IP20140004 |  |  |  | Improve safety and mobility along KY 8 (Mary Ingles Highway) from milepoint 2.78 to Willow Creek Road. | Minor Widening | Bracken | 012-KY-0008 -000 | 2.78 | 3.597 | 0.817 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 1000000 |  | 500000 |  | 13000000 |  | 2015-01-28 10:20 | To improve safety and mobility | Improve safety and mobility along KY 8 by doing minor widening of the road
Y | 6 | Buffalo Trace ADD | IP20140005 |  |  |  | Reconstruct KY 8 from Wrangling Run Rd to Old KY 19. | Reconstruction | Bracken | 012-KY-0008 -000 | 9.666 | 12.717 | 3.051 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2500000 |  | 1500000 |  | 15360000 |  | 2014-02-03 09:47 | To improve safety and mobility | Reconstruct KY 8 from Wrangling Run Rd to Old KY 19
Y | 6 | Northern Kentucky ADD | IP20140017 | 6-8951 |  | A | IMPROVE EXISTING ALIGNMENT WITH BUTTERMILK PIKE, ORPHANAGE ROAD, AND US 25. FT. MITCHELL WILL PAY $50,000 TOWARD DESIGN. (16CCN)(18CCN) | RECONSTRUCTION(O) | Kenton | 059-KY-0371 -000 | 1.6 | 1.817 | 0.217 | Realign Intersection | 26 |  |  |  | 520000 | 2019 | 19680000 | 2021 | 2250000 | 2022 | 4260000 | 2023 | 2018-07-10 08:18 |  | Project Benefits • Improved east/west connector between I- 71/ 75, U.S. 25 and KY 17 corridors all of which support numerous Kenton County population and employment centers. Enhanced traffic flow for U.S. 25. • Preservation of established businesses, co | Cincinnati/Northern Kentucky MPO | North | 21.9346 | 4.6154 | 4.4308 | 6.1962 | 2.5692 | 0 | 0 | 4.1231 | 22
Y | 6 | Northern Kentucky ADD | IP20140018 |  |  |  | Improve safety and mobility at the intersection of KY 8 (Third St) and KY 2374 (West Third St). | Reconstruction | Kenton | 059-KY-0008 -000 | 6.306 | 6.332 | 0.026 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 1000000 |  | 500000 |  | 1000000 |  | 2014-08-13 12:28 |  | Project Benefits • Roundabout will help ease congestion by creating free-flow traffic patterns. • Improved safety for motorists, pedestrians, bicyclists and transit riders. • Improved air quality, noise reduction and visual aesthetics for local residen
Y | 6 | Northern Kentucky ADD | IP20140019 |  |  |  | Improve safety and mobility along New Buffington Rd from the Kenton County Line to Garvey Ave. | Reconstruction | Kenton | 059-CS-5075 -000 | 0.22 | 0.711 | 0.491 | Other Improvement Types | 0 |  | 0 |  | 230000 |  | 890000 |  | 400000 |  | 1520000 |  | 2014-08-13 12:40 |  | This is a HIGH priority recommendation in the KCTP 6/14. Project Benefits • This improvement would expand multi-modal safety and use by expanding bicycle and pedestrian accommodations with existing paths on Garvey Avenue and Industrial Boulevard. • Cons
Y | 6 | Northern Kentucky ADD | IP20140020 |  |  |  | Improve safety and mobility along US 25 (Clay Wade Bailey Bridge) from KY 8 (Fourth St) to Ohio State Line. | Reconstruction | Kenton | 059-US-0025 -000 | 13.368 | 13.976 | 0.608 | Other Improvement Types | 0 |  | 0 |  | 5000 |  | 0 |  | 0 |  | 22000 |  | 2014-08-13 12:47 |  | Project Benefits • Motorist awareness of bicyclists will be improved, thereby increasing safety for all modes traveling these urban, high volume corridors. Project Challenges • Due to right of way limitations and narrow lane widths, bike lanes are no
Y | 6 | Bluegrass ADD | IP20140025 |  |  |  | Minor widening of KY 1842 from US 62 to KY 3044 in southwestern Harrison County to improve safety. | Minor Widening | Harrison | 049-KY-1842 -000 | 0 | 3.105 | 3.105 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3500000 |  | 2000000 |  | 17000000 |  | 2014-10-23 11:13 | Minor widening of KY 1842 from US 62 to KY 3044 in southwestern Harrison County to improve safety. | KY 1842 in a narrow winding two lane road with little or no shoulders that does not meet geometric standards. The road functions as a connector from KY 32 to US 62. Safety is a concern and lanes need to be widened with paved shoulders.
Y | 6 | Bluegrass ADD | IP20140026 |  |  |  | Minor widening of KY 1842 from KY 3044 to KY 32 in southwest Harrison County to improve safety. | Minor Widening | Harrison | 049-KY-1842 -000 | 3.105 | 6.214 | 3.109 | Other Improvement Types | 0 |  | 0 |  | 3500000 |  | 2500000 |  | 2000000 |  | 17000000 |  | 2014-10-23 11:29 | Minor widening of KY 1842 from KY 3044 to KY 32 in southwest Harrison County to improve safety. | KY 1842 is a narrow winding road with no shoulders that connects US 62 to KY 32 in Harrison County. The road does not meet current design standards and needs to be widened to improve safety and mobility through the region.
Y | 6 | Northern Kentucky ADD | IP20150012 |  |  |  | Improve safety and mobility and address geometric deficiencies along KY 36 from 0.1 mile east of Four Mile Road to KY 1204 (Goose Creek Road). | Minor Widening | Carroll | 021-KY-0036 -000 | 13 | 16.739 | 3.739 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 3000000 |  | 2000000 |  | 28000000 |  | 2015-02-06 15:53 | Improve safety and mobility and address geometric deficiencies along KY 36 from 0.1 mile east of Four Mile Road to KY 1204 (Goose Creek Road). | RI and CRF may be high. The Judge Executive and local residents are concerned with the high truck traffic on KY 36. This roadway needs to be brought up to modern standards to address safety and mobility issues.
Y | 6 | Northern Kentucky ADD | IP20150015 |  |  |  | Add a truck climbing lane on northbound US 27 from Menzie Bottoms Road to improve safety and mobility. | Minor Widening | Pendleton | 096-US-0027 -000 | 13.524 | 14.2 | 0.676 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 500000 |  | 200000 |  | 4000000 |  | 2015-02-13 09:05 | Add a truck climbing lane on northbound US 27 from Menzie Bottoms Road to improve safety and mobility will help provide through capacity up the hill. | A truck climbing lane on northbound US 27 from Menzie Bottoms Road is needed in large part due to the bus traffic coming from Sharp Middle School. A truck lane would help traffic flow up the hill here. | NORTHERN KENTUCKY ADD | North | 26.6362 | 5.7785 | 6.5538 | 3.4269 | 1.3538 | 0 | 3.4615 | 6.0615 | 27
Y | 6 | Northern Kentucky ADD | IP20150029 |  |  |  | Improve safety & mobility, reduce congestion and address geometric deficiencies along Camp Ernst Road (CR 1001) from KY 536 (Hathaway Rd) to Longbranch Rd (CR 1002). | Major Widening | Boone | 008-CR-1001 -000 | 2.169 | 4.108 | 1.939 | Local Roadway Improvements | 3 |  | 0 |  | 1700000 |  | 7000000 |  | 600000 |  | 11200000 |  | 2015-02-18 16:00 |  | Improve safety and multi-modal mobility associated to the continual growth of Boone Co. Subdivisions have and are developing along this corridor. Further, the corridor serves as access to Central Park / Arboretum, Knothole Ball fields and school campus.
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20150030 |  |  |  | Improve safety & mobility, reduce congestion and address geometric deficiencies along Camp Ernst Road (CR 1001) from Long Branch Rd. to KY 237 (Pleasant Valley Rd.) | Major Widening | Boone | 008-CR-1001 -000 | 0 | 2.169 | 2.169 | Modernize Roadway-Rural | 26 |  | 0 |  | 2400000 |  | 9500000 |  | 800000 |  | 15300000 |  | 2015-06-26 14:16 | TBD | Improve safety and multi-modal mobility associated to the continual growth of Boone Co. Subdivisions have & are developing along this corridor. Further, the corridor serves as access to Central Park / Arboretum, Knothole Ballfields and school campus. T | Cincinnati/Northern Kentucky MPO | North | 39.5269 | 3.8523 | 9.6 | 9.5423 | 3.8615 | 6.4308 | 0 | 6.24 | 40
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20150034 |  |  |  | Improve safety and reduce congestion along KY 842 (Richardson Rd) from Boone County line to KY 1303 (Turkeyfoot Rd) | Minor Widening | Kenton | 059-KY-0842 -000 | 0 | 0.713 | 0.713 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 400000 |  | 5000000 |  | 2017-05-05 13:28 | TBD | Improve safety and reduce congestion along an east-west route that connects Boone and Kenton Counties for people, goods and services. | Cincinnati/Northern Kentucky MPO | North | 29.8631 | 6.2092 | 7.3846 | 5.5154 | 2.2308 | 0 | 3.2308 | 5.2923 | 30
Y | 6 | Northern Kentucky ADD | IP20150053 |  |  |  | Improve safety, mobility, and geometrics along KY 22 (Gratz Road) from milepoint 2.3 to Morgan Road. | Spot Improvement | Owen | 094-KY-0022 -000 | 2.3 | 3.978 | 1.678 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 1500000 |  | 500000 |  | 13000000 |  | 2015-02-26 12:42 | Improve safety and mobility and address geometric deficiencies along KY 22 (Gratz Road) from milepoint 2.3 to Morgan Road. | KY 22 from Gratz to Owenton is a winding two lane road with little or no shoulders. Safety and mobility are a concern along this roadway. | NORTHERN KENTUCKY ADD | North | 16.7708 | 0.24 | 2.4462 | 1.5 | 4.3692 | 0 | 0 | 8.2154 | 17
Y | 6 | Northern Kentucky ADD | IP20150058 |  |  |  | Dry Ridge-Florence Road; 5-lane US 25 from Winning Colors Drive to Beesom Drive. (2006BOPC)(10CCR)(No build)(14CCN) Formerly 6-351.2 | Major Widening | Boone | 008-US-0025 -000 | 5.085 | 7.431 | 2.346 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 10000000 |  | 2000000 |  | 14000000 |  | 2015-03-04 15:18 |  | US 25 is a long established 2-lane corridor that serves as access to industry, commercial interests and residents. Traffic has significantly increased with corresponding detriment to safety and reliability. US 25 also provides a redundant roadway system
Y | 6 | Northern Kentucky ADD | IP20150059 |  |  |  | Reduce congestion and improve mobility along US 25 from Aristocrat Drive to RR spur crossing.(2004BOPC)(2006BOPC)(10CCR)(No build)(14CCN) Formerly 6-351.4 now part of 6-447. | Major Widening | Boone | 008-US-0025 -000 | 7.81 | 9.2 | 1.39 | Other Improvement Types | 0 |  | 0 |  | 1400000 |  | 6000000 |  | 1600000 |  | 9000000 |  | 2015-03-05 09:40 |  | US 25 is a long established 2-lane corridor that serves as access to industry, commercial interests and residents. Traffic has significantly increased with corresponding detriment to safety and reliability. US 25 also provides a redundant roadway system
Y | 6 | Buffalo Trace ADD | IP20150175 | 6-8711 |  | A | IMPROVE CURVE ON KY 616 AND IMPROVE ROADWAY FROM THE NEW ROBERTSON COUNTY SCHOOL TO MT OLIVET. (12CCN)(14CCR)(18CCN) | RECONSTRUCTION(O) | Robertson | 101-KY-0616 -000 | 6.3 | 6.514 | 0.214 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 270000 | 2020 | 220000 | 2020 | 2710000 | 2021 | 2018-07-10 08:18 | The purpose of this project is to improve a curve on KY 616 and improve the roadway from the new school to Mt. Olivet | Improve a curve on KY 616 | BUFFALO TRACE ADD | North | 12.7469 | 0.16615 | 2.2615 | 0.057692 | 4.9385 | 5.3231 | 0 | 0 | 13
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20150193 |  |  |  | US 25 (Dry Ridge - Florence Road); 5-lane US-25 from Beesom Drive to Aristocrat Drive with grade separation at KY 536. (2006BOPC) (10CCR)(14CCN) Formerly 6-351.3. | Major Widening | Boone | 008-US-0025 -000 | 7.431 | 7.81 | 0.379 | Improve Intersection | 26 |  | 0 |  | 2250000 |  | 13000000 |  | 1000000 |  | 15000000 |  | 2017-05-05 08:56 | TBD | From 2001 to 2011 the intersection of US 25 & KY 536 has experienced large increases in ADT with a corresponding increase in CRF. Three of the 4 legs have a CRF>1 and the south leg CRF is > 2. US 25 is a long established 2-lane corridor that serves | Cincinnati/Northern Kentucky MPO | North | 36.9985 | 7.76 | 9.0462 | 10.3154 | 1.5231 | 0 | 3.9538 | 4.4 | 37
Y | 6 | Bluegrass ADD | IP20150204 | 6-8708 |  | A | RECONSTRUCT US 27 FROM MP 11.9 TO MP 12.4. (12CCN)(14CCR)(18CCN) | RECONSTRUCTION(O) | Harrison | 049-US-0027 -000 | 12.9 | 13.4 | 0.5 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 530000 | 2021 | 0 |  | 5950000 | 2023 | 2018-07-10 08:18 | Improve safety | There have been five crashes reported on this section of road between 1-1-15 and 11-1-18; all of these crashes only involved property damage. | 6 | North | 23.1485 | 1.7292 | 3.0923 | 1.2346 | 3.4154 | 6.7077 | 2.1385 | 4.8308 | 23
Y | 6 | Northern Kentucky ADD | IP20150244 | 6-162.10 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-1303 FROM KY-536 TO BEECHGROVE ELEMENTARY (PRIORITY SECTION 4). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(16CCR)(18CCR) | RECONSTRUCTION(O) | Kenton | 059-KY-1303 -000 | 0 | 1.1 | 1.1 | Modernize Roadway-Rural | 26 | [5 empty] | 3000000 | 2023 | 3000000 | 2023 | 9000000 | 2024 | 2018-07-10 08:18 |  |  | 6 | North | 77.2423 | 8.6154 | 9.5077 | 8.5962 | 3.7385 | 7.2 | 2.4769 | 7.1077 | 47 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20150257 | 6-447 |  | A | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-25 FROM WINNING COLORS DRIVE TO THE NORFOLK SOUTHERN RAILROAD CROSSING SOUTH OF KY-1829 (INDUSTRIAL ROAD); EXCLUDES GRADE SEPARATION AT KY-536. | MAJOR WIDENING(O) | Boone | 008-US-0025 -000 | 5.085 | 9.2 | 4.115 | Modernize Roadway-Rural | 26 |  |  |  | 3300000 | 2023 | [6 empty] | 2018-07-10 08:17 |  |  | 6 | North | 85.7969 | 7.12 | 12.1846 | 13.6615 | 1.5231 | 8.8615 | 3.8923 | 8.5538 | 56 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20150287 | 6-162.30 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM KY 1303 TO WILLIAMSWOOD ROAD/CALVARY DRIVE (PRIORITY SECTION 2). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCN) | AIR QUALITY(P) | Kenton | 059-KY-0536 -000 | 1.061 | 2.542 | 1.481 | Arterial to Partial Control | 23 | [5 empty] | 3000000 | 2020 | 1500000 | 2020 | 13500000 | 2022 | 2018-07-10 08:18 |  |  | 6 | North | 53.9862 | 4.8862 | 6.6462 | 6.6231 | 3.3231 | 8.1538 | 3.3231 | 6.0308 | 39 | 15
Y | 6 | Northern Kentucky ADD | IP20150312 | 6-162.40 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM WILLIAMSWOOD ROAD/CALVARY DRIVE TO KY-17 (PRIORITY SECTION 3). DESIGN PHASE UNDER PARENT NO. 6-162.01. (2012BOP)(18CCR) | RECONSTRUCTION(O) | Kenton | 059-KY-0536 -000 | 2.542 | 4.062 | 1.52 | Arterial to Partial Control | 23 | [5 empty] | 11500000 | 2022 | 1500000 | 2024 | 18800000 |  | 2018-07-10 08:18 |  |  | 6 | North | 74.28 | 4.6954 | 8.2154 | 10.1077 | 4.4154 | 7.6923 | 2.9077 | 6.2462 | 44 | 15 | 15
Y | 6 | Buffalo Trace ADD | IP20150411 |  |  |  | Shoulder Improvements along KY 1504. (14CCN) | Safety-Haz-Elm | Robertson | 101-KY-1504 -000 | 0 | 6.857 | 6.857 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 6490000 |  | 2017-03-23 08:47 | Improve safety and mobility in the BTADD region | Shoulder improvements
Y | 6 | Northern Kentucky ADD | IP20150458 |  |  |  | Improve safety and mobility for KY 9 by making slide repairs, profile corrections, curb and gutter replacement and drainage restoration from KY 1632 (Moock Rd.) to CSX RR Bridge. | Reconstruction | Campbell | 019-KY-0009 -000 | 20.18 | 21.75 | 1.57 | Maintenance Improvement | 10 |  | 0 |  | 300000 |  | 0 |  | 0 |  | 3000000 |  | 2015-06-26 14:51
Y | 6 | Northern Kentucky ADD | IP20160006 |  |  |  | Improve mobility, safety and connectivity on KY 8x at the intersection with O'Fallon Ave in the City of Dayton. | Reconstruction | Campbell | 019-KY-0008X -000 | 1.468 | 1.568 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 5000000 |  | 1000000 |  | 4000000 |  | 2016-02-25 12:58
Y | 6 | Northern Kentucky ADD | IP20160014 | 6-80 |  | A | REDUCE CONGESTION AND IMPROVE TRAFFIC MOBILITY AT THE INTERCHANGE OF I-75 AND KY-14 IN WALTON. | CONGESTION MITIGTN(O) | Boone | 008-I -0075 -000 | 171 | 171.8 | 0.8 | Innovative Interchange | 40 | Y | 500000 | 2021 | [10 empty] | This interchange experiences a lot of congestion due to the close proximity of the intersection of KY 14 and KY 1292. Also the truck stop located at this intersection causes a lot of truck traffic that further causes traffic jams. | 6 | North | 67.3869 | 8.4677 | 6.1385 | 10.2115 | 1.1231 | 0 | 4.8308 | 6.6154 | 37 | 15 | 15
Y | 6 | Northern Kentucky ADD | IP20160090 | 6-8910 |  | A | IMPROVE GEOMETRICS ON I-71 FROM US-127 TO MP 64. (16CCN)(18CCR) | RECONSTRUCTION(O) | Gallatin | 039-I -0071 -000 | 62.8 | 64 | 1.2 | Modernize Roadway-Rural | 26 | Y |  |  | 0 | 2021 | 1740000 | 2022 | 570000 | 2022 | 36270000 | 2025 | 2018-07-10 08:18 | RECONSTRUCT I-71 FROM US 127 FROM MP 62.8 TO MP 64 TO IMPROVE GEOMETRICS UP TO MODERN STANDARDS. (16CCN). | This section of I 71 is heavily traveled by pedestrian and truck traffic. This improvement will improve safety of this hazardous S Curve by improving the Geometrics. | 6 | Statewide | 59.3667 | 13.2687 | 8.5463 | 5.9141 | 6.0793 | 8.6344 | 7.7093 | 9.2147
Y | 6 | Northern Kentucky ADD | IP20160104 |  |  |  | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 17 FROM KY 14 (MP 3.974) TO 0.143 MI NORTH OF HERGOTT DRIVE (MP 8.969). (2016BOP) | Safety-Haz-Elm | Kenton | 059-KY-0017 -000 | 3.974 | 8.969 | 4.995 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 15:10
Y | 6 | Northern Kentucky ADD | IP20160158 |  |  |  | WIDEN FOUR MILE ROAD TO WEST GHENT CITY LIMIT.(SECTION 4)(2006BOPC)(00CCN)(10CCR) | Minor Widening | Carroll | 021-US-0042 -000 | 9.9 | 13.2 | 3.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 1000000 |  | 1000000 |  | 20400000 |  | 2018-12-20 15:21 | Improve safety and mobility and address geometric deficiencies along US 42 by WIDENING FOUR MILE ROAD TO WEST GHENT CITY LIMIT.(SECTION 4)(2006BOPC)(00CCN)(10CCR) | There is 5 billion dollars worth of investment in the US-42 corridor in Carroll county and it could expand. Roads are the single most important issue to local businesses. 5000 jobs are available to local residents. 2 plants are currently looking to loc
Y | 6 | Bluegrass ADD | IP20160196 |  |  |  | Duplicate of CHAF IP20150341 (6-8300) | Bypass | Harrison | 049-US-0027 -000 | 9.08 | 10.259 | 1.179 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-27 10:27 | CONSTRUCT WEST US-27 CYNTHIANA BYPASS: SECTION THREE FROM US-27 NORTH TO US 62 EAST. (06CCN) | Extending W US 27 to KY 392 will provide access from US 27 N and US 27 W to US 62 and KY 392 without traffic moving through Cynthiana.
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20160302 | 6-8916 |  | A | EXTEND HOUSTON ROAD TO CINEMA PROPERTY. (16CCN)(18CCN) | NEW ROUTE(O) | Kenton | 059-CS-3000 -000 | 0 | 0.31 | 0.31 | Construct Road in New Location | 0 |  |  |  | 0 | 2019 | 500000 |  | 300000 |  | 3500000 |  | 2016-09-22 | Improve connectivity along KY 2978 (Hartman Rd) connecting with Erlanger Rd. | Hartman Road (KY 2978) extends about 1/3 miles from the Houston Road (KY 842) and Donaldson Road (KY 236) intersection to Erlanger Road. The facility serves the Erlanger Commercial Park, several other commercial businesses and provides access to the for | General Assembly | North | 21.2049 | 8.1774 | 0 | 3.3486 | 4.0214 | 5.6575 | 0 | 0 | 21
Y | 6 | Northern Kentucky ADD | IP20170001 | 6-80001 |  | A | EXPANSION OF ROUNDABOUTS ALONG KY-237 AT CARDINAL COVE AND GRAVES RD(18CCN) | CONGESTION MITIGTN(O) | Boone | 008-KY-0237 -000 | 11.2 | 12.259 | 1.059 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2019 | 250000 | 2019 | 250000 | 2019 |  |  | 2018-07-10 08:18 |  | Reduce congestion and improve mobility along the KY 237 North Bend Road corridor. Additional residential sub-divisions anticipated. Existing bike lanes would be removed and existing sidewalk will be widened to 10 ft shared-use path. | 6 | North | 37.1831 | 7.1754 | 9.5538 | 8.0538 | 3.4923 | 0 | 2.7538 | 6.1538 | 37
Y | 6 | Northern Kentucky ADD | IP20170015 |  |  |  | Construct a new connector road from South Airfield Road to the intersection of KY 236 and KY 3076 (Mineola Pike) to help freight mobility. | New Route | Boone | 008-KY-0236 -000 | 1.366 | 1.594 | 0.228 | Construct Road in New Location | 0 |  | 0 |  | 500000 |  | 300000 |  | 200000 |  | 3000000 |  | 2017-04-26 14:42 |  | Provide access for freight to/from CVG to I-275 via the Mineola Pike/South Airfield Road corridors. Truck traffic is expected to increase with the growth of the industries around CVG.(DHL, Wayfair & Amazon) | 6 | North | 20.6392 | 5.8277 | 0 | 2.8731 | 0 | 8.1846 | 3.7538 | 0 | 21
Y | 6 | Northern Kentucky ADD | IP20170019 |  |  |  | Reduce congestion at the intersection of KY 8 at Riviera Drive. | Reconstruction | Campbell | 019-KY-0008X -000 | 0.715 | 0.914 | 0.199 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 900000 |  | 200000 |  | 2200000 |  | 2017-02-09 14:20 |  |  | 6 | North | 39.3508 | 7.0585 | 12.8308 | 10.9385 | 0 | 0 | 4.4615 | 4.0615 | 39
Y | 6 | Northern Kentucky ADD | IP20170020 |  |  |  | Improve safety and traffic mobility at the intersection of US 25 and KY 491 (Gardnersville Road) and the railroad at-grade crossing. | Major Widening | Grant | 041-US-0025 -000 | 22.114 | 22.418 | 0.304 | Improve Railroad Crossing | 55 |  | 0 |  | 500000 |  | 750000 |  | 750000 |  | 2400000 |  | 2017-05-22 07:40 | Improve safety and traffic mobility at the intersection of US 25 and KY 491 (Gardnersville Road) and the railroad at-grade crossing. | There is a need for major safety improvements to the intersection of US 25 and KY 491 (Gardnersville Rod and the RR crossing. | 6 | North | 23.9115 | 2.8308 | 12.9231 | 5.8962 | 2.2615 | 0 | 0 | 0 | 24
Y | 6 | Buffalo Trace ADD | IP20170041 |  |  |  | Widen the bridge on US 62 over N Branch Cedar Creek near Kentontown to improve safety and mobility. | Minor Widening | Robertson | 101-US-0062 -000 | 4.85 | 4.95 | 0.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 100000 |  | 100000 |  | 500000 |  | 2017-03-09 10:25 | Improve safety and mobility in Robertson County | Bridge is too narrow (20' wide) to allow two trucks to pass side by side, thus creating a safety issue. | BUFFALO TRACE ADD | North | 13.3262 | 0.48615 | 2.4 | 0 | 2.2615 | 0 | 1.9385 | 6.24 | 13
Y | 6 | Northern Kentucky ADD | IP20170043 |  |  |  | Reduce congestion and improve safety and mobility on KY 371 Amsterdam Road from Collins Road to Valley Trails Drive. | Reconstruction | Kenton | 059-KY-0371 -000 | 4.536 | 5.456 | 0.92 | Improve Intersection | 26 |  | 0 |  | 1000000 |  | 2000000 |  | 1000000 |  | 6500000 |  | 2017-05-19 11:19 |  | Installation of a modern roundabout at the intersection of Collins and Amsterdam would ease the congestion associated with a major development in the City of Villa Hills. The proposed roundabout would minimize impacts to the residential property on the so | Cincinnati/Northern Kentucky MPO | North | 19.4231 | 7.0154 | 3.8308 | 2.8846 | 0 | 0 | 0 | 5.6923 | 19
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20170044 |  |  |  | Improve mobility and safety at the intersections of US 27 and Pat Fanning Way/KY 709. | Reconstruction | Campbell | 019-US-0027 -000 | 11.866 | 11.981 | 0.115 | Improve Intersection | 26 |  | 0 |  | 200000 |  | 300000 |  | 150000 |  | 600000 |  | 2017-03-13 15:18 | TBD | Currently the ADT on US-27 in this area is 29,303. Severe congestion issues occur at the intersection with KY-709. Safety is a major concern with existing signalized intersections at US-27/KY-709 and the entrance to Arcadia (local road) nearby on US-27 c | Cincinnati/Northern Kentucky MPO | North | 31.6923 | 7.3538 | 13.6154 | 4.3846 | 0 | 0 | 2.4615 | 3.8769 | 32
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20170050 |  |  |  | Improve safety and reduce congestion at the intersection of KY 1017 (Turfway Road) and KY 717 (Thoroughbred Blvd). | Reconstruction | Boone | 008-KY-1017 -000 | 2.45 | 2.549 | 0.099 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 200000 |  | 100000 |  | 500000 |  | 2017-03-15 09:52 | TBD | With the Amazon development at CVG on Aero Parkway and other smaller industrial developments in the same area, the intersection of Turfway Road and Thoroughbred Blvd serves as key node to access I-75 for freight and employees. Upgrades to the intersectio
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20170081 |  |  |  | Configure shoulder for use by express bus | Air Quality (P) | Kenton | 059-I -0075 -000 | 183.312 | 190.8 | 7.488 | Other Improvement Types | 0 | Y | 0 |  | 100000 |  | 0 |  | 0 |  | 550000 |  | 2017-04-26 12:38 | TBD | Corridor is highly congested. Project would reduce the number of drive alone vehicles. | Cincinnati/Northern Kentucky MPO | North | 32.2554 | 9.8708 | 0 | 15 | 2.4 | 0 | 4.9846 | 0 | 32
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20170083 |  |  |  | Realign Royal Drive from KY 371 (Buttermilk Pike) to Grace Ave. | Relocation | Kenton | 059-CS-7091 -000 | 0 | 0.413 | 0.413 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 500000 |  | 250000 |  | 4000000 |  | 2017-05-21 12:25 | TBD | Realign Royal Drive from Buttermilk Pike to Grace Ave to help facilitate the proposed development at the former Drawbridge Inn site. | Cincinnati/Northern Kentucky MPO | North | 21.7654 | 6.6769 | 7.8 | 3.3346 | 3.9538 | 0 | 0 | 0 | 22
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20170084 |  |  |  | Reconstruct Wayman Branch Road from KY 1501 (Hands Pike) to KY 16 (Pride Parkway) to improve safety and mobility. | Reconstruction | Kenton | 059-KY-3716 -000 | 0 | 0.615 | 0.615 | Modernize Roadway-Rural | 26 |  | 0 |  | 2700000 |  | 3500000 |  | 2500000 |  | 18000000 |  | 2017-05-21 13:26 | TBD | Reconstruct Wayman Branch Road from Hands Pike to Pride Parkway to improve safety and repair slides. | Cincinnati/Northern Kentucky MPO | North | 23.6015 | 3.9631 | 5.9077 | 5.6077 | 2.4615 | 5.6615 | 0 | 0 | 24
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20170085 |  |  |  | Improve safety and reduce congestion along KY 8 (4th St) from US 25 (Main St) to KY 3090 (Philadelphia St); includes multi-modal needs of peds, bikes and transit. | Reconstruction | Kenton | 059-KY-0008 -001 | 6.667 | 6.801 | 0.134 | Modernize Roadway-Rural | 26 | Y | 250000 |  | 3000000 |  | 5000000 |  | 5000000 |  | 15000000 |  | 2019-02-20 10:06 | Improve safety and reduce congestion along KY 8 (4th St) from US 25 (Main St) to KY 3090 (Philadelphia St); includes multi-modal needs of peds, bikes and transit. | KY 8 provides access to Covington, Newport, access to Cincinnati via I-75 (W terminus of Project) and US 25 (Clay Wade Bailey Bridge) near E terminus of Project. Also is located near Mainstrasse. Multi-modal activity in this area includes peds, bikes an | Cincinnati/Northern Kentucky MPO | North | 33.3877 | 9.2185 | 9.7846 | 11.3538 | 0 | 0 | 3.0308 | 0 | 33
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20180072 |  |  |  | (TEST PROJECT for CHAF Guidance) Construct a new interchange for I-275 in between Exit 11 and Exit 8, and realign several of the local roads to accommodate this new interchange and the increase in truck traffic to the area. (This test project is based o | New Interchange | Boone | 008-I -0275 -000 | 8.545 | 9.908 | 1.363 | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-10-19 16:08 | CHAF Guidance Test | CHAF Guidance Test
Y | 6 | Northern Kentucky ADD | IP20180086 |  |  |  | Reconstruct KY 36 from KY 330 in Grant County to KY 1032 in Harrison County | Reconstruction | Grant | 041-KY-0036 -000 | 21.1 | 24.311 | 3.211 | Modernize Roadway-Rural | 26 |  | 0 |  | 1750000 |  | 2000000 |  | 1250000 |  | 26000000 |  | 2018-12-04 13:30 | Reconstruct KY 36 from KY 330 in Grant County to KY 1032 in Harrison County | Improve safety and correct geometric deficiencies along KY 36
Y | 6 | Northern Kentucky ADD | IP20180088 |  |  |  | Reconstruct KY 36 from US 25 to KY 330 west junction. | Reconstruction | Grant | 041-KY-0036 -000 | 14.761 | 21.1 | 6.339 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 3000000 |  | 2000000 |  | 40000000 |  | 2018-12-04 13:21 | Reconstruct KY 36 from US 25 to KY 330 west junction. | Improve safety and correct geometric deficiencies on KY 36
Y | 6 | Northern Kentucky ADD | IP20180089 |  |  |  | Reconstruct KY 35 from Kentucky Speedway Boulevard to US 42 | Reconstruction | Gallatin | 039-KY-0035 -000 | 2.5 | 8.7 | 6.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 6000000 |  | 2500000 |  | 44000000 |  | 2018-12-04 11:06 | Reconstruct KY 35 from Kentucky Speedway Boulevard to US 42 by bringing the road up to modern geometric standards. | KY 35 serves industrial, commercial, recreational and residential access to/from Warsaw to I-71, including access to the KY Speedway. Existing corridor is windy, has poor sight distance in multiple areas.
Y | 6 | Northern Kentucky ADD | IP20180091 |  |  |  | Reconstruction of route 1992 from US 42 to mile point 5.9 to connect to Southfork Rd | Reconstruction | Gallatin | 039-KY-1992 -000 | 0 | 5.9 | 5.9 | [14 empty] | Reconstruction of route 1992 from US 42 to mile point 5.9 to connect to Southfork Rd | Improve and widen Route 1992 to provide access to Southfork Rd and to access and help develop a new County park.
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20190052 |  |  |  | Improve congestion and mobility along KY 17 from E 20th Street to the John Roebling Bridge. | Transportation Study | Kenton | 059-KY-0017 -000 | 22.15 | 23.9 | 1.75 | Transportation Studies | 0 |  | 75000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-20 09:59 | Improve congestion and mobility along KY 17 from E 20th Street to the John Roebling Bridge. | KY 17 is a high ADT, urban road in Covington, Ky. KY 17 meanders at its intersection with East 20th Street. At East 20th Street, KY 17 becomes a one-way couplet.
Y | 6 | Northern Kentucky ADD | IP20190053 |  |  |  | Increase safety and mobility at KY 9 from Town Drive to Gloria Terrell Drive. Evaluate access management. | Transportation Study | Campbell | 019-KY-0009 -000 | 16.54 | 17.6 | 1.06 | Transportation Studies | 0 |  | 200000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-21 10:45 | Increase safety and mobility at KY 9 from Town Drive to Gloria Terrell Drive. Evaluate access management. | The Town Drive intersection is very close to the I-275 interchange on KY 9. This causes unsafe weaving movements and left turns.
Y | 6 | Northern Kentucky ADD | IP20190058 |  |  |  | Superstreet on KY 18 from McGrath to Boone Aire Road. | Reconstruction | Boone | 008-KY-0018 -000 | 12.138 | 14.026 | 1.888
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20190059 |  |  |  | Realign and widen Bullittsville Road from KY 18 to KY 20. | Major Widening | Boone | 008-CR-1052 -000 | 0 | 3.483 | 3.483 | [14 empty] | Improve mobility along Bullittsville Road from KY 18 to KY 20. | Industry is developing along Bullittsville Road. It has been identified as a road that may be incorporated into the state system in the future.
Y | 6 | Cincinnati-Northern Kentucky MPO | IP20190060 |  |  |  | Improve access to KY 237 for Litton Lane. | Relocation | Boone | 008-KY-0237 -000 | 0.14 | 0.26 | 0.12 | [14 empty] | TBD | TBD
Y | 6 | Northern Kentucky ADD | IP20190061 |  |  |  | Duplicate | Reconstruction | Boone | 008-I -0275 -010 | 1.582 | 2.665 | 1.083
Y | 6 | Northern Kentucky ADD | IP20190062 |  |  |  | Extend Grand National to Chambers Rd. | New Route | Boone | 008-KY-2951 -000 | 1.4 | 1.6 | 0.2
Y | 6 | Northern Kentucky ADD | IP20190063 |  |  |  | Reconstruct I-75 interchange at KY 18. Requires IMR. (Pending CVG study) | Reconstruction | Boone | 008-I -0075 -000 | 180.6 | 181.85 | 1.25
Y | 6 | Northern Kentucky ADD | IP20190064 |  |  |  | Paired Grade-Separated Intersections along KY 18 at KY 842 and Mall Road. (Pending CVG study) | Congestion Management | Boone | 008-KY-0018 -000 | 14.5 | 15.1 | 0.6
Y | 6 | Northern Kentucky ADD | IP20190066 |  |  |  | Reconstruct I-75 interchange at KY 1017 (Turfway Road). Interchange is part of 6-79 IMR; include southbound exit. Investigate innovative access management to Turfway Rd and Thoroughbred Blvd. | Reconstruction | Boone | 008-I -0075 -000 | 182.2 | 183.312 | 1.112
Y | 6 | Buffalo Trace ADD | IP20190067 |  |  |  | Improve safety by identifying concerns at intersections along KY 9 - install left turn lanes. | Spot Improvement | Bracken | 012-KY-0009 -000 | 0 | 19.857 | 19.857
Y | 6 | Northern Kentucky ADD | IP20190072 |  |  |  | Study egress improvements along KY 9 near intersections of Glenridge, Shadow Lake, KY 919 to increase safety | Transportation Study | Campbell | 019-KY-0009 -000 | 15.1 | 16.1 | 1
Y | 6 | Northern Kentucky ADD | IP20190073 |  |  |  | Reconstruct I-75 interchange at KY 236 (Donaldson Road). Interchange is part of 6-79 IMR. Investigate DCD. | Reconstruction | Kenton | 059-I -0275 -000 | 79.5 | 81 | 1.5
Y | 6 | Northern Kentucky ADD | IP20190178 | 6-80003 |  | A | INCREASE CAPACITY AND REDUCE CONGESTION ON US 42 AT I 71/75(18CCN) | RECONSTRUCTION(O) | Boone | 008-US-0042 -000 | 13.802 | 14.16 | 0.358 | [5 empty] | 650000 | 2019 | [6 empty] | 2018-07-10 08:18
Y | 7 | Lexington MPO | IP20000035 |  |  |  | Capacity improvements on US 60 (Winchester Rd) from Fortune Dr to I-75. Additional through lane (3rd through lane between I-75 and Patchen Wilkes Development) and associated pedestrian improvements on both the EB and WB US 60. | Major Widening | Fayette | 034-US-0060 -000 | 10.511 | 11.801 | 1.29 | Modernize Roadway-Rural | 26 | Y | 0 |  | 600000 |  | 200000 |  | 300000 |  | 4000000 |  | 2015-06-29 13:52 | Address congestion and improve mobility on US 60 (Winchester Rd) from Fortune Dr to I-75. - See pg 31 of MOW study | Address congestion, improve mobility and safety
Y | 7 | Lexington MPO | IP20000036 |  |  |  | Modernize Roadway, with widening, turn lanes, safety improvements at intersections, to incorporate and include bicycle, pedestrian, and transit facilities on US 60 (Versailles Road) from Viley Road to west end of Norfolk Southern railroad bridge. | Minor Widening | Fayette | 034-US-0060 -000 | 5 | 7.53 | 2.53 | Modernize Roadway-Rural | 26 | Y | 0 |  | 975000 |  | 3900000 |  | 1500000 |  | 8500000 |  | 2017-05-18 18:02 | Improve mobility and Modernize Roadway, with widening, turn lanes, safety improvements at intersections, to incorporate and include bicycle, pedestrian, and transit facilities on US 60 (Versailles Road) from Viley Road to west end of Norfolk Southern rail | The following needs have been identified on this project: 1)Improve mobility. | Lexington MPO | North | 47.8146 | 7.0646 | 14.4 | 14.1346 | 0 | 0 | 3.9692 | 8.2462 | 48
Y | 7 | Lexington MPO | IP20000040 |  |  |  | Reconstruct KY 1267/1966 (Military Pk) from KY 1967 in Woodford County to US 68 in Fayette County. | Reconstruction | Fayette | 034-KY-1267 -000 | 0.907 | 1.216 | 0.309 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2750000 |  | 3000000 |  | 11500000 |  | 2017-05-19 10:20 | Improve safety on KY 1267/1966 (Military Pk) from KY 1967 in Woodford County to US 68 in Fayette County. | The following needs have been identified on this project: 1) Improve Safety. | 7 | North | 17.5362 | 1.8708 | 4.5692 | 3.1731 | 1.5231 | 6.4 | 0 | 0 | 18
Y | 7 | Lexington MPO | IP20000041 |  |  |  | Major widening of KY 1425 (Man o' War Blvd) from I-75 to US 60 (Winchester Rd). | Major Widening | Fayette | 034-KY-1425 -000 | 0 | 1.429 | 1.429 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 2070000 |  | 1600000 |  | 5000000 |  | 2017-05-19 10:29 | Improve mobility and access management and modernize roadway on KY 1425 (Man o' War Blvd) from I-75 to US 60 (Winchester Rd). | The following needs have been identified on this project: 1) Improve Mobility, 2) Modernize Roadway, 3) Improve Access Management. | Lexington MPO | North | 46.2446 | 4.96 | 12.3231 | 10.5923 | 0 | 8.1231 | 2.9538 | 7.2923 | 46
Y | 7 | Lexington MPO | IP20000042 |  |  |  | Reconstruct intersection of KY 1681 at Forbes Rd. | Reconstruction | Fayette | 034-KY-1681 -000 | 6.648 | 6.748 | 0.1 | Improve Intersection | 26 |  | 0 |  | 750000 |  | 520000 |  | 2500000 |  | 1320000 |  | 2010-10-28 14:00 |  | The existing traffic peak hour volumes, and the high percentage of trucks, single (11%) and combination (3.5%)trucks accessing the industrial areas in and adjacent to the vicinity significantly lower the level-of-service and contributes to safety problem
Y | 7 | Lexington MPO | IP20000043 |  |  |  | PARKERS MILL RD - MAJOR WIDENING FROM VERSAILLES RD TO MAN-O-WAR BLVD IN LEXINGTON | Major Widening | Fayette | 034-KY-1968 -000 | 3.873 | 6.019 | 2.146 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 2000000 |  | 3750000 |  | 5000000 |  | 2017-05-19 10:40 | Modernize roadway and improve mobility on Parkers Mill Rd. from Versailles Rd. to Man-O-War Blvd. in Lexington. | The following needs have been identified on this project: 1) Modernize Roadway, 2) Improve Mobility. | 7 | North | 45.8285 | 6.5169 | 11.6769 | 9.7731 | 3.6154 | 7.0462 | 0 | 7.2 | 46
Y | 7 | Lexington MPO | IP20000045 |  |  |  | Tates Creek Road - Major widening from Armstrong Mill to Man O War Blvd. in Lexington. | Minor Widening | Fayette | 034-KY-1974 -000 | 7.782 | 8.825 | 1.043 | Other Improvement Types | 0 | Y | 0 |  | 1050000 |  | 1415000 |  | 1460000 |  | 6270000 |  | 2010-10-28 14:39
Y | 7 | Lexington MPO | IP20000046 |  |  |  | Reconstruct Old Todds Rd from Codell Dr to Liberty Rd. | Major Widening | Fayette | 034-CS-2690 -000 | 0.237 | 1.793 | 1.556 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 5500000 |  | 5750000 |  | 14000000 |  | 2017-05-19 11:05 | Improve safety and modernize roadway on Old Todds Rd from Codell Dr to Liberty Rd. | The following needs have been identified on this project: 1) Improve Safety, 2) Modernize Roadway. | Lexington MPO | North | 35.0362 | 5.4092 | 9.8308 | 11.0423 | 1.3385 | 7.4154 | 0 | 0 | 35
Y | 7 | Lexington MPO | IP20000047 |  |  |  | E. LOUDON AVE - MAJOR WIDENING FROM N. Limestone Street TO Magoffin St IN LEXINGTON | Minor Widening | Fayette | 034-CS-1376 -000 | 0 | 0.558 | 0.558 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 0 |  | 750000 |  | 1200000 |  | 1000000 |  | 3900000 |  | 2017-05-19 11:13 | Improve safety and mobility and reduce congestion on E. Loudon Ave. from N. Limestone Street TO Magoffin St. in Lexington. | The following needs have been identified on this project: 1) Improve Mobility, 2) Reduce Congestion, 3) Improve Safety. | Lexington MPO | North | 29.13 | 6.9723 | 0 | 11.4808 | 2.3692 | 8.3077 | 0 | 0 | 29
Y | 7 | Lexington MPO | IP20000049 |  |  |  | Alumni Drive (CS 3016)- Major widening from Tates Creek to Chinoe Rd in Lexington. Improve roadway to accommodate multimodal transportation with a minor widening to a 4-lane boulevard, a bike lane (BL) or a Shared Use Path (SUP), curb and gutter. | Major Widening | Fayette | 034-CS-3016 -000 | 1.223 | 1.919 | 0.696 | 2 Lane to 4 Lane Divided - Urban | 10 |  | 0 |  | 1000000 |  | 3250000 |  | 3750000 |  | 5000000 |  | 2017-05-19 13:50 | Improve safety, capacity, accessibility and mobility and modernize roadway on Alumni Drive (CS 3016) from Tates Creek to Chinoe Rd in Lexington. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Capacity, 3) Improve Accessibility, 4) Improve Mobility, 5) Modernize Roadway. | Lexington MPO | North | 23.8323 | 7.1631 | 0 | 8.0538 | 0 | 8.6154 | 0 | 0 | 24
Y | 7 | Lexington MPO | IP20000050 |  |  |  | ALUMNI DRIVE - MAJOR WIDENING FROM EDGEWATER DR TO MAN O WAR BLVD IN LEXINGTON | Major Widening | Fayette | 034-CS-3016 -000 | 2.904 | 3.876 | 0.972 | Modernize Roadway-Rural | 26 | Y | 0 |  | 1250000 |  | 3500000 |  | 2750000 |  | 12000000 |  | 2017-05-19 13:53 | Improve capacity and safety on Alumni Drive from Edgewater Drive to Man-O-War Blvd. in Lexington. | The following needs have been identified on this project: 1) Improve Capacity, 2) Improve Safety | Lexington MPO | North | 51.7062 | 9.2123 | 12.4154 | 12.7846 | 3.0462 | 9.5077 | 0 | 4.74 | 52
Y | 7 | Lexington MPO | IP20000051 |  |  |  | ARMSTRONG MILL RD - MAJOR WIDENING FROM KY 1974 (TATES CREEK PIKE) TO MAN O WAR BLVD IN LEXINGTON | Major Widening | Fayette | 034-CS-3037 -000 | 0 | 1.407 | 1.407 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 4500000 |  | 3750000 |  | 6500000 |  | 2017-05-19 13:57 | Improve mobility, safety and accessibility, and modernize roadway on Armstrong Mill Rd. from KY 1974 (Tates Creek Pike) to Man O War Blvd. in Lexington. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Accessibility, 3) Improve Safety, 4) Modernize Roadway. | Lexington MPO | North | 38.0515 | 4.3938 | 10.4308 | 10.9385 | 0 | 7.9385 | 0 | 4.35 | 38
Y | 7 | Lexington MPO | IP20000052 |  |  |  | MAN O WAR BLVD - MAJOR WIDENING FROM US 25 (RICHMOND RD) TO ARMSTRONG MILL RD IN LEXINGTON | Major Widening | Fayette | 034-CS-4524 -000 | 10.237 | 12.786 | 2.549 | Local Roadway Improvements | 3 | Y | 0 |  | 1500000 |  | 2080000 |  | 3000000 |  | 13200000 |  | 2010-10-28 14:16
Y | 7 | Lexington MPO | IP20000053 |  |  |  | MAN O WAR BLVD - Major widening to six (6) lanes from KY 1974 (Tates Creek Rd.) to US 27 (Nicholasville Rd.) in Lexington; to include adding bike lanes or a shared use path; and improved transit services. | Major Widening | Fayette | 034-CS-4524 -000 | 6.55 | 8.561 | 2.011 | Other Improvement Types | 0 | Y | 0 |  | 1200000 |  | 1670000 |  | 2400000 |  | 10560000 |  | 2010-10-28 14:14
Y | 7 | Lexington MPO | IP20000056 |  |  |  | RECONSTRUCT INTERSECTION AT MAPLELEAF AND MILES RD TO IMPROVE SIGHT DISTANCE AND TO REALIGN MAPLELEAF WITH MILES RD | Reconstruction | Jessamine | 057-KY-0039 -000 | 8.836 | 8.906 | 0.07 | Improve Intersection | 26 |  | 0 |  | 400000 |  | 675000 |  | 600000 |  | 4160000 |  | 2017-05-19 14:56 | Improve safety and sight distance at the intersection of Mapleleaf and Miles Rd. | The following needs have been identified on this project: 1) Improve Safety, 2) Roadway Geometrics. | 7 | North | 19.5569 | 8.5415 | 3.9692 | 4.4769 | 2.5692 | 0 | 0 | 0 | 20
Y | 7 | Lexington MPO | IP20000057 |  |  |  | NORTH 3RD ST/KEENE RD - MAJOR WIDENING FROM OAK ST TO US 27 (NICHOLASVILLE BYPASS) IN NICHOLASVILLE | Major Widening | Jessamine | 057-KY-0169 -000 | 10.478 | 11.978 | 1.5 | Modernize Roadway-Rural | 26 |  | 750000 |  | 1650000 |  | 1664000 |  | 1600000 |  | 5830000 |  | 2010-12-09 14:57
Y | 7 | Bluegrass ADD | IP20040018 |  |  |  | Reconstruct US 460 from I-75 in Scott County to KY 353 (Russell Cave Rd) in Bourbon County. | Reconstruction | Bourbon | 009-US-0460 -000 | 0 | 1.394 | 1.394 | Modernize Roadway-Rural | 26 |  | 450000 |  | 2500000 |  | 7500000 |  | 8000000 |  | 10500000 |  | 2017-05-18 14:59 | Improve mobility on US 460 between I-75 in Scott County and Russell Cave Rd in Bourbon County. | The following needs have been identified on this project: 1) Improve Mobility. | 7 | North | 62.5877 | 3.0031 | 4.2462 | 3.2769 | 3.0615 | 7.4769 | 2.8769 | 8.6462 | 33 | 15 | 15
Y | 7 | Bluegrass ADD | IP20040019 |  |  |  | RECONSTRUCT KY 52 FROM KY 1805 (Goggin Ln) TO KY 590. | Major Widening | Boyle | 011-KY-0052 -000 | 1.586 | 3.773 | 2.187 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 3000000 |  | 6500000 |  | 2017-05-18 17:50 | Reconstruction on KY 52 from KY 1805 (Goggin Ln) to KY 590 to improve connectivity and address safety concerns. | Critical Rate Factor indicates serious safety concerns. Horizontal alignment rating of 3 indicates infrequent curves with design speeds less than the prevailing speed limit. Also lack of connectivity from Danville to I-75. | BLUEGRASS ADD | North | 68.7615 | 1.8462 | 8.9077 | 6.1615 | 4.1231 | 7.3231 | 2 | 8.4 | 39 | 15 | 15
Y | 7 | Bluegrass ADD | IP20040023 |  |  |  | Reconstruct KY 876 from KY 595 to 1.05mi E of KY 595 (location of former Acres of Land Winery). | Reconstruction | Madison | 076-KY-0876 -000 | 0 | 1.05 | 1.05 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 750000 |  | 750000 |  | 3000000 |  | 2015-06-29 21:48 | To reconstruct KY 876 from KY 595 to 1.05 mi E of KY 595 (location of former Acres of Land Winery) in order to address safety concerns. | Very high Critical Rates Factor indicates numerous crashes and safety problems. Roadway has many horizontal and vertical curves. Area has been identified as probable area of development.
Y | 7 | Bluegrass ADD | IP20050009 |  |  |  | Reconstruct KY 1678 (Clintonville Rd) from the New Providence Church to Castle Blvd. | Major Widening | Bourbon | 009-KY-1678 -000 | 5.4 | 8.251 | 2.851 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 1500000 |  | 1500000 |  | 8500000 |  | 2015-06-29 10:52 | The reconstruction of KY 1678 (Clintonville Rd) from the New Providence Church to Castle Blvd. due to narrow lanes and safety concerns. | Adequacy Rating not available. Narrow 8' lanes with little or no shoulders, geometric concerns and sight distance problems impair safety on this corridor leading from southern Bourbon County to Winchester. Route provides access to Drive-in Theater in Clar
Y | 7 | Lexington MPO | IP20060245 | 7-438 |  | A | REDUCE CONGESTION ON KY-4 (NEW CIRCLE RD) FROM TRADE CENTER DR TO WOODHILL DR. | MAJOR WIDENING(O) | Fayette | 034-KY-0004 -000 | 13.195 | 14.508 | 1.313 | Modernize Roadway-Rural | 26 | Y |  |  | 2000000 | 2024 | [6 empty] | 2018-07-10 08:17 | Improve safety and mobility, reduce congestion on KY 4 (New Circle Rd) from Trade Center Dr to Woodhill Dr. | The following needs have been identified on this project: 1) Improve Mobility, 2) Reduce Congestion, 3) Improve Safety. | 7 | North | 89.2038 | 9.5385 | 14.0769 | 13.5115 | 0 | 9.5077 | 4.8769 | 7.6923 | 59 | 15 | 15
Y | 7 | Gateway ADD | IP20060246 |  |  |  | Widen, improve safety, and reduce congestion on US 460 from Cardinal Lane to High Street in Mount Sterling. | Major Widening | Montgomery | 087-US-0460 -000 | 8.537 | 9.425 | 0.888 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 1000000 |  | 6250000 |  | 2017-05-19 16:51 | The purpose of this project is to: improve safety, reduce congestion, and widen the roadway. | The following needs have been identified for this project: 1) Reduce Congestion; 2) Widen the Roadway; 3) Repair Rough Pavement; and 4) Improve Roadway Safety. | GATEWAY ADD | North | 47.2654 | 8.8308 | 12.2308 | 8.25 | 0 | 8.7692 | 3 | 6.1846 | 47
Y | 7 | Lexington MPO | IP20070214 |  |  |  | Intersection improvements at S Broadway and Virginia Ave. | Major Widening | Fayette | 034-US-0027 -000 | 5.653 | 5.714 | 0.061 | Improve Intersection | 26 | Y | 0 |  | 500000 |  | 1500000 |  | 1500000 |  | 2000000 |  | 2017-05-19 09:51 | Address congestion and Improve mobility at the Intersection of S Broadway and Virginia Ave. | The following needs have been identified: 1) Improve mobility 2) Address congestion 3) Improve safety | 7 | North | 44.5292 | 8.4369 | 14.1692 | 12.2769 | 1.5231 | 0 | 3.3538 | 4.7692 | 44
Y | 7 | Lexington MPO | IP20070216 |  |  |  | Reconstruct KY 1978 (Greendale Rd) from US 421 (Leestown Rd) to Citation Blvd. | Major Widening | Fayette | 034-KY-1978 -000 | 0 | 1.326 | 1.326 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1250000 |  | 1750000 |  | 3000000 |  | 2017-05-19 10:47 | Modernize roadway and improve mobility and safety on KY 1978 (Greendale Rd) from US 421 (Leestown Rd) to Citation Blvd. | The following needs have been identified on this project: 1) Modernize Roadway, 2) Improve Mobility, 3) Improve Safety. | Lexington MPO | North | 44.6185 | 4.1723 | 12.6923 | 10.2462 | 3.9692 | 7.2308 | 0 | 6.3077 | 45
Y | 7 | Bluegrass ADD | IP20080405 |  |  |  | Roadway safety improvements on Russell Cave Road (KY 353) in Bourbon County. | Safety-Haz-Elm | Bourbon | 009-KY-0353 -000 | 3.835 | 4.005 | 0.17 | Modernize Roadway-Rural | 26 |  | 0 |  | 75000 |  | 100000 |  | 250000 |  | 500000 |  | 2017-05-18 15:04 | To add roadway safety improvements on Russell Cave Road (KY 353) in Bourbon County. These are needed due to sight restrictions. | This section of Russell Cave Road (KY 353) is located in a dangerous curve. Many traffic accidents are occurring at this location and have demonstrated a safety concern for motorists. There are advance warning signs and chevrons in place to inform motor | BLUEGRASS ADD | North | 29.4077 | 1.2 | 13.5692 | 7.1769 | 3.4308 | 0 | 0 | 4.0308 | 29
Y | 7 | Bluegrass ADD | IP20080406 |  |  |  | Improve safety on KY 627 (Winchester Rd) from Clark/Bourbon CL to US 68X (High St). | Reconstruction | Bourbon | 009-KY-0627 -000 | 0 | 9.276 | 9.276 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 6000000 |  | 6000000 |  | 20000000 |  | 2017-05-18 15:16 | To improve safety on KY 627 (Winchester Rd) from Clark/Bourbon CL to US 68X (High St). | Roadway provides connectivity between Winchester and Paris and provides access from Paris to I-64. East Kentucky Power is building a coal-fired facility in Maysville. This route could provide access from Maysville to Eastern Kentucky. Route has previously | BLUEGRASS ADD | North | 41.1408 | 1.4831 | 7.7538 | 10.95 | 4.7077 | 6.2769 | 0 | 9.9692 | 41
Y | 7 | Bluegrass ADD | IP20080408 |  |  |  | Reduce congestion, improve safety and provide pedestrian access from US 27 along KY 1939 for 1.90 miles. | Major Widening | Bourbon | 009-KY-1939 -000 | 5.812 | 7.712 | 1.9 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 3600000 |  | 2300000 |  | 6200000 |  | 2017-05-18 15:20 | To reduce congestion, improve safety and provide pedestrian access from US 27 along KY 1939 for 1.90 miles. | Narrow shoulders and lane width along KY 1939 in Paris present a safety concern. There is no pedestrian access available. IRI indicates surfaces issues. | BLUEGRASS ADD | North | 31.1123 | 2.6277 | 7.5231 | 8.2385 | 4.9692 | 7.7538 | 0 | 0 | 31
Y | 7 | Bluegrass ADD | IP20080411 |  |  |  | Improve safety, level of service on KY 33 from Lexington Ave. to KY 2168 (Danville Bypass). | Major Widening | Boyle | 011-KY-0033 -000 | 0.22 | 2.29 | 2.07 | Other Improvement Types | 0 |  | 0 |  | 1925000 |  | 6000000 |  | 1500000 |  | 14070000 |  | 2010-10-26 11:03 | To improve both safety and level of service on KY 33 from Lexington Ave. to KY 2168 (Danville Bypass). | High CRF indicates safety problems present.Various minor improvements have been made over the years (bridge replacements, widening) leaving the overall section area inconsistent causing driver confusion. Improved section would also provide access to the K
Y | 7 | Bluegrass ADD | IP20080412 |  |  |  | Reduce congestion and reduce crashes on KY 34 (Lexington Road) from Main St. to KY 2324 in Danville | Minor Widening | Boyle | 011-KY-0034 -000 | 13.629 | 13.891 | 0.262 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1500000 |  | 1500000 |  | 3000000 |  | 2017-05-18 17:42 | To reduce congestion and crashes on KY 34 (Lexington Road) from Main St. to KY 2324 in Danville. | KY 34 is the main route into downtown Danville from the US 27 vicinity and the current 2 lane road is experiencing congestion, particularly during the AM and PM peak Hours. The 20 year ADT projection will significantly increase the problem. | BLUEGRASS ADD | North | 30.1938 | 7.9631 | 6.3231 | 3.8308 | 4.4154 | 0 | 3.4154 | 4.2462 | 30
Y | 7 | Bluegrass ADD | IP20080417 |  |  |  | Improving both safety capacity and congestion on I-64 from East of the Bert T. Combs Pkwy. to the Clark/Montgomery County Line. | Major Widening | Clark | 025-I -0064 -000 | 97.775 | 104.26 | 6.485 | Other Improvement Types | 0 | Y | 0 |  | 2200000 |  | 210000 |  | 250000 |  | 49500000 |  | 2010-10-26 13:40 | To improve both safety capacity and congestion on I-64 from East of the Bert T. Combs Pkwy. to the Clark/Montgomery County Line. | I-64 is the major east west interstate connecting Louisville to Huntington WV. This corridor is a major automotive industry distribution route for major manufacturing plants, including the Toyota facility in West Virginia that access the Toyota facility
Y | 7 | Bluegrass ADD | IP20080419 |  |  |  | Access management improvements on US 60 (W Lexington Ave) at Carol Rd intersection. | Reconstruction | Clark | 025-US-0060 -000 | 4.67 | 4.892 | 0.222 | Improve Intersection | 26 |  | 0 |  | 750000 |  | 800000 |  | 500000 |  | 7400000 |  | 2017-05-18 17:56 | Improve safety and reduce congestion on W Lexington Ave at Carol Rd intersection. | The following needs have been identified for this project: 1) Improve safety at intersection, 2) Reduce Congestion. | 7 | North | 36.6323 | 5.9938 | 11.3077 | 10.8692 | 0 | 0 | 3.4769 | 4.9846 | 37
Y | 7 | Bluegrass ADD | IP20080424 |  |  |  | Reconstruct approaches and bridge on KY 974 from Elizabeth St to 0.237mi E of Elizabeth St. | Reconstruction | Clark | 025-KY-0974 -000 | 0.363 | 0.6 | 0.237 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 500000 |  | 500000 |  | 2000000 |  | 2015-06-29 11:23 | To reconstruct approaches and bridge on KY 974 from Elizabeth St to 0.237mi E of Elizabeth St. | The bridge over CSX railroad and approaches on KY 974 in Winchester are substandard and have safety concerns for motorists. There are substandard curves at both ends of the bridge. The sight distance is restricted by the barrier walls of the existing brid
Y | 7 | Bluegrass ADD | IP20080427 |  |  |  | Reconstruct KY 1927 from 1000ft W of KY 1923 to Winchester Byp. | Minor Widening | Clark | 025-KY-1927 -000 | 0.181 | 0.371 | 0.19 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3500000 |  | 3500000 |  | 20000000 |  | 2015-06-29 11:26 | To reconstruct KY 1927 from 1000 ft. W of KY 1923 to Winchester bypass. | Substandard geometrics and 2 8-9' lanes for current and projected ADT. The corridor is unsafe as indicated by the extremely high CRF this segment of KY 1927 (Colby Road). KY 1927 serves as an alternate route between Winchester and Lexington.
Y | 7 | Lexington MPO | IP20080430 | 7-439 |  | A | NEW CIRCLE RD: IMPROVE SAFETY AND REDUCE CONGESTION FROM US-68 (HARRODSBURG RD) TO US-60 (VERSAILLES RD). SEE SEGMENTS 2A & 2B IN AUGUST, 1998 ADVANCE PLANNING STUDY. | MINOR WIDENING(O) | Fayette | 034-KY-0004 -000 | 2.224 | 4.335 | 2.111 | Modernize Roadway-Rural | 26 | Y |  |  | 2200000 | 2024 | [6 empty] | 2018-07-10 08:17 | Improve safety and mobility and address congestion and modernize roadway on New Circle Rd. from US 68 (Harrodsburg Rd.) to US 60 (Versailles Rd.). | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility, 3) Address Congestion, 4) Modernize Roadway. | 7 | North | 39.6231 | 7.9077 | 7.2462 | 8.9769 | 1.1231 | 0 | 4.7385 | 9.6308 | 40
Y | 7 | Bluegrass ADD | IP20080431 |  |  |  | Improve safety on KY 52 from Boone Creek Road to KY 1150 in Garrard County. | Major Widening | Garrard | 040-KY-0052 -000 | 2.422 | 4.231 | 1.809 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 1800000 |  | 9000000 |  | 2017-05-19 14:20 | To improve safety on KY 52 from Boone Creek Road to KY 1150 in Garrard County. | High Critical Rate Factor indicates serious safety concerns on KY 52 from Boone Creek Road to KY 1150. Sight distance problems and poor roadway geometry on KY 52 from mile point 0.000 to 4.353. Horizontal alignment is rated 3 in one segment. Also there is | BLUEGRASS ADD | North | 37.1338 | 2.5723 | 7.0615 | 5.1 | 3.8462 | 7.5077 | 2.0615 | 8.9846 | 37
Y | 7 | Bluegrass ADD | IP20080437 |  |  |  | Reconstruct US 25 from KY 1156 (Jacks Creek Rd) to I-75. | Major Widening | Madison | 076-US-0025 -000 | 21.02 | 28.161 | 7.141 | Modernize Roadway-Rural | 26 |  | 0 |  | 2200000 |  | 5616000 |  | 7200000 |  | 25168000 |  | 2010-12-09 13:26 | To reconstruct US 25 from KY 1156 (Jacks Creek Rd) to I-75. | The recent completion of sanitary sewer in this portion of Madison County is expected to result in large residential and commercial growth. US 25 is a parallel route to I-75, and is heavily traveled when I-75 is closed to traffic.
Y | 7 | Bluegrass ADD | IP20080441 |  |  |  | Reconstruct KY 21 from KY 1617 to US 421. | Relocation | Madison | 076-KY-0021 -000 | 11.511 | 14.641 | 3.13 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3500000 |  | 7000000 |  | 10500000 |  | 2017-05-19 16:16 | Improve mobility and safety on KY 21 from KY 1617 to US 421. | The following needs have been identified for this project: 1) Improve Mobility, 2) Improve Safety. | BLUEGRASS ADD | North | 36.0354 | 3.6431 | 8.9538 | 6.8538 | 4.6462 | 0 | 2.2462 | 9.6923 | 36
Y | 7 | Bluegrass ADD | IP20080444 |  |  |  | Reconstruct KY 52 from KY 374 (Charlie Norris Rd) to Drowning Creek Bridge #033B00017N at Estill CL. | Reconstruction | Madison | 076-KY-0052 -000 | 16.334 | 22.707 | 6.373 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 10000000 |  | 14500000 |  | 22000000 |  | 2017-05-19 16:19 | Improve mobility and safety on KY 52 from KY 374 (Charlie Norris Rd) to Drowning Creek Bridge #033B00017N at Estill CL. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Safety. | BLUEGRASS ADD | North | 49.1723 | 5.6185 | 9.6923 | 11.4923 | 1.4923 | 8.2462 | 3.2154 | 9.4154 | 49
Y | 7 | Gateway ADD | IP20080461 |  |  |  | Improve safety, capacity, and congestion on I 64 from the Clark/Montgomery County line to approximately 0.2 miles east of the Grassy Lick Road underpass. | Major Widening | Montgomery | 087-I -0064 -000 | 104.26 | 107.5 | 3.24 | Modernize Roadway-Rural | 26 | Y | 0 |  | 2013000 |  | 476000 |  | 457500 |  | 26053500 |  | 2015-03-09 10:00 | The purpose of this project is to improve safety, capacity, and congestion. | The following needs have been identified for this project: 1) improve safety; 2) improve capacity; 3) improve congestion; 4) heavy freight traffic and project traffic volumes are projected to double over the next 20 years; and 5) the only major east-west
Y | 7 | Bluegrass ADD | IP20080466 |  |  |  | Improve roadway capacity & typical section on US 460 from E Main St to 300ft W of Cherry Blossom Way. | Reconstruction | Scott | 105-US-0460 -000 | 10.185 | 10.763 | 0.578 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 1000000 |  | 4500000 |  | 2013-08-12 11:04 | Improve roadway capacity & typical section on US 460 from E Main St to 300 ft W of Cherry Blossom Way. | The US 460 Corridor serves as access to I-75 north and Frankfort for traffic from Bourbon County and from along the US 68 corridor between Paris and Maysville. Trucks use route to travel from Paris to I-75 and/or the Toyota manufacturing facility. The l
Y | 7 | Bluegrass ADD | IP20080468 |  |  |  | Reconstruct US 460 from Soards Road to Belvedere Dr. | Major Widening | Scott | 105-US-0460 -000 | 4.008 | 6.072 | 2.064 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 1500000 |  | 1250000 |  | 5000000 |  | 2017-05-19 17:10 | Reconstruct US 460 from Soards Road to Belvedere Dr. | US 460 from Soars Road to KY 227 is part of a corridor between Frankfort and Toyota and from Frankfort to Paris. High CRF indicates serious safety concerns are present. IRI varies from 100 to 128. Congestion is present during peak AM and PM hours on this | BLUEGRASS ADD | North | 41.3431 | 4.32 | 11.2615 | 6.7615 | 4.7538 | 6.6462 | 0 | 7.6 | 41
Y | 7 | Bluegrass ADD | IP20080472 |  |  |  | Address safety issues on KY 32 in Scott County from Salem Road to the Harrison County line. | Reconstruction | Scott | 105-KY-0032 -000 | 20.71 | 23.003 | 2.293 | Other Improvement Types | 0 |  | 0 |  | 1650000 |  | 5304000 |  | 1700000 |  | 20350000 |  | 2010-12-07 11:56 |  | Critical Rate Factor indicates possible safety oncerns in some segments. IRI notes pavement problems present. Some segments are in the lower Percentile indicating that similar roads are in better condition. Horizontal Alignment on most segments of 3 and
Y | 7 | Bluegrass ADD | IP20080475 |  |  |  | Address safety issues on KY 1962 (Lemmon's Mill Road) From Military Street in Georgetown to Lisle Road at I-75. | Reconstruction | Scott | 105-KY-1962 -000 | 0.518 | 2.118 | 1.6 | Other Improvement Types | 0 |  | 0 |  | 770000 |  | 416000 |  | 400000 |  | 4400000 |  | 2010-12-07 11:59 | Address safety issues on KY 1962 (Lemmon's Mill Road) From Military Street in Georgetown to Lisle Road at I-75. | High CRF signifies safety concerns. Road is rated in very low Percentile, meaning that most similar roads are in better condition. Route has narrow 9' lanes, 1' or no shoulders and is rated 4 for Horizontal Alignment indicating uncomfortable or unsafe cur
Y | 7 | Bluegrass ADD | IP20080476 |  |  |  | Address roadway geometric deficiencies on Lisle Rd from US 25 TO KY 1962 in Georgetown. | Reconstruction | Scott | 105-KY-1963 -000 | 0 | 2.684 | 2.684 | Modernize Roadway-Rural | 26 |  | 0 |  | 825000 |  | 1560000 |  | 115000 |  | 6820000 |  | 2010-12-07 11:59 | Address roadway geometric deficiencies on Lisle Rd from US 25 TO KY 1962 in Georgetown. | KY 1963 (Lisle Road) from US 25 to KY 1962 in Georgetown has narrow lanes with 2' shoulders provide poor geometrics on a highway expecting increased traffic due to new subdivisions planned nearby and a new soccer field on the route.
Y | 7 | Bluegrass ADD | IP20080477 |  |  |  | Reconstruct KY 2906 (Connector Rd) from US 460 (Paris Pk) to US 62 (Cherry Blossom Way). | Reconstruction | Scott | 105-KY-2906 -000 | 0 | 1.118 | 1.118 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 1250000 |  | 7000000 |  | 2015-06-30 15:04 | Reconstruct KY 2906 (Connector Rd) from US 460 (Paris Pk) to US 62 (Cherry Blossom Way). | V/SF indicates congestion on the route. The area the facility serves has experienced major development since it was originally constructed. A Wal-Mart and a Lowe's Superstore, along with various commercial businesses, banks, restaurants, residential and a
Y | 7 | Bluegrass ADD | IP20080478 |  |  |  | Widening on I-64 from Franklin/Woodford CL to I-64/I-75 northern split in Fayette County. | Major Widening | Woodford | 120-I -0064 -000 | 59.431 | 67.106 | 7.675 | Modernize Roadway-Rural | 26 | Y | 0 |  | 4000000 |  | 500000 |  | 500000 |  | 105000000 |  | 2011-10-18 12:30 | Widening on I-64 from Franklin/Woodford CL to I-64/I-75 northern split in Fayette County. | Composite Ratings on this segment of I-64 in the counties of Woodford, Scott and Fayette along with Critical Rate Factor indicates existing safety concerns on a portion of the corridor. I-64 through Kentucky is the major east/west interstate and a major
Y | 7 | Bluegrass ADD | IP20080482 |  |  |  | Improve intersection at US 60X (N Main St & Frankfort St) at KY 1659 (Elm St) and Broadway in Versailles. | Reconstruction | Woodford | 120-US-0060X -000 | 0.68 | 0.78 | 0.1 | Improve Intersection | 26 |  | 0 |  | 400000 |  | 950000 |  | 750000 |  | 2000000 |  | 2013-10-31 16:46 | Improve intersection at US 60X (N Main St & Frankfort St) at KY 1659 (Elm St) and Broadway in Versailles. | Safety concerns are present at the intersection Of US 60X/US 62 (N. Main St.), KY 1659 (Elm St.) and Broadway in Versailles. The US 60X/US 62 leg of this intersection is expected to increase ADT by the year 2020, according to the 1999 Woodford County Tra
Y | 7 | Bluegrass ADD | IP20080483 |  |  |  | Reconstruct intersection at US 62 (Rose Hill Ave & Tyrone Pk) and KY 1964 (Clifton Rd) in Versailles. | Reconstruction | Woodford | 120-US-0062 -000 | 6.496 | 6.7 | 0.204 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 750000 |  | 1000000 |  | 2000000 |  | 2017-05-19 17:16 | Reconstruct intersection at US 62 (Rose Hill Ave & Tyrone Pk) and KY 1964 (Clifton Rd) in Versailles. | Safety issues at the intersection of US 62 and KY 1964 (Rose Hill Avenue) in Versailles. Project is in a low percentile, indicating similar roads are in better condition. The project is located on a corridor connecting Versailles to Lawrenceburg and truc | BLUEGRASS ADD | North | 32.6692 | 4.3077 | 12.4615 | 6.4385 | 3.2769 | 0 | 2.3385 | 3.8462 | 33
Y | 7 | Bluegrass ADD | IP20080484 |  |  |  | Improve safety and reduce congestion on US 62 from South Main Street to Woodford County Park in Versailles, provide bicycle and pedestrian access and consider access management. | Reconstruction | Woodford | 120-US-0062 -000 | 5.4 | 7.046 | 1.646 | Other Improvement Types | 0 |  | 150000 |  | 1122000 |  | 3432000 |  | 1100000 |  | 7343000 |  | 2010-12-07 11:37 | Improve safety and reduce congestion on US 62 from South Main Street to Woodford County Park in Versailles, provide bicycle and pedestrian access and consider access management. | Adequacy Ratings indicate safety and congestion issues in portions of the project limits. Traffic volumes are high. Roadway has a connection to the Woodford County Park and recreational facility, but does not provide dedicated facilities to pedestrians an
Y | 7 | Bluegrass ADD | IP20080487 |  |  |  | Intersection improvements on KY 1681 (Old Frankfort Pk) at KY 1967 (Pisgah Pk) and CR 1013 (Paynes Depot Rd). | Safety-Haz-Elm | Woodford | 120-KY-1681 -000 | 11 | 11.2 | 0.2 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 250000 |  | 400000 |  | 1250000 |  | 2013-10-31 17:17 | Intersection improvements on KY 1681 (Old Frankfort Pk) at KY 1967 (Pisgah Pk) and CR 1013 (Paynes Depot Rd). | This section of Old Frankfort Pike (KY 1681) includes two offset approaches; Paynes Depot Road and Pisgah Pike (KY 1967) in Woodford County. Many traffic accidents are occuring within the vicinity of these two intersections. There are no left turn lanes b
Y | 7 | Bluegrass ADD | IP20080488 |  |  |  | Curve revision on KY 1681 (Old Frankfort Pike) from CR 1010 (Browns Mill Rd) to Woodford/Fayette CL. | Safety-Haz-Elm | Woodford | 120-KY-1681 -000 | 11.9 | 12.325 | 0.425 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 100000 |  | 100000 |  | 1000000 |  | 2013-10-31 17:13 | Curve revision on KY 1681 (Old Frankfort Pike) from CR 1010 (Browns Mill Rd) to Woodford/Fayette CL. | This section of Old Frankfort Pike (KY 1681) in Woodford and Fayette Counties is located in a dangerous curve. Many traffic accidents are occuring at this location and have demonstrated a safety concern for motorists. There are chevrons in place to inform
Y | 7 | Bluegrass ADD | IP20080741 |  |  |  | Construct new route from KY 1989 (Cornishville Rd) to KY 152 including improvements at RR crossing on KY 1989. | New Route | Mercer | 084-US-0127 -000 | 4.402 | 4.9 | 0.498 | Construct Road in New Location | 0 |  | 0 |  | 200000 |  | 450000 |  | 450000 |  | 1500000 |  | 2017-05-19 16:31 | Construct new route from KY 1989 (Cornishville Rd) to KY 152 including improvements at RR crossing on KY 1989. | Due to heavy railroad traffic thru Harrodsburg, the at-grade crossing at Cornishville Road (KY 1989) is causing traffic to back up along Cornishville Road with no relief route for motorists. This route will allow motorists to travel bewteen the southwest | BLUEGRASS ADD | North | 29.2969 | 3.6431 | 2.3077 | 9.6692 | 0 | 9.9385 | 3.7385 | 0 | 29
Y | 7 | Lexington MPO | IP20110148 |  |  |  | Capacity improvements on KY 4 (New Circle Rd) from N Limestone to Eastland Dr. | Major Widening | Fayette | 034-KY-0004 -000 | 10.9 | 12.515 | 1.615 | Modernize Roadway-Rural | 26 | Y | 0 |  | 2000000 |  | 5000000 |  | 3500000 |  | 12500000 |  | 2015-06-29 13:39
Y | 7 | Bluegrass ADD | IP20110182 |  |  |  | Corridor / Scoping Study (approx. 10 miles) from KY 33 (Shakertown entrance)in Mercer County to KY 29 / US 68 "Y intersection" in Jessamine County. | Relocation | Mercer | 084-US-0068 -000 | 14.452 | 20.058 | 5.606 | Other Improvement Types | 0 |  | 500000 |  | 6000000 |  | 10000000 |  | 5000000 |  | 50000000 |  | 2011-10-27 10:53 | Corridor / Scoping Study (approx. 10 miles) from KY 33 (Shakertown entrance)in Mercer County to KY 29 / US 68 "Y intersection" in Jessamine County. | US 68 is primary route from Lexington to Harrodsburg and has a high critical rate factor between Wilmore and Harrodsburg. Roadway typical section and vertical and horizontal geometric deficiencies especially in the KY River Basin area. Common landslides
Y | 7 | Bluegrass ADD | IP20110183 |  |  |  | Corridor scoping study on US 60 (Lexington Rd) from Fayette/Clark CL to KY 1958 (Veterans Memorial Pkwy). | Major Widening | Clark | 025-US-0060 -000 | 0 | 4.678 | 4.678 | Transportation Studies | 0 |  | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2013-10-31 17:20 | Corridor scoping study on US 60 (Lexington Rd) from Fayette/Clark CL to KY 1958 (Veterans Memorial Pkwy). | US 60 West of the Winchester bypass is nearing capacity due to high ADT, including high truck volumes. This route serves as a relief route to I-64.
Y | 7 | Lexington MPO | IP20110184 |  |  |  | Typical section & pavement improvements from I-64 to Bluegrass Station, with improvements on KY 57 (Briar Hill Rd) from KY 2335 (Houston-Antioch Rd) to Bluegrass Station north entrance and KY 859 (Haley Rd) from I-64 to KY 57. | Reconstruction | Fayette | 034-KY-0057 -000 | 7.8 | 9.608 | 1.808 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 3000000 |  | 3000000 |  | 16500000 |  | 2013-08-12 09:55 |  | Lockheed Martin is anticipating expanding their facilities increasing their number of employees and truck traffic. KY 57 provides access to the Bluegrass Station (Avon), where Lockheed Martin is located. This roadway has narrow lanes, narrow shoulders,
Y | 7 | Bluegrass ADD | IP20110191 |  |  |  | Improve drainage from southern bypass intersection at US 27 to northern bypass intersection at US 68, including Main St & High St (1-way segments). | Drainage Improvement | Bourbon | 009-US-0068X -000 | 0 | 2.772 | 2.772 | Maintenance Improvement | 10 |  | 0 |  | 550000 |  | 1040000 |  | 400000 |  | 3410000 |  | 2017-05-18 14:38 | Improve drainage between the southern bypass intersection at US 27 and northern bypass intersection at US 68, including Main St. & High St. | The following needs have been identified in this project: 1) Improve Drainage. | 7 | North | 25.8315 | 5.7969 | 0 | 13.3269 | 3.3077 | 0 | 3.4 | 0 | 26
Y | 7 | Bluegrass ADD | IP20120025 |  |  |  | Construct a left turn lane on US 127 to Hawthorne Lane in Anderson County. | Spot Improvement | Anderson | 003-US-0127 -000 | 1.028 | 1.128 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 50000 |  | 20000 |  | 75000 |  | 250000 |  | 2013-03-01 16:10 | Construct a left turn lane on US 127 to Hawthorne Lane in Anderson County. | Due to high traffic volume, high speed, and high CRF, a dedicated turn lane is needed to improve safety and traffic flow.
Y | 7 | Bluegrass ADD | IP20120027 |  |  |  | Construct left turn lanes on KY 44 to Scenic Gardens Drive & Nautical Way in Lawrenceburg. | Spot Improvement | Anderson | 003-KY-0044 -000 | 11.726 | 12.372 | 0.646 | Improve Intersection | 26 |  | 0 |  | 75000 |  | 100000 |  | 300000 |  | 480000 |  | 2017-05-18 13:58 | Construct left turn lanes on KY 44 to Scenic Gardens Drive & Nautical Way in Lawrenceburg. | Due to high truck volume and high speed, a dedicated turn lane is needed to improve safety and traffic flow. | BLUEGRASS ADD | North | 19.7292 | 5.0831 | 3.5077 | 1.5231 | 2.5692 | 0 | 0 | 7.0462 | 20
Y | 7 | Bluegrass ADD | IP20120029 |  |  |  | Develop a new route from US 150 to KY 34 in Danville. | New Route | Boyle | 011-KY-1805 -000 | 0 | 2.712 | 2.712 | Construct Road in New Location | 0 |  | 0 |  | 1650000 |  | 1000000 |  | 750000 |  | 16500000 |  | 2013-03-04 17:07 | Develop a new route from US 150 to KY 34 in Danville. | Develop a new route from US 150 to KY 34 in Danville.
Y | 7 | Bluegrass ADD | IP20120031 |  |  |  | Improve safety on KY 52 from KY 590 in Boyle County to Martin Lane in Garrard County. | Major Widening | Garrard | 040-KY-0052 -000 | 0 | 1.53 | 1.53 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 3000000 |  | 3500000 |  | 20000000 |  | 2017-05-19 14:13 | Improve safety on KY 52 from KY 590 in Boyle County to Martin Lane in Garrard County. | Due to high speeds, reduced shoulder widths, and high CRF, roadway geometrics need to be changed to improve safety. | BLUEGRASS ADD | North | 54.5454 | 2.5723 | 6.8308 | 7.8808 | 3.8308 | 7.5077 | 2.0615 | 8.8615 | 40 |  | 15
Y | 7 | Bluegrass ADD | IP20120033 |  |  |  | Safety improvements and access management on US 127 (Danville Road) from Brightleaf Drive to Adams Lane. | Spot Improvement | Mercer | 084-US-0127 -000 | 1.23 | 1.457 | 0.227 | Access Consolidation | 25 | Y | 0 |  | 500000 |  | 2000000 |  | 1000000 |  | 4000000 |  | 2017-05-19 16:27 | Safety improvements and access management on US 127 (Danville Road) from Brightleaf Drive to Adams Lane. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Access, 3) Improve Mobility. | BLUEGRASS ADD | North | 18.8454 | 2.7262 | 5.4 | 1.1192 | 1 | 0 | 4.0462 | 4.5538 | 19
Y | 7 | Bluegrass ADD | IP20120036 | 7-80001 |  | A | IMPROVE US-62 (VERSAILLES RD.) FROM HILLTOP DR. TO WEST END OF BRIDGE OVER KENTUCKY RIVER AT TYRONE(18CCN) | SPOT IMPROVEMENTS(O) | Anderson | 003-US-0062 -000 | 20.54 | 22.813 | 2.273 | Modernize Roadway-Rural | 26 |  |  |  | 1200000 | 2020 | 3300000 | 2021 | 4000000 | 2022 | 11300000 | 2023 | 2018-07-10 08:18 | Improve US 62 (Versailles Rd) from Hilltop Dr to west end of bridge over Kentucky River at Tyrone. | Due to high CRF and anticipated truck volume increase (Wild Turkey Distillery Expansion), the road geometrics need to be improved, including possible widening. | BLUEGRASS ADD | North | 70.3438 | 2.9785 | 8.8154 | 7.6038 | 3.7077 | 6.5231 | 2.2154 | 8.5 | 40 | 15 | 15
Y | 7 | Bluegrass ADD | IP20120044 |  |  |  | Improve draining in vertical curve on US 62 around the railroad overpass near Midway. | Spot Improvement | Woodford | 120-US-0062 -000 | 16.1 | 16.2 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 200000 |  | 200000 |  | 1500000 |  | 2013-10-31 17:06 | Improve draining in vertical curve on US 62 around the railroad overpass near Midway. | Periodic flooding issues on US 62 around the railroad overpass near Midway need to be addressed to improve traffic safety and mobility.
Y | 7 | Bluegrass ADD | IP20130003 | 7-440 |  | A | IMPROVE KY-169 FROM NORTH OF CLEAR CREEK RD IN JESSAMINE COUNTY TO NORTH OF KY-1967 IN WOODFORD COUNTY. | RECONSTRUCTION(O) | Woodford | 120-KY-0169 -000 | 0 | 3 | 3 | Modernize Roadway-Rural | 26 |  |  |  | 800000 | 2023 | [6 empty] | 2018-07-10 08:17 | Improve safety and mobility on KY 169 from approximately 0.54 mi N of Clear Creek Rd in Jessamine County to 0.879 mi N of KY 1967 in Woodford County. | The following needs have been identified for this project: 1) Improve Safety, 2) Improve Mobility. | 7 | North | 71.5069 | 2.9415 | 11.2154 | 8.6423 | 3.3538 | 6.1231 | 0 | 9.2308 | 42 | 15 | 15
Y | 7 | Lexington MPO | IP20130091 |  |  |  | Widening and drainage improvements on US 421 under RR overpass 0.1mi NW of CR 1314 (Dolan Ln). | Minor Widening | Fayette | 034-US-0421 -000 | 7.071 | 7.221 | 0.15 | Modernize Roadway-Rural | 26 |  | 0 |  | 470000 |  | 240000 |  | 120000 |  | 5210000 |  | 2017-05-19 09:56 | Improve safety and roadway geometrics, address storm water issues | The following needs have been identified on this project: 1) Improve safety, 2) Improve Roadway Geometrics. | 7 | North | 19.9769 | 6.4308 | 3 | 0.62308 | 2.4154 | 0 | 2.8615 | 4.6462 | 20
Y | 7 | Gateway ADD | IP20130094 |  |  |  | Reconstruct KY 646 from approximately 0.09 miles north of McDonald Rd (CR 1237) to approximately 0.19 miles north of McDonald Rd (CR 1237). | Spot Improvement | Montgomery | 087-KY-0646 -000 | 9.6 | 9.7 | 0.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 250000 |  | 150000 |  | 1000000 |  | 2017-05-19 16:55 | The purpose of this project is to: complete spot improvements and modernize the roadway. | The following needs have been identified for this project: 1) Complete Spot Improvements; 2) Modernize Roadway; and 3) Reconstruct Roadway. | 7 | North | 16.8585 | 0.38154 | 5.1231 | 7.5692 | 3.7846 | 0 | 0 | 0 | 17
Y | 7 | Gateway ADD | IP20130095 |  |  |  | Intersection improvement at KY 646 (Kiddville Rd) 0.373mi S of Tonkin Rd including turn lanes & improved sight distance. | Spot Improvement | Montgomery | 087-KY-0011 -000 | 6.95 | 7.15 | 0.2 | Improve Intersection | 26 |  | 0 |  | 75000 |  | 50000 |  | 50000 |  | 750000 |  | 2013-08-12 11:00 | The purpose of this project is to improve: safety, intersection, and sight-distance. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Intersection; and 3) Improve Sight-Distance; and 4) Add Turn Lanes.
Y | 7 | Lexington MPO | IP20130101 |  |  |  | Reconstruct KY 169 (Richmond Ave) from proposed East Nicholasville Byp to US 27X (North Main St). | Reconstruction | Jessamine | 057-KY-0169 -000 | 8.45 | 10.458 | 2.008 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 1200000 |  | 1500000 |  | 9000000 |  | 2015-06-29 20:55
Y | 7 | Gateway ADD | IP20130102 |  |  |  | Improve safety and widen US 60 and I-64 interchange (exit 113). | Major Widening | Montgomery | 087-US-0060 -000 | 8.4 | 8.95 | 0.55 | Innovative Interchange | 40 |  | 0 |  | 2000000 |  | 1250000 |  | 500000 |  | 23500000 |  | 2017-05-19 16:41 | The purpose of this project is to improve safety and widen the roadway. | The following needs have been identified for this project: 1) Improve Safety, and 2) Widen the Roadway. | 7 | North | 21.7538 | 2.6462 | 5.2154 | 8.8154 | 0 | 0 | 0 | 5.0769 | 22
Y | 7 | Gateway ADD | IP20150057 |  |  |  | Address safety issues and high traffic volumes from the Mount Sterling bypass (KY 686) to the Powell County line. | Safety-Haz-Elm | Montgomery | 087-KY-0011 -000 | 0 | 9.246 | 9.246 | Modernize Roadway-Rural | 26 |  | 465000 |  | 3806000 |  | 13225000 |  | 3600000 |  | 37070000 |  | 2015-03-04 12:01 | The purpose of this project is to improve safety and congestion. | The following needs have been identified for this project: 1) improve safety; 2) address high traffic volumes from Mount Sterling to Powell County; and 3) promote safe and efficient movement of people, goods, and services to benefit residents of the regio
Y | 7 | Gateway ADD | IP20150064 |  |  |  | Construct new route of I 64 connecting KY 11 near US 460 (Paris Pike) extending approximately 2.0 miles east to Hinkston Pike. | New Route | Montgomery | 087-I -0064 -000 | 109.5 | 111 | 1.5 | Construct Road in New Location | 0 | Y | 0 |  | 750000 |  | 750000 |  | 1000000 |  | 5000000 |  | 2015-03-09 09:44 | The purpose of this project is to construct a new route. | The following needs have been identified for this project: 1) provide additional east-west connectivity; and 2) promote safe and efficient movement of people goods, and services to benefit residents of the region.
Y | 7 | Bluegrass ADD | IP20150117 |  |  |  | Improve intersection at KY 34 and US 150 and address safety, congestion, and level of service from Cowan Street to US 150. | Congestion Management | Boyle | 011-KY-0034 -000 | 13.19 | 13.629 | 0.439 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 1500000 |  | 1500000 |  | 2000000 |  | 2017-05-18 17:34 | Improve safety and congestion at the intersection of KY 34 and US 150, and improve mobility and reduce congestion from Cowan St. to US 150. | The following needs have been identified for this project: 1) Improve Intersection Safety, 2) Reduce Intersection Congestion, 3) Improve Roadway Safety, 4) Reduce Roadway Congestion. | BLUEGRASS ADD | North | 25.0469 | 3.92 | 6.2769 | 3.9577 | 2.5538 | 0 | 2.5846 | 5.7538 | 25
Y | 7 | Bluegrass ADD | IP20150123 |  |  |  | Improve safety on Jacks Creek Rd (KY 1156) from US 25 to Clay Lane. | Safety-Haz-Elm | Madison | 076-KY-1156 -000 | 0 | 4.651 | 4.651 | [14 empty] | Improve safety on Jacks Creek Rd (KY 1156) from US 25 to Clay Lane. | Improve safety on Jacks Creek Rd (KY 1156) from US 25 to Clay Lane.
Y | 7 | Bluegrass ADD | IP20150126 |  |  |  | Minor widening to improve safety and level of service from Chestnut Lane to Aiken Road in Woodford County | Minor Widening | Woodford | 120-US-0062 -000 | 7.38 | 9.247 | 1.867 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 400000 |  | 300000 |  | 4000000 |  | 2017-05-19 17:19 | Improve safety and level of service from Chestnut Lane to Aiken Road in Woodford County. | The following needs have been identified for this project: 1) Improve Safety, 2) Improve Mobility. | BLUEGRASS ADD | North | 29.0938 | 3.7169 | 11.0769 | 5.1462 | 2.2615 | 0 | 0 | 6.8923 | 29
Y | 7 | Bluegrass ADD | IP20150128 |  |  |  | New road to extend from Menelaus Road (KY 1983) to Mayde Road in Berea. | New Route | Madison | 076-KY-1983 -000 | 0 | 1 | 1 | [14 empty] | The purpose of this project is to: - Improve Safety - Improve Access and Mobility | New road to extend from Menelaus Road (KY 1983) to Mayde Road in Berea.
Y | 7 | Lexington MPO | IP20150142 | 7-412 |  | A | REPLACE L&N RAILROAD BRIDGE OVERPASS (MP 8.378), IMPROVE DRAINAGE AND TYPICAL SECTION ON US 27 (NORTH BROADWAY)(12CCR)(14CCR)(16CCR)(18CCN) | RECONSTRUCTION(O) | Fayette | 034-US-0027 -000 | 8.565 | 8.691 | 0.126 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 2560000 | 2020 | 1610000 | 2021 | 12290000 | 2023 | 2019-03-12 11:36 | Improve pedestrian safety, accessibility and bridge vertical clearance, and reduce congestion on L&N railroad bridge overpass (MP 8.378), and improve drainage and typical section on US 27 (NORTH BROADWAY). | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Accessibility, 3) Reduce Congestion, 4) Improve Vertical Clearance, 5) Improve Drainage. | Lexington MPO | North | 73.7108 | 4.7569 | 9.8769 | 10.1538 | 2.5692 | 9.0769 | 3.5846 | 3.6923 | 44 | 15 | 15
Y | 7 | Gateway ADD | IP20150256 | 7-8810 |  | A | WIDEN EXISTING PAVEMENT & IMPROVE VERTICAL & HORIZONTAL CURVES FROM EXISTING MT STERLING BYPASS (KY 686) TO 500' W OF BENTBROOK SUBDIVISION. ADD FULL WIDTH SHOULDERS & A CENTER TURNING LANE IN CONGESTION AREAS FROM MP 2.2 TO 4.311.(14CCN)(16CCR)(18CCN) | MAJOR WIDENING(O) | Montgomery | 087-US-0060 -000 | 2.007 | 4.311 | 2.304 | Modernize Roadway-Rural | 26 |  |  |  | 800000 | 2020 | 4600000 | 2022 | 1090000 | 2022 | 9600000 | 2024 | 2019-03-04 08:19 | The purpose of this project is to: improve safety, geometrics, traffic flow, and turning movements. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Horizontal/Vertical Alignment, 3) Add Shoulders, 4) Add a Center Turning Lane in Congestion Areas from approximately Milepoint 2.2 to approximately Milepoin | GATEWAY ADD | North | 68.36 | 3.2677 | 10.0615 | 9.3231 | 1.5231 | 7.1077 | 0 | 7.0769 | 38 | 15 | 15
Y | 7 | Bluegrass ADD | IP20150261 | 7-8858 |  | A | SAFETY IMPROVEMENTS ON US 127 IN SALVISA. (14CCN)(18CCN) | SAFETY(P) | Mercer | 084-US-0127 -000 | 14.469 | 16.903 | 2.434 | Access Consolidation | 25 | Y |  |  | 100000 | 2019 | 100000 | 2025 | 0 |  | 400000 | 2025 | 2018-07-10 08:18 | Improve safety on US 127 between the Oregon Rd. and the intersection of Main St. and US 127 in Salvisa. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility. | BLUEGRASS ADD | North | 36.5392 | 3.4585 | 14.5846 | 4.7423 | 1 | 0 | 4.2615 | 8.4923 | 36
Y | 7 | Bluegrass ADD | IP20150280 | 7-117 | 401769 | A | IMPROVE US 60 (VERSAILLES ROAD) FROM THE BLUEGRASS PARKWAY/HUNTERTOWN PIKE TO PISGAH PIKE. (18CCR) | MAJOR WIDENING(O) | Woodford | 120-US-0060 -000 | 11.238 | 12.612 | 1.374 | Modernize Roadway-Rural | 26 | Y |  |  |  | 2021 | 260000 | 2025 | 310000 | 2025 | 2410000 | 2025 | 2018-07-10 08:18 | Improve on US 60 (VERSAILLES ROAD) from the Bluegrass Pkwy/Huntertown Pike to Pisgah Pike. | The following needs have been identified on this project: 1) Improve Mobility, 2) Reduce Congestion. | 7 | Statewide | 70.8484 | 15.7181 | 19.207 | 9.6476 | 0 | 9.6696 | 8.5903 | 8.0158
Y | 7 | Gateway ADD | IP20150302 | 7-240 / 7-240.01 / 7-240.01 / 7-8501 / 7-8501 | 401783 | A | WIDEN KY-1991 FROM MAYSVILLE ROAD TO MIDLAND TRAIL INDUSTRIAL PARK. (2005HPP-KY129) TO BE DONE IN CONJUNCTION WITH 7-240.00. (08CCN)(12CCR) | MINOR WIDENING(O) | Montgomery | 087-KY-1991 -000 | 0 | 1.768 | 1.768 | Modernize Roadway-Rural | 26 | [5 empty] | 410000 | 2025 | 1000000 | 2025 | 7400000 | 2016 | 2018-07-10 08:18 | The purpose of this project is to: widen and modernize the roadway. | The following needs have been identified for this project: 1) Widen the Roadway; and 2) Modernize the Roadway. | 7 | North | 36.7796 | 2.1046 | 11.7231 | 6.0231 | 4.7692 | 5.7846 | 0 | 6.375 | 37
Y | 7 | Bluegrass ADD | IP20150317 | 7-8853 |  | A | PROPOSED ROADWAY IMPROVEMENTS FROM DUNCANNON RD TO THE MADISON CO AIRPORT TO INCLUDE CALEAST RD (KY 2881 MP.783-MP 2.780), JOHN BALLARD RD (KY 2877 MP0-MP.806 & CR 1236 MP0-MP.429) FROM MENELAUS TO AIRPORT RD, & A NEW BRIDGE OVER SILVER CR.(14CCN)(16CCR) | SPOT IMPROVEMENTS(O) | Madison | 076-KY-2881 -000 | 0.783 | 2.78 | 1.997 | Modernize Roadway-Rural | 26 |  |  |  | 1040000 | 2019 | 5520000 | 2020 | 2930000 | 2021 | 10530000 | 2022 | 2018-07-10 08:18 | Improve mobility and connectivity from Duncanoon Rd. to the Madison Co. airport to include Caleast Rd., John Ballard Rd. from Menelaus to Airport Rd., & a new bridge over Silver Creek. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Connectivity. | 7 | North | 20.4769 | 0.83077 | 4.9846 | 5.1346 | 4.8769 | 0 | 0 | 4.65 | 20
Y | 7 | Bluegrass ADD | IP20150329 | 7-8401 | 2021-07-15 | A | EXTEND THE WINCHESTER EAST BYPASS (KY 1958) FROM IRVINE ROAD (KY 89) TO KY 627 SOUTH OF WINCHESTER. (08CCN)(10CCR)(18CCN) | NEW ROUTE(O) | Clark | 025-KY-0627 -000 | 6.3 | 8.1 | 1.8 | Construct Road in New Location | 0 |  |  |  | 0 | 2019 | 0 | 2020 | 0 | 2022 | 37500000 | 2024 | 2018-07-10 08:18 | Improve mobility on Winchester East Bypass from Irvine Rd. to KY 627, South of Winchester. | The following needs have been identified for this project: 1) Improve Roadway Mobility, 2) Improve Roadway Access. | BLUEGRASS ADD | North | 65.9223 | 5.1262 | 3.6462 | 12.6115 | 3.4923 | 8 | 3.0462 | 0 | 36 | 15 | 15
Y | 7 | Bluegrass ADD | IP20150330 | 7-8639 |  | A | EXTEND FULTON ROAD. (BY COUNTY)(10CCN)(18CCN) | NEW ROUTE(O) | Clark | 025-US-0060 -000 | 4.605 | 6.183 | 1.578 | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 1580000 | 2021 | 2018-07-10 08:18 | The purpose of this project is to: - Reduce Congestion - Improve Mobility and Access - Improve Safety | US 60 is a major East/West corridor that connects Winchester in Clark County to Lexington in Fayette County. Population growth has been a contributing factor in the congestion and safety concerns on US 60, limiting mobility and increasing drive time for d | BLUEGRASS ADD | North | 5.6369 | 0.16 | 0 | 0 | 0 | 5.4769 | 0 | 0 | 6
Y | 7 | Lexington MPO | IP20150333 | 7-113.02 |  | A | IMPROVE NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR)(18CCR) | MAJOR WIDENING(O) | Fayette | 034-KY-0004 -000 | 7.26 | 8.26 | 1 | Modernize Roadway-Rural | 26 | Y |  |  |  |  | 9500000 | 2021 | 16000000 | 2021 | 73540000 | 2024 | 2019-03-08 09:53 | Improve capacity and mobility on NEW CIRCLE ROAD FROM LEESTOWN ROAD TO NEAR GEORGETOWN ROAD. (12CCR)(14CCR) | The following needs have been identified on this project: 1) Improve Capacity, 2) Improve Mobility. | 7 | Statewide | 52.6168 | 16.7753 | 8.7225 | 5.3359 | 5.815 | 0 | 5.9031 | 10.0651
Y | 7 | Lexington MPO | IP20150334 | 7-593.03 / 7-593.30 |  | A | NEWTOWN PIKE EXTENSION FROM WEST MAIN ST. TO SOUTH LIMESTONE ST. IN LEXINGTON. (ADDITIONAL FUNDING FOR DESIGN FOR CLT)(05KYD-KY095) | NEW ROUTE(O) | Fayette | 034-US-0027 -000 | 6.207 | 6.441 | 0.234 | Construct Road in New Location | 0 | Y |  |  | 250000 | 2025 | 11200000 | 2016 | 5700000 | 2016 | 15800000 | 2018 | 2017-05-18 15:04 | Improve mobility and safety, and reduce congestion on Newtown Pike from existing Newtown Pike & Patterson to South Limestone. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Safety, 3) Reduce Congestion. | Lexington MPO | North | 52.5062 | 9.3908 | 0 | 12.7154 | 1.5231 | 9.5077 | 4.3692 | 0 | 38 | 15
Y | 7 | Lexington MPO | IP20150437 | 7-414 / 7-414.10 |  | A | IMPROVE ROADWAY GEOMETRICS, TYPICAL SECTION, AND ROADWAY HAZARDS ON KY 1980 (BRANNON RD) FROM US 68 (HARRODSBURG RD) TO US 27 (NICHOLASVILLE RD). BEGIN RIGHT OF WAY PURCHASE FROM US-68 EASTWARD TO RAILROAD CROSSING.(18CCN) | SAFETY(P) | Jessamine | 057-KY-1980 -000 | 0 | 3.205 | 3.205 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 9880000 | 2020 | 5200000 | 2023 | 16380000 | 2024 | 2018-07-10 08:18 | IMPROVE ROADWAY GEOMETRICS, TYPICAL SECTION, AND ROADWAY HAZARDS ON KY 1980 (BRANNON RD) FROM US 68 (HARRODSBURG RD) TO US 27 (NICHOLASVILLE RD)(12CCR)replaces 07 057 D1980 1.00 | The following needs have been identified on this project: 1) Improve Roadway Geometrics, 2) Improve Safety, 3) Improve Mobility. | 7 | North | 70.6546 | 6.9354 | 10.2923 | 10.1654 | 4.5231 | 0 | 0 | 8.7385 | 41 | 15 | 15
Y | 7 | Bluegrass ADD | IP20150466 |  |  |  | Reconstruct KY 57 (Bryan Station Rd) from Hermitage Dr to Preakness Dr. | Reconstruction | Fayette | 034-KY-0057 -000 | 0.912 | 1.292 | 0.38 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 750000 |  | 750000 |  | 4500000 |  | 2015-06-29 14:41 | Reconstruct KY 57 (Bryan Station Rd) from Hermitage Dr to Preakness Dr. | Reconstruct KY 57 (Bryan Station Rd) from Hermitage Dr to Preakness Dr.
Y | 7 | Bluegrass ADD | IP20150468 |  |  |  | Reconstruct interchange at KY 32 and I-75 (exit 136). | Reconstruction | Scott | 105-KY-0032 -000 | 22.466 | 23.003 | 0.537 | Innovative Interchange | 40 |  | 0 |  | 1500000 |  | 1000000 |  | 1250000 |  | 16000000 |  | 2015-06-30 15:23 | Reconstruct interchange at KY 32 and I-75 (exit 136). | Reconstruct interchange at KY 32 and I-75 (exit 136).
Y | 7 | Gateway ADD | IP20160065 | 7-411 | 401783 | A | UPGRADE HINKSTON PIKE IN MT. STERLING FROM NEW MIDLAND TRAIL TO THE NEW INDUSTRIAL PARK ENTRANCE (INCLUDES EXTENSION OF INDUSTRIAL ACCESS ROAD TO HINKSTON PIKE). (12CCR)(18CCN) | MINOR WIDENING(O) | Montgomery | 087-KY-1991 -000 | 1.768 | 2.8 | 1.032 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 4510000 | 2019 | 2018-07-10 08:18 | The purpose of this project is to: widen and modernize the roadway. | The following needs have been identified for this project: 1) Widen the Roadway; and 2) Modernize the Roadway. | 7 | North | 17.7792 | 0.52923 | 3.1846 | 1.3038 | 4.2615 | 0 | 0 | 8.5 | 18
Y | 7 | Bluegrass ADD | IP20160093 |  |  |  | Regional Corridor Feasibility Study to evaluate east-west connectivity between US 127 and I-75. Study region includes the following counties: Anderson, Fayette, Franklin, Jessamine, Mercer, Scott & Woodford. | New Route | Fayette | 034-US-0060 -000 | 0 | 4.5 | 4.5 | Transportation Studies | 0 | Y | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-05-30 11:53 | Regional Corridor Feasibility Study to evaluate east-west connectivity between US 127 and I-75. | Regional Corridor Feasibility Study to evaluate east-west connectivity between US 127 and I-75. Study region includes the following counties: Anderson, Fayette, Franklin, Jessamine, Mercer, Scott & Woodford. | 7 | North | 27.0785 | 9.2246 | 0 | 12.9462 | 0 | 0 | 4.9077 | 0 | 27
Y | 7 | Bluegrass ADD | IP20160130 |  |  |  | FOURTH STREET CORRIDOR IMPROVEMENTS BETWEEN JEFFERSON AND UPPER STREET AT TRANSYLVANIA UNIVERSITY IN LEXINGTON (2014BOP) | Congestion Management | Fayette | 034-CS-1375 -000 | 0.071 | 0.503 | 0.432 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 14:15 | FOURTH STREET CORRIDOR IMPROVEMENTS BETWEEN JEFFERSON AND UPPER STREET AT TRANSYLVANIA UNIVERSITY IN LEXINGTON (2014BOP) | FOURTH STREET CORRIDOR IMPROVEMENTS BETWEEN JEFFERSON AND UPPER STREET AT TRANSYLVANIA UNIVERSITY IN LEXINGTON (2014BOP)
Y | 7 | Lexington MPO | IP20160131 | 7-8909 |  | A | REDUCE CONGESTION ON I-64/I-75 FROM THE C&O RAILROAD BRIDGE TO THE NORTHERN SPLIT (SECTION 1). (16CCN)(18CCR) | MAJOR WIDENING(O) | Fayette | 034-I -0075 -000 | 112.012 | 117.665 | 5.653 | Add Lane to Full Control Facility | 25 | Y |  |  | 0 | 2021 | 8820000 | 2021 | 3250000 | 2021 | 81670000 | 2022 | 2018-07-10 08:18 | Reduce congestion and improve mobility on I-64/I-75 from Bryan Station Overpass to Northern Split. | The following needs have been identified on this project: 1) Reduce Congestion, 2) Improve Mobility. | 7 | Statewide | 79.3511 | 18.3789 | 11.63 | 12.6872 | 4.4053 | 8.0617 | 9.3833 | 14.8048
Y | 7 | Lexington MPO | IP20160135 | 7-8902 |  | A | IMPROVE LIBERTY ROAD FROM GRAFTONS MILL LANE TO NEW CIRCLE ROAD AND IMPROVE INTERSECTION WITH NEW CIRCLE ROAD. (16CCN)(18CCR) | MAJOR WIDENING(O) | Fayette | 034-KY-1927 -000 | 0 | 1.175 | 1.175 | Modernize Roadway-Urban | 16 |  |  |  | 0 |  | 8600000 | 2021 | 8660000 | 2022 | 22500000 | 2024 | 2018-07-10 08:18 | Improve safety, modernize roadway and address congestion on Liberty Rd. from Graftons Mill Ln. (Approximately MP 1.145) to New Circle Rd. (MP 0.0) and improve intersection with New Circle Rd. | The following needs have been identified on this project: 1) Improve Safety, 2) Modernize Roadway, 3) Address Congestion. | Lexington MPO | North | 73.2238 | 7.6123 | 11.9077 | 12.0115 | 1.5231 | 0 | 3.5231 | 6.6462 | 43 | 15 | 15
Y | 7 | Bluegrass ADD | IP20160200 | 7-8952 |  | A | RECONSTRUCT US 60 FOR SAFETY IMPROVEMENTS FROM I-64 IN CLARK COUNTY (MP 14.210)) TO 500 FEET WEST OF SEWELL SHOP ROAD (MP 17.032).(16CCN)(18CCN) | AIR QUALITY(P) | Clark | 025-US-0060 -000 | 14.21 | 17.032 | 2.822 | Modernize Roadway-Rural | 26 |  |  |  | 2080000 | 2022 | 4060000 | 2024 | 3940000 | 2024 | 14000000 | 2024 | 2018-07-10 08:18 | Improve safety and mobility on US from I-64 in Clark Co. (MP 14.210), to 500 ft. west of Sewell Shop Rd (MP 17.032). | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility. | BLUEGRASS ADD | North | 39.63 | 4.5108 | 10.0154 | 7.0731 | 3.7231 | 6.5846 | 0 | 7.7231 | 40
Y | 7 | Bluegrass ADD | IP20160225 | 7-8905 |  | A | ACCESS MANAGEMENT IMPROVEMENTS ON US 60 FROM LEXINGTON ROAD AT WOODFORD FEED TO MARSAILLES DRIVE (MP 9.38 TO MP 9.70).(16CCN)(18CCN) | CONGESTION MITIGTN(O) | Woodford | 120-US-0060 -000 | 9.38 | 9.7 | 0.32 | Access Consolidation | 25 | Y |  |  | 0 | 2020 | 950000 | 2021 | 750000 | 2022 | 2000000 | 2023 | 2018-07-10 08:18 | Improve accessibility and safety and reduce congestion on US 60 from Lexington Rd. at Woodford Feed to Marsailles Dr. | The following needs have been identified for this project: 1) Improve Accessibility, 2) Improve Safety, 3) Reduce Congestion. | 7 | North | 72.0131 | 6.5169 | 13.4769 | 9.2654 | 3.4923 | 0 | 4.5231 | 4.7385 | 42 | 15 | 15
Y | 7 | Bluegrass ADD | IP20160243 |  |  |  | Modernize Roadway to improve horizontal & vertical curves, widen shoulders, improve safety. | Reconstruction | Bourbon | 009-KY-0537 -000 | 0 | 3.58 | 3.58 | Modernize Roadway-Rural | 26 |  | 0 |  | 450000 |  | 2250000 |  | 3500000 |  | 7500000 |  | 2017-05-18 15:11 | Improve roadway geometrics, mobility, and safety on Cane Ridge Rd. between North Middletown Rd. and 0.8 miles East of Steele Rd. | The following needs have been identified for this project: 1) Improve Roadway Geometrics, 2) Improve Mobility, 3) Improve Safety. | 7 | North | 20.7077 | 0.64615 | 5.5385 | 4.7538 | 4.2 | 5.5692 | 0 | 0 | 21
Y | 7 | Bluegrass ADD | IP20160271 | 7-192.20 | 767011 | A | CONSTRUCT 4-LANE BEREA BYPASS SECTION 2; FROM 150' EAST OF US-25, SE TO KY-21. PHASE 1 - BEREA BYPASS FROM US-25 TO KY-1016.(2004BOPC)(08CCR)(12CCR)(18CCN) | NEW ROUTE(O) | Madison | 076-US-0025X -000 | 0 | 3.654 | 3.654 | Construct Road in New Location | 0 | [9 empty] | 23720000 | 2019 | 2019-03-07 14:19 | Improve safety and mobility on Berea Bypass from approximately 150' East of US-25, SE to KY-21. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility. | 7 | North | 66.8269 | 5.2308 | 3.2308 | 14.2731 | 2.3231 | 8.4923 | 3.2769 | 0 | 37 | 15 | 15
Y | 7 | Bluegrass ADD | IP20160272 |  |  |  | Construct roundabout on US 150 (Stanford Ave) at E Walnut St. | Reconstruction | Boyle | 011-US-0150 -000 | 13.85 | 13.95 | 0.1 | Improve Intersection | 26 |  | 0 |  | 450000 |  | 250000 |  | 400000 |  | 3500000 |  | 2017-05-18 17:47 | Improve mobility and reduce congestion on Stanford Ave at E Walnut St. | The following needs have been identified for this project: 1) Improve Roadway Mobility, 2) Reduce Congestion. | BLUEGRASS ADD | North | 25.8046 | 4.9354 | 6.3692 | 4.9615 | 3.1077 | 0 | 2.7692 | 3.6615 | 26
Y | 7 | Lexington MPO | IP20160273 |  |  |  | A significant portion of traffic utilizing the MOW/I-75 SB exit ramp are from the several neighborhoods to the south. It is anticipated that a full or partial I-75 interchange with Todds Road will relieve the congestion. (PG 15 of the study) | New Interchange | Fayette | 034-I -0075 -000 | 105.8 | 106.6 | 0.8 | Full Control to Interstate | 10 | Y | 0 |  | 0 |  | 2741750 |  | 0 |  | 3109000 |  | 2016-11-03 18:05
Y | 7 | Bluegrass ADD | IP20170031 | 7-8100.10 |  | A | WIDENING WITH ACCESS IMPROVEMENTS TO ANDERSON CROSSING ON US62, FROM 0.2MI W OF CORPORATE DR TO US127B (LAWRENCEBURG BYPASS). PRIORITY SECTION (2016BOP) | SAFETY(P) | Anderson | 003-US-0062 -000 | 17.842 | 18.276 | 0.434 | Modernize Roadway-Rural | 26 |  |  |  | 175000 | 2025 | 1500000 | 2025 | 1500000 | 2025 | 2250000 | 2025 | 2018-07-10 08:18 | This project has the following purpose: 1) Reduce Roadway Congestion, 2) Improve Access and Mobility. | Reduce congestion and improve mobility to Anderson Crossing on US 62 from 0.2 miles West of Corporate Dr. to US 127 B. | BLUEGRASS ADD | North | 22.8215 | 2.1292 | 8.6308 | 5.2154 | 1.5231 | 0 | 0 | 5.3231 | 23
Y | 7 | Bluegrass ADD | IP20170036 |  |  |  | Reconstruct US25 from Cherry Blossom Way (KY 620) to Double Culvert Rd (KY 620). | Reconstruction | Scott | 105-US-0025 -000 | 8.827 | 14.975 | 6.148 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 4000000 |  | 3750000 |  | 24000000 |  | 2017-05-19 17:02 | Improve safety and mobility on US 25 from Cherry Blossom Way (KY 620) to Double Culvert Rd (KY 620). | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility. | BLUEGRASS ADD | North | 67.2892 | 1.92 | 7.1077 | 9.8308 | 2.4923 | 6.0615 | 0 | 9.8769 | 37 | 15 | 15
Y | 7 | Lexington MPO | IP20170077 |  |  |  | Liberty Road - Reconstruct from Appletree Lane to New Circle Road, Reconstruct 2 lanes, add curb, gutter, sidewalk, bike lane, transit improvements | Reconstruction | Fayette | 034-CS-2418 -000 | 0.56 | 1.297 | 0.737 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 2080000 |  | 1500000 |  | 2510000 |  | 2017-05-19 11:00 | Modernize roadway and improve safety on Liberty Road from Appletree Lane to New Circle Road. | The following needs have been identified on this project: 1) Modernize Roadway, 2) Improve Safety. | Lexington MPO | North | 36.9208 | 7.6246 | 10.8 | 10.0962 | 0 | 8.4 | 0 | 0 | 37
Y | 7 | Bluegrass ADD | IP20170094 |  |  |  | East Danville Connector | New Route | Boyle | 011-US-0150 -000 | 13.84 | 15.101 | 1.261 | Construct Road in New Location | 0 |  | 0 |  | 1500000 |  | 5600000 |  | 2500000 |  | 16000000 |  | 2017-09-01 13:53 | East Danville Connector | East Danville Connector
Y | 7 | Lexington MPO | IP20190154 |  |  |  | Modernize roadway & improve capacity on US60 from end of four-lane section near Polo Club Blvd to KY 859 (Haley Rd). | Major Widening | Fayette | 034-US-0060 -000 | 12.5 | 16.4 | 3.9 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 1500000 |  | 1000000 |  | 1000000 |  | 12000000 |  | 2019-03-14 17:36 | Modernize roadway & improve capacity on US60 from end of four-lane section near Polo Club Blvd to KY 859 (Haley Rd). | Address congestion & Improve Safety
Y | 7 | Bluegrass ADD | IP20190155 |  |  |  | Improved access to Central Kentucky Regional Airport from proposed KY 52. | New Route | Madison | 076-KY-0052 -000 | 5.3 | 7 | 1.7 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1500000 |  | 200000 |  | 200000 |  | 20000000 |  | 2019-03-12 11:28 | The purpose of this project is to: - Improve Safety - Improve Access | The Central Kentucky Regional Airport is located to the West of I-75 in Madison County. This airport has regional significance due to it's proximity to Interstate 75, the Bluegrass Army Depot, and it's partnership with EKU's Aviation Program. The current
Y | 7 | Lexington MPO | IP20190156 |  |  |  | Extend route from US 25/Jacks Creek Pike (KY 1975) intersection through W.T. Young estate area to KY 1980 (Ashgrove Rd) at Tates Creek intersection in Jessamine County. | New Route | Fayette | 034-US-0025 -000 | 4.6 | 5 | 0.4 | [14 empty] | Increase regional connectivity and access | Improved connectivity and access
Y | 7 | Bluegrass ADD | IP20190157 |  |  |  | Extend Farristown Industrial Drive at Menelaus Rd (KY 1983) to the east to connect to US 25. | New Route | Madison | 076-PV-1208 -000 | 0 | 0.53 | 0.53 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 800000 |  | 100000 |  | 100000 |  | 9000000 |  | 2019-03-12 11:26 | The purpose of this project is to: - Improve Safety - Improve Access | Farristown Industrial Drive is located in Berea and connects to Mayde Rd., which services the nearby industrial development. The extension of Farristown Industrial Drive to US 25 would provide a more direct route for current industries as well as provide
Y | 7 | Lexington MPO | IP20190160 |  |  |  | Address congestion and improve safety on US 60 (Winchester Rd) and Man O' War Blvd (KY 1425 & CS 4524) creating an alternative route between Sir Barton Way (CS 2636) and Polo Club Blvd (CS 2548) | New Route | Fayette | 034-US-0060 -000 | 11.45 | 12.45 | 1 | Construct Road in New Location | 0 |  | 4880000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-07 08:52 | Address congestion and improve safety on US 60 (Winchester Rd) and Man O' War Blvd (KY 1425 & CS 4524) creating an alternative route between Sir Barton Way (CS 2636) and Polo Club Blvd (CS 2548) | Address congestion and improve safety on US 60 (Winchester Rd) and Man O' War Blvd (KY 1425 & CS 4524) creating an alternative route between Sir Barton Way (CS 2636) and Polo Club Blvd (CS 2548)
Y | 7 | Lexington MPO | IP20190163 |  |  |  | Improve congestion, safety and mobility on Man O War from Liberty Road (KY 1927) to I-75 | Major Widening | Fayette | 034-CS-4524 -000 | 14.255 | 15.241 | 0.986 | Major Widening-Urban Streets | 25 |  | 0 |  | 1000000 |  | 3300000 |  | 1100000 |  | 8600000 |  | 2019-03-01 10:03 | Address Congestion, Improve Safety, and Improve Mobility options on Man O War Blvd between Liberty Road and I-75 | Address Congestion, Improve Safety, and Improve Mobility options on Man O War Blvd between Liberty Road and I-75
Y | 7 | Lexington MPO | IP20190164 |  |  |  | Address Congestion, Improve Safety, and Improve mobility on Man O War from Richmond Road to Liberty Road | Major Widening | Fayette | 034-CS-4524 -000 | 12.786 | 14.255 | 1.469 | Major Widening-Urban Streets | 25 |  | 0 |  | 1380000 |  | 4554000 |  | 1518000 |  | 11868000 |  | 2019-03-01 10:01 | Address Congestion, Improve Safety, and Improve Mobility options on Man O War Blvd between Richmond Road and Liberty Road | Address Congestion, Improve Safety, and Improve Mobility options on Man O War Blvd between Richmond Road and Liberty Road
Y | 8 | Bluegrass ADD | IP19980001 |  |  |  | Improve connectivity between US 27 between Logans Creek Culvert and US 150 west of Stanford. | New Route | Lincoln | 069-US-0027 -000 | 15.5 | 18 | 2.5 | Other Improvement Types | 0 | Y | 0 |  | 2300000 |  | 4500000 |  | 3300000 |  | 23000000 |  | 2013-05-14 14:34 | Improving connectivity on US 27 between Logans Creek Culvert and US 150 west of Stanford. | This project is a proposed Western Bypass of Stanford and provides access to US 150 west of Stanford from US 27 south of Stanford. Project would improve connectivity between two major routes and decrease travel time. Current ADT on US 27 from the Logan
Y | 8 | Lake Cumberland ADD | IP20000062 |  |  |  | HEARTLAND PARKWAY - UPGRADE KY 55 CORRIDOR FROM COLUMBIA BYPASS TO TAYLOR C\L. SEE OPTION 2, SEGMENT 3, SECTION C IN FEBRUARY 2005 HEARTLAND PARKWAY STUDY. | Major Widening | Adair | 001-KY-0055 -000 | 15.101 | 21.305 | 6.204 | Arterial to Partial Control | 23 | Y | 0 |  | 1824000 |  | 2589000 |  | 11171000 |  | 26052000 |  | 2015-03-04 12:29 |  | Upgrade KY 55 from the Columbia Bypass to Taylor Co. line The US 68/KY 55/555 corridor links the cities of Columbia, Campbellsville, Lebanon and Springfield to both the Louie B. Nunn/Cumberland Parkway and the Martha Layne Collins/Bluegrass Parkway. The s
Y | 8 | Lake Cumberland ADD | IP20000063 |  |  |  | Reconstruction from Columbia Bypass (KY 55) to Green County Line. See Alternate 4 Priority Section in December 2002 scoping study. | Reconstruction | Adair | 001-KY-0061 -000 | 12.213 | 19.745 | 7.532 | Modernize Roadway-Rural | 26 |  | 150000 |  | 3800000 |  | 9100000 |  | 4000000 |  | 45000000 |  | 2015-03-04 15:24 |  | This Project is needed to link Green County and North eastern Adair County to the LBN Cumberland Parkway & HWY 55. Currently KY 61 is a narrow 2 lane Road with little to no sholders.
Y | 8 | Lake Cumberland ADD | IP20000064 |  |  |  | Reduce congestion and improve mobility on KY 92 between the railroad overpass to US 27. | Major Widening | McCreary | 074-KY-0092 -000 | 15.588 | 16.612 | 1.024 | Modernize Roadway-Rural | 26 |  | 40000 |  | 900000 |  | 1500000 |  | 1200000 |  | 8400000 |  | 2017-05-16 15:45 | This project is needed because the capacity of KY 92 between the railroad overpass to US 27 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 30.5604 | 4.6066 | 6.9668 | 4.7453 | 0.92417 | 7.9621 | 0 | 5.3555 | 31
Y | 8 | Lake Cumberland ADD | IP20000065 |  |  |  | SOMERSET SOUTHEAST BYPASS - MAJOR WIDENING TO 4 LANES FROM KY 769 TO KY 80 | Major Widening | Pulaski | 100-KY-0914 -000 | 10.1 | 13.301 | 3.201 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 500000 |  | 300000 |  | 300000 |  | 8500000 |  | 2012-05-04 09:07 |  | This section of KY 914 has problems with congestion and traffic flow. It is used largely by Truck traffic and tourism.
Y | 8 | Cumberland Valley ADD | IP20000067 |  |  |  | Improve safety and reduce congestion along I-75 by constructing 2 additional lanes (4 to 6 lanes) from US-25 at Mt. Vernon to US-25 at Renfro Valley. See Segment 9 in August 1998 Advance Planning Study. | Major Widening | Rockcastle | 102-I -0075 -000 | 58.95 | 62.008 | 3.058 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 0 |  | 0 |  | 1800000 |  | 34000000 |  | 2015-03-16 11:04 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on I-75. | This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. The project will serve to upgrade the existing system and will provide congestion relief and improve roadway surface.
Y | 8 | Cumberland Valley ADD | IP20000068 |  |  |  | Major widening for 2 additional lanes (4 to 6 lanes) from US-25 at Renfro Valley to 2.0 miles south of Rockcastle County/Madison County Line | Major Widening | Rockcastle | 102-I -0075 -000 | 62.063 | 69.32 | 7.257 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 46000000 |  | 2013-05-14 16:12 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on I-75. | This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. The project will serve to upgrade the existing system and provide congestion relief and upgrade surface conditions.
Y | 8 | Lake Cumberland ADD | IP20000069 |  |  |  | Improve safety and congestiong along KY 80 from Western City Limit of Russell Springs to US 127. | Reconstruction | Russell | 104-KY-0080 -000 | 1.861 | 3.958 | 2.097 | Modernize Roadway-Rural | 26 |  | 150000 |  | 1100000 |  | 5900000 |  | 1700000 |  | 10500000 |  | 2015-02-24 16:24 |  | Ky 80 is east/west corridor through Russell Springs, it has two 10' driving lanes and 4' shoulders. The ADT ranges between 7,230 and 10,217. A school is located on this road and several businesses sit in close proximity to the roadway. This segment of K
Y | 8 | Bluegrass ADD | IP20000088 |  |  |  | Improve connectivity, decrease travel time, improve emergency service response time, improve access to Cedar Creek Lake, and improve economic development potential by establishing a more direct connection between US 150 and I-75. | New Route | Lincoln | 069-US-0150 -000 | 14 | 18.7 | 4.7 | Construct Road in New Location | 0 |  | 20000 |  | 4200000 |  | 3500000 |  | 2000000 |  | 51000000 |  | 2017-05-18 11:43 | To improve connectivity, emergency service response time, access to Cedar Creek Lake, and economic development potential while decreasing travel time by establishing a more direct connection between US 150 and I-75. | Currently there is no direct or convenient access to I-75 for regional and local traffic travelling south on US 150 until reaching the town of Mt. Vernon. Direct access is needed to make I-75 more accessible for communities within Lincoln and Rockcastle | 8 | South | 24.1813 | 4.9573 | 0 | 9.5794 | 0 | 6.0664 | 3.5782 | 0 | 24
Y | 8 | Bluegrass ADD | IP20020003 |  |  |  | Address congestion, level of service and connectivity on US 27 from Halls Gap Hill south of Stanford to US 150 east of Stanford. | New Route | Lincoln | 069-US-0027 -000 | 11.8 | 18 | 6.2 | Construct Road in New Location | 0 | Y | 20000 |  | 3000000 |  | 3800000 |  | 2000000 |  | 27000000 |  | 2017-05-18 11:40 | On US 27, from Halls Gap Hill south of Stanford to US 150 east of Stanford, multiple concerns need to be addressed, such as: congestion, level of service and connectivity. | This project is an Eastern Bypass of Stanford, and is a possible alternate to Companion Project to 08 069 C0000 2.20 This route begins at Hall's Gap Hill and extends North and Eastward to US 150. Current ADT on US 27 from just north of Kings Mountain to | 8 | South | 33.6256 | 6.872 | 0 | 13.5071 | 0.78199 | 8.436 | 4.0284 | 0 | 34
Y | 8 | Bluegrass ADD | IP20020004 |  |  |  | Address congestion, level of service and connectivity on from US 150 east of Stanford to the Dix River Country Club on US 27. | New Route | Lincoln | 069-US-0027 -000 | 18 | 20.5 | 2.5 | Construct Road in New Location | 0 | Y | 20000 |  | 2000000 |  | 1900000 |  | 1000000 |  | 23100000 |  | 2017-05-18 11:42 | To address congestion, level of service and connectivity on from US 150 east of Stanford to the Dix River Country Club on US 27. | Companion Project to 08 069 C0000 2.10. This project extends from US 150 east of Stanford, north to US 27 north of Stanford. The current ADT on US 27 from just north of Kings Mountain to the Dix River Country Club is significant, including significant tru | 8 | South | 31.7891 | 7.0616 | 0 | 11.1967 | 0.78199 | 8.7678 | 3.981 | 0 | 32
Y | 8 | Lake Cumberland ADD | IP20040024 |  |  |  | Improve safety and reduce congestion along KY 3491 between KY 80 and Russell Creek Bridge. | Minor Widening | Adair | 001-KY-3491 -000 | 0 | 1.286 | 1.286 | Modernize Roadway-Rural | 26 |  | 130000 |  | 775000 |  | 1100000 |  | 800000 |  | 9000000 |  | 2017-05-16 12:35 | This project is needed because the capacity of KY 3491 between KY 80 and Russell Creek Bridge is inadequate to meet current and future traffic volumes, resulting in congestion and reduced mobility on this stretch of highway. There are also safety issues | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 18.1251 | 2.6161 | 5.2607 | 3.3235 | 3.8389 | 0 | 0 | 3.086 | 18
Y | 8 | Lake Cumberland ADD | IP20040025 |  |  |  | Improve safety and mobility along KY 449 between KY 90 and KY 1206. | Reconstruction | Cumberland | 029-KY-0449 -000 | 4.407 | 8.994 | 4.587 | Modernize Roadway-Rural | 26 |  | 150000 |  | 2300000 |  | 4500000 |  | 2000000 |  | 23000000 |  | 2017-05-16 14:07 | This project is needed because the geometrics along KY 449 between KY 90 and KY 1206 are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 22.2137 | 0.70142 | 4.2654 | 4.1765 | 4.4076 | 4.3128 | 0 | 4.35 | 22
Y | 8 | Lake Cumberland ADD | IP20040026 |  |  |  | Reduce congestion and improve safety, capacity, and mobility along KY 90 between the Wayne County line and the new Cumberland River Bridge. | Reconstruction | Pulaski | 100-KY-0090 -000 | 0 | 2.75 | 2.75 | Modernize Roadway-Rural | 26 |  | 150000 |  | 1300000 |  | 6000000 |  | 2100000 |  | 19000000 |  | 2017-05-16 16:43 | This project is needed because the capacity along KY 90 between the Wayne County line and the new Cumberland River Bridge is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 66.205 | 8.5213 | 11.09 | 10.2192 | 0 | 8.7204 | 3.6019 | 9.0521 | 51 |  | 15
Y | 8 | Lake Cumberland ADD | IP20040028 |  |  |  | Reduce congestion and improve safety, capacity, and mobility along KY 1247 From KY 1575 to Camelot Way in Somerset. | Safety-Haz-Elm | Pulaski | 100-KY-1247 -000 | 8.414 | 9.605 | 1.191 | Modernize Roadway-Rural | 26 |  | 150000 |  | 600000 |  | 2500000 |  | 1200000 |  | 4800000 |  | 2017-05-16 16:55 | This project is needed because the capacity along KY 1247 From KY 1575 to Camelot Way in Somerset is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 30.2642 | 8.6825 | 10.0237 | 9.3306 | 2.2275 | 0 | 0 | 0 | 30
Y | 8 | Lake Cumberland ADD | IP20040029 |  |  |  | Reduce congestion and improve safety, capacity and mobility along KY 1577 between KY 1642 and KY 3261 near Oak Hill Baptist Church in Somerset. | Reconstruction | Pulaski | 100-KY-1577 -000 | 0 | 2.213 | 2.213 | Modernize Roadway-Rural | 26 |  | 75000 |  | 1100000 |  | 3500000 |  | 2200000 |  | 8850000 |  | 2017-05-16 16:56 | This project is needed because the capacity along KY 1577 between KY 1642 and KY 3261 near Oak Hill Baptist Church in Somerset is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this st | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 37.9964 | 2.2085 | 9.455 | 8.7263 | 2.9621 | 5.9716 | 0 | 8.673 | 38
Y | 8 | Lake Cumberland ADD | IP20040030 |  |  |  | CORRIDOR IMPROVEMENTS FROM MONTICELLO TO US 127 | Major Widening | Wayne | 116-KY-0090 -000 | 0 | 9.601 | 9.601 | Modernize Roadway-Rural | 26 |  | 400000 |  | 8500000 |  | 10000000 |  | 11200000 |  | 85000000 |  | 2013-05-14 10:15 |  | KY 90 in southern Kentucky connects US 27 to the Louie B Nunn Parkway and I-65. This corridor serves as a major trucking route for the southern portion of the LCADD including Clinton, Cumberland, Wayne, and Pulaski Counties. This road has an ADT range o
Y | 8 | Lake Cumberland ADD | IP20040031 |  |  |  | MAJOR WIDENING\RECONSTRUCTION FROM KY 90 AT MONTICELLO TO LAKE CUMBERLAND | Reconstruction | Wayne | 116-KY-0092 -000 | 0 | 7.536 | 7.536 | Modernize Roadway-Rural | 26 |  | 375000 |  | 3800000 |  | 3500000 |  | 3000000 |  | 37000000 |  | 2013-05-14 10:27 |  | KY 92 is the only route leading to Beaver Creek Resort and Marina, and is in a rapidly growing area of Wayne County. It is a rural 2 lane road with 9' driving lanes and 3' shoulders. Adequacy rating data is not available for the first 6.1 miles of road.
Y | 8 | Lake Cumberland ADD | IP20060247 |  |  |  | Improve Safety along KY 55 from US 127 to Cumberland Parkway. | Reconstruction | Adair | 001-KY-0055 -000 | 0 | 10.059 | 10.059 | Modernize Roadway-Rural | 26 |  | 220000 |  | 6700000 |  | 8000000 |  | 6900000 |  | 60100000 |  | 2017-05-16 07:55 |  | KY 55 between US 127 in Russell County and the LBN Cumberland Parkway in Adair County is a narrow rural roadway characterized by 9 ft driving lanes and shoulder widths varying from 0' - 4'. The Gaddie Shamrock Rock Quarry is located on the Adair County po | LAKE CUMBERLAND ADD | South | 71.1161 | 1.5071 | 7.7488 | 13.8981 | 3.2701 | 4.6919 | 0 | 10 | 41 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20060248 |  |  |  | Improve safety and reduce congestion on US 27 between KY 1567 and KY 478. | Major Widening | McCreary | 074-US-0027 -000 | 6.991 | 9.093 | 2.102 | Install Two-way Left Turn Lane | 28 | Y | 100000 |  | 1050000 |  | 4000000 |  | 2320000 |  | 16800000 |  | 2017-05-16 14:57 | This project is needed because the capacity of US 27 between KY 1567 and KY 478 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 65.9313 | 7.2227 | 9.5261 | 10.628 | 0.47393 | 9.6209 | 4.6919 | 8.7678 | 51 |  | 15
Y | 8 | Lake Cumberland ADD | IP20060249 |  |  |  | Reduce congestion and improve capacity, safety and mobility KY 2292 between US 27 and KY 1577 Extension in Somerset. | Major Widening | Pulaski | 100-KY-2292 -000 | 0 | 1.87 | 1.87 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1870000 |  | 11220000 |  | 4675000 |  | 18700000 |  | 2017-05-16 16:59 | This project is needed because the capacity of KY 2292 between US 27 and KY 1577 Extension in Somerset is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 48.5261 | 7.0806 | 7.6777 | 12.0853 | 4.3128 | 7.346 | 2.9147 | 7.109 | 48
Y | 8 | Lake Cumberland ADD | IP20060250 |  |  |  | Reduce congestion and improve capacity, safety and mobility on US 127 between the west bypass of Jamestown to the Cumberland Parkway. See segment 12 in June 1998 Advance Planning Study | Reconstruction | Russell | 104-US-0127 -000 | 14.142 | 18.195 | 4.053 | Modernize Roadway-Rural | 26 | Y | 100000 |  | 2000000 |  | 10000000 |  | 5300000 |  | 28500000 |  | 2015-02-24 15:42 | This project is needed because the capacity of US 127 between the west bypass of Jamestown to the Cumberland Parkway is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of h | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 66.955 | 5.1185 | 11.1611 | 13.1161 | 1.9905 | 9.0047 | 4.2654 | 7.2986 | 52 |  | 15
Y | 8 | Lake Cumberland ADD | IP20060251 |  |  |  | Reduce congestion and improve safety, capacity and mobility along US 127 from the Cumberland Parkway to Lakeway drive KY 379 in Russell Springs. | Reconstruction | Russell | 104-US-0127 -000 | 17.872 | 19.086 | 1.214 | Modernize Roadway-Rural | 26 | Y | 150000 |  | 750000 |  | 1700000 |  | 2000000 |  | 8000000 |  | 2017-05-18 10:15 | This project is needed because the capacity of US 127 from the Cumberland Parkway to Lakeway drive KY 379 in Russell Springs is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stre | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 64.9882 | 6.1611 | 12.5118 | 12.3341 | 0.47393 | 8.91 | 4.5735 | 5.0237 | 50 |  | 15
Y | 8 | Lake Cumberland ADD | IP20060252 |  |  |  | Reduce congestion and improve capacity, safety and mobility on US 127 between the intersection of Bernard Lane/Cortez Lane and the Northridge Shopping Center traffic light in Russell Springs. | Minor Widening | Russell | 104-US-0127 -000 | 18.318 | 18.8 | 0.482 | Improve Intersection | 26 | Y | 50000 |  | 250000 |  | 300000 |  | 300000 |  | 1500000 |  | 2017-05-18 10:17 | This project is needed because the capacity of US 127 between the intersection of Bernard Lane/Cortez Lane and the Northridge Shopping Center traffic light in Russell Springs is inadequate to meet current and future traffic volumes, resulting in congesti | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 68.096 | 5.7915 | 14.2891 | 7.8732 | 0.47393 | 0 | 4.5972 | 5.0711 | 38 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20060253 |  |  |  | RECONSTRUCT KY 696\KY 1076 CORRIDOR FROM KY 90 AT WAIT TO US 127 AT STATIC | Reconstruction | Wayne | 116-KY-0696 -000 | 0 | 0.84 | 0.84 | Modernize Roadway-Rural | 26 |  | 200000 |  | 5500000 |  | 6500000 |  | 8000000 |  | 50000000 |  | 2013-05-14 10:53 |  | Wayne County has no existing good southern route for accessing I 40 in Tennessee. Traffic heading south must either travel west to Albany and take US 127 to Static, travel east to Whitley City and take US 27, or travel on existing narrow roadways to conne
Y | 8 | Lake Cumberland ADD | IP20070220 |  |  |  | Address safety and geometric deficiencie along KY 439 from Stults Street and Marshall Street in Columbia. | Safety-Haz-Elm | Adair | 001-KY-0439 -000 | 1.3 | 1.565 | 0.265 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 750000 |  | 500000 |  | 1200000 |  | 2013-05-14 11:38 |  | This particular curve on KY 439 in Columbia is a near 90 degree curve, with inadequate superelevation. This section of road has several street and driveway entrances within the curve itself. A review of accident data from the CRASH database did not show a
Y | 8 | Lake Cumberland ADD | IP20070221 |  |  |  | Improve safety by improving the geometrics along KY 70 from Green River Bridge in Liberty to KY 198 at Yosemite. | Safety-Haz-Elm | Casey | 023-KY-0070 -000 | 16.758 | 23.608 | 6.85 | Modernize Roadway-Rural | 26 |  | 150000 |  | 3500000 |  | 8000000 |  | 6800000 |  | 34000000 |  | 2015-03-10 13:09 |  | KY 70 is Casey County's major East-West corridor connecting US 127 in Liberty to US 27 in Pulaski County. This route also collects traffic from several intersecting state and local roadways. This segment of roadway has 2 - 9' driving lanes and 2' shoulde
Y | 8 | Lake Cumberland ADD | IP20070222 |  |  |  | Improve safety, mobility, and geometrics on KY 70 between KY 198 at Yosemite to KY 1247 at Science Hill. | Reconstruction | Casey | 023-KY-0070 -000 | 23.608 | 32.65 | 9.042 | Modernize Roadway-Rural | 26 |  | 250000 |  | 9500000 |  | 16000000 |  | 13000000 |  | 75000000 |  | 2017-05-16 13:17 | This project is needed because the geometrics along KY 70 between KY 198 at Yosemite to KY 1247 at Science Hill are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 31.5581 | 1.0427 | 3.7678 | 9.1884 | 3.436 | 4.5024 | 0 | 9.6209 | 32
Y | 8 | Bluegrass ADD | IP20070223 |  |  |  | Improve Safety and Reduce Congestion along US 27 to KY 78 East of Standford. See Segment 1 in July, 1998 Advance Planning Study. | Major Widening | Lincoln | 069-US-0150 -000 | 5.7 | 7.869 | 2.169 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 25000 |  | 500000 |  | 8500000 |  | 2015-02-23 10:37 | To improve safety and reduce congestion along US 27 to KY 78 East of Standford through major widening. For more information, see Segment 1 in July, 1998 Advance Planning Study. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 8 | Lake Cumberland ADD | IP20070224 |  |  |  | Improve Safety and Reduce Congestion along US 27, by adding a 5th lane where needed from KY 2792 to KY 1567. | Major Widening | McCreary | 074-US-0027 -000 | 4.608 | 6.991 | 2.383 | Install Two-way Left Turn Lane | 28 | Y | 100000 |  | 1100000 |  | 4600000 |  | 1900000 |  | 12000000 |  | 2015-02-24 08:05 |  | US 27 in McCreary County is a major north-south arterial route for the county, as well as for the region and state. The improvement of this segment would be a continuation of the improvements made to US 27 in this area and statewide. This segment of US 27
Y | 8 | Lake Cumberland ADD | IP20070225 |  |  |  | RECONSTRUCT FROM US 27 IN PARKERS LAKE TO WHITLEY C/L | Reconstruction | McCreary | 074-KY-0090 -000 | 0 | 11.92 | 11.92 | Modernize Roadway-Rural | 26 |  | 150000 |  | 6000000 |  | 6000000 |  | 5000000 |  | 60000000 |  | 2013-05-08 15:01 |  | KY 90 in McCreary County is classified as a Rural Minor Arterial Route, and provides direct access to Cumberland Falls State Park. This road directly links US 27 in McCreary County with I-75 in Whitley County. Ky 90 also serves as the boundary between th
Y | 8 | Lake Cumberland ADD | IP20070226 |  |  |  | RECONSTRUCT FROM BLUE HERON TO KY 741 | Reconstruction | McCreary | 074-KY-0742 -000 | 0 | 4.66 | 4.66 | Modernize Roadway-Rural | 26 |  | 130000 |  | 2600000 |  | 2500000 |  | 2000000 |  | 20000000 |  | 2013-05-10 16:15 |  | KY 742 is a rural 2 lane roadway with 9' - 11' driving lanes and 4' - 6' shoulds. The area is mostly residential and agricultural, with several private access points. This route is a primary route into the Big South Fork National River and Recreational Ar
Y | 8 | Lake Cumberland ADD | IP20070227 |  |  |  | Improve safety and mobility along KY 1363 between KY 92 and KY 3258. | Safety-Haz-Elm | McCreary | 074-KY-1363 -000 | 9.385 | 11.013 | 1.628 | Modernize Roadway-Rural | 26 |  | 150000 |  | 850000 |  | 1600000 |  | 1000000 |  | 8200000 |  | 2017-05-16 15:51 | This project is needed because the geometrics along KY 1363 between KY 92 and KY 3258 are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 8.34 | 0.17062 | 2.4882 | 1.1552 | 4.5261 | 0 | 0 | 0 | 8
Y | 8 | Lake Cumberland ADD | IP20070228 |  |  |  | Reduce congestion and improve safety and mobility along KY 1470 between the entrance to the National Park and US 27. | Reconstruction | McCreary | 074-KY-1470 -000 | 0 | 2.342 | 2.342 | Modernize Roadway-Rural | 26 |  | 150000 |  | 2500000 |  | 2800000 |  | 2500000 |  | 18800000 |  | 2017-05-18 11:50 | This project is needed because the capacity of KY 1470 between the entrance to the National Park and US 27 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 18.4704 | 0.88152 | 5.0474 | 4.6742 | 3.4597 | 4.4076 | 0 | 0 | 18
Y | 8 | Lake Cumberland ADD | IP20070229 |  |  |  | Reduce congestion and improve safety, capacity, and mobility along US 27 between Lewis Bray Road and General Burnside Island. | Major Widening | Pulaski | 100-US-0027 -000 | 6.624 | 8.05 | 1.426 | Modernize Roadway-Rural | 26 | Y | 50000 |  | 1000000 |  | 3000000 |  | 2500000 |  | 11000000 |  | 2017-05-16 15:53 | This project is needed because the capacity along US 27 between Lewis Bray Road and General Burnside Island is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 75.096 | 7.981 | 10.9479 | 7.0201 | 1.2796 | 8.1517 | 3.7915 | 5.9242 | 45 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20070230 | 8-272 |  | A | WIDEN AND RECONSTRUCT US-27 FROM KY-90 SOUTH OF SOMERSET TO GENERAL BURNSIDE ISLAND. (02KYD) | RECONSTRUCTION(O) | Pulaski | 100-US-0027 -000 | 8.05 | 9.193 | 1.143 | Modernize Roadway-Rural | 26 | Y |  |  |  |  | 5780000 | 2025 | 2490000 | 2025 | 10770000 | 2025 | 2018-07-10 08:18 |  | US 27 is a heavily travelled north-south corridor linking multiple states and passing through Pulaski County. From the Cumberland River Bridge in Burnside extending north to KY, US 27 is either 4 or 6 lanes, or currently in the process of being expanded t | LAKE CUMBERLAND ADD | South | 82.0154 | 6.2275 | 12.2275 | 12.7073 | 2.1327 | 8.9573 | 4.1232 | 5.6398 | 52 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20070232 |  |  |  | IMPROVE ALIGNMENT AND GRADE FROM CUMBERLAND PKY. TO KY 910 IN CASEY CO. | Reconstruction | Pulaski | 100-KY-0080 -000 | 0 | 5.807 | 5.807 | Modernize Roadway-Rural | 26 |  | 150000 |  | 3750000 |  | 5000000 |  | 3500000 |  | 37000000 |  | 2013-05-13 09:00 |  | KY 80 is a rural route having two 10' driving lanes and 3' earthen shoulders. KY 80 is used regionally as access to the Louie B. Nunn Parkway. This segment of KY 80 in Pulaski County has an acccident CRF of 1.49, indicating a possibly statistically signi
Y | 8 | Lake Cumberland ADD | IP20070233 |  |  |  | Russell Springs Rd. - Improve Safety and Reduce Congestion along KY 80X from KY 1225 to Ohio St. in Somerset. | Reconstruction | Pulaski | 100-KY-0080X -000 | 1.339 | 3.145 | 1.806 | Modernize Roadway-Rural | 26 |  | 150000 |  | 2700000 |  | 3100000 |  | 3800000 |  | 11700000 |  | 2015-02-23 11:45
Y | 8 | Cumberland Valley ADD | IP20070235 |  |  |  | Address capacity issues from KY-461 to US-25 in Mt. Vernon to continue corridor improvements to US 150 as identified in the 1998 planning study. | Minor Widening | Rockcastle | 102-US-0150 -000 | 8.403 | 10.205 | 1.802 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1000000 |  | 2700000 |  | 2600000 |  | 12750000 |  | 2017-05-18 09:35 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on US 150. | This project is a part of an overall plan to improve US 150 from Stanford to Mt. Vernon. US 150 functions as a connector to both US 27 in Stanford, and to Interstate 75 in Mt. Vernon. This corridor functions as a significant commuter route for south-cen | CUMBERLAND VALLEY ADD | South | 40.3341 | 6.2938 | 11.2322 | 9.5616 | 3.1754 | 0 | 4.4787 | 5.5924 | 40
Y | 8 | Lake Cumberland ADD | IP20070236 |  |  |  | Improve safety along KY 92 by improve geometrics along the route from US 127 (Court Square) to Jamestown Marina. | Reconstruction | Russell | 104-KY-0092 -000 | 6.999 | 11.244 | 4.245 | Modernize Roadway-Rural | 26 |  | 150000 |  | 2300000 |  | 5100000 |  | 1800000 |  | 21000000 |  | 2015-03-03 14:11 |  | This segment of KY 92 leads to Lake Cumberland and Jamestown Marina, and is a rapidly growing area of Russell County. Its is a two lane rural collector route with 10' driving lanes, and 3' shoulders. This segment has a horizontal rating of 2, which indic
Y | 8 | Lake Cumberland ADD | IP20070238 |  |  |  | Provide connectivity and improved mobility from Northern Wayne County to Southern Russell County via KY 196 in Jabez. The project includes two new bridges over Lake Cumberland. The new system milage is approx. 7.5 miles. | New Route | Wayne | 116-KY-0092 -000 | 0 | 0.1 | 0.1 | Construct Road in New Location | 0 |  | 375000 |  | 4500000 |  | 7500000 |  | 3000000 |  | 120000000 |  | 2015-03-16 09:33 |  | Wayne County has no direct access to the north due to the location of Lake Cumberland. Northbound Traffic must travel east to Somerset, or west to Albany to bypass the lake, greatly increasing travel times. The new connection could benefit regional touri
Y | 8 | Lake Cumberland ADD | IP20070239 |  |  |  | Improve safety and mobility along KY 1275 between KY 90 at Monticello and KY 1765 near Conley Bottom Boat Dock Road. | Reconstruction | Wayne | 116-KY-1275 -000 | 3.995 | 10.634 | 6.639 | Modernize Roadway-Rural | 26 |  | 220000 |  | 4200000 |  | 4800000 |  | 3250000 |  | 36000000 |  | 2017-05-18 10:45 | This project is needed because the geometrics along KY 1275 between KY 90 at Monticello and KY 1765 near Conley Bottom Boat Dock Road are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 25.3199 | 1.7536 | 5.4739 | 7.9265 | 4.5735 | 5.5924 | 0 | 0 | 25
Y | 8 | Lake Cumberland ADD | IP20070240 |  |  |  | Improve safety and mobility along KY 1275 between KY 1765 and KY 90 near Touristville. | Reconstruction | Wayne | 116-KY-1275 -000 | 10.634 | 14.366 | 3.732 | Modernize Roadway-Rural | 26 |  | 240000 |  | 2400000 |  | 3600000 |  | 3600000 |  | 21000000 |  | 2017-05-18 10:49 | This project is needed because the geometrics along KY 1275 between KY 1765 and KY 90 near Touristville are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 14.686 | 0.75829 | 2.9858 | 2.7903 | 4.0284 | 4.1232 | 0 | 0 | 15
Y | 8 | Lake Cumberland ADD | IP20070241 |  |  |  | Improve safety and mobility along KY 1765 between KY 1275 and end of state maintenance near Conley Bottom boat dock. | Reconstruction | Wayne | 116-KY-1765 -000 | 0 | 0.978 | 0.978 | Modernize Roadway-Rural | 26 |  | 150000 |  | 550000 |  | 2600000 |  | 1200000 |  | 5000000 |  | 2017-05-18 10:52 | This project is needed because the geometrics along KY 1765 between KY 1275 and end of state maintenance near Conley Bottom boat dock are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 14.9491 | 0.36967 | 3.128 | 3.0391 | 4.5735 | 3.8389 | 0 | 0 | 15
Y | 8 | Lake Cumberland ADD | IP20080489 |  |  |  | Improve safety and geometrics on KY 70 between US 127 East and the Green River bridge. | Reconstruction | Casey | 023-KY-0070 -000 | 14.195 | 14.595 | 0.4 | Modernize Roadway-Rural | 26 |  | 100000 |  | 500000 |  | 450000 |  | 400000 |  | 5000000 |  | 2017-05-16 12:55 | This project is needed because the geometrics along KY 70 between US 127 East and the Green River bridge are inadequate and causes safety issues. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 26.7341 | 1.9336 | 6.4692 | 3.3945 | 2.6777 | 6.019 | 0 | 6.24 | 27
Y | 8 | Lake Cumberland ADD | IP20080490 |  |  |  | Realignment, lane widening and shouldering of KY-1649 from mp1.0 to near Popular Springs Road for development of future Air Port. | Reconstruction | Casey | 023-KY-1649 -000 | 1 | 3.281 | 2.281 | Modernize Roadway-Rural | 26 |  | 70000 |  | 1200000 |  | 2500000 |  | 2000000 |  | 10500000 |  | 2013-05-08 14:00 |  | KY 1649 ( Dry Ridge Hill Road) is a characterized by narrow driving lanes (9'), minimal shoulders (2' earth) and several sharp horizontal curves. The county has proposed adding an Industrial park and airport on this highway, likely resulting in increase
Y | 8 | Lake Cumberland ADD | IP20080491 |  |  |  | Improve Safety and Reduce Congestion along KY 90/KY 61 in the western portion of Burkesville between KY 90 and Rocky Branch Drive. | Bypass | Cumberland | 029-KY-0061 -000 | 12.869 | 14.557 | 1.688 | Construct Road in New Location | 0 |  | 100000 |  | 1500000 |  | 3250000 |  | 1200000 |  | 19000000 |  | 2017-05-16 13:55 | This project is needed because the capacity of KY 90/KY 61 in the western portion of Burkesville between KY 90 and Rocky Branch Drive is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility 4.) Improve access | LAKE CUMBERLAND ADD | South | 34.6884 | 6.2938 | 2.0616 | 10.1481 | 3.8863 | 8.5308 | 3.7678 | 0 | 35
Y | 8 | Bluegrass ADD | IP20080492 |  |  |  | Continue ongoing improvements to US 27 corridor from Somerset to Lexington. Improve Level of Service and safety on US 27 from KY 70 at Eubank in Pulaski to KY 328 in Lincoln County. | Major Widening | Lincoln | 069-US-0027 -000 | 0 | 3.127 | 3.127 | Modernize Roadway-Rural | 26 | Y | 20000 |  | 3200000 |  | 9200000 |  | 2600000 |  | 19000000 |  | 2017-05-16 14:28 | Continue ongoing improvements to US 27 corridor from Somerset to Lexington. Improve Level of Service and safety on US 27 from KY 70 at Eubank in Pulaski to KY 328 in Lincoln County. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 8 | South | 39.2867 | 5.5545 | 6.5403 | 8.4242 | 1.09 | 6.872 | 3.1754 | 7.6303 | 39
Y | 8 | Bluegrass ADD | IP20080493 |  |  |  | Continue ongoing improvements to US 27 Corridor from Somerset to Lexington. Improve Level of Service and safety on US 27 from KY 328 to KY 501 in Lincoln County. | Major Widening | Lincoln | 069-US-0027 -000 | 3.127 | 7.22 | 4.093 | Modernize Roadway-Rural | 26 | Y | 20000 |  | 4000000 |  | 11500000 |  | 3500000 |  | 24500000 |  | 2017-05-16 14:36 | Continue ongoing improvements to US 27 Corridor from Somerset to Lexington. Improve Level of Service and safety on US 27 from KY 328 to KY 501 in Lincoln County. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 8 | South | 42.737 | 6.1137 | 7.3223 | 9.1351 | 1.09 | 7.2986 | 3.3886 | 8.3886 | 43
Y | 8 | Bluegrass ADD | IP20080494 |  |  |  | Continue ongoing improvements to US 27 Corridor from Somerset to Lexington. Improve Level Of Service and Safety on US 27 from KY 501 to KY 1247 in Lincoln County. | Major Widening | Lincoln | 069-US-0027 -000 | 7.22 | 11.169 | 3.949 | Modernize Roadway-Rural | 26 | Y | 20000 |  | 4000000 |  | 9950000 |  | 3200000 |  | 24000000 |  | 2017-05-16 14:43 | Continue ongoing improvements to US 27 Corridor from Somerset to Lexington. Improve Level Of Service and Safety on US 27 from KY 501 to KY 1247 in Lincoln County. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 8 | South | 43.3578 | 6.3791 | 7.0379 | 9.1351 | 1.09 | 7.6303 | 3.8389 | 8.2464 | 43
Y | 8 | Lake Cumberland ADD | IP20080495 |  |  |  | ADDRESS LANE AND SHOULDER WIDTH, HORIZONTAL AND VERTICAL ALIGNMENT AND SAFETY ISSUES ON THE KY-92 CORRIDOR FROM KY-1651 AT STEARNS TO THE MOTICELLO CITY LIMITS. | Reconstruction | McCreary | 074-KY-0092 -000 | 0 | 15.361 | 15.361 | Modernize Roadway-Rural | 26 |  | 250000 |  | 13800000 |  | 21000000 |  | 11200000 |  | 138500000 |  | 2013-05-08 15:06 |  | KY 92 is McCreary and Wayne County's major East-West corridor, connecting the arterials US 27 in McCreary County to Ky. 90 in Monticello. This roadway consists of two driving lanes with 9'-10' pavement with 4' earth shoulders. A composite rating as low as | General Assembly | South | 35.8196 | 0.89623 | 4.5283 | 11.1262 | 4.6462 | 4.6226 | 0 | 10 | 36
Y | 8 | Lake Cumberland ADD | IP20080496 |  |  |  | Improve safety by addressing lane and shoulder widths as well as horizontal and vertical alignmnets on along KY 700. | Reconstruction | McCreary | 074-KY-0700 -000 | 5.487 | 16.539 | 11.052 | Modernize Roadway-Rural | 26 |  | 150000 |  | 5500000 |  | 5600000 |  | 11200000 |  | 44200000 |  | 2015-02-24 11:12 |  | KY 700 is a rural collector route with two 8' driving lanes and 3' shoulders. The 2003 adequacy rating of 72 corresponds to a percentile rating of 14, which indicates that 86% of all roadways in this classification statewide are in better condition than
Y | 8 | Lake Cumberland ADD | IP20080497 |  |  |  | LANE WIDENING AND SHOULDERING FROM KY-742 TO KY-1651 | Reconstruction | McCreary | 074-KY-0741 -000 | 0.1 | 0.812 | 0.712 | Modernize Roadway-Rural | 26 |  | 100000 |  | 400000 |  | 1275000 |  | 500000 |  | 3500000 |  | 2013-05-10 15:54 |  | KY 741 is a rural 2 lane roadway with 9 ft lanes and minimal shouldering. The area is mostly residential and agricultural, with several private access points. Ky 741 provides a link between Ky. 1651 and Ky 742, which provides direct access to the Big Sout
Y | 8 | Lake Cumberland ADD | IP20080498 |  |  |  | ADDRESS CONGESTION SAFETY AND SERVICE ISSUES IN PULASKI COUNTY BETWEEN MILEPOINT 7.914 AND 8.464. BETWEEN KY 39 AND KY 1575. | Reconstruction | Pulaski | 100-KY-1247 -000 | 7.864 | 8.414 | 0.55 | Modernize Roadway-Rural | 26 |  | 150000 |  | 300000 |  | 2650000 |  | 2500000 |  | 3500000 |  | 2010-12-09 15:52 |  | This segment of KY 1247 lies on the outskirts of downtown Somerset and has an ADT that ranges from 7,770 to 8,210 vehicles per day. This 2 lane road has many driveways, both residential and commercial, and several intersecting streets. A adequacy rating
Y | 8 | Lake Cumberland ADD | IP20080499 |  |  |  | Improve Safety and Congestion along KY 1642 from MP 0.00 - MP 3.478 (KY 1577 Oak Hill Rd.) | Reconstruction | Pulaski | 100-KY-1642 -000 | 0 | 3.478 | 3.478 | Modernize Roadway-Rural | 26 |  | 75000 |  | 1740000 |  | 5000000 |  | 2500000 |  | 14000000 |  | 2011-10-11 09:06 |  | KY 1642 (Slate Branch Rd) runs through one of the fastest growing residential areas of Somerset. The road has two 9' driving lanes with 2' earthen shoulders, numerous intersections, and several locations with sight distance problems due to horizontal and
Y | 8 | Lake Cumberland ADD | IP20080500 |  |  |  | Improve Safety and Reduce Congestion along KY 1642 from KY 914 to US 27. | Reconstruction | Pulaski | 100-KY-1642 -000 | 3.971 | 4.621 | 0.65 | Modernize Roadway-Rural | 26 |  | 0 |  | 450000 |  | 2500000 |  | 600000 |  | 3000000 |  | 2011-10-11 09:11
Y | 8 | Cumberland Valley ADD | IP20080501 |  |  |  | Reconstruct KY-1326 from KY-461 intersection to Quarry Street (CS-1075) in Mt. Vernon. | Major Widening | Rockcastle | 102-KY-1326 -000 | 4.179 | 4.996 | 0.817 | Modernize Roadway-Rural | 26 |  | 75000 |  | 540000 |  | 2520000 |  | 1200000 |  | 4800000 |  | 2017-05-18 09:41 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on ky 1326. | The purpose of this project is to expand KY 1326 from the KY 461 intersection to the existing curb and gutter section in Mt. Vernon. The project area contains a mix of residential and commercial sectors, and also provides direct access to the Rockcastle | CUMBERLAND VALLEY ADD | South | 24.0699 | 3.6493 | 5.1896 | 5.6339 | 2.4882 | 7.109 | 0 | 0 | 24
Y | 8 | Cumberland Valley ADD | IP20080502 |  |  |  | Address access and lane width issues on KY-2549 from Rockcastle County Industrial Park #2 to US-150 | Reconstruction | Rockcastle | 102-KY-2549 -000 | 2.201 | 2.63 | 0.429 | Modernize Roadway-Rural | 26 |  | 50000 |  | 300000 |  | 500000 |  | 630000 |  | 2500000 |  | 2017-05-18 09:48 | The purpose of this project is to improve access to the Rockcastle County Industrial Park # 2 entrance via KY 2549 from US 150. | An improved KY 2549 will provide better access to the industrial park, and provide for more efficient freight movement for B & H Tools, a tool and die facility located in the industrial park, as well as any potential industies. | CUMBERLAND VALLEY ADD | South | 13.0545 | 1.5735 | 4.0521 | 0.67536 | 2.0142 | 4.7393 | 0 | 0 | 13
Y | 8 | Lake Cumberland ADD | IP20080503 |  |  |  | IMPROVE THE INTERCHANGE AT THE INTERSECTION OF US-127 AND THE LBN PARKWAY AT MP 62.419 | Reconstruction | Russell | 104-LN-9008 -000 | 62.369 | 62.469 | 0.1 | Innovative Interchange | 40 | Y | 0 |  | 450000 |  | 1200000 |  | 600000 |  | 6500000 |  | 2011-10-17 13:42
Y | 8 | Lake Cumberland ADD | IP20080504 |  |  |  | Address future congestion and economic development issues on KY 90. Improve Level of Service and safety on KY 90 from KY 90X/KY3284 to KY 90X/KY 1275. | Major Widening | Wayne | 116-KY-0090 -000 | 9.601 | 12.721 | 3.12 | Modernize Roadway-Rural | 26 |  | 0 |  | 1560000 |  | 6000000 |  | 1900000 |  | 19000000 |  | 2015-03-12 11:13 |  | The KY 90 corridor in southern Kentucky is an arterial route connecting US 27 to the Louie B Nunn Parkway and I- 65. This segment of Ky. 90 links the people of Cumberland, Clinton, and Wayne Counties to US 27 and Somerset, providing a direct link for im
Y | 8 | Lake Cumberland ADD | IP20080505 |  |  |  | Reduce congestion and improve safety, capacity, and mobility of KY 90 between KY 90X/KY 1275 in and KY 3106. | Major Widening | Wayne | 116-KY-0090 -000 | 12.721 | 15.617 | 2.896 | Modernize Roadway-Rural | 26 |  | 20000 |  | 1450000 |  | 5000000 |  | 2400000 |  | 17500000 |  | 2017-05-18 10:34 | This project is needed because the capacity of KY 90 between KY 90X/KY 1275 in and KY 3106 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 46.0474 | 6.9005 | 9.5972 | 8.9573 | 0 | 9.2417 | 4.3839 | 6.9668 | 46
Y | 8 | Lake Cumberland ADD | IP20080506 |  |  |  | Reduce congestion and improve safety, capacity, and mobility of KY 90 between KY 1275/KY 1619 and KY 1568. | Major Widening | Wayne | 116-KY-0090 -000 | 19.267 | 23.077 | 3.81 | Modernize Roadway-Rural | 26 |  | 20000 |  | 2040000 |  | 8900000 |  | 5200000 |  | 33800000 |  | 2017-05-18 10:36 | This project is needed because the capacity of KY 90 between KY 1275/KY 1619 and KY 1568 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 44.4893 | 7.6588 | 5.8294 | 8.3709 | 0 | 9.0995 | 4.0521 | 9.4787 | 44
Y | 8 | Lake Cumberland ADD | IP20080507 |  |  |  | Reduce congestion and improve safety, capacity, and mobility of KY 90 between KY 1568 in Wayne County and MP 2.757 in Pulaski County. | Major Widening | Wayne | 116-KY-0090 -000 | 23.077 | 25.235 | 2.158 | Modernize Roadway-Rural | 26 |  | 20000 |  | 2900000 |  | 12900000 |  | 2600000 |  | 44200000 |  | 2017-05-18 10:40 | This project is needed because the capacity of KY 90 between KY 1568 in Wayne County and MP 2.757 in Pulaski County is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of hi | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 40.2855 | 8.3602 | 4.6209 | 5.8116 | 0 | 9.4313 | 3.4834 | 8.5782 | 40
Y | 8 | Lake Cumberland ADD | IP20090015 |  |  |  | New construction connecting Monticello to the Louie B. Nunn Parkway in Pulaski County, including a new bridge across Lake Cumberland. | New Route | Wayne | 116-KY-3283 -000 | 0 | 1.7 | 1.7 | Construct Road in New Location | 0 |  | 350000 |  | 11000000 |  | 13200000 |  | 10000000 |  | 120000000 |  | 2013-05-14 11:16 |  | Wayne County has no direct access to the north due to the location of Lake Cumberland. Northbound Traffic must travel east to Somerset, or west to Albany to bypass the lake, greatly increasing travel times. The new connection could benefit regional touris
Y | 8 | Lake Cumberland ADD | IP20090016 |  |  |  | Construction of a 2 lane extension of KY 790 from Pueblo to KY 92 to improve the regional transportation infrastructure. Approx. 4 miles. | New Route | Wayne | 116-KY-0790 -000 | 0 | 0.001 | 0.001 | Construct Road in New Location | 0 |  | 150000 |  | 2600000 |  | 1500000 |  | 1200000 |  | 20000000 |  | 2013-05-14 11:06
Y | 8 | Lake Cumberland ADD | IP20090017 |  |  |  | Address safety and conditions issuses on KY 910 and KY80, from Phil (Casey) to Nancy (Pulaski) (approx. 16 miles) | New Route | Casey | 023-KY-0910 -000 | 0 | 1.464 | 1.464 | Modernize Roadway-Rural | 26 |  | 200000 |  | 9600000 |  | 19000000 |  | 16000000 |  | 80000000 |  | 2017-05-16 12:49 | This project is needed because the capacity of KY 910 and KY 80 between Phil and Nancy is inadequate to meet current and future traffic volumes, resulting in congestion and reduced mobility on this stretch of highway. There are also safety issues with th | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | LAKE CUMBERLAND ADD | South | 30.2737 | 2.436 | 4.5498 | 9.4727 | 4.0047 | 0 | 0 | 9.8104 | 30
Y | 8 | Lake Cumberland ADD | IP20090021 |  |  |  | Increase Capacity on KY 1247 (Murphy Avenue) from Gover Lane (mp. 5.219) To KY 1247 (mp. 6.378). | Reconstruction | Pulaski | 100-KY-1247 -000 | 5.219 | 6.378 | 1.159 | Modernize Roadway-Rural | 26 |  | 150000 |  | 700000 |  | 2000000 |  | 1750000 |  | 10600000 |  | 2016-12-09 10:01 |  | KY 1247, Murphy Avenue, is the principle route through downtown Ferguson, and provides direct access to Ky. 914, the Somerset Bypass. The roadway is traveled by both residential, and industrial traffic. With the completion of the current widening of Mai
Y | 8 | Lake Cumberland ADD | IP20100058 |  |  |  | Provide connectivity and improved mobility from KY 80 to KY 1577. | New Route | Pulaski | 100-US-0027 -000 | 15.5 | 17 | 1.5 | Construct Road in New Location | 0 | Y | 50000 |  | 665000 |  | 1700000 |  | 1325000 |  | 8000000 |  | 2017-05-16 15:59 | This project is needed because the capacity of KY 80 to KY 1577 near the Lake Cumberland Regional Hospital is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility 4.) Improve access | 8 | South | 38.0889 | 7.0995 | 2.7725 | 14.5912 | 0 | 9.6682 | 3.9573 | 0 | 38
Y | 8 | Bluegrass ADD | IP20110027 |  |  |  | Reconstruct US 27 from the US 150 Bypass in Lincoln County to the proposed West Lancaster Bypass in Garrard County. BMP is 18.155 (Lincoln Co.) and EMP in Garrard County is 0.444. Project length is 4.30 miles. | Major Widening | Lincoln | 069-US-0027 -000 | 18.155 | 21.982 | 3.827 | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 16757000 |  | 5000000 |  | 30401995 |  | 2012-05-04 09:13 | Reconstruct US 27 from the US 150 Bypass in Lincoln County to the proposed West Lancaster Bypass in Garrard County. BMP is 18.155 (Lincoln Co.) and EMP in Garrard County is 0.444. Project length is 4.30 miles. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 8 | Lake Cumberland ADD | IP20110192 |  |  |  | Improve safety and mobility along KY 1577 between Grand Central Boulevard and Thurman Road. | Safety-Haz-Elm | Pulaski | 100-KY-1577 -000 | 2.8 | 3.4 | 0.6 | Modernize Roadway-Rural | 26 |  | 20000 |  | 300000 |  | 900000 |  | 500000 |  | 1800000 |  | 2017-05-16 16:58 | This project is needed because the geometrics along KY 1577 between Grand Central Boulevard and Thurman Road are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | 8 | South | 36.718 | 8.3886 | 13.5782 | 9.7749 | 0 | 0 | 0 | 4.9763 | 37
Y | 8 | Lake Cumberland ADD | IP20110193 |  |  |  | Improve safety and mobility along KY 39 between Oak Leaf lane and the Northern Bypass. | Reconstruction | Pulaski | 100-KY-0039 -000 | 1.13 | 4.5 | 3.37 | Modernize Roadway-Rural | 26 |  | 20000 |  | 1400000 |  | 6000000 |  | 2000000 |  | 15000000 |  | 2017-05-16 16:22 | This project is needed because the geometrics along KY 39 between Oak Leaf lane and the Northern Bypass are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | 8 | South | 46.5367 | 5.5829 | 11.3033 | 11.641 | 2.2275 | 6.4929 | 0 | 9.2891 | 46
Y | 8 | Lake Cumberland ADD | IP20110194 |  |  |  | Improve safety and mobility along KY 39 between KY 80 and Oak Leaf Lane. | Reconstruction | Pulaski | 100-KY-0039 -000 | 0.286 | 1.13 | 0.844 | Modernize Roadway-Rural | 26 |  | 20000 |  | 425000 |  | 1500000 |  | 425000 |  | 2600000 |  | 2017-05-16 16:20 | This project is needed because the geometrics along KY 39 between KY 80 and Oak Leaf Lane are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | 8 | South | 36.3957 | 6.9289 | 12.654 | 9.4194 | 1.327 | 0 | 0 | 6.0664 | 36
Y | 8 | Bluegrass ADD | IP20120054 |  |  |  | Improve safety on KY 1194 just east of Frog Branch Road to just east of Hanging Fork Creek in Lincoln County. | Reconstruction | Lincoln | 069-KY-1194 -000 | 1.5 | 4.1 | 2.6 | Modernize Roadway-Rural | 26 |  | 75000 |  | 1300000 |  | 2000000 |  | 950000 |  | 7900000 |  | 2017-05-16 14:51 | Improve safety on KY 1194 just east of Frog Branch Road to just east of Hanging Fork Creek in Lincoln County. | Reconstruction needed on KY 1194 just east of Frog Branch Road to just east of Hanging Fork Creek in Lincoln County in order to improve commuter safety. | BLUEGRASS ADD | South | 29.5145 | 1.6493 | 9.3839 | 5.545 | 4.0521 | 4.8341 | 0 | 4.05 | 30
Y | 8 | Bluegrass ADD | IP20120055 |  |  |  | Reconstruct KY 78 from Turnersville to US 150 in Lincoln County. | Reconstruction | Lincoln | 069-KY-0078 -000 | 8.65 | 15.448 | 6.798 | Modernize Roadway-Rural | 26 |  | 50000 |  | 4250000 |  | 9200000 |  | 3300000 |  | 26000000 |  | 2017-05-16 14:18 | Reconstruct KY 78 from Turnersville to US 150 in Lincoln County. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity. | BLUEGRASS ADD | South | 37.4384 | 1.763 | 7.2512 | 12.4052 | 3.8863 | 4.9763 | 0 | 7.1564 | 37
Y | 8 | Bluegrass ADD | IP20120056 |  |  |  | Reconstruct KY 78 from Turnersville to US 127 in Lincoln County. | Reconstruction | Lincoln | 069-KY-0078 -000 | 2.225 | 8.2 | 5.975 | Modernize Roadway-Rural | 26 |  | 20000 |  | 3000000 |  | 6000000 |  | 2500000 |  | 19200000 |  | 2017-05-18 11:44 | Reconstruct KY 78 from Turnersville to US 127 in Lincoln County. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | BLUEGRASS ADD | South | 32.8697 | 1.9336 | 6.1848 | 9.4194 | 2.0142 | 4.5972 | 0 | 8.7204 | 33
Y | 8 | Lake Cumberland ADD | IP20120067 |  |  |  | The proposed roadway would help alleviate traffic on existing KY 206, KY3491, as well as traffic thru town on KY 55X and KY80. Eastern Columbia Bypass. | New Route | Adair | 001-KY-0055X -000 | 0 | 3 | 3 | Construct Road in New Location | 0 |  | 210000 |  | 3200000 |  | 18300000 |  | 1800000 |  | 32500000 |  | 2015-03-04 15:47
Y | 8 | Lake Cumberland ADD | IP20120074 |  |  |  | Narrow two lane road with little to no shoulders and poor visibility, with a high volume of truck traffic for this type of road. Major connector route between two cities. | Reconstruction | Casey | 023-KY-0070 -000 | 11.665 | 13.583 | 1.918 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1750000 |  | 1000000 |  | 10000000 |  | 2013-05-14 14:44 |  | Lane widening and horizontal alignemen improvements to KY 70 From Linnie - Rheber Rd - Begin MP 11.665 End MP 13.583
Y | 8 | Lake Cumberland ADD | IP20120075 |  |  |  | Narrow two lane road with little to no shoulders and poor visibility, with a high volume of traffic for this type of road. Major connector route between two cities | Reconstruction | Casey | 023-KY-0049 -000 | 0.114 | 1.8 | 1.686 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2400000 |  | 1750000 |  | 10000000 |  | 2013-05-14 11:48 |  | RECONSTRUCT KY 49, From KY 2314 to MP 1.8 - Begin MP 0.114 End MP 1.8
Y | 8 | Lake Cumberland ADD | IP20120076 |  |  |  | Narrow two lane road with little to no shoulders and poor visibility, with a high volume of traffic for this type of road. Major connector route between two cities | Reconstruction | Casey | 023-KY-0049 -000 | 2.8 | 5.098 | 2.298 | Modernize Roadway-Rural | 26 |  | 0 |  | 1200000 |  | 2000000 |  | 1300000 |  | 11500000 |  | 2013-05-14 11:51 |  | RECONSTRUCT KY 49, From MP 2.8 to Carr- Sasser Rd - Begin MP 2.8 End MP 5.098
Y | 8 | Lake Cumberland ADD | IP20120077 |  |  |  | Narrow two lane road with little to no shoulders and poor visibility, with a high volume of traffic for this type of road. Major connector route between two cities | Reconstruction | Casey | 023-KY-0049 -000 | 5.098 | 8.008 | 2.91 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 2500000 |  | 1300000 |  | 14600000 |  | 2013-05-14 11:54 |  | RECONSTRUCT KY 49, From Carr- Sasser Rd to KY 1547 - Begin MP 5.098 End MP 8.008
Y | 8 | Lake Cumberland ADD | IP20120078 |  |  |  | Improve safety and geometrice along KY 49 from KY 1547 to KY 49 is a rural 2 lane roadway with 9' lanes and 2' shoulders The area is mostly residential and agricultural, with several private access points This route connects US 68 in Lebanon to US 127 | Reconstruction | Casey | 023-KY-0049 -000 | 8.008 | 9.594 | 1.586 | Modernize Roadway-Rural | 26 |  | 50000 |  | 800000 |  | 1250000 |  | 650000 |  | 8000000 |  | 2015-03-10 15:27 |  | RECONSTRUCT KY 49, From KY 1547 to .02 mile past Martins Creek Rd - Begin MP 8.008 End MP 9.594
Y | 8 | Lake Cumberland ADD | IP20120079 |  |  |  | Reduce congestion and improve mobility on US 127X between Ferguson St and McWhorter Rd. | Spot Improvement | Clinton | 027-US-0127X -000 | 3.895 | 5.191 | 1.296 | Install Two-way Left Turn Lane | 28 |  | 50000 |  | 800000 |  | 700000 |  | 1300000 |  | 8000000 |  | 2017-05-16 13:34 | This project is needed because the capacity of US 127X between Ferguson St and McWhorter Rd. is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility 4.) Improve pedestrian safety | LAKE CUMBERLAND ADD | South | 30.2808 | 8.8531 | 2.7014 | 1.1197 | 1.327 | 6.9194 | 3.1991 | 6.1611 | 30
Y | 8 | Lake Cumberland ADD | IP20120080 |  |  |  | Improve safety and mobility of KY 558 between KY 90 and KY 3045. | Reconstruction | Clinton | 027-KY-0558 -000 | 1.129 | 7.729 | 6.6 | Modernize Roadway-Rural | 26 |  | 20000 |  | 2200000 |  | 4400000 |  | 3300000 |  | 22000000 |  | 2017-05-16 13:50 | This project is needed because the geometrics along KY 558 between KY 90 and KY 3045 are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 38.9159 | 0.75829 | 6.327 | 8.9396 | 3.8152 | 4.0758 | 0 | 0 | 24 | 15
Y | 8 | Lake Cumberland ADD | IP20120081 |  |  |  | Improve safety and mobility of KY 558 between KY 3045 and the end of state maintenance in Russell county. | Reconstruction | Clinton | 027-KY-0558 -000 | 7.729 | 10.753 | 3.024 | Modernize Roadway-Rural | 26 |  | 150000 |  | 2000000 |  | 3000000 |  | 2400000 |  | 19000000 |  | 2017-05-18 11:20 | This project is needed because the geometrics along KY 558 between KY 3045 and the end of state maintenance in Russell county are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 11.2287 | 0.1327 | 2.346 | 1.6173 | 3.3412 | 3.7915 | 0 | 0 | 11
Y | 8 | Lake Cumberland ADD | IP20120082 |  |  |  | Improve safety and mobility on KY 90 between Allens Creek Rd and Norris Branch Rd. | Reconstruction | Cumberland | 029-KY-0090 -000 | 9.654 | 10.432 | 0.778 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 780000 |  | 400000 |  | 4000000 |  | 2018-11-28 16:41 | This project is needed because the geometrics along KY 90 between Allens Creek Rd and Norris Branch Rd are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility
Y | 8 | Lake Cumberland ADD | IP20130050 |  |  |  | Provide connectivity and improved mobility from US 127 to Hospital in Liberty. | New Route | Casey | 023-US-0127 -000 | 13.9 | 14 | 0.1 | Construct Road in New Location | 0 | Y | 50000 |  | 100000 |  | 500000 |  | 200000 |  | 800000 |  | 2017-05-16 12:46 | This project is needed because the capacity of US 127 to Hospital in Liberty is inadequate to meet current and future traffic volumes, resulting in congestion and reduced mobility on this stretch of highway, especially around the elementary school. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility and access | 8 | South | 23.9313 | 5.7441 | 0 | 2.4526 | 1.9431 | 9.3839 | 4.4076 | 0 | 24
Y | 8 | Bluegrass ADD | IP20130054 |  |  |  | Relocate intersection of Goshen Cutoff road to signalized intersection with US 27 to improve safety and traffic flow on US 27. | Reconstruction | Lincoln | 069-CR-1071T -000 | 0 | 0.21 | 0.21 | Local Roadway Improvements | 3 |  | 20000 |  | 75000 |  | 600000 |  | 250000 |  | 1100000 |  | 2017-05-16 14:55 | Relocate intersection of Goshen Cutoff road to signalized intersection with US 27 to improve safety and traffic flow on US 27. | Address safety and improve traffic flow on US 27 | 8 | South | 7.1967 | 0.028436 | 0 | 4.372 | 2.7962 | 0 | 0 | 0 | 7
Y | 8 | Lake Cumberland ADD | IP20130066 |  |  |  | Extend the Louie B Nunn Parkway from KY 39 to KY 80 completing the northern bypass HAL ROGERS PARKWAY NORTHEAST BYPASS AROUND SOMERSET. 2006KYD) | New Route | Pulaski | 100-KY-0080 -000 | 18.846 | 19.933 | 1.087 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 29360000 |  | 2016-10-31 14:04
Y | 8 | Lake Cumberland ADD | IP20130149 |  |  |  | Reduce congestion and improve safety, capacity, and mobility of KY 1247 in Pulaski County between MP 8.38 and 8.45 at the intersection of KY 1247 and KY 1575. | Reconstruction | Pulaski | 100-KY-1247 -000 | 8.35 | 8.45 | 0.1 | Improve Intersection | 26 |  | 150000 |  | 200000 |  | 500000 |  | 630000 |  | 3000000 |  | 2017-05-16 16:53 | This project is needed because the capacity of KY 1247 in Pulaski County between MP 8.38 and 8.45 at the intersection of KY 1247 and KY 1575 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobil | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 31.9218 | 9.0427 | 5.9716 | 8.0687 | 2.2275 | 0 | 3.2938 | 3.3175 | 32
Y | 8 | Lake Cumberland ADD | IP20150083 |  |  |  | Improve safety and mobility of KY 738 between US 127 and US 127X. | Safety-Haz-Elm | Clinton | 027-KY-0738 -000 | 5.519 | 6.706 | 1.187 | Modernize Roadway-Rural | 26 |  | 50000 |  | 600000 |  | 1500000 |  | 720000 |  | 6000000 |  | 2017-05-18 11:25 | This project is needed because the geometrics along KY 738 between US 127 and US 127X are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 21.2773 | 1.1469 | 9.6682 | 5.7938 | 4.6682 | 0 | 0 | 0 | 21
Y | 8 | Lake Cumberland ADD | IP20150084 |  |  |  | Spot improvements along KY 738 from KY 1576 to US 127. To correct horizontal and vertical alignment and address safety. | Safety-Haz-Elm | Clinton | 027-KY-0738 -000 | 4.773 | 5.519 | 0.746 | Modernize Roadway-Rural | 26 |  | 50000 |  | 400000 |  | 1000000 |  | 500000 |  | 4000000 |  | 2015-03-11 13:18 |  | KY 738 is a narrow road (9' lanes) with minimal shoulders (2' earth) and several sharp horizontal curves. This route leads to Wolf River Dock on Dale Hollow Lake, which compounds the problems listed above by adding boat and RV traffic. The project will i
Y | 8 | Lake Cumberland ADD | IP20150087 |  |  |  | Improve safety by improving the geometrics along US 127X from KY 696 to KY 738 in Albany. | Safety-Haz-Elm | Clinton | 027-US-0127X -000 | 1.28 | 2.563 | 1.283 | Modernize Roadway-Rural | 26 |  | 50000 |  | 1000000 |  | 700000 |  | 1300000 |  | 5100000 |  | 2015-03-11 15:44 |  | This is a major highway through Albany & Clinton Co. This section of roadway is narrow & curvey.
Y | 8 | Lake Cumberland ADD | IP20150088 |  |  |  | Improve safety and mobility on KY 76 at the intersection of KY 910 in the Salem area. | Reconstruction | Russell | 104-KY-0076 -000 | 5.731 | 5.931 | 0.2 | Improve Intersection | 26 |  | 20000 |  | 100000 |  | 240000 |  | 120000 |  | 1000000 |  | 2017-05-18 10:19 | This project is needed because the geometrics along KY 76 at the intersection of KY 910 in the Salem area are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 12.9313 | 2.4455 | 4.4787 | 3.519 | 2.4882 | 0 | 0 | 0 | 13
Y | 8 | Lake Cumberland ADD | IP20150090 | 8-8852 |  | A | IMPROVE KY-90 FROM NORRIS BRANCH ROAD EXTENDING WESTERLY TO PA DUERSON ROAD NEAR MARROWBONE. (14CCN)(18CCR) | RECONSTRUCTION(O) | Cumberland | 029-KY-0090 -000 | 5.182 | 10.432 | 5.25 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2020 | 3200000 | 2025 | 1800000 | 2025 | 22000000 | 2025 | 2018-07-10 08:18 |  | Spot improvements along KY 90 between Pa Dureson rd. and Norris Branch Rd. - Begin MP 5.182 end MP 10.432 | LAKE CUMBERLAND ADD | South | 71.4336 | 3.6967 | 8.6019 | 9.2062 | 3.0806 | 6.3033 | 2.6303 | 7.9147 | 41 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20150091 |  |  |  | Provide connectivity and improved mobility from in the Western portion of Adair County by adding a new interchange on the Cumberland Parkway at KY 80 near Gradyville. | New Interchange | Adair | 001-KY-0080 -000 | 2.997 | 3.197 | 0.2 | Construct Road in New Location | 0 |  | 60000 |  | 395000 |  | 1840000 |  | 800000 |  | 9340000 |  | 2017-05-16 12:33 | The project is needed because the access point to the Louie B Nunn Cumberland Parkway is more than 10 miles away in either direction along narrow curvy roads. | The following needs have been identified for this project: 1.) Provide connectivity 2.) Provide mobility 3.) Improve access. | LAKE CUMBERLAND ADD | South | 9.782 | 0.4455 | 3.0569 | 1.4218 | 0.92417 | 3.9336 | 0 | 0 | 10
Y | 8 | Bluegrass ADD | IP20150127 |  |  |  | Provide connectivity of KY 1194 in Lincoln County to continue from MP 6.602 overland to Brock Drive near where it crosses the Stanford city limits. | New Route | Lincoln | 069-KY-1194 -000 | 6.6 | 6.602 | 0.002 | Construct Road in New Location | 0 |  | 50000 |  | 900000 |  | 200000 |  | 1800000 |  | 2086720 |  | 2017-05-16 14:53 | Provide connectivity of KY 1194 in Lincoln County to continue from MP 6.602 overland to Brock Drive near where it crosses the Stanford city limits. | The extension of KY 1194 to Brock Drive will provide connectivity from the western portion of the county, US 127 to US 27 near Standford. | BLUEGRASS ADD | South | 7.455 | 1.4597 | 0 | 0 | 2.0142 | 3.981 | 0 | 0 | 8
Y | 8 | Lake Cumberland ADD | IP20150161 | 8-8704 |  | A | RECONSTRUCT BRUSHY CREEK HILL FROM MP 1.8 TO MP 2.8.(12CCN)(16CCR)(18CCN) | RECONSTRUCTION(O) | Casey | 023-KY-0049 -000 | 1.8 | 2.8 | 1 | Modernize Roadway-Rural | 26 |  |  |  | 1250000 | 2019 | 1320000 | 2023 | 1040000 | 2024 | 4500000 | 2025 | 2018-07-10 08:18 | This project is needed because the geometrics of KY 49 at Brush Creek Hill between MP 1.8 and MP 2.8 is inadequate resulting in safety issues on this stretch of highway. | The following needs have been identified for this project: 1.) Improve geometrics 2.) Improve roadway safety | LAKE CUMBERLAND ADD | South | 62.2226 | 1.5924 | 6.8957 | 7.3045 | 4.0995 | 5.3555 | 0 | 6.975 | 32 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20150191 |  |  |  | Correct Rockfall Hazard @ Mp 4.7 To 5.05 (Both Sides Of Roadway)(10Ccr)(12Ccr)(14Ccr) | Safety-Haz-Elm | Pulaski | 100-US-0027 -000 | 4.7 | 5.05 | 0.35 | Maintenance Improvement | 10 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 4160000 |  | 2017-05-16 15:53
Y | 8 | Lake Cumberland ADD | IP20150258 | 8-8601.30 |  | A | RELOCATION OF US-127 FROM EAST OF THE AARON RIDGE RD AND OLD US-127 INTERSECTION, EXTENDING NORTHERLY TO NORTH OF THE KY-3063 AND OLD US-127 INTERSECTION. (SEE 8-108 AND 8-115 FOR PE&ENV)(12CCR) | RELOCATION(O) | Clinton | 027-US-0127 -000 | 16.135 | 19.99 | 3.855 | Construct Road in New Location | 0 | Y |  |  | 1600000 | 2024 | 1680000 | 2025 | 580000 | 2025 | 27000000 | 2025 | 2018-07-10 08:18 |  | This section of the US 127 corridor provides very limited passing opportunities for more than 2.3 miles, causing congestion and interrupting the natural traffic flow. | 8 | South | 32.2073 | 1.2417 | 0 | 4.9941 | 4.1943 | 4.2654 | 2.5118 | 0 | 17 | 15
Y | 8 | Lake Cumberland ADD | IP20150262 |  |  |  | Somerset Norther Bypass (I-66) Section 4; "Surfacing" for section 4 from East of the KY 39 Interchange, East to KY 80 East of Somerset (Includes Interchange at KY 80). (CONST SEQ 4) (2002BOP)(05KYD)(2012BOP) | New Route | Pulaski | 100-KY-0080 -000 | 20 | 21.5 | 1.5 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 10750000 |  | 2016-10-26 09:32 |  | This project will complete the bypass around Somerset. This bypass in necessary to improve safety and reduce congestion in Somerset.
Y | 8 | Lake Cumberland ADD | IP20150269 |  |  |  | Improving safety and congestion by reconstructing US 127 from approx 0.36 mi E of intersection KY 1730 & Manntown Rd extend N to N Bank of Cumberland River including new bridge over Lake Cumberland Fr Clinton Co to Russell Co(See 8-108&8-115 For Pe&Env)(1 | Relocation | Russell | 104-US-0127 -000 | 0.923 | 2.621 | 1.698 | Construct Road in New Location | 0 | Y | 0 |  | 1900000 |  | 2100000 |  | 810000 |  | 25880000 |  | 2016-10-26 09:46 |  | This section of the US 127 corridor provides no passing opportunities for more than 2.5 miles, causing congestion and interrupting the natural traffic flow.
Y | 8 | Lake Cumberland ADD | IP20150289 | 8-8703 |  | A | RECONSTRUCT BELL HILL FROM MP 10.4 TO MP 11.9.(12CCN)(16CCR)(18CCN) | RECONSTRUCTION(O) | Casey | 023-KY-0070 -000 | 10.4 | 11.9 | 1.5 | Modernize Roadway-Rural | 26 |  |  |  | 1560000 | 2021 | 3420000 | 2023 | 890000 | 2025 | 9500000 | 2025 | 2018-07-10 08:18 | This project is needed because the geometrics along KY 70 at Bell Hill between MP 10.4 and MP 11.9 are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 30.3199 | 4.4076 | 5.1185 | 5.0118 | 2.9858 | 6.2559 | 0 | 6.5403 | 30
Y | 8 | Bluegrass ADD | IP20150349 |  |  |  | RELOCATE A SHORT SECTION OF GOSHEN ROAD FROM ITS EXISTING INTERSECTION WITH US 27 TO A NEW LOCATION OPPOSITE THE EXISTING WAL-MART SIGNAL. | Relocation | Lincoln | 069-US-0150 -000 | 5.5 | 6.1 | 0.6 | Realign Intersection | 26 |  | 0 |  | 0 |  | 750000 |  | 500000 |  | 850000 |  | 2018-11-08 15:59 | RELOCATE A SHORT SECTION OF GOSHEN ROAD FROM ITS EXISTING INTERSECTION WITH US 27 TO A NEW LOCATION OPPOSITE THE EXISTING WAL-MART SIGNAL. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 8 | Lake Cumberland ADD | IP20150382 |  |  |  | RECONSTRUCTION OF US 127 FROM THE NORTH BANK OF THE CUMBERLAND RIVER TO KY 55 NEAR FREEDOM. (SEE 8-108 AND 8-115 FOR PE & ENV)(12CCR) | Relocation | Russell | 104-US-0127 -000 | 2.515 | 8.092 | 5.577 | Construct Road in New Location | 0 | Y | 0 |  | 1900000 |  | 5600000 |  | 1720000 |  | 0 |  | 2016-10-26 09:47
Y | 8 | Bluegrass ADD | IP20150386 | 8-167 |  | A | US-27 CORRIDOR FROM SOMERSET TO LEXINGTON. IMPROVE SAFETY AND REDUCE CONGESTION ON US-27 FROM KY-1247 TO EDUCATION WAY. | RECONSTRUCTION(O) | Lincoln | 069-US-0027 -000 | 11.169 | 15.881 | 4.712 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 23600000 | 2022 | 15000000 | 2022 | 66000000 | 2025 | 2018-07-10 08:18 | Improve safety and reduce congestion along US 27 From KY 1247 to Education Way. Replaces 08 069 B0027 21.80 | Continue Ongoing Improvements To US 27 Corridor From Somerset To Lexington. Improve Level Of Service And Safety On US 27 From KY-1247 To Education Way. | 8 | South | 77.6564 | 6.3886 | 7.891 | 12.1209 | 1.09 | 7.6777 | 3.8626 | 8.6256 | 48 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20150451 |  |  |  | I-66 SOMERSET TO LONDON. (2006KYD)(10CCR) | New Route | Pulaski | 100-KY-0080 -000 | 18.5 | 39 | 20.5 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 2000000 |  | 2016-10-26 09:37
Y | 8 | Lake Cumberland ADD | IP20150452 | 8-59.10 |  | A | LOCATE I-66 FROM KY-80 EAST OF SOMERSET TO I-75 SOUTH OF LONDON. (98KYDN) (2000KYD) (01KYD)(04KYD)(05KYD) | PE & ENVIRONMENTAL(O) | Pulaski | 100-KY-0080 -000 | 18.5 | 39 | 20.5 | Transportation Studies | 0 | Y | 0 |  | 0 |  | 0 | 2025 | 0 | 2025 | 0 | 2025 | 2018-07-10 08:18 |  |  | 8 | Statewide | 25.2247 | 6.4141 | 0 | 11.63 | 1.8062 | 0 | 5.3744 | 0
Y | 8 | Lake Cumberland ADD | IP20150453 |  |  |  | Improve safety on KY 3260 by improving the geometric design of the roadway from approximately 0.194 Mile west of Stewart Drive to 0.173 Mile east of Kiteck Lane. | Safety-Haz-Elm | Pulaski | 100-KY-3260 -000 | 0.1 | 1.1 | 1 | Modernize Roadway-Rural | 26 |  | 10000 |  | 900000 |  | 1000000 |  | 1000000 |  | 6000000 |  | 2015-06-16 10:03 |  | To improve the alignment of KY 3260 which will reduce the number of road departure in this area.
Y | 8 | Lake Cumberland ADD | IP20150462 |  |  |  | Improve safety and reduce congestion along US 27 from KY 478, extending Northerly to 0.123 Mlle North of KY 927. | Minor Widening | McCreary | 074-US-0027 -000 | 9.093 | 17 | 7.907 | Modernize Roadway-Rural | 26 | Y | 0 |  | 4000000 | 2020 | 8000000 | 2021 | 8000000 | 2022 | 32000000 | 2023 | 2019-02-27 10:10 | Improve safety and reduce congestion along US 27 from KY 478, extending Northerly to 0.123 Mlle North of KY 927. | US 27 in McCreary County is a major north-south arterial route for the county, as well as for the region and state. The improvement of this segment would be a continuation of the improvements made to US 27 in this area and statewide. This segment of US 27
Y | 8 | Bluegrass ADD | IP20150463 | 8-80002 |  | A | US 127 NEW TURNING LANE AT KY 1194(18CCN) | NEW INTERCHANGE(O) | Lincoln | 069-US-0127 -000 | 6.8 | 7.1 | 0.3 | Improve Intersection | 26 | Y |  |  | 100000 | 2019 | 50000 | 2019 | 50000 | 2019 | 800000 | 2019 | 2018-07-10 08:18 | Improve Safety along US 127 at the KY 1194 intersection. | There have been 8 accidents in this are between 6-2010 and 6-2015. There is a new Dollar General Store being built which will lead to more cars using KY 1194 to access the store. The construction of new turning lanes on US 127 will improve the safety to | 8 | South | 33.4076 | 7.0806 | 13.9336 | 3.7678 | 1.2322 | 0 | 3.7441 | 3.6493 | 33
Y | 8 | Lake Cumberland ADD | IP20150464 |  |  |  | Improve safety along KY 90 between the Clinton County line and the Pulaski County line. | Spot Improvement | Wayne | 116-KY-0090 -000 | 0 | 25.235 | 25.235 | Modernize Roadway-Rural | 26 |  | 10000 |  | 25000 |  | 0 |  | 0 |  | 7000000 |  | 2017-05-18 10:30 | This project is needed because the geometrics along KY 90 between the Clinton County line and the Pulaski County line are inadequate and causes safety issues. | The following needs have been identified for this project: 1.)Improve roadway safety | 8 | South | 69.0284 | 7.5355 | 15 | 14.5024 | 2.7962 | 0 | 4.2891 | 9.9052 | 54 |  | 15
Y | 8 | Lake Cumberland ADD | IP20160097 |  |  |  | RESHAPE AND SURFACE SHOULDERS, CORRECT DRAINAGE AND INSTALL GUARDRAIL ALONG KY 70 FROM DOE CREEK ROAD (MP 18.531) EXTENDING EAST TO KY 198 (MP 21.422). (2016BOP) | Safety-Haz-Elm | Casey | 023-KY-0070 -000 | 18.531 | 21.422 | 2.891 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 10:43
Y | 8 | Lake Cumberland ADD | IP20160099 |  |  |  | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS ROCKCASTLE RIVER BRIDGE AND APPROACHES. (SEGMENT 3)(16CCN) | Reconstruction | Pulaski | 100-KY-0080 -000 | 39.35 | 39.682 | 0.332 | Arterial to Full Control | 36 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 12:25
Y | 8 | Lake Cumberland ADD | IP20160100 |  |  |  | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 192 FROM KY 692 (MP 1.076) TO JAMES MEECE RD (CR-1233) AT (MP 7.435) IN PULASKI COUNTY. (2016BOP) | Safety-Haz-Elm | Pulaski | 100-KY-0192 -000 | 1.076 | 7.435 | 6.359 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 12:28
Y | 8 | Lake Cumberland ADD | IP20160101 |  |  |  | US-127 FROM NORTH BANK OF THE CUMBERLAND RIVER TO THE JAMESTOWN BYPASS. (00CCR) (08CCR)(10CCR)(12CCR)(G&D)(14CCR) | Reconstruction | Russell | 104-US-0127 -000 | 8.129 | 11.573 | 3.444 | Modernize Roadway-Rural | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 12:31
Y | 8 | Lake Cumberland ADD | IP20160102 |  |  |  | PLANNING STUDY FOR KY 92 EAST IN WAYNE AND RUSSELL COUNTIES. (16CCN) | Reconstruction | Wayne | 116-KY-0092 -000 | 0 | 7.536 | 7.536 | Transportation Studies | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-17 14:59
Y | 8 | Lake Cumberland ADD | IP20170008 |  |  |  | RELOCATION(O) | Relocation | Clinton | 027-US-0127 -000 | 0 | 11 | 11 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-01-06 14:38
Y | 8 | Lake Cumberland ADD | IP20170026 |  |  |  | Provide connectivity and improve mobility from KY 461 onto the proposed Northern Bypass. Provide safety improvement. This is an alternate to the Dahl Road (CR-1038) widening and connector onto KY 80. (CN 08 100 C0000 4.00) | New Route | Pulaski | 100-KY-0461 -000 | 0 | 0.9 | 0.9 | Construct Road in New Location | 0 | Y | 500000 |  | 2000000 |  | 1200000 |  | 1000000 |  | 4500000 |  | 2017-05-16 16:09 | This project is needed to provide connectivity from KY 461 onto the proposed Northern Bypass to meet current and future traffic volumes on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve connectivity 3.) Improve mobility | 8 | South | 27.3993 | 7.9147 | 0 | 5.1007 | 1.019 | 8.5782 | 4.7867 | 0 | 27
Y | 8 | Lake Cumberland ADD | IP20170027 |  |  |  | To reduce congestion and improve safety from KY 461 onto KY 80. This is an alternate to the KY 461 Connector from existing KY 461 to proposed Northern Bypass(CN 08 100 C0000 3.00) | New Route | Pulaski | 100-KY-0461 -000 | 0 | 1.2 | 1.2 | Construct Road in New Location | 0 | Y | 100000 |  | 750000 |  | 1500000 |  | 1200000 |  | 4000000 |  | 2017-05-16 16:05 | This project is needed because the capacity from KY 461 onto KY 80 is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility 4.) Provide Connectivity | LAKE CUMBERLAND ADD | South | 27.9325 | 7.9147 | 0 | 5.6339 | 1.019 | 8.5782 | 4.7867 | 0 | 28
Y | 8 | Lake Cumberland ADD | IP20170028 |  |  |  | Provide connectivity and improve mobility from US 27 to McCreary High School. | New Route | McCreary | 074-KY-0092 -000 | 16.4 | 16.6 | 0.2 | Construct Road in New Location | 0 |  | 50000 |  | 500000 |  | 100000 |  | 1000000 |  | 3000000 |  | 2017-05-16 15:42 | This project is needed because the capacity of US 27 between US 27 and McCreary High School is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility 4.) Provide access | LAKE CUMBERLAND ADD | South | 17.545 | 4.6066 | 0 | 4.0521 | 0.92417 | 7.9621 | 0 | 0 | 18
Y | 8 | Cumberland Valley ADD | IP20170046 |  |  |  | To improve safety and connectivity along I-75. This interchange at KY 1505 will assist in relieving congestion when traffic slowing incidents occur on I-75. | New Interchange | Rockcastle | 102-I -0075 -000 | 67.84 | 68.84 | 1 | Construct Road in New Location | 0 | Y | 250000 |  | 1500000 |  | 2000000 |  | 500000 |  | 10000000 |  | 2017-05-16 10:45 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on I-75. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 8 | South | 62.6019 | 9.9242 | 0 | 7.2512 | 0.47393 | 10 | 4.9526 | 0 | 33 | 15 | 15
Y | 8 | Lake Cumberland ADD | IP20170061 |  |  |  | Section 3 of Northeast Bypass. Extend the Louie B Nunn Parkway from US 27 to KY 39. HAL ROGERS PARKWAY NORTHEAST BYPASS AROUND SOMERSET. 2006KYD) | New Route | Pulaski | 100-KY-0080 -000 | 18.846 | 19.933 | 1.087 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 29360000 |  | 2017-06-14 18:20 |  | This project will complete the bypass around Somerset. This bypass in necessary to improve safety and reduce congestion in Somerset.
Y | 8 | Lake Cumberland ADD | IP20170062 |  |  |  | Section 4 of the Northeast Bypass KY 39 Interchange to KY 80 East of Somerset (Includes Interchange at KY 80). (CONST SEQ 4) (2002BOP)(05KYD)(2012BOP) | New Route | Pulaski | 100-KY-0080 -000 | 19.933 | 26.302 | 6.369 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 46400000 |  | 2017-06-14 18:22 |  | This project will complete the bypass around Somerset. This bypass in necessary to improve safety and reduce congestion in Somerset.
Y | 8 | Bluegrass ADD | IP20180031 | 8-80000 |  | A | NEW TURNING LANE AT ARCADIA VIEW DRIVE(18CCN) | NEW INTERCHANGE(O) | Lincoln | 069-US-0127 -000 | 9.4 | 9.88 | 0.48 | Improve Intersection | 26 | Y |  |  | 100000 | 2019 | 50000 | 2019 | 50000 | 2019 | 800000 | 2019 | 2018-07-10 08:18 | Improve Safety along US 127 at Arcadia View Drive. | The following needs have been identified for this project is to improve roadway safety. | General Assembly | South | 34.5767 | 8.5566 | 13.0896 | 2.8833 | 1.2264 | 0 | 4.0566 | 4.7642 | 35
Y | 8 | Lake Cumberland ADD | IP20180034 | 8-80003 |  | A | KY 55 NEW TURNING LANE AT BETTY'S OK COUNTRY COOKING(18CCN) | SAFETY(P) | Adair | 001-KY-0055 -000 | 15.7 | 16.15 | 0.45 | Improve Intersection | 26 | Y |  |  | 250000 | 2020 | [6 empty] | 2018-07-10 08:18 | KY 55 NEW TURNING LANE AT BETTY'S OK COUNTRY COOKING | The following needs have been identified for this project: 1)Improve Roadway Safety. 2) Improve Mobility | General Assembly | South | 26.7936 | 7.283 | 0 | 10.5248 | 0.4717 | 0 | 3.75 | 4.7642 | 27
Y | 8 | Lake Cumberland ADD | IP20180036 |  |  |  | ADD A RIGHT TURNING ON US 127 SOUTHBOUND BEGINNING AT THE EASTBOUND EXIT OF THE CUMBERLAND PARKWAY FOR 0.2 MILES | Minor Widening | Russell | 104-US-0127 -000 | 17.5 | 17.8 | 0.3 | Improve Intersection | 26 | Y | 0 |  | 20000 | 2018 | 0 |  | 20000 | 2018 | 400000 | 2019 | 2018-11-27 15:50 | ADD A RIGHT TURNING ON US 127 SOUTHBOUND BEGINNING AT THE EASTBOUND EXIT OF THE CUMBERLAND PARKWAY FOR 0.2 MILES | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and increase Capacity for all vehicle types. | General Assembly | South | 43.4517 | 6.0755 | 15 | 11.3384 | 2.8774 | 0 | 4.3396 | 3.8208 | 43
Y | 8 | Bluegrass ADD | IP20180037 | 8-80008 |  | A | ADD A TURNING LANE ON US 150 AT WILDERNESS TRAIL ROAD(18CCN) | SAFETY(P) | Lincoln | 069-US-0150 -000 | 1.3 | 1.7 | 0.4 | Improve Intersection | 26 | Y |  |  | 100000 | 2019 |  |  | 50000 | 2019 | 350000 | 2019 | 2018-07-10 08:18 | ADD A TURNING LANE ON US 150 AT WILDERNESS TRAIL ROAD | The following needs have been identified for this project is to improve roadway safety: 1) Improve mobility, 2) Reduce Congestion. | General Assembly | South | 26.2995 | 4.8491 | 7.0755 | 4.5637 | 0.4717 | 0 | 4.5755 | 4.7642 | 26
Y | 8 | Lake Cumberland ADD | IP20180042 |  |  |  | IMPROVE CURVE ON KY 1275 AT KY 833/ROGERS GROVE ROAD AND RESURFACE FROM KY 1275 FROM BELL LANE TO KY 833/ROGERS GROVE ROAD | Spot Improvement | Wayne | 116-KY-1275 -000 | 4.55 | 4.75 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 40000 | 2019 | 30000 | 2019 | 100000 | 2020 | 250000 | 2021 | 2018-11-27 16:00 | To improve safety and correct horizontal alignment. | The need for this project to improve the horizontal deficiencies at KY 833 on KY 1275. | General Assembly | South | 32.9764 | 4.3679 | 15 | 5.8019 | 4.5519 | 0 | 0 | 3.2547 | 33
Y | 8 | Lake Cumberland ADD | IP20180068 |  |  |  | Improve safety and traffic flow on US 27 from 0.05 miles north of Lost Lodge Rd. to Boat Dock Rd. | Major Widening | Pulaski | 100-US-0027 -000 | 10.38 | 11.374 | 0.994 | Other Improvement Types | 0 | Y | 50000 | 2018 | 1000000 | 2019 | 1200000 | 2020 | 1400000 | 2021 | 6000000 | 2023 | 2018-11-27 15:30 | This project is needed because the capacity of US 27 between Lost Lodge Road and Boat Dock Road is inadequate to meet current and future traffic volumes, resulting in safety and traffic flow issues. | The following needs have been identified for this project: 1.) Improve roadway safety, 2.) Improve traffic flow and capacity
Y | 8 | Lake Cumberland ADD | IP20180069 |  |  |  | Reduce congestion and improve mobility from US 127 to Belden St. in Liberty. | Reconstruction | Casey | 023-KY-0070X -000 | 2.407 | 2.8 | 0.393 | Other Improvement Types | 0 |  | 0 |  | 200000 | 2018 | 500000 | 2019 | 400000 | 2020 | 1500000 | 2021 | 2018-11-27 13:49 | This project is needed because of the capacity on KY 70X between US 127 and Belden Street is inadequate to meet current and future traffic volumes, resulting in congestion and reduced mobility. | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion, 2.) Improve mobility
Y | 8 | Lake Cumberland ADD | IP20180070 |  |  |  | Improve safety along KY 70 from Taylor County line to Bee Lee Road | Reconstruction | Casey | 023-KY-0070 -000 | 0 | 10.4 | 10.4 | Local Roadway Improvements | 3 |  | 0 |  | 5000000 | 2018 | 12500000 | 2021 | 10400000 | 2023 | 35000000 | 2025 | 2018-11-27 13:57 | This project is needed because the geometrics of KY 70 between the Taylor County line and Bee Lee Road is in adequate and creates mobility and safety concerns. | The following needs have been identified for this project: 1.) Improve roadway safety, 2.) Improve mobility
Y | 8 | Lake Cumberland ADD | IP20180093 |  |  |  | Improve the existing city and county routes by widening and extending. This improvement with improve connectivity and will relieve some congestion on US 127 during peak traffic volumes. | New Route | Russell | 104-CS-2098 -000 | 0 | 0.453 | 0.453 | Construct Road in New Location | 0 |  | 0 |  | 500000 | 2020 | 750000 | 2021 | 750000 | 2021 | 2000000 | 2022 | 2018-12-18 09:35 | Improve the existing city and county routes by widening and extending. This improvement with improve connectivity and will relieve some congestion on US 127 during peak traffic volumes. | The following needs have been identified for this project: 1) Improve roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 8 | Cumberland Valley ADD | IP20190031 |  |  |  | Address safety, mobility, and congestion with access management along US-25 (Richmond Street) from the US-25/US-461 Intersection to I-75. | Major Widening | Rockcastle | 102-US-0025 -000 | 15.116 | 15.666 | 0.55 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 800000 | 2020 | 1000000 | 2021 | 1000000 | 2022 | 4500000 | 2023 | 2019-02-25 15:58 | Address safety, mobility, and congestion with access management along US-25 (Richmond Street) from the US-25/US-461 Intersection to I-75. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and increase Capacity for all vehicle types.
Y | 8 | Cumberland Valley ADD | IP20190032 |  |  |  | Planning study on US 25 to address Connectivity for future development in Mt. Vernon on the western side of I-75 between exit 57 and exit 62. | New Route | Rockcastle | 102-US-0025 -000 | 11.893 | 15.666 | 3.773 | Construct Road in New Location | 0 |  | 250000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-22 10:37 | Planning study on US 25 to address Connectivity for future development in Mt. Vernon on the western side of I-75 between exit 57 and exit 62. This area has been a recent growth corridor for Rockcastle County. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity, 3) Provide Connectivity.
Y | 8 | Lake Cumberland ADD | IP20190036 |  |  |  | Improve safety by constructing multiple turning lanes into Community Park Road and Whitley City Elementary School. | Minor Widening | McCreary | 074-US-0027 -000 | 10.9 | 12 | 1.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 | 2020 | 650000 | 2021 | 900000 | 2022 | 3000000 | 2023 | 2019-02-25 15:46 | Improve safety by constructing multiple turning lanes into Community Park Road and Whitley City Elementary School. | The following needs have been identified for this project: 1)Improve Roadway Safety. 2) Improve Mobility
Y | 8 | Cumberland Valley ADD | IP20190069 |  |  |  | Planning study on US 25 to address access management for future development in Mt. Vernon along US 25 Between KY 461/US 25 intersection to I-75 NB on ramp/US 25 intersection. | Major Widening | Rockcastle | 102-US-0025 -000 | 15.018 | 15.91 | 0.892 | Major Widening-Rural Mutilane | 34 |  | 250000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-25 16:01 | Planning study on US 25 to address access management for future development in Mt. Vernon along US 25 Between KY 461/US 25 intersection to I-75 NB on ramp/US 25 intersection. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and increase Capacity for all vehicle types.
Y | 8 | Bluegrass ADD | IP20190071 |  |  |  | Preliminary Engineering Study for Improving Safety and Access Control Alternates from Danville to Stanford. | Spot Improvement | Lincoln | 069-US-0150 -000 | 0 | 5.467 | 5.467 | Other Improvement Types | 0 |  | 250000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-27 10:05 | Preliminary Engineering Study for Improving Safety and Access Control Alternates from Danville to Stanford. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Mobility.
Y | 8 | Lake Cumberland ADD | IP20190096 |  |  |  | Improve safety and mobility along KY 829 by improving the geometrics for future marina development. | Spot Improvement | Clinton | 027-KY-0829 -000 | 1 | 1.8 | 0.8 | Local Roadway Improvements | 3 |  | 0 |  | 450000 | 2020 | 75000 | 2021 | 75000 | 2021 | 1500000 | 2022 | 2019-02-27 08:32 | Improve safety and mobility along KY 829 by improving the geometrics for future marina development. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility for all types of vehicles.
Y | 8 | Lake Cumberland ADD | IP20190146 |  |  |  | Improve safety and mobility along KY 55 by relocating KY 55 near KY 704 and relocating to KY 55 bypass. | Relocation | Adair | 001-KY-0055 -000 | 9.1 | 10.1 | 1 | Construct Road in New Location | 0 |  | 0 |  | 750000 | 2020 | 225000 | 2021 | 175000 | 2022 | 4500000 | 2023 | 2019-02-27 13:29 | Improve safety and mobility along KY 55 by relocating KY 55 near KY 704 and relocating to KY 55 bypass. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility
Y | 8 | Lake Cumberland ADD | IP20190149 |  |  |  | Address safety, capacity and access issues along KY-461 from 0.28 mile south of Buck Creek extending northerly to Pulaski/Rockcastle Line. | Major Widening | Pulaski | 100-KY-0461 -000 | 3.55 | 8.441 | 4.891 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 2500000 | 2020 | 4800000 | 2022 | 4000000 | 2024 | 20000000 | 2026 | 2019-02-27 13:42 | Address safety, capacity and access issues along KY-461 from 0.28 mile south of Buck Creek extending northerly to Pulaski/Rockcastle Line. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 8 | Cumberland Valley ADD | IP20190150 |  |  |  | Address safety, capacity and access issues along KY-461 from Pulaski/Rockcastle County Line to KY 1250. | Major Widening | Rockcastle | 102-KY-0461 -000 | 0 | 4.213 | 4.213 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 2000000 | 2020 | 4800000 | 2022 | 4000000 | 2024 | 16000000 | 2026 | 2019-02-27 13:47 | Address safety, capacity and access issues along KY-461 from Pulaski/Rockcastle County Line to KY 1250. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 8 | Cumberland Valley ADD | IP20190151 |  |  |  | Address safety, capacity and access issues along KY-461 from KY 1250 to US 150. | Major Widening | Rockcastle | 102-KY-0461 -000 | 4.213 | 6.998 | 2.785 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 1500000 | 2020 | 3600000 | 2022 | 3000000 | 2024 | 14000000 | 2026 | 2019-02-27 13:53 | Address safety, capacity and access issues along KY-461 from KY 1250 to US 150. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity
Y | 8 | Lake Cumberland ADD | IP20190161 |  |  |  | Improve the existing route, CS-2078 (Progress Drive) and CS-2067 (Brian Walters Drive), by widening and extending them to join. This improvement with improve connectivity and will relieve some congestion on US 127 during peak traffic volumes. | New Route | Russell | 104-CS-2078 -000 | 0 | 0.531 | 0.531 | Construct Road in New Location | 0 |  | 0 |  | 450000 | 2020 | 750000 | 2021 | 600000 | 2021 | 1750000 | 2022 | 2019-03-01 09:49 | Improve the existing route, CS-2078 (Progress Drive) and CS-2067 (Brian Walters Drive), by widening and extending them to join. This improvement with improve connectivity and will relieve some congestion on US 127 during peak traffic volumes. | The following needs have been identified for this project: 1) Improve roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 8 | Lake Cumberland ADD | IP20190162 |  |  |  | Preliminary Engineering Study for Improving Safety, Increase Mobility and Capacity from US 127X/Clear Springs Rd to KY 80. | Major Widening | Russell | 104-US-0127 -000 | 14.142 | 18.902 | 4.76 | Major Widening-Urban Streets | 25 |  | 250000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-01 10:32 | Preliminary Engineering Study for Improving Safety, Increase Mobility and Capacity from US 127X/Clear Springs Rd to KY 80. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all Vehicles.
Y | 8 | Lake Cumberland ADD | IP20190165 |  |  |  | Improve the existing route, CS-2098 (Erik Ln), by widening and extending it to connect to KY 1381 (Voils Road). This improvement with improve connectivity and will relieve some congestion on US 127 during peak traffic volumes. | New Route | Russell | 104-CS-2098 -000 | 0 | 0.453 | 0.453 | Construct Road in New Location | 0 |  | 0 |  | 500000 | 2020 | 750000 | 2021 | 500000 | 2022 | 2500000 | 2023 | 2019-03-01 10:41 | Improve the existing route, CS-2098 (Erik Ln), by widening and extending it to connect to KY 1381 (Voils Road). This improvement with improve connectivity and will relieve some congestion on US 127 during peak traffic volumes. | The following needs have been identified for this project: 1) Improve roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
Y | 9 | Gateway ADD | IP20000070 |  |  |  | Improve safety on KY 36 from Prickley Ash Bridge to the intersection of US 60. | Reconstruction | Bath | 006-KY-0036 -000 | 11.283 | 11.847 | 0.564 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 500000 |  | 350000 |  | 3000000 |  | 2013-06-05 09:55 | The purpose of this project is to improve safety. | The following needs have been identified for this project: 1) improve safety; and 2) improve pavement conditions.
Y | 9 | Gateway ADD | IP20000071 |  |  |  | Improve system connectivity, geometry, and safety on KY 36 from 0.5 mile east of KY 965 to 1.0 mile west of Olympia at Elk Lick Road. | Reconstruction | Bath | 006-KY-0036 -000 | 17.6 | 18.719 | 1.119 | Modernize Roadway-Rural | 26 |  | 125000 |  | 750000 |  | 1000000 |  | 1000000 |  | 10000000 |  | 2013-06-05 10:14 | The purpose of this project is to improve: system connectivity, geometry, and safety. | The following needs have been identified for this project: 1) improve highways connecting other counties; 2) improve safety; and 3) improve horizontal alignment.
Y | 9 | Buffalo Trace ADD | IP20000072 |  |  |  | This project is designed to create a left turn lane on KY9 at the BP Truck stop that is located to the west of Maysville on KY 9 (AA) near Slack Pike Road. | Safety-Haz-Elm | Mason | 081-KY-0009 -000 | 12.7 | 13.1 | 0.4 | Other Improvement Types | 0 | Y | 0 |  | 50000 |  | 10000 |  | 30000 |  | 500000 |  | 2014-08-20 14:15 | To improve safety. | AA Highway-construct left turn lanes into BP Truck stop there are several accidents that occur on an annual basis at this intersection which can become extremely busy with truck and automobile traffic during certain times of the day and night. This truck
Y | 9 | Bluegrass ADD | IP20000073 |  |  |  | MAJOR WIDENING TO 4 LANES FROM MILLERSBURG BYPASS TO KY 32 AT CARLISLE (SECTION 3). SEE JUNE, 1998 ADVANCE PLANNING STUDY. | Major Widening | Nicholas | 091-US-0068 -000 | 1.014 | 4.841 | 3.827 | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 16000000 |  | 2014-08-20 14:25 | To widen Millersburg bypass to KY 32 at Carlisle (Section 3) to 4 lanes in order to address safety concerns. For more information, see June, 1998 Advance Planning Study. | Current and projected ADT, particuarly trucks indicate future capacity and congestion along US 68 between Carlisle and Millersburg. Narrow shoulders contribute to safety concerns. Project is part of upgrade of the Lexington to Maysville corridor.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20040035 |  |  |  | Improve Riverside Drive (CS-5009) to provide access to airport and to prevent flooding between the cities of Wurtland and Worthington. | Reconstruction | Greenup | 045-CS-5009 -000 | 0 | 1.318 | 1.318 | Other Improvement Types | 0 |  | 300000 |  | 2000000 |  | 7500000 |  | 3000000 |  | 20000000 |  | 2013-06-12 11:33 | The purpose of this project is to improve Riverside Drive (CS-5009) to provide access to airport and to prevent flooding between the cities of Wurtland and Worthington. | CS-5009 between MP 0.0 and MP 1.318 is known to flood during excess rainfall and melting snow which prohibits emergency vehicles to respond to calls from the airport and the neighborhood. Measures need to be taken to access for emergency vehicles, the ai
Y | 9 | Buffalo Trace ADD | IP20040042 |  |  |  | Correct horizontal deficiencies on KY32 beginning 0.4 miles E of Ward Elementary School and ending 0.6 miles west of KY 1013 to improve sight distance restrictions, operational efficiency and overall driver safety. | Reconstruction | Fleming | 035-KY-0032 -000 | 24.7 | 25.3 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 405000 |  | 350000 |  | 3000000 |  | 2013-06-12 11:23 | To improve safety | This segment of KY32 beginning at 0.4 miles east of Ward Elementary to 0.6 miles West of KY 1013 contains a severe curve that restricts sight distance for traveling motorists. The area is more heavily traveled by large vehicles (buses, delivery trucks an
Y | 9 | Buffalo Trace ADD | IP20050014 |  |  |  | Improve visibility and safety on KY 32 in Fleming County from Indian Creek BR (MP 25.30) to .04 mile West of the Rowan C/L (MP 27.9)by correcting horizontal and vertical alignment deficiencies. This route is a major link from Maysville to Morehead and | Reconstruction | Fleming | 035-KY-0032 -000 | 25.3 | 27.9 | 2.6 | Other Improvement Types | 0 |  | 224000 |  | 1500000 |  | 5000000 |  | 1300000 |  | 13000000 |  | 2013-06-12 10:46 | To improve safety and mobility | KY32 is a thoroughfare for individuals traveling to employment opportunities in both Rowan and Fleming counties. Also, there are many travelers to Morehead State University on this route. The segment of KY32 is curvy and going uphill toward the county l
Y | 9 | Buffalo Trace ADD | IP20050015 |  |  |  | Improve geometric deficiencies of curves on KY 32 in Fleming County from Goddard Covered Bridge (MP 18.50) to Indian Creek Bridge (MP 25.30) | Reconstruction | Fleming | 035-KY-0032 -000 | 18.5 | 25.3 | 6.8 | Other Improvement Types | 0 |  | 200000 |  | 3500000 |  | 5000000 |  | 3400000 |  | 34000000 |  | 2013-06-12 11:29 | To improve safety and mobility. | The segment of KY32 joins the previously listed project of 09 035 D0032 54.00. The characteristics of the project are very similar in nature. The traffic on the route flows to and from industry and employment opportunity as well as Morehead State Univer
Y | 9 | Buffalo Trace ADD | IP20050016 |  |  |  | RECONSTRUCTION FROM ROWAN C\L TO VANCEBURG. SEE ROWAN CO. KY 377 LISTING FOR CONTINUATION OF ROUTE RECONSTRUCTION NEED TO MOREHEAD. | Reconstruction | Lewis | 068-KY-0377 -000 | 0 | 8.555 | 8.555 | Other Improvement Types | 0 |  | 200000 |  | 7560000 |  | 19440000 |  | 12960000 |  | 68040000 |  | 2010-02-25 16:51 | To improve safety and mobility | There is an apparent need to improve N-S systems connectivity between the cities of Vanceburg in Lewis County and Morehead in Rowan County. There is a high number of Lewis County residents that commute to Rowan County for employment, education and recrea
Y | 9 | Bluegrass ADD | IP20050017 |  |  |  | WIDENING FROM 0.5 MI S OF NICHOLAS\FLEMING C\L TO 1.0 MI N OF NICHOLAS\FLEMING C\L | Reconstruction | Nicholas | 091-KY-0032 -000 | 17.362 | 17.862 | 0.5 | Other Improvement Types | 0 |  | 50000 |  | 825000 |  | 1350000 |  | 900000 |  | 6000000 |  | 2010-02-25 16:51 | Widening of from 0.5 MI S of Nicholas/Fleming C/L to 1.0 MI N of Nicholas/Fleming C/L in order to address safety concerns, including: substandard curves, lack of shoulders and poor geometrics. | KY 32 is a main route for motorists traveling from Flemingsburg to Lexington via KY 32, US 68 and US 27. Existing KY 32 from Carlisle (MP 8.8-17.873) to Flemingsburg (0.0-10.60) is a rural, narrow (2-9ft lane), very winding roadway with no usable shoulder
Y | 9 | Bluegrass ADD | IP20050018 |  |  |  | CARLISLE SOUTHERN BYPASS - RELOCATE KY 36 FROM KY 13 SW OF CARLISLE TO APPROX. 1.0 MI W OF WHETSTONE RD (2 LANE ON 4 LANE R\W). SEE SEGMENT 2 IN JUNE 1999 CORRIDOR PLANNING STUDY. | Relocation | Nicholas | 091-KY-0036 -000 | 3.283 | 5.726 | 2.443 | Other Improvement Types | 0 |  | 70000 |  | 1500000 |  | 2000000 |  | 1000000 |  | 12500000 |  | 2013-06-13 08:57 | To relocate KY 36 from KY 13 SW of Carlisle approx. 1.0 MI West of Whetstone Rd; 2 lane on 4 lane R\W. For more information, see segment 2 in June 1999 Corridor Planning Study. | IRI indicates possible pavement issues. Alignment of 3 in some sections indicate unsafe curves at prevailing speeds. Additionally, narrow shoulders are a safety concern. 2025 Level of Service is projected to be C. Project is part of corridor between US 6
Y | 9 | Huntington-Ashland-Ironton MPO | IP20050031 |  |  |  | Provide safer access to US-23 via KY-67 beginning at KY-503 (MP 8.0) near Wurtland extending to KY-67 (Industrial Parkway). | New Route | Greenup | 045-KY-0503 -000 | 8 | 9 | 1 | Other Improvement Types | 0 |  | 150000 |  | 1000000 |  | 1500000 |  | 1000000 |  | 7000000 |  | 2013-06-12 11:55 | Provide safer access to US-23 via KY-67 beginning at KY-503 (MP 8.0) near Wurtland extending to KY-67 (Industrial Parkway). | KY-503 between MP8.0 and MP 9.0 has a history of landslide problems. A folder containing info. on these slides exists in D9 Division of Design dating back to 1993. Landslide problems were originally to be addressed in SYP Project # 09-5001.00. Geotechni
Y | 9 | Buffalo Trace ADD | IP20060254 |  |  |  | Correct geometric and width deficiencies on this segment of KY 57 begins 1.0 mile north of the Fleming County Courthouse (MP 0.800) and extends to the approximate intersection of the new Flemingsburg bypass extension (MP 1.500) to improve operational effi | Reconstruction | Fleming | 035-KY-0057X -000 | 0.8 | 1.5 | 0.7 | Other Improvement Types | 0 |  | 150000 |  | 650000 |  | 1200000 |  | 825000 |  | 4300000 |  | 2013-06-12 10:43 | To improve safety and mobility. | KY 57 provides direct access to KY 9 (AA Highway) from Flemingsburg to Tollesboro in Lewis County. This project is one of three segments of KY 57. (2 in Fleming Co., 1 in Lewis Co.) This segment of KY 57 begins 1.0 mile north of the Fleming
Y | 9 | Buffalo Trace ADD | IP20060255 |  |  |  | Increase capacity and decrease conflict points on KY 9 from the Lewis County Line, MP 0.00 to existing 4 lanes near KY 11 (MP 7.60) to support 2025 traffic volumes, address sight distance concerns, improve intersection safety and reduce speed differentia | Major Widening | Mason | 081-KY-0009 -000 | 0 | 7.56 | 7.56 | Other Improvement Types | 0 | Y | 0 |  | 5184000 |  | 8360000 |  | 2592000 |  | 46980000 |  | 2010-02-25 16:51 | Improve mobility. | Existing KY 9 will not provide adequate capacity for projected design year 2025 traffic volumes, the number of vehicle crashes at intersections is relatively high, existing roadway geometry restricts sight distance in numerous locations and speed dif
Y | 9 | Buffalo Trace ADD | IP20060256 |  |  |  | Increase capacity and decrease conflict points on KY 9 from the New Maysville Bridge (MP 10.26), west to KY435 (MP 14.987) to support 2025 traffic volumes, address sight distance concerns, improve intersection safety and reduce speed differentials. | Major Widening | Mason | 081-KY-0009 -000 | 10.26 | 14.93 | 4.67 | Other Improvement Types | 0 | Y | 0 |  | 1300000 |  | 1600000 |  | 2300000 |  | 9400000 |  | 2014-08-20 14:08 | Improve mobility | Existing KY 9 will not provide adequate capacity for projected design year 2025 traffic volumes, the number of vehicle crashes at intersections is relatively high, existing roadway geometry restricts sight distance in numerous locations and speed dif
Y | 9 | Buffalo Trace ADD | IP20060257 |  |  |  | Correct width deficiencies, improve ped and bike usability, and improve operational efficiency of KY 1448 from US 68 (MP 5.423) to KY 9 (MP 7.00) This project is in the HWY plan as 9-8303.00 with the D Phase (800K)funded with SPB. R-2010 $2,500,000 SP | Major Widening | Mason | 081-KY-1448 -000 | 5.423 | 7.003 | 1.58 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 2500000 |  | 1000000 |  | 10000000 |  | 2014-08-20 13:44 |  | This segment of KY 1448 is a narrow 2 lane roadway with no usable shoulders (9 ft driving lanes). It serves as a thorough fare from KY 9 to US 68/62. There are several residential houses located along the route as well as a Boys & Girls Club on the KY
Y | 9 | Gateway ADD | IP20060258 |  |  |  | Improve safety and congestion on US 60 from the intersection of KY 799 to the intersection of KY 174 at Hayes Crossing. | Reconstruction | Rowan | 103-US-0060 -000 | 12.8 | 14.58 | 1.78 | Modernize Roadway-Rural | 26 |  | 200000 |  | 1000000 |  | 2500000 |  | 1100000 |  | 9000000 |  | 2015-03-10 16:07 | The purpose of this project is to improve safety and congestion. | The following needs have been identified for this project: 1)improve safety; and 2) primary access route into Morehead from the east and used by large trucks to detour the scales on I 64.
Y | 9 | Gateway ADD | IP20070243 |  |  |  | Improve safety and geometry on US 60 beginning near the Lakeside Christian Academy entrance (MP 5.45) and extending eastward into the 3-lane section of the Morehead bypass (MP 7.050) to provide improved access into the City of Morehead from the West (KY 5 | Reconstruction | Rowan | 103-US-0060 -000 | 5.45 | 7.05 | 1.6 | Modernize Roadway-Rural | 26 |  | 50000 |  | 1000000 |  | 8000000 |  | 1750000 |  | 10000000 |  | 2017-05-01 14:42 | The purpose of this project is to improve safety, correct geometric deficiencies, and enhance connectivity. | The following needs have been identified for this project: 1) improve safety; 2) correct geometric deficiencies; 3) provide improved access into the City of Morehead from the west (KY 519); and 4) this route draws boat/recreation traffic to and from Cave | 9 | East | 46.0269 | 6.9102 | 10.9581 | 10.4641 | 1.1078 | 8.9222 | 0 | 7.6647 | 46
Y | 9 | Gateway ADD | IP20080508 |  |  |  | Improve safety and sight-distance on US 60 between Milepoints 11.1 and 11.2, west of KY 965. | Spot Improvement | Bath | 006-US-0060 -000 | 11.1 | 11.2 | 0.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 100000 |  | 100000 |  | 500000 |  | 2017-05-01 08:19 | The purpose of this project is to improve: safety and sight-distance. | The following needs have been identified for this project: 1) Improve Roadway Safety, and 2) Improve Sight-Distance. | 9 | East | 12.1796 | 4.6946 | 3.4132 | 0 | 1.3174 | 0 | 0 | 2.7545 | 12
Y | 9 | Gateway ADD | IP20080509 |  |  |  | Improve safety and geometrics on KY 36 from slightly north of Tunnel Hill Rd to Prickley Ash Bridge. | Spot Improvement | Bath | 006-KY-0036 -000 | 10.3 | 11.25 | 0.95 | Modernize Roadway-Rural | 26 |  | 50000 |  | 750000 |  | 850000 |  | 600000 |  | 6500000 |  | 2017-05-01 08:27 | The purpose of this project is to improve: safety and geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety , 2) Improve Insufficient Lane, Shoulder, and Ditch Widths, 3) Correct Horizontal Curve, 4) Improve Drainage, and 4) Improve Stopping and Passing Distances. | GATEWAY ADD | East | 19.5689 | 2.3234 | 4.3114 | 3.9521 | 2.8144 | 0 | 0 | 6.1677 | 20
Y | 9 | Gateway ADD | IP20080510 |  |  |  | Improve safety and correct geometric and capacity deficiencies on KY 36 from the intersection of KY1325 (MP 7.0) to the intersection of US 60 in Owingsville (MP 11.847). | Reconstruction | Bath | 006-KY-0036 -000 | 6.97 | 11.847 | 4.877 | Modernize Roadway-Rural | 26 |  | 386000 | 2020 | 2385000 | 2021 | 3135000 | 2022 | 1300000 | 2022 | 26265000 | 2023 | 2019-03-05 14:41 | The purpose of this project is to: improve safety, correct geometric deficiencies, and correct capacity deficiencies. | The following needs have been identified for this project: 1) improve safety; 2) correct geometric deficiencies, and 3) correct capacity deficiencies.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080512 |  |  |  | Improve operational efficiency on Segment 2 of KY-168 from From US-60 (MP 5.8) to Hood Creek Road (MP 7.4) in Ashland to decrease congestion, conflict points with turning vehicles, rear-end collisions and allow for freer traffic flow. | Minor Widening | Boyd | 010-KY-0168 -000 | 5.804 | 7.458 | 1.654 | Other Improvement Types | 0 |  | 0 |  | 560000 |  | 1440000 |  | 960000 |  | 5040000 |  | 2010-02-25 16:51 | Improve operational efficiency on Segment 2 of KY-168 from From US-60 (MP 5.8) to Hood Creek Road (MP 7.4) in Ashland to decrease congestion, conflict points with turning vehicles, rear-end collisions and allow for freer traffic flow. | THIS IS SEGMENT 2 OF 3 PROPOSED FOR KY-168. Segment 2 (09 010 D0168 21.00) – From US-60 (MP 5.8) to Hood Creek Road (MP 7.4) in Ashland. KY-168 is an urban, 2-lane neighborhood route with curb and gutter and sidewalks. The route is lined with houses
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080513 |  |  |  | Improve operational efficiency on Segment 3 of KY-168 from Hoods Creek Road (MP 7.458) to US-23 (MP 8.179) to decrease congestion, conflict points with turning vehicles, rear-end collisions and allow for a freer flow of traffic. | Minor Widening | Boyd | 010-KY-0168 -000 | 7.458 | 8.179 | 0.721 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1000000 |  | 500000 |  | 3500000 |  | 2017-05-01 08:35 | Improve operational efficiency on Segment 3 of KY-168 from Hoods Creek Road (MP 7.458) to US-23 (MP 8.179) to decrease congestion, conflict points with turning vehicles, rear-end collisions and allow for a freer flow of traffic. | THIS IS SEGMENT 3 OF 3 PROPOSED FOR KY-168. (Control No. 09 010 D0168 22.00) - from Hoods Creek Road (MP 7.458) to US-23 (MP 8.179). KY-168 is an urban, 2-lane neighborhood route with curb and gutter and sidewalks. The route is lined with houses which | Huntington/KYOVA MPO | East | 39.9147 | 8.7545 | 11.497 | 11.6093 | 2.6647 | 0 | 0 | 5.3892 | 40
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080514 |  |  |  | Improve intersection sight distance at South Belmont Street (KY 1012) MP 3.871 near Ashland | Safety-Haz-Elm | Boyd | 010-KY-0168 -000 | 3.871 | 3.971 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 250000 |  | 100000 |  | 500000 |  | 2013-06-05 10:26 | Improve intersection sight distance at South Belmont Street (KY 1012) MP 3.871 near Ashland | The junction of KY-1012 (S. Belmont Street) and KY-168 is a "T" intersection. It is located in a very populationd area and sight distance is restricted at this intersection. The limited sight distance needs to be addressed to provide for a safer, more e
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080515 |  |  |  | Improve operational efficiency on Segment 1 of KY 168 from KY 1012 (S. Belmont Street, MP 3.871) to US 60 (MP 5.804) to decrease congestion, conflict points with turning vehicles, rear-end collisions and allow for a freer flow of traffic. (End MP r | Minor Widening | Boyd | 010-KY-0168 -000 | 3.871 | 5.804 | 1.933 | Other Improvement Types | 0 |  | 300000 |  | 1000000 |  | 2700000 |  | 2000000 |  | 9300000 |  | 2010-02-25 16:51 | Improve operational efficiency on Segment 1 of KY 168 from KY 1012 (S. Belmont Street, MP 3.871) to US 60 (MP 5.804) to decrease congestion, conflict points with turning vehicles, rear-end collisions and allow for a freer flow of traffic. | THIS IS SEGMENT 1 OF 3 PROPOSED FOR KY-168. (Control No. 09 010 D0168 24.00) - From KY-1012 (S. Belmont Street, MP 3.871) to Hurrican Fork Bridge (MP 6.830). KY-168 is an urban, 2-lane neighborhood route with curb and gutter and sidewalks. The route i
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080516 |  |  |  | Correct geometric and width deficiencies on KY-1937 from KY-707 in Lawrence County (2.074 miles) to KY-3 at Mavity (MP 6.726) | Major Widening | Boyd | 010-KY-1937 -000 | 0 | 6.726 | 6.726 | Other Improvement Types | 0 |  | 0 |  | 3080000 |  | 7920000 |  | 5280000 |  | 43000000 |  | 2013-06-05 10:56 | Correct geometric and width deficiencies on KY-1937 from KY-707 in Lawrence County (2.074 miles) to KY-3 at Mavity (MP 6.726) | KY-1937 begins in Lawrence County as a very narrow (almost one-lane) very rural, very curvy road. The pavement is in extremely poor condition and the road winds around a hillside. Slips and broken pavement are evident in this section. Centerline stripi
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080517 |  |  |  | Improve width deficiencies on KY-1945 from KY-773 (MP 0.0) to KY-854 (MP 3.91) to increase safety for motorists meeting traffic traveling in the opposite direction. | Minor Widening | Boyd | 010-KY-1945 -000 | 0 | 3.91 | 3.91 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 5000000 |  | 1500000 |  | 20000000 |  | 2013-06-05 11:27 | Improve width deficiencies on KY-1945 from KY-773 (MP 0.0) to KY-854 (MP 3.91) to increase safety for motorists meeting traffic traveling in the opposite direction. | KY-1945 is a very rural, very narrow, curvy country road. Traffic meeting on-coming vehicles must almost completely stop to pass safely. KY-1945 is sparsely populated and makes several creek crossings with the creek running parallel either right or left
Y | 9 | FIVCO ADD | IP20080518 |  |  |  | Provide a western I-64 access to Grayson (MP 168) to alleviate traffic congestion and decrease collision on existing routes and encourage economic development and growth for the City of Grayson. | New Interchange | Carter | 022-I -0064 -000 | 168.512 | 168.612 | 0.1 | Other Improvement Types | 0 | Y | 150000 |  | 3000000 |  | 1500000 |  | 2000000 |  | 25000000 |  | 2011-02-28 20:02 |  | The City of Grayson has only one I-64 access (EXIT 172). With it's ADT increassing from 15900 to 16600 in just two years and it's CRF moving into a significantly statistical crash problem (.77 to 1.26), this limited access to the city has resulted in KY 1
Y | 9 | FIVCO ADD | IP20080519 |  |  |  | Improve US 60 geometry beginning at the termini of new construction at Olive Hill (MP 12.4) (Item No. 9-159.00) extending 1.1 miles to the I-64 Exit 161 to improve systems connectivity and increase operational efficiency of the route. | Reconstruction | Carter | 022-US-0060 -000 | 12.1 | 13.3 | 1.2 | Modernize Roadway-Rural | 26 |  | 80000 |  | 1650000 |  | 2750000 |  | 2300000 |  | 7500000 |  | 2017-05-01 13:48 |  | This segment of US 60 consists of 2-11' driving lanes with narrow shoulders and has shown an increase in ADT. There are both horizontal and vertical deficiencies throughout resulting in decreased sight distance and inefficient traffic flow, which is empha | FIVCO ADD | East | 79.0793 | 8.8024 | 9.3413 | 7.7021 | 2.1257 | 8.982 | 3.9222 | 8.2036 | 49 | 15 | 15
Y | 9 | FIVCO ADD | IP20080520 |  |  |  | Correct inadequate drainage and improve safety on KY 1 from MP 8.0 @ Robin Run to MP 9.0 near Damron Branch. | Reconstruction | Carter | 022-KY-0001 -000 | 8 | 9 | 1 | Other Improvement Types | 0 |  | 0 |  | 450000 |  | 375000 |  | 250000 |  | 3500000 |  | 2013-06-12 10:03 |  | KY1 between MP8 Robin Run Road and MP9 Damron Branch Road tends to flood due to inadequate drainage. The environmental map indicates it is also in a Zone 1 and a Wetland area is located near the roadway. Also the CRF has increased, indicating a accident
Y | 9 | FIVCO ADD | IP20080521 |  |  |  | Improve for safety and better accessibility for delivery and passenger vehicles. | Reconstruction | Carter | 022-KY-0001 -000 | 11.502 | 16.52 | 5.018 | Other Improvement Types | 0 |  | 250000 |  | 3000000 |  | 4000000 |  | 2500000 |  | 25000000 |  | 2013-06-18 14:43 |  | The Carter County portion of this Project is rural and within the ADD region. The portion of this project from MP-0 to MP11.502 is in the Ashland Area MPO in Greenup County. The statistics indicate both good and bad stretches of highway with safety issu
Y | 9 | FIVCO ADD | IP20080522 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 1 from the Lawrence Co Line (MP 0.0) to US 60 in Grayson (MP 10.6) to improve safety, sight distances, systems connectivity, and operational efficiency, and southern access into Grayson for area re | Reconstruction | Carter | 022-KY-0001 -000 | 0 | 10.646 | 10.646 | Other Improvement Types | 0 |  | 585000 |  | 7137000 |  | 16960000 |  | 4095000 |  | 68210000 |  | 2010-06-14 09:47 |  | Existing KY1 from the Lawrence County Line (mp0.0) to US 60 in Grayson (mp10.6)is a very rural, winding, narrow (10')2-lane roadway with no usable shoulders(2'). The high ride ability index (IRI)number moving from a low of 85 to 136 indicates that KY-1 c
Y | 9 | FIVCO ADD | IP20080524 |  |  |  | Correct horizontal and width deficiencies on KY 2 from 0.3 mi S of Smokey Ck. (MP 5.0) to KY 474 (MP 12.6) near Carter City. | Major Widening | Carter | 022-KY-0002 -000 | 5.026 | 12.592 | 7.566 | Other Improvement Types | 0 |  | 216000 |  | 2808000 |  | 7480000 |  | 4968000 |  | 38000000 |  | 2013-06-05 13:21 |  | This segment of KY2 begins 0.3 miles S of Smokey Creek (MP5) and extends to KY474 MP12.6 near Carter City. This segment has 2-12' lanes with 2' shoulders and it carries large trucks going to and leaving from a rock quarry located on the route. Several c
Y | 9 | FIVCO ADD | IP20080525 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 7 from the Elliott Co. Line (MP 0.0) to KY 1496 (MP 4.8) to improve access and systems connectivity between Grayson and Sandy Hook, increase efficiency of route and enhance economic growth in area | Major Widening | Carter | 022-KY-0007 -000 | 0 | 4.789 | 4.789 | Other Improvement Types | 0 |  | 350000 |  | 3650000 |  | 5000000 |  | 3000000 |  | 20000000 |  | 2011-03-04 10:19 |  | Existing KY 7 from the Elliott County Line (MP 0.0) to KY 1496 (MP4.8)is a narrow (11'driving lane) 2-lane roadway with narrow 3ft shoulders. KY7 is currently used by residents, tourists, commercial users and others for access to I-64, Grayson Lake and a
Y | 9 | FIVCO ADD | IP20080526 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 7 KY 1496 (MP 4.8) to KY 1661 (MP 9.2) to improve access and systems connectivity between Grayson and Sandy Hook, increase efficiency of route and enhance economic growth in area. | Major Widening | Carter | 022-KY-0007 -000 | 4.789 | 9.157 | 4.368 | Other Improvement Types | 0 |  | 175000 |  | 3000000 |  | 5000000 |  | 2500000 |  | 22000000 |  | 2013-06-05 11:34 |  | This road segment is a continuation of 09 022 D0007 41.00 and reflects the same problems in the second half of it's length as the first half. Existing KY 7 from KY1496 (mp 4.8)to KY1661 (MP 9.2) is a 2-lane roadway consisting of 11' driving lanes and 12'
Y | 9 | FIVCO ADD | IP20080527 |  |  |  | Correct geometric and width deficiencies on KY 7 from KY 1661 (MP 9.2) to and including the Little Sandy Bridge (MP 10.3) to improve access and systems connectivity between Grayson and Sandy Hook, increase efficiency of route and enhance economic growth | Major Widening | Carter | 022-KY-0007 -000 | 9.157 | 10.296 | 1.139 | Other Improvement Types | 0 |  | 0 |  | 1250000 |  | 2000000 |  | 1500000 |  | 4750000 |  | 2011-03-04 10:42 |  | Existing KY7 from KY1661(mp9.2) to the existing 4 lane section in Grayson(including the Bridge over the little sandy River - mp 10.3)is a 2-lane roadway consisting of 11' driving lanes and a 12' unpaved shoulders. KY7 is currently used by local residents
Y | 9 | FIVCO ADD | IP20080528 |  |  |  | Relieve traffic congestion and improve operational efficiency of KY 9 beginning at KY 1 in Grayson (MP 0.0) and ending at the Lewis County Line (MP 18.3). | Major Widening | Carter | 022-KY-0009 -000 | 0 | 18.262 | 18.262 | Other Improvement Types | 0 | Y | 216000 |  | 11232000 |  | 29480000 |  | 18360000 |  | 101528000 |  | 2010-02-25 16:51 |  | KY9 in its entirety is a main N_S connector from Alexandria, KY to Grayson, KY for the trucking industry as well as passenger car travels. This segment beginning at KY1 in Grayson(MP 0.0)to the Lewis County Line (MP 18.3)is a 2 lane very heavily traveled
Y | 9 | FIVCO ADD | IP20080530 |  |  |  | Complete construction to ultimate 4 lane facility of KY 67 from I-64 in Carter County (MP 0.0) to Wurtland in Greenup County (MP 12.97), a total of 15 miles. | Major Widening | Carter | 022-KY-0067 -000 | 0 | 0.335 | 0.335 | Other Improvement Types | 0 |  | 0 |  | 1350000 |  | 0 |  | 750000 |  | 56160000 |  | 2017-05-01 13:56 |  | Existing KY 67 is currently a 2-lane facility with truck climbing lanes with r/w and roadbeds available for an ultimate construction of 4 lanes. KY67 has become a major connector between US23 and I64 as the ADT reflects. There is an industrial park and | FIVCO ADD | East | 18.2111 | 8.8623 | 0 | 4.5584 | 0 | 0 | 4.7904 | 0 | 18
Y | 9 | FIVCO ADD | IP20080531 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 773 from Coal Camps Road (MP 4.205) to Body Shop Road (MP 5.414) to improve safety and increase sight distance (over Piney Hill). | Major Widening | Carter | 022-KY-0773 -000 | 4.2 | 5.4 | 1.2 | Other Improvement Types | 0 |  | 216000 |  | 702000 |  | 1760000 |  | 1188000 |  | 5940000 |  | 2010-06-23 10:41 |  | Existing KY773 from MP4.205-MP5.414 is a very narrow (10'lanes w/2'shoulders)winding, 2-lane facility with virtually no shoulders. This section of KY773 is very curvy and traverses a hillside known as "Piney Hill". There are numerous horizontal and vert
Y | 9 | FIVCO ADD | IP20080532 |  |  |  | Reconstruct KY 773 from KY 7 (MP 0.00) to KY 1 at Hitchens (MP 3.50) EXCLUDING the replacement of 2-one lane bridges (see Item 9-8506) to correct horizontal, vertical and width deficiencies and to improve operation efficiency, systems connectivity and saf | Reconstruction | Carter | 022-KY-0773 -000 | 0 | 3.505 | 3.505 | Other Improvement Types | 0 |  | 0 |  | 2000000 | 2021 | 2500000 | 2022 | 1750000 | 2023 | 20000000 | 2024 | 2019-03-15 08:52 | Reconstruct KY 773 from KY 7 (MP 0.00) to KY 1 at Hitchens (MP 3.50) EXCLUDING the replacement of 2-one lane bridges (see Item 9-8506) to correct horizontal, vertical and width deficiencies and to improve operation efficiency, systems connectivity and saf | Existing KY 773 is a narrow 2-lane roadway with virtually no shoulders (10'lanes w/2'shoulders). The approach connection with KY 7 (MP0.00) has a sight distance problem involving a 90 degree bend in KY 773. There are two one-lane bridges located within
Y | 9 | FIVCO ADD | IP20080533 |  |  |  | Improve sight distance and correct horizontal deficiencies on KY 955 from MP 6.05 -6.15 over the old RR near the junction with KY 174. | Major Widening | Carter | 022-KY-0955 -000 | 6.05 | 6.15 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 400000 |  | 135000 |  | 1500000 |  | 2013-06-05 11:45 |  | This section of KY955 is in a very severe curve over the old RR near the junction with KY174 causing restricted sight distance for motorists.
Y | 9 | FIVCO ADD | IP20080534 |  |  |  | Geometric improvements on KY 1025 from US 60 (MP 0.0),East of Olive Hill extending North 0.30 miles providing access to West Carter Middle and High Schools and facilities. | Major Widening | Carter | 022-KY-1025 -000 | 0 | 0.3 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 500000 |  | 500000 |  | 2000000 |  | 2017-05-01 14:08 |  | This is the access for both West Carter High School and West Carter Middle School, school related recr fields located on this segment of KY 1025. There is a vertical sight distance deficiency in front of the schools. Large vehicles use this access as wel | 9 | East | 5.1587 | 1.521 | 0 | 1.2126 | 2.4251 | 0 | 0 | 0 | 5
Y | 9 | FIVCO ADD | IP20080535 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 1496 beginning 0.6 miles N of KY 1122 extending west to MP 3.1 (Deer Creek Hill). | Major Widening | Carter | 022-KY-1496 -000 | 2.3 | 3.1 | 0.8 | Other Improvement Types | 0 |  | 216000 |  | 454000 |  | 1210000 |  | 810000 |  | 4050000 |  | 2010-02-25 16:51 |  | Existing KY 1496 ia VERY RURAL VERY NARROW (8'DRIVING LANES 2' SHOULDERS)roadway with no usable shoulder. This segment of KY1496 beginning 0.6 miles north of KY1122 extending west to MP 3.1 is particularly hazardous as it winds around Deer Creek Hill.
Y | 9 | FIVCO ADD | IP20080536 |  |  |  | Improve operational efficiency and provide congestion relief on KY 3297 beginning at Rupert Lane (MP 0.279) extending east to the Bridge over the Little Sandy River (MP 1.634) | Major Widening | Carter | 022-KY-3297 -000 | 0.2 | 1.634 | 1.434 | Other Improvement Types | 0 |  | 75000 |  | 750000 |  | 3000000 |  | 1500000 |  | 7000000 |  | 2013-06-05 13:23 |  | Existing KY3297 is a narrow (11' driving lanes 2' shoulders)roadway with virtually no shoulders. KY 3297 services several major traffic generators along the route including apartment complex, East Carter Middle School, numerous residential houses and sev
Y | 9 | FIVCO ADD | IP20080537 |  |  |  | Correct geometric and width deficiencies on KY 3297 from the Little Sandy River Bridge (MP 1.750) extending to the US 60 intersection (MP 2.932) to improve operational efficiency and systems connectivity. | Major Widening | Carter | 022-KY-3297 -000 | 1.75 | 2.93 | 1.18 | Other Improvement Types | 0 |  | 100000 |  | 750000 |  | 2000000 |  | 1500000 |  | 5000000 |  | 2013-06-05 11:32 |  | Existing KY3297 is a narrow(11'driving lanes) roadway with virtually no shoulders(2'). This segment of KY3297 is a continuation of 09 022 D3297 39.00 and begins at the Little Sandy River Bridge MP1.75 and ends at the junction of US60 mp2.93.
Y | 9 | FIVCO ADD | IP20080538 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 32 from KY 7 at Sandy Hook (MP 8.586) to the Lawrence Co.Line (MP 18.058) to improve operational efficiency, sight distance restrictions, and travel time for the residents of Elliott and Lawrence | Major Widening | Elliott | 032-KY-0032 -000 | 8.656 | 18.047 | 9.391 | Other Improvement Types | 0 |  | 0 |  | 5400000 |  | 14520000 |  | 9360000 |  | 49020000 |  | 2010-02-25 16:51 |  | This segment of KY32 is a very narrow 2-lane roadway with no usable shoulder(9' to 12'lanes, w/2'to 10'shoulders). It is characterized throughout its length by winding, switchback curves, hillsides on one side and steep ravines on the other, poor sight di
Y | 9 | Buffalo Trace ADD | IP20080539 |  |  |  | Improve the sight distance along KY 32 in Fleming County between 0.3 Mi E of KY 111(MP 13.50) to 0.5 Mi W of KY 156 (MP 18.00) | Reconstruction | Fleming | 035-KY-0032 -000 | 13.5 | 18 | 4.5 | Other Improvement Types | 0 |  | 224000 |  | 2000000 |  | 5000000 |  | 2250000 |  | 22500000 |  | 2013-06-12 11:19 | To improve safety. | This project on KY32 references and partners with project numbers 54 and 55 on KY32 in Fleming County. The traffic volumes increase the closer to Flemingsburg as the segments are split in data, but there were no varying CRF factors or other rating inform
Y | 9 | Buffalo Trace ADD | IP20080540 |  |  |  | Increase safety and decrease rear-end crash frequency on KY 32 from MP 14.7-MP 15.3 at the intersection of Asbury Lane (CR 1028A) This project is located in a vertical curve with commercial/residential development along the East side of the project with | Safety-Haz-Elm | Fleming | 035-KY-0032 -000 | 14.7 | 15.3 | 0.6 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 500000 |  | 750000 |  | 1780000 |  | 2015-03-10 16:56 | To improve safety. | There is a Shell Station, Greenbrook Subdivision and two other new businesses on this segment of KY 32-east of Flemingsburg. There has been an increase in the number of crashes, particularly rear end crashes, in the project vicinity. This is not reflect
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080541 |  |  |  | Correct Sight Distance and visibility problems on KY 1 (MP 14.0-14.2), 0.2 miles South of West Hollow Road (KY 2433) | Safety-Haz-Elm | Greenup | 045-KY-0001 -000 | 14 | 14.2 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 100000 |  | 100000 |  | 500000 |  | 2013-06-12 11:54 | Correct Sight Distance and visibility problems on KY 1 (MP 14.0-14.2), 0.2 miles South of West Hollow Road (KY 2433) | KY-1 is an access route from Carter County to US-23 at Greenup. This route is a narrow 2-lane roadway with a winding alignment. This particular segment of KY-1 (MP 14.0 to MP 14.2) is not out of character with the rest of the route. However, there is
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080542 | 9-132 |  | A | RECONSTRUCT KY-2 FROM MP 13.2 TO US-23 (MP 17.2)(08CCN)(14CCR)(16CCR)(18CCN) | PE & ENVIRONMENTAL(O) | Greenup | 045-KY-0002 -000 | 13.165 | 17.188 | 4.023 | Modernize Roadway-Rural | 26 | [5 empty] | 5780000 | 2021 | 3120000 | 2023 | 45000000 | 2024 | 2019-03-08 07:04 | Safety improvements on KY-2 from Little Sandy Bridge to US-23 (MP 13.2 MP 17.2) | KY-2 beginning at the Little Sandy Bridge (MP 13.165) to US-23 (MP 17.188) is a very rural, very curvy 2-lane 9 foot roadway. Shoulder width, if any , is only 2 feet. Portions of the roadway traverse alonside the Little Sandy River with only a guaradrai | Huntington/KYOVA MPO | East | 34.3495 | 5.3054 | 10.1497 | 12.1257 | 3.6826 | 0 | 0 | 3.086 | 34
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080543 |  |  |  | Improve Sight Distance through curve on KY-7 near Allen Church Road (MP 16.30- MP 16.60). | Safety-Haz-Elm | Greenup | 045-KY-0007 -000 | 16.3 | 16.6 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 400000 |  | 200000 |  | 1000000 |  | 2013-06-12 11:42 | Improve Sight Distance through curve on KY-7 near Allen Church Road (MP 16.30- MP 16.60). | Existing KY-7 is a narrow, curvy, 2-lane roadway with no usable shoulders. This segment of KY-7 near Allen Church Road (MP 16.60) consists of an extreme curve that has no visibility and causes a reduction in the prevailing speed limit when encountered.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080544 |  |  |  | Improve KY-244 between the cities of Raceland and Worthington to allow for 2-way traffic to improve emergency vehicle access and to provide a second egress/ingress for the city of Worthington during times of flooding. | Reconstruction | Greenup | 045-KY-0244 -000 | 3.238 | 3.338 | 0.1 | Other Improvement Types | 0 |  | 100000 |  | 2500000 |  | 2000000 |  | 5000000 |  | 25000000 |  | 2013-06-12 11:39 | Improve KY-244 between the cities of Raceland and Worthington to allow for 2-way traffic to improve emergency vehicle access and to provide a second egress/ingress for the city of Worthington during times of flooding. | Exisiting KY-244 between the cities of Raceland and Worthington passes under a one-lane CSX Railroad overpass. The segment of KY-244 through the Railroad Tunnel is subject to flooding. In times of high water this leaves only one means of ingress/egress
Y | 9 | Huntington-Ashland-Ironton MPO | IP20080545 |  |  |  | Correct horizontal, vertical and width deficiencies on KY-750 from Pond Run (MP 0.37) to KY-207 (MP 1.595) to improve safety and operational efficiency of roadway. | Reconstruction | Greenup | 045-KY-0750 -000 | 0.37 | 1.595 | 1.225 | Modernize Roadway-Rural | 26 |  | 75000 |  | 2000000 |  | 5000000 |  | 4000000 |  | 7500000 |  | 2017-05-01 14:24 | Correct horizontal, vertical and width deficiencies on KY-750 from Pond Run (MP 0.37) to KY-207 (MP 1.595) to improve safety and operational efficiency of roadway. | Existing KY 750 consists of 2 narrow driving lanes with no usable shoulders. The roadway is very curvy and has poor sight distance both horizontally and vertically. | 9 | East | 63.2725 | 6.3114 | 10.0599 | 11.003 | 2.7545 | 8.3832 | 3.7126 | 6.0479 | 48 |  | 15
Y | 9 | Buffalo Trace ADD | IP20080548 |  |  |  | INSTALL HIGH MAST LIGHTING AND RUMBLE STRIPS (ADD SAFETY MEASURES) AND MAKE THE INTERESECTION MORE VISIBLE/NOTICEABLE TO MOTORISTS TRAVELING ON KY-9 NB. THIS IS A 55MPH SEGMENT AND IS IN A DENSE FOG WARNING AREA. | Safety-Haz-Elm | Lewis | 068-KY-0009 -000 | 7.5 | 8.5 | 1 | Other Improvement Types | 0 | Y | 20000 |  | 175000 |  | 200000 |  | 150000 |  | 1350000 |  | 2010-02-25 16:51 | To improve safety and mobility | This project is along the very busy AA (KY9) highway in Lewis County which carries a large volume of truck traffic from Northern KY to West Virginia. The intersection of KY10 with KY9 is along a horizontal curve, vertical curve and superelevated at the m
Y | 9 | Buffalo Trace ADD | IP20080549 | 9-8807 |  | A | RECONSTRUCT KY-57 FROM KY-9 TO FLEMING/LEWIS COUNTY LINE. (14CCN)(16CCR)(18CCN) | RECONSTRUCTION(O) | Lewis | 068-KY-0057 -000 | 0 | 4.557 | 4.557 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2022 | 5740000 | 2023 | 3830000 | 2023 | 36500000 | 2024 | 2018-07-10 08:18 | To improve safety and mobility | KY 57 provides direct access to KY 9 from Flemingsburg in Fleming Co. to Tollesboro in Lewis Co. This project is one of three segments of KY 57 on the UPL (2 segments in Fleming Co.-09 032 D0057 58.00 & 52.00, 1 segment in Lewis). Existing KY 57 is a | 9 | East | 75.0599 | 3.5928 | 7.5449 | 9.9701 | 3.3533 | 7.8443 | 3.4731 | 9.2814 | 45 | 15 | 15
Y | 9 | Buffalo Trace ADD | IP20080550 |  |  |  | Spot improvement/Safety enhancements are needed along US 62(X) and the intersection of KY 10 (Forest Ave) continuing past Mullberry Alley. This intersection has had signal improvements and needs to be re-evaluated to improve effieciency and safety for m | Safety-Haz-Elm | Mason | 081-US-0062 -000 | 17 | 17.6 | 0.6 | Other Improvement Types | 0 |  | 15000 |  | 225000 |  | 350000 |  | 275000 |  | 1000000 |  | 2011-03-09 11:44 | To improve safety | Make improvements to US 62X in downtown Maysville from Forest Avenue intersection to just past Mulberry Alley (library). Safety enhancements are needed: better striping, thermo arrows, thermo cross walkwalks, improved sidewalks, improved lighting for bot
Y | 9 | Buffalo Trace ADD | IP20080551 |  |  |  | Relieve congestion on US 68 from KY 324 in Mayslick, MP 4.6 to 1.0 mile south of Washington, MP 10.854 to improve traffic flow, decrease collisions, improve safety and overall efficiency. CUT SLOPE REVISIONS to improve visibility, ADD LT & RT TURN L | Congestion Management | Mason | 081-US-0068 -000 | 4.6 | 10.4 | 5.8 | Other Improvement Types | 0 | Y | 50000 |  | 2500000 |  | 4000000 |  | 2500000 |  | 30000000 |  | 2015-03-11 08:46 | To improve mobility | US68 provides a vital link between Lexington, Paris, Maysville and the smaller communities in between. The current highway facility is not adequate for present traffic volumes and service flow. Operational characteristics will continue to deteriorate wi
Y | 9 | Buffalo Trace ADD | IP20080552 |  |  |  | Correct geometric and width deficiencies and improve long-term stability of KY 8 from KY 3056 (MP 9.20) to the new Maysville Bridge (MP 11.04). Foundation stabilization and roadway rehab to provide a safer more stable roadway into Maysville. | Reconstruction | Mason | 081-KY-0008 -000 | 9.2 | 11.04 | 1.84 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 2500000 |  | 1500000 |  | 10000000 |  | 2013-06-12 13:59 | To improve saferty and mobility. | Existing KY 8 is a rural, narrow, 2-lane roadway with virtually no usable shoulders. The Ohio River runs parallel to this road in several segments and as a result, roadway slippage is occurring. According to ADT counts, traffic has increased over the
Y | 9 | Buffalo Trace ADD | IP20080554 |  |  |  | Improvements to KY 10 from Germantown (Bracken County Border) to KY 9 in Mason County to address the safety issue as well as the geometric deficiencies along the roadway | Relocation | Mason | 081-KY-0010 -000 | 0 | 3.804 | 3.804 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 2000000 |  | 1750000 |  | 20000000 |  | 2013-06-12 13:50 | To improve safety and mobility. | This is a road with curves in agricultural areas of the counties with many points of potential sight distance problems with intersections and farm equipment. The route has a high CRF and needs to be evaluated. There is a study for the reconstruction o
Y | 9 | Bluegrass ADD | IP20080555 |  |  |  | Correct horizontal and vertical alignment and width deficiencies to improve operational efficiency and systems connectivity of KY 36 from US 68 NW of Carlisle (0.00) to KY 13 SW of Carlisle (3.075) | Reconstruction | Nicholas | 091-KY-0036 -000 | 0 | 3.075 | 3.075 | Modernize Roadway-Rural | 26 |  | 324000 |  | 1500000 |  | 2695000 |  | 1771000 |  | 15000000 |  | 2013-06-13 08:32 | Correct horizontal and vertical alignment and width deficiencies to improve operational efficiency and systems connectivity of KY 36 from US 68 NW of Carlisle (0.00) to KY 13 SW of Carlisle (3.075) | Existing roadway from US 68 to KY 13 does not meet current federal standards and is not part of the truck network, yet it is the main route through Nicholas County and serves its industrial community. CRF indicates safety concerns. Existng KY 36 is very | BLUEGRASS ADD | East | 58.024 | 5.0299 | 10.4192 | 10.2395 | 1.4072 | 7.9042 | 0 | 8.024 | 43 |  | 15
Y | 9 | Bluegrass ADD | IP20080556 |  |  |  | Reconstruct KY 36 and correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY 36 from just east of KY 57 in Nicholas County to KY 11 in Bath County (MP 0.759). | Relocation | Nicholas | 091-KY-0036 -000 | 11 | 12.807 | 1.807 | Other Improvement Types | 0 |  | 75000 |  | 1750000 |  | 2000000 |  | 1000000 |  | 12500000 |  | 2013-06-13 08:31 | Reconstruct KY 36 and correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY 36 from just east of KY 57 in Nicholas County to KY 11 in Bath County (MP 0.759). | Existing KY 36 is a very narrow (9'lanes) rural roadway with no usable shoulders. KY 36 from Owingsville in Bath County to US 68 in Nicholas County was the subject of a 1999 KY 36 Cooridor Planning Study. Operational efficiency has diminished as a result
Y | 9 | Gateway ADD | IP20080557 |  |  |  | Improve safety, capacity, and operational efficiency on KY 377 from approximately the intersection of KY 799 to approximately 0.1 mile north of Buckner Branch. | Reconstruction | Rowan | 103-KY-0377 -000 | 8 | 12 | 4 | Modernize Roadway-Rural | 26 |  | 250000 |  | 2500000 |  | 4000000 |  | 2000000 |  | 25000000 |  | 2017-05-01 14:44 | The purpose of this project is to improve safety, capacity, and operational efficiency. | The following needs have been identified for this project: 1) improve safety; 2) improve capacity; 3) improve operational efficiency; 4) the small bridge ways make it impossible for two larger vehicles to pass at the same time; and 5) the narrow roadway | 9 | East | 38.0419 | 2.503 | 7.8144 | 11.0479 | 1.9461 | 6.2874 | 0 | 8.4431 | 38
Y | 9 | Gateway ADD | IP20080558 |  |  |  | Improve safety, capacity, and operational efficiency on KY 377 from 0.1 mile north of Buckner Branch to the Lewis County Line. | Reconstruction | Rowan | 103-KY-0377 -000 | 12 | 15.339 | 3.339 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1750000 |  | 4000000 |  | 1500000 |  | 14000000 |  | 2013-06-13 09:18 | The purpose of this project is to improve safety, capacity, and operational efficiency. | The following needs have been identified for this project: 1) improve safety; 2) improve capacity; 3) improve operational efficiency; 4) this section of roadway includes a long narrow hill; and 5) the narrow roadway has no usable shoulder.
Y | 9 | Gateway ADD | IP20080559 |  |  |  | Improve safety, enhance operational efficiency, and correct geometric deficiencies on KY 1167 from Talmadge Catron Road to Clack Mountain Road. | Spot Improvement | Rowan | 103-KY-1167 -000 | 4.5 | 5.1 | 0.6 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1000000 |  | 1230000 |  | 786000 |  | 4128000 |  | 2013-06-13 09:45 | The purpose of this project is to improve safety, enhance operational efficiency, and correct geometric deficiencies. | The following needs have been identified for this project: 1) improve safety; 2) enhance operational efficiency; 3) correct horizontal and vertical alignments; 4) widen the roadway; and 5) a steep hillside and rock overhang are directly adjacent to the ro
Y | 9 | Gateway ADD | IP20080560 |  |  |  | Improve safety, correct geometric deficiencies, and improve sight distance on KY 3319 from East Reynolds Road to Bratton Branch Road. | Spot Improvement | Rowan | 103-KY-3319 -000 | 1.2 | 1.7 | 0.5 | Modernize Roadway-Rural | 26 |  | 75000 |  | 600000 |  | 450000 |  | 250000 |  | 2500000 |  | 2013-06-13 09:41 | The purpose of this project is to improve safety, correct geometric deficiencies, and improve sight distances. | The following needs have been identified for this project: 1) improve safety; 2) correct horizontal and vertial deficiencies; 3) widen the roadway; and 4) improve sight distances.
Y | 9 | Gateway ADD | IP20100057 |  |  |  | Realign roadway on US 60 near Owingsville beginning in the vicinity of Rose Bush Ln and ending at Wells Road near I 64 Exit 123 | Reconstruction | Bath | 006-US-0060 -000 | 8.2 | 9.4 | 1.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 400000 |  | 550000 |  | 6500000 |  | 2017-05-01 08:24 | The purpose of this project is to improve: safety, sight-distance, and geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Sight-Distance, 3) Improve Horizontal Deficiencies, and 4)Improve Roadway Width and Shoulder Deficiencies. | GATEWAY ADD | East | 27.5449 | 4.012 | 3.7725 | 2.6048 | 3.2635 | 7.3054 | 0 | 6.5868 | 28
Y | 9 | Buffalo Trace ADD | IP20110003 |  |  |  | Correct geometric and width deficiencies on this segment of KY57, including bridge replacement, beginning 0.5 mile south (MP 8.512) ofthe Fleming/Lewis County line (MP 9.183) to 0.6 north of the Fleming/Lewis County line, to improve operational efficiency | Reconstruction | Fleming | 035-KY-0057 -000 | 8.512 | 9.183 | 0.671 | Other Improvement Types | 0 |  | 50000 |  | 650000 |  | 400000 |  | 300000 |  | 4500000 |  | 2013-06-12 10:27 | To improve safety | This bridge is extremely narrow with 11' lanes. KY57 is used by large trucks, heavy farm equipment and is oftern too narrow for two large vehicles to pass safely. This bridge often becomes a choke point for KY57 and poses a safety problem. This route i
Y | 9 | Buffalo Trace ADD | IP20110004 |  |  |  | Correct geometric and width deficiencies ob this segment of KY 57 beginning at Sleepy Run Bridge (MP 2.300) extending to Mineer Road (MP 5.282) to improve operational efficiency, sight distance restrictions and overall flow of traffic. Project is in | Reconstruction | Fleming | 035-KY-0057 -000 | 2.3 | 5.282 | 2.982 | Other Improvement Types | 0 |  | 100000 |  | 2000000 |  | 2500000 |  | 1500000 |  | 15000000 |  | 2013-06-12 11:22 | To improve safety and mobility. | KY 57 provides direct access to KY 9 (AA hwy) from Flemingsburg to Tollesboro in Lewis county. Existing KY 57 is a curvy-narrow 2 lane roadway (11' lanes) with virtually no usuable shoulder. It has both horizontal and vertical deficiencies. The CRF of 1.2
Y | 9 | Buffalo Trace ADD | IP20110005 |  |  |  | Correct geometric and width deficiencies on this segment of KY 57 beginning at Mineer Road (MP 5.282) extending to 0.5 mile south of Lewis County Line (MP 9.183) to improve operational efficiency, sight distance restrictions and overall flow of traffic. | Reconstruction | Fleming | 035-KY-0057 -000 | 5.282 | 9.183 | 3.901 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 8000000 |  | 5000000 |  | 32000000 |  | 2017-03-08 16:37 | To improve safety and mobility | KY 57 provides direct access to KY 9 (AA hwy) from Flemingsburg to Tollesboro. Existing KY 57 is a curvy-narrow 2 lane roadway (11' lanes) with no usuable shoulder. It has horizontal and vertical alignment deficiences. Limited sight distances result in lo
Y | 9 | Buffalo Trace ADD | IP20110006 | 9-80051 |  | A | IMPROVE SAFETY AND SIGHT DISTANCE ON KY-32 BEGINNING AT 0.4 MILES WEST OF FLEMING/ROWAN CO LINE AND ENDING 0.3 MILES EAST OF THE LINE.(18CCN) | SAFETY(P) | Fleming | 035-KY-0032 -000 | 27.893 | 28.293 | 0.4 | Other Improvement Types | 0 |  | 50000 | 2020 | 800000 | 2021 | 1000000 | 2023 | 750000 | 2023 | 7000000 | 2024 | 2018-07-10 08:18 | To improve safety. | Fleming/Rowan; KY 32 is a thoroughfare for motorists traveling to employment in both Rowan and Fleming Counties. Also, many travelers to and from Morehead State utilize this route. This segment of KY 32 is curvy and goes uphill toward the county line. Th | 9 | East | 13.9895 | 7.3653 | 0 | 1.4147 | 2.0359 | 0 | 3.1737 | 0 | 14
Y | 9 | Buffalo Trace ADD | IP20110025 |  |  |  | Construct right and left turn lanes at the intersection of KY 989 (MP 18.553) to improve safety and decrease collisions. This intersection has a high volume of turning movements and is located in a long sweeping curve. A Park and Ride is located at | Safety-Haz-Elm | Lewis | 068-KY-0009 -000 | 18.2 | 18.8 | 0.6 | Improve Intersection | 26 | Y | 0 |  | 250000 |  | 100000 |  | 250000 |  | 750000 |  | 2017-05-01 14:29 | To improve safety and mobility. | The intersection of KY 9 and KY 989 poses safety issues for motorists. There are near misses at the intersection daily. Motorists on the AA travel at much greater speeds than 55mph. Vehicles making left turns to KY 989 stop on the AA whcih creates safety | 9 | East | 37.5434 | 7.1018 | 13.2934 | 5.3219 | 0.41916 | 0 | 4.4611 | 6.9461 | 38
Y | 9 | Buffalo Trace ADD | IP20110026 |  |  |  | Reconstruct KY324 from US68 (MP 4.9) to (MP 6.0). Eliminate the sharp curve and improve the intersection with KY 161. KY 324 is a connector road between US 68 and KY 11 in southern Mason County. This section of KY 324 has a sharp curves that is near 9 | Minor Widening | Mason | 081-KY-0324 -000 | 4.9 | 6 | 1.1 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 750000 |  | 500000 |  | 5000000 |  | 2013-06-12 13:41 | To improve safety. | Improve the radii to the curve (20 mph) and improve the intersection with KY 161. This section has horizontal and vertical deficiencies. Several wrecks have occurred in this section of KY 324. This is located close to US 68 and growth is anticipated in
Y | 9 | Buffalo Trace ADD | IP20110034 |  |  |  | Minor widening along KY 8 through Quincy to improve safety, decrease collisions, and to promote economic opportunity. Address lane widths, sight distances, improve intersections and overall geometric deficiencies. | Safety-Haz-Elm | Lewis | 068-KY-0008 -000 | 24.016 | 25.4 | 1.384 | Other Improvement Types | 0 |  | 10000 |  | 1500000 |  | 3500000 |  | 1000000 |  | 7000000 |  | 2015-03-10 14:44 | To improve safety and mobility. | Correct horizontal deficiencies (sharp curves), correct cross slopes, remove obstacles near the edge of the roadway, improve narrow lane widths, add sidewalks in locations that wil provide a benefit to the residents and community.
Y | 9 | Buffalo Trace ADD | IP20110044 |  |  |  | Reconstruct KY 32 Correct width and alignment deficiencies on KY32 beginning (MP 7.3) near the Elizaville City Limits and ending at (MP 9.935)west of the FC High School. 3 Bridges located in this section of KY 32 Construct this section similar to | Reconstruction | Fleming | 035-KY-0032 -000 | 7.3 | 9.935 | 2.635 | Other Improvement Types | 0 |  | 75000 |  | 1500000 |  | 4000000 |  | 1300000 |  | 13000000 |  | 2013-06-12 11:20 | To improve safety and mobility | KY32 is a rural narrow (2-9ft lanes) road with no usable shoulders. Vertical and horizontal curve deficiencies. Guardrail is located at the edge of the small shoulder. Very flat grade near the 3 bridges with potential drainage issues. This segment need
Y | 9 | Buffalo Trace ADD | IP20110045 |  |  |  | Relocate/extend the truck passing lane near the bottom of the hill, so that the "merge" area can be moved away from the top of the hill/left-hand turn/end of bridge to improve safety and prevent accidents. Utilize the existing shoulder for the lane tap | Safety-Haz-Elm | Mason | 081-KY-0011 -000 | 4.3 | 5.1 | 0.8 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 0 |  | 0 |  | 1000000 |  | 2013-06-12 13:50 | To improve safety and mobility. | Construct the truck lane extension to the South of the existing location. This will allow motorists to safely pass and merge back into traffic. The present situation in the merge area is in a horizontal/vertical curve and the merge lane ends at the brid
Y | 9 | Buffalo Trace ADD | IP20110046 |  |  |  | Add right-turn on KY 11 SB into KY 419 to reduce risk of rear-end crashes and improve operational efficiency. | Safety-Haz-Elm | Mason | 081-KY-0011 -000 | 6.19 | 6.287 | 0.097 | Improve Intersection | 26 |  | 0 |  | 125000 |  | 0 |  | 75000 |  | 500000 |  | 2017-05-01 14:33 | To improve safety and mobility. | Construct a right turn lane or right turn taper to reduce the potential for accidents. KY 419 has a sharp curve as it approaches KY 11 and makes the turn hard to make on KY 11 without slowing down considerably which results in daily near misses. | 9 | East | 22.2425 | 7.976 | 6.3772 | 1.2126 | 0 | 0 | 4.1018 | 2.5749 | 22
Y | 9 | Buffalo Trace ADD | IP20110047 |  |  |  | Make improvements to KY 32 through Elizaville. There are width and geomtric deficiencies on KY32 beginning at (MP 6.4) the East side of Elizaville City Limits and continuing through Elizaville to the (MP 7.3) to the west of Elizaville. | Spot Improvement | Fleming | 035-KY-0032 -000 | 6.412 | 7.3 | 0.888 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 5000000 |  | 600000 |  | 5000000 |  | 2013-06-12 11:31 | To improve safety. | KY 32 through Elizaville has several local roads and a major intersection with KY 170. This segment is in a historic area and also has environmental issues with auto repair and old gas stations. This section needs improved sidewalks to promote a safe lo
Y | 9 | Buffalo Trace ADD | IP20110048 |  |  |  | Reconstruct KY 32 from (MP 5.4) to (MP 6.4) starting west of Pike Bluff Road to the Elizaville City Limits. Reconstruct KY32 and KY165 Intersection (MP 5.920). Reconstruct KY165 from (MP 0.0) to (MP 0.964) near the Ewing City Limits. Correct vertical s | Reconstruction | Fleming | 035-KY-0032 -000 | 5.4 | 5.833 | 0.433 | Other Improvement Types | 0 |  | 100000 |  | 350000 |  | 1500000 |  | 850000 |  | 4500000 |  | 2014-08-20 13:17 | To improve safety and mobility. | KY 32 and KY 165 need reconstructed. These roads have narrow lane widths, vertical deficiencies and pose safety concerns. This intersection also is the area of the new Ewing Elementary School and is located in a vertical curve with approach roads with li
Y | 9 | Buffalo Trace ADD | IP20110050 |  |  |  | Reconstruct KY 165 from Lake View Drive (MP0.964) through the City of Ewing to Fryman Lane (MP 1.9). Make improvements to: roadway/shoulder widths, sidewalks, drainage, entrances, bridge widths, side street approaches. | Reconstruction | Fleming | 035-KY-0165 -000 | 0.968 | 1.904 | 0.936 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 1000000 |  | 5000000 |  | 2013-06-12 11:21 | To improve safety and mobility. | This section includes the City of Ewing. There are numerous city streets, retaining wall, sidewalks and a bridge over TTI Railroad.
Y | 9 | Buffalo Trace ADD | IP20110051 |  |  |  | Reconstruct KY 165 from the end of Ewing City limits (MP 1.9) to Deer Lick Road (MP 4.7). Improve geometric and width deficiencies. This route connects US 68 to Flemingsburg. | Reconstruction | Fleming | 035-KY-0165 -000 | 1.904 | 4.704 | 2.8 | Other Improvement Types | 0 |  | 125000 |  | 1750000 |  | 3500000 |  | 1500000 |  | 14000000 |  | 2013-06-12 10:45 | To improve safety. | Reconstruct KY 165 west of Ewing The exisiting route is not classified as a truck route and needs upgraded for this route to be a connector between US 68 and Flemingsburg/Tollesboro/Greenup. Width, shoulder, horizontal, vertical deficiencies.
Y | 9 | Buffalo Trace ADD | IP20110052 |  |  |  | Reconstruction from Deer Lick Road (MP 4.7) to US68 (MP 6.239). KY 165 is not weight classed for truck traffic, this road needs upgraded for this route to be a viable connector. This route provides connectivity from US 68 to Flemingsburg and surroundi | Reconstruction | Fleming | 035-KY-0165 -000 | 4.704 | 6.243 | 1.539 | Other Improvement Types | 0 |  | 125000 |  | 800000 |  | 2000000 |  | 850000 |  | 7500000 |  | 2013-06-12 10:47 | To improve safety | KY165 has narrow lanes of 9' with narrow 2' shoulders and does not meet standards to be classified as a truck route. There are several sharp curves and the road has little to no shoulders.
Y | 9 | Gateway ADD | IP20110060 |  |  |  | Improve connectivity on the Morehead State University frontage road, in front of the Athletic Complex to connect Old US 60. | Reconstruction | Rowan | 103-US-0060 -000 | 0 | 0.001 | 0.001 | Local Roadway Improvements | 3 |  | 0 |  | 50000 |  | 100000 |  | 75000 |  | 450000 |  | 2011-02-28 17:14 | The purpose of this project is to improve connectivity. | The following need has been identified for this project: improve connectivity of local roads instead of using the US 60 bypass.
Y | 9 | Gateway ADD | IP20110061 | 9-8915 |  | A | WIDEN KY 801 FROM NEAR MMRC REGIONAL PARK TO KY 158 IN FLEMING CO. (16CCN)(18CCN) | MAJOR WIDENING(O) | Rowan | 103-KY-0801 -000 | 15.85 | 17.011 | 1.161 | Modernize Roadway-Rural | 26 |  | 80000 | 2019 | 1560000 |  | 2320000 |  | 1170000 |  | 15820000 |  | 2018-07-10 08:18 | The purpose of this project is to improve: safety, substandard geometrics (deteriorating pavement and horizontal, vertical, and width deficiencies), regional connectivity , and access (including intermodal access to the Regional Airport). | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Roadway Geometrics, 3) Improve Regional Connectivity, and 4) Improve Access and Intermodal Access. | 9 | East | 39.8533 | 5.4371 | 7.994 | 10.015 | 1.5569 | 7.7246 | 0 | 7.1257 | 40
Y | 9 | FIVCO ADD | IP20110065 |  |  |  | Existing KY 556 consists of a narrow undivided two-lane roadway (9-10' driving lanes) with narrow shoulders (0-2') and both horizontal & vertical deficiencies. This section of roadway runss along the top of a cliff following Little Sandy Creek and then p | Reconstruction | Elliott | 032-KY-0556 -000 | 4.3 | 6.45 | 2.15 | Other Improvement Types | 0 |  | 0 |  | 40000 |  | 0 |  | 0 |  | 360000 |  | 2011-02-25 12:18 |  | Existing KY 556 (North Ruin Road) consists of a narrow undivided two-lane roadway with narrow shoulders and both horizontal & vertical deficiencies.
Y | 9 | FIVCO ADD | IP20110066 |  |  |  | Existing KY 755 consists of a narrow undivided two-lane roadway (9-10' driving lanes) with narrow shoulders (0-2') and both horizontal & vertical deficiencies. This section of roadway runs along the top of a cliff following and crossing South Ruin Creek. | Safety-Haz-Elm | Elliott | 032-KY-0755 -000 | 5.1 | 5.5 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 550000 |  | 500000 |  | 200000 |  | 2000000 |  | 2013-06-12 10:06 |  | Existing KY 755 (South Ruin Road) consists of a narrow undivided two-lane roadway with narrow shoulders and both horizontal & vertical deficiencies. Safety enhancements are needed along this segment.
Y | 9 | FIVCO ADD | IP20110069 |  |  |  | Correct horizontal, vertical and width deficiencies on KY 32 from (MP 11.5) to (MP 13.5) to improve operational efficiency, sight distance restrictions, and travel time for the residents of Elliott and Lawrence Counties. | Reconstruction | Elliott | 032-KY-0032 -000 | 11.5 | 13.5 | 2 | Modernize Roadway-Rural | 26 |  | 75000 |  | 1500000 |  | 1750000 |  | 750000 |  | 12500000 |  | 2017-05-01 14:14 |  | This segment of KY 32 is a very narrow 2-lane roadway with no usable shoulder(9' to 12' lanes, w/2' to 10' shoulders). It is characterized throughout its length by winding, switchback curves, hillsides on one side and steep ravines on the other, poor sig
Y | 9 | FIVCO ADD | IP20110070 |  |  |  | Existing KY 173 consists of an undivided narrow (9-10' driving lanes) with narrow shoulders (2-3') with both horizontal and vertical geometric deficiencies. KY 173 needs a complete realignment, however the existing road travels a ridge top and involves ma | Reconstruction | Elliott | 032-KY-0173 -000 | 0.5 | 2.4 | 1.9 | Other Improvement Types | 0 |  | 100000 |  | 750000 |  | 500000 |  | 200000 |  | 10000000 |  | 2013-06-12 10:22 |  | Existing KY 173 consists of an undivided narrow (9-10' driving lanes) with narrow shoulders (2-3') with both horizontal and vertical geometric deficiencies.
Y | 9 | FIVCO ADD | IP20110071 |  |  |  | Existing KY 173 consists of an undivided narrow (9-10' driving lanes) with narrow shoulders (2-3') with both horizontal and vertical geometric deficiencies. Roadway is in need of complete realignment, however existing KY 173 travels a ridge top, and would | Reconstruction | Elliott | 032-KY-0173 -000 | 3.4 | 5.4 | 2 | Other Improvement Types | 0 |  | 100000 |  | 1250000 |  | 2000000 |  | 1000000 |  | 10000000 |  | 2013-06-12 10:07 |  | Existing KY 173 consists of an undivided narrow (9-10' driving lanes) with narrow shoulders (2-3') with both horizontal and vertical geometric deficiencies.
Y | 9 | Gateway ADD | IP20110090 |  |  |  | Planning Study to determine the feasibility of the original project described below: Provide a second access for Bath County High School and recreational facilities to improve traffic flow and congestion on US 60 through Owingsville as well as to incre | New Route | Bath | 006-US-0060 -000 | 0 | 1 | 1 | Transportation Studies | 0 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-03-27 07:15 | The purpose of this project is to conduct a planning study to determine feasibility. | The following need has been identified for this project: 1) Planning/Feasibility Study.
Y | 9 | Buffalo Trace ADD | IP20110091 |  |  |  | 2 Safety Improvement/Intersections curves reconstruction at KY 419 near(mp 7) & Ward Pike near (mp 8). KY 324 is a connector road between US 68 and KY 11 in southern Mason County. This section of KY 324 has 2 curves that are near 90° and have roads that | Safety-Haz-Elm | Mason | 081-KY-0324 -000 | 6.4 | 8 | 1.6 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1000000 |  | 400000 |  | 5000000 |  | 2013-06-12 13:44 | To improve safety. | Make improvements to the 3 sharp curves and approach roads within these curves. Curve widening, addition of shoulders, widen lane widths, make improvements to both horizontal and vertical geometrics. KY 324 intersecting with: KY 161, KY 419, & Wards Pik
Y | 9 | Buffalo Trace ADD | IP20110092 |  |  |  | Increase capacity and decrease conflict points on KY 9. from the Mason County Landfill to the KY 11 intersection. Widen roadway to a 4-lane facility, add turn lanes to side roads, and provide overhead lighting at side road approaches to increase safety | Major Widening | Mason | 081-KY-0009 -000 | 5 | 7.56 | 2.56 | Other Improvement Types | 0 | Y | 0 |  | 1500000 |  | 1000000 |  | 1000000 |  | 14000000 |  | 2013-06-12 13:43 | To improve mobility | Widen the AA Highway beginnning north of the Mason County Landfill access to KY 11. This needs to be a 4-lane roadway with a raised median as it is in the conecting 4 lane segement. There are several approach roads in this segment and has a combination
Y | 9 | Buffalo Trace ADD | IP20110093 |  |  |  | Increase capacity, safety, and decrease conflict points on KY9 (AA Hwy) from the Lewis County Line to just North of the Mason County Landfill access road; to support 2025 traffic volumes, address sight distance concerns, improve intersection safety and re | Major Widening | Mason | 081-KY-0009 -000 | 0 | 5 | 5 | Other Improvement Types | 0 | Y | 0 |  | 2500000 |  | 3000000 |  | 2500000 |  | 25000000 |  | 2013-06-12 14:02 | To improve safety and mobility | Widen to 4 lanes to increase safety for motorists on the AA Hwy and increase operational efficiency. This traffic on this route is increasing significantly as a major truck route from I-75 to I-64. Reconstruct high accident location intersections and in
Y | 9 | Bluegrass ADD | IP20110094 |  |  |  | Correct horizontal, vertical and width deficiencies to improve safety and drive-ability at various locations. Beginning at the intersection of KY 36/KY 32 in Carlisle and ending before Lake Road (KY 1455). Urban design with curb and gutter and sidewalks. | Reconstruction | Nicholas | 091-KY-0032 -000 | 8.8 | 9.5 | 0.7 | Other Improvement Types | 0 |  | 25000 |  | 400000 |  | 1000000 |  | 500000 |  | 3500000 |  | 2013-06-12 15:44 | Correct horizontal, vertical and width deficiencies to improve safety and drive-ability at various locations. Beginning at the intersection of KY 36/KY 32 in Carlisle and ending before Lake Road (KY 1455). Urban design with curb and gutter and sidewalks. | This section of KY 32 is going into downtown Carlisle. An urban design with sidewalks is preferred. Parking improvements are also desired and approach street sight distances should be evaluated. Evaluate the use of a TWLTL and right turn lanes or large ta
Y | 9 | Bluegrass ADD | IP20110095 |  |  |  | Correct horizontal, vertical and width deficiencies to improve safety and drive-ability along KY 32. Beginning near the Scrubgrass Creek Culvert to the Fleming Creek Bridge (mile point 15.406 (Sawmill road). This will also include reconstructing the appro | Reconstruction | Nicholas | 091-KY-0032 -000 | 14.03 | 17.152 | 3.122 | Modernize Roadway-Rural | 26 |  | 75000 |  | 2000000 |  | 1750000 |  | 1000000 |  | 14000000 |  | 2017-06-02 15:42 | Correct horizontal, vertical and width deficiencies to improve safety and drive-ability along KY 32. Beginning near the Scrubgrass Creek Culvert to the Fleming Creek Bridge (mile point 15.406 (Sawmill road). This will also include reconstructing the appro | Existing KY 32 from Carlisle to Flemingsburg is a rural, narrow (9'lane), very winding roadway with no usable shoulders. There are steep cut slopes as well as deep valleys bordering KY 32. Traffic normally flows slower than the posted speed limits due to | BLUEGRASS ADD | East | 28.6587 | 0.57485 | 3.5928 | 6.6467 | 2.2156 | 6.0479 | 0 | 9.5808 | 29
Y | 9 | Bluegrass ADD | IP20110096 |  |  |  | Correct horizontal, vertical and width deficiencies to improve safety and drive-ability along KY 32; from Mexico Road to 1/2 mile West of the Nicholas/Fleming line. | Reconstruction | Nicholas | 091-KY-0032 -000 | 15.989 | 17.362 | 1.373 | Other Improvement Types | 0 |  | 25000 |  | 500000 |  | 750000 |  | 500000 |  | 6000000 |  | 2013-06-12 15:54 | Correct horizontal, vertical and width deficiencies to improve safety and drive-ability along KY 32; from Mexico Road to 1/2 mile West of the Nicholas/Fleming line. | Reconstruct KY 32 from Mexico Road to 1/2 West of the County line. This section is a segment of the Nicholas County KY 32 upgrade from Carlisle to Flemingsburg. This section will inlcude 1 bridge reconstruction.
Y | 9 | Bluegrass ADD | IP20110097 |  |  |  | Reconstruct KY 36, beginning 1 mile West of Whetstone Road and ending just West of Locust Grove Road. Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY 36. | Reconstruction | Nicholas | 091-KY-0036 -000 | 5.726 | 7.2 | 1.474 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1750000 |  | 850000 |  | 9500000 |  | 2017-05-01 14:40 | Reconstruct KY 36, beginning 1 mile West of Whetstone Road and ending just West of Locust Grove Road. Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY 36. | Reconstruct KY 36 from 1 mile West of Whetstone Road (And reconstruct Whetstone approach) to just west of Locust Grove Road. KY 36 from Carlisle to Sharpsburg/Bath County via I-64 needs reconstructed. This section has a high CRF and safety improvements ar | BLUEGRASS ADD | East | 39.8668 | 2.8383 | 10.7784 | 9.7231 | 2.5749 | 6.9461 | 0 | 7.006 | 40
Y | 9 | Bluegrass ADD | IP20110098 |  |  |  | Reconstruct KY 36 beginning near Locust Grove Road and ending at Old Moorefield Road. Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY 36. | Reconstruction | Nicholas | 091-KY-0036 -000 | 7.2 | 9.7 | 2.5 | Other Improvement Types | 0 |  | 75000 |  | 1500000 |  | 1500000 |  | 1000000 |  | 12500000 |  | 2013-06-13 08:34 | Reconstruct KY 36 beginning near Locust Grove Road and ending at Old Moorefield Road. Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY 36. | Reconstruct KY 36 to improve efficiency and provide a better E/W route through Nicholas County and to surrounding counties.
Y | 9 | Bluegrass ADD | IP20110099 |  |  |  | Reconstruct KY 36 beginning at Moorefield Road(East) and ending 1/2 East of KY 57 intersections. Reconstruct KY 57 approaches (1/2 miles N and S). Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivi | Reconstruction | Nicholas | 091-KY-0036 -000 | 9.7 | 11 | 1.3 | Other Improvement Types | 0 |  | 75000 |  | 1000000 |  | 1000000 |  | 750000 |  | 9000000 |  | 2019-02-14 08:31 | Reconstruct KY 36 beginning at Moorefield Road(East) and ending 1/2 East of KY 57 intersections. Reconstruct KY 57 approaches (1/2 miles N and S). Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivi | Reconstruct KY 36 and the offset KY 57 approaches. Ky 36 is a major E/W corridor that needs improving to provide a better route for trucks and motorists traveling through Nicholas County.
Y | 9 | Buffalo Trace ADD | IP20110101 |  |  |  | Minor widening along this KY8 section to improve safety, decrease collisions and provide a better route for trucks traveling from US 23 in Ohio and Northeastern Greenup County (west) to the AA Highway. Improve the Level of Service/Capacity. This sectio | Reconstruction | Lewis | 068-KY-0008 -000 | 31 | 32.36 | 1.36 | Other Improvement Types | 0 |  | 100000 |  | 1500000 |  | 2500000 |  | 1500000 |  | 9000000 |  | 2013-06-12 11:56 | To improve safety and mobility. | Make improvements to the roadway deficiencies, add turn lanes, add shoulders, & increase overall safety of the roadway. The CRF does not reflect the large amount of accidents in Greenup County. The truck traffic is increasing and this section of KY 8 orvi
Y | 9 | Buffalo Trace ADD | IP20110102 |  |  |  | Reconstruct KY59 from Rock Run Road through the intersection of KY9 and KY59 to KY 1149/Washington Avenue approach. Improve horiz/vertical deficiencies, construct 4' shoulders, improve approach road intersections, provide a stabilized roadway into Vanceb | Reconstruction | Lewis | 068-KY-0059 -000 | 21.3 | 23.57 | 2.27 | Other Improvement Types | 0 |  | 100000 |  | 650000 |  | 950000 |  | 750000 |  | 7000000 |  | 2011-03-25 15:11 | To improves safety and mobility. | This section of road is a maintenance issue and is very hilly, curvy, narrow lanes, little to no shoulder, and has a high CRF as indicated. This area is called "Vanceburg Hill". Reconstruct to improve geometrics, overall efficiency, reduce maintenance
Y | 9 | Buffalo Trace ADD | IP20110103 |  |  |  | Reconstruct KY 9 (AA Highway) from south of the KY 59 intersection to north of Hazel Branch. Improve Safety, lengthen left turn lanes, add right turn lanes, add street lighting, cut slope revisions to increase sight distance and reduce maintenance cost | Reconstruction | Lewis | 068-KY-0009 -000 | 10.5 | 13.5 | 3 | Other Improvement Types | 0 | Y | 50000 |  | 1000000 |  | 500000 |  | 200000 |  | 10000000 |  | 2013-06-12 12:06 | To improve safety and mobility | The AA highway has a high volume of thru traffic including trucks. Vanceburg is growing to this section of the AA. Businesses, schools, small industry, and other traffic generators are locating to this area. There are several side roads with local traffic
Y | 9 | Buffalo Trace ADD | IP20110165 |  |  |  | RECONSTRUCTION FROM ROWAN C\L TO VANCEBURG. SEE ROWAN CO. KY 377 LISTING FOR CONTINUATION OF ROUTE RECONSTRUCTION NEED TO MOREHEAD. | Reconstruction | Lewis | 068-KY-0344 -000 | 13.843 | 18.5 | 4.657 | Other Improvement Types | 0 |  | 250000 |  | 2000000 |  | 3500000 |  | 2500000 |  | 35000000 |  | 2012-02-20 15:54 | To improve safety and mobility. | There is an apparent need to improve N-S systems connectivity between the cities of Vanceburg in Lewis County and Morehead in Rowan County. There is a high number of Lewis County residents that commute to Rowan County for employment, education and recrea
Y | 9 | Buffalo Trace ADD | IP20110166 | 9-231 / 9-8904.10 |  | A | RECONSTRUCT KY-59 FROM KY-9 (AA) IN VANCEBURG TO JUNCTION OF KY-344 MP 18.1 TO MP 23.19.(16CCN)(18CCN) | RECONSTRUCTION(O) | Lewis | 068-KY-0059 -000 | 18.1 | 23.19 | 5.09 | Modernize Roadway-Rural | 26 |  |  |  | 7600000 | 2021 | 2870000 | 2022 | 1580000 | 2023 | 92770000 | 2021 | 2019-03-13 10:57 | To improve safety and mobility | There is an apparent need to improve N-S systems connectivity between the Cities of Vanceburg in Lewis Co. and Morehead in Rowan County. There is a high number of Lewis County residents that commute to Rowan County for employment, education and recreatio | 9 | East | 70.0195 | 2.1078 | 6.5569 | 11.744 | 2.7844 | 7.3653 | 0 | 9.4611 | 40 | 15 | 15
Y | 9 | Huntington-Ashland-Ironton MPO | IP20110167 |  |  |  | Improve geometrics and safety by reconstruction of alignment for KY-766 to intersection with KY-1134. | Safety-Haz-Elm | Boyd | 010-KY-0766 -000 | 1.004 | 1.261 | 0.257 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 500000 |  | 500000 |  | 1750000 |  | 2017-05-01 08:38 | Improve geometrics and safety by reconstruction of alignment for KY-766 to intersection with KY-1134. | KY-766 intersects KY-1134 at an approximate 30-degree angle, causing limited to no sight distance to the right when pulling onto KY-1134. Approximately 350 feet from the intersection is a railroad crossing KY-766, where vehicles tend to back up in a short | 9 | East | 30.5299 | 5.7246 | 10.6886 | 7.3204 | 3.503 | 0 | 0 | 3.2934 | 30
Y | 9 | Huntington-Ashland-Ironton MPO | IP20110175 |  |  |  | Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY-3, beginning at milepoint 5.075 (PV 1215) to milepoint 7.802 (intersection with KY-180). | Safety-Haz-Elm | Boyd | 010-KY-0003 -000 | 5.075 | 7.802 | 2.727 | Modernize Roadway-Rural | 26 |  | 500000 |  | 2000000 |  | 5000000 |  | 2000000 |  | 18000000 |  | 2017-05-01 08:32 | Correct horizontal, vertical and width deficiencies to improve operational efficiency and systems connectivity of KY-3, beginning at milepoint 5.075 (PV 1215) to milepoint 7.802 (intersection with KY-180). | KY-3 is a curvy, narrow, 2-lane roadway with virtually no usable shoulder. Improvement to both the horizontal and vertical alignment deficiencies would improve operational efficiency and systems connectivity on KY-3 beginning at MP 5.075 (PV-1215) to M | Huntington/KYOVA MPO | East | 33.8458 | 5.3653 | 7.006 | 11.0254 | 2.8443 | 0 | 0 | 7.6048 | 34
Y | 9 | Gateway ADD | IP20110210 |  |  |  | Improve safety, capacity, and operational efficiency on KY 32 from the US 60 intersection to the intersection of KY 504. | Major Widening | Rowan | 103-KY-0032 -000 | 8.439 | 16.619 | 8.18 | Modernize Roadway-Rural | 26 |  | 500000 |  | 4500000 |  | 5000000 |  | 3000000 |  | 40000000 |  | 2013-06-13 09:44 | The purpose of this project is to improve safety, capacity, and operational efficiency. | The following needs have been identified for this project: 1) improve safety; 2) improve capacity; 3) improve operational efficiency; and 4) address issues associated with narrow driving lanes and improve shoulders on the roadway.
Y | 9 | Gateway ADD | IP20110211 |  |  |  | Improve geometric deficiencies, safety, and congestion on KY 158 from the Fleming County Line to the intersection of KY 32. | Major Widening | Rowan | 103-KY-0158 -000 | 0 | 2.766 | 2.766 | Modernize Roadway-Rural | 26 |  | 250000 |  | 1500000 |  | 2000000 |  | 1500000 |  | 15000000 |  | 2011-11-21 14:31 | The purpose of this project is to improve geometric deficiencies, safety, and congestion. | The following needs have been identified for this project: 1) improve safety; 2) correct horizontal and vertical alignments; 3) add turn lanes to county roads and subdivisions; 4) replace box culvert; 5) add turn lanes; and 6) provide an improved east t
Y | 9 | FIVCO ADD | IP20110212 |  |  |  | Reconstruct KY 2 to correct horizontal and vertical deficiencies from 0.02 mi W of Dean Loop Road (MP 3.80) to approximately 0.20 mi W of Smokey Valley Road (MP 4.90). | Reconstruction | Carter | 022-KY-0002 -000 | 3.8 | 4.9 | 1.1 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 750000 |  | 350000 |  | 5000000 |  | 2013-06-05 11:29
Y | 9 | Bluegrass ADD | IP20120057 |  |  |  | Reconstruct KY 32 beginning at the KY 32 / KY 36 intersection and ending at new US 68 in Nicholas County | Reconstruction | Nicholas | 091-KY-0032 -000 | 6.132 | 8.313 | 2.181 | Modernize Roadway-Rural | 26 |  | 10000 |  | 1700000 |  | 1500000 |  | 1000000 |  | 14000000 |  | 2017-05-01 14:37 | Reconstruct KY 32 beginning at the KY 32 / KY 36 intersection and ending at new US 68 in Nicholas County | This is to improve KY 32 from it’s junction with KY 36 in Carlisle, to the approximate point where current project to realign US 68 through Bourbon and Nicholas counties is set to cross KY 32. The belief is that when this project is complete, that the gen | BLUEGRASS ADD | East | 38.6512 | 4.2275 | 8.1737 | 9.3638 | 3.1138 | 6.5269 | 0 | 7.2455 | 39
Y | 9 | Gateway ADD | IP20130089 |  |  |  | Increase mobility, correct geometry, and improve safety on KY 965 from the intersection of Blevins Valley Road (MP 6.4) to the Mill Creek Bridge (MP 6.9). | Reconstruction | Bath | 006-KY-0965 -000 | 6.4 | 6.918 | 0.518 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 600000 |  | 250000 |  | 2500000 |  | 2013-08-08 09:21 | The purpose of this project is to improve safety, correct geometry, and increase mobility. | The following needs have been identified for this project: 1) extend clear zones to increase mobility; 2) correct horizontal and vertical alignment; 3) add shoulders; and 4) improve safety.
Y | 9 | FIVCO ADD | IP20130090 |  |  |  | Install fencing on top of existing concrete bridge railing of the Little Sandy River/Laurel Gorge bridge (032B00035N)to prevent debris being thrown over side of bridge onto the roadway underneath (The Laurel Curves Road). This creates a safety hazard for | Safety-Haz-Elm | Elliott | 032-KY-0007 -000 | 9.75 | 9.922 | 0.172 | Other Improvement Types | 0 |  | 0 |  | 10000 |  | 0 |  | 0 |  | 300000 |  | 2013-08-12 12:04 |  | There exists a history of debris/trash being thrown over the side of the Laurel Gorge Bridge (032B00035N), allowing it to fall onto the county road (The Laurel Curves Rd.) below. This creates a safety hazard to motorists, boaters, pedestrians and bicycli
Y | 9 | Huntington-Ashland-Ironton MPO | IP20130096 |  |  |  | Reconstruct KY-716 from MP 0.0 (US 60) to MP .560 (KY 3293)to improve safety and decrease congestion. | Reconstruction | Boyd | 010-KY-0716 -000 | 0 | 0.56 | 0.56 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1000000 |  | 4000000 |  | 1500000 |  | 4000000 |  | 2017-05-01 08:36 | Reconstruct KY-716 from MP 0.0 (US 60) to MP .560 (KY 3293)to improve safety and decrease congestion. | Reconstruct KY-716 from MP 0.0 (US 60) to MP .560 (KY 3293) to improve safety and decrease congestion. | 9 | East | 78.9686 | 8.8263 | 10.5988 | 10.8009 | 2.7246 | 8.2635 | 3.2635 | 4.491 | 49 | 15 | 15
Y | 9 | Huntington-Ashland-Ironton MPO | IP20130098 |  |  |  | Reconstruct intersection at KY-5 and KY-1458 to improve safety and mobility and to address geometrics. | Reconstruction | Boyd | 010-KY-0005 -000 | 8.9 | 9.3 | 0.4 | Improve Intersection | 26 |  | 0 |  | 500000 |  | 2000000 |  | 500000 |  | 3000000 |  | 2017-05-01 08:34 | Reconstruct intersection at KY-5 and KY-1458 to improve safety and mobility and to address geometrics. | Reconstruct intersection at KY-5 and KY-1458 to improve safety and mobility and to address geometrics. | 9 | East | 37.485 | 8.9222 | 11.3174 | 9.8802 | 1.3772 | 0 | 0 | 5.988 | 38
Y | 9 | FIVCO ADD | IP20130100 |  |  |  | Reconstruct Harvey Branch Road (CR 1080) to facilitate heavy truck traffic between KY 7 and KY 9. This will provide a safer intersection than the existing KY7/KY 9 intersection. Reconstructed route will potentially be accepted into the SPRS. | New Route | Carter | 022-CR-1080 -000 | 0 | 0.148 | 0.148 | Local Roadway Improvements | 3 |  | 0 |  | 500000 |  | 500000 |  | 75000 |  | 1000000 |  | 2017-05-01 14:12 |  | Reconstruct Harvey Branch Road (CR 1080) to facilitate heavy truck traffic between KY 7 and KY 9. This will provide a safer intersection than the existing KY7/KY 9 intersection. Reconstructed route will potentially be accepted into the SPRS. | 9 | East | 1.982 | 0.035928 | 0 | 0 | 1.9461 | 0 | 0 | 0 | 2
Y | 9 | FIVCO ADD | IP20130103 |  |  |  | Reconstruct US 60 @ KY 182 to improve intersection geometry and sight distance. | Reconstruction | Carter | 022-US-0060 -000 | 14.5 | 15 | 0.5 | Improve Intersection | 26 |  | 0 |  | 600000 |  | 1000000 |  | 350000 |  | 2500000 |  | 2017-05-01 13:47 |  | Reconstruct US 60 @ KY 182 to improve intersection geometry and sight distance. Upgrade horizontal and vertical geometries to current design standards. | FIVCO ADD | East | 32.6871 | 5.1497 | 12.6647 | 6.3099 | 2.6946 | 0 | 0 | 5.8683 | 33
Y | 9 | Huntington-Ashland-Ironton MPO | IP20130104 |  |  |  | Reconstruct KY-1 to improve horizontal and vertical alignment deficiencies, add shoulders and improve clear zones. Turn lanes may be considered at location of Argillite Elementary School and KY-207 intersection. | Safety-Haz-Elm | Greenup | 045-KY-0001 -000 | 12.4 | 13.2 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 500000 |  | 1000000 |  | 4000000 |  | 2017-05-01 14:21 | Reconstruct KY-1 to improve horizontal and vertical alignment deficiencies, add shoulders and improve clear zones. | Reconstruct KY-1 to improve horizontal and vertical alignment deficiencies, add shoulders and improve clear zones. Turn lanes may be considered at location of Argillite Elementary School and KY-207 intersection. | Huntington/KYOVA MPO | East | 20.1272 | 2.7545 | 4.6707 | 5.5464 | 2.0659 | 0 | 0 | 5.0898 | 20
Y | 9 | Huntington-Ashland-Ironton MPO | IP20130105 |  |  |  | Rehabilitate KY-503 (between MP 5.481 to MP 9.104) by improving pavement, drainage, guardrail, clear zones, etc., to increase safety and improve pavement conditions. | Safety-Haz-Elm | Greenup | 045-KY-0503 -000 | 5.481 | 9.104 | 3.623 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 2000000 |  | 2000000 |  | 7500000 |  | 2015-03-11 11:53 | Rehabilitate KY-503 (between MP 5.481 to MP 9.104) by improving pavement, drainage, guardrail, clear zones, etc., to increase safety and improve pavement conditions. | Rehabilitate KY-503 (between MP 5.481 to MP 9.104) by improving pavement, drainage, guardrail, clear zones, etc., to increase safety and improve pavement conditions.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20130106 |  |  |  | Rehabilitate KY-1458 (between MP 0.0-Boyd/Greenup County Line and MP 4.016-KY-693) to improve pavement conditions, drainage and overall mobility. | Safety-Haz-Elm | Greenup | 045-KY-1458 -000 | 0 | 4.016 | 4.016 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1000000 |  | 2000000 |  | 3000000 |  | 10000000 |  | 2017-05-01 14:26 | Rehabilitate KY-1458. | Rehabilitate KY-1458 (between MP 0.0-Boyd/Greenup County Line and MP 4.016-KY-693) to improve pavement conditions, drainage and overall mobility. | 9 | East | 31.0763 | 5.9641 | 9.9701 | 11.8787 | 3.2635 | 0 | 0 | 0 | 31
Y | 9 | Buffalo Trace ADD | IP20130107 |  |  |  | Reconstruct US 62/KY 10 intersection to improve safety, congestion and intersection function. | Reconstruction | Mason | 081-US-0062 -000 | 17 | 17.3 | 0.3 | Other Improvement Types | 0 |  | 25000 |  | 1500000 |  | 2500000 |  | 750000 |  | 5000000 |  | 2013-08-12 14:37 | To improve safety and mobility | Reconstruct US 62/KY 10 intersection to improve safety, congestion and intersection function.
Y | 9 | Buffalo Trace ADD | IP20130108 |  |  |  | Rehabilitate US 68 to improve pavement conditions, drainage, shoulders, guardrail, etc. | Safety-Haz-Elm | Mason | 081-US-0068 -000 | 0 | 4.6 | 4.6 | Other Improvement Types | 0 | Y | 10000 |  | 500000 |  | 0 |  | 250000 |  | 10000000 |  | 2013-08-12 14:45 | To improve mobility. | Rehabilitate US 68 to improve pavement conditions, drainage, shoulders, guardrail, etc.
Y | 9 | Buffalo Trace ADD | IP20130109 |  |  |  | Reconstruct KY 8 to improve safety and regional connectivity. | Reconstruction | Lewis | 068-KY-0008 -000 | 28.4 | 32.36 | 3.96 | Other Improvement Types | 0 |  | 10000 |  | 3000000 |  | 4000000 |  | 1500000 |  | 20000000 |  | 2013-08-12 15:07 | To improve safety and mobility | Reconstruct KY 8 to improve safety and regional connectivity.
Y | 9 | Buffalo Trace ADD | IP20130110 | 9-8806 / 9-8806.10 |  | A | RECONSTRUCT KY-8 FROM KY-8C IN GARRISON TO SCAFFOLD LICK ROAD.(14CCN)(16CCR) | RECONSTRUCTION(O) | Lewis | 068-KY-0008 -000 | 24.016 | 28.95 | 4.934 | Modernize Roadway-Rural | 26 |  | 500000 |  | 1560000 | 2017 | 5790000 | 2019 | 3940000 | 2019 | 36500000 | 2021 | 2017-04-26 11:05 | Improve safety and mobility | Reconstruct KY 8 to improve safety and regional connectivity. | BUFFALO TRACE ADD | East | 36.759 | 2.994 | 8.8024 | 10.1722 | 3.0539 | 0 | 2.994 | 8.7425 | 37
Y | 9 | Buffalo Trace ADD | IP20130151 |  |  |  | Reconstruct US 62 in Mason County from the Robertson County line (milepoint 0.000) through the community of Sardis and to the junction of KY 324 (milepoint 3.528). This includes the area known as the "twin bridges" where two bridges are within 150 feet f | Reconstruction | Mason | 081-US-0062 -000 | 0.7 | 3.528 | 2.828 | Other Improvement Types | 0 |  | 300000 |  | 3000000 |  | 5000000 |  | 2000000 |  | 20000000 |  | 2017-03-17 11:31 | To improve safety and mobility | The reconstruction is proposed to correct a narrow roadway width as well as correcting horizontal curve deficiencies.
Y | 9 | Buffalo Trace ADD | IP20140003 |  |  |  | To improve safety by realigning the intersection of KY 1325 at Martha Mills Road and improving the horizontal and vertical curves. Realigning the intersection would correct/eliminate extremely limited site distance looking south KY 1325. School buses make | Safety-Haz-Elm | Fleming | 035-KY-1325 -000 | 9.7 | 10.6 | 0.9 | Realign Intersection | 26 |  | 0 |  | 750000 |  | 275000 |  | 200000 |  | 5000000 |  | 2017-05-01 14:18 | To improve safety and mobility | Realign the intersection of KY 1325 at Martha Mills Road and improving the horizontal and vertical curves. Realigning the intersection would correct/eliminate extremely limited site distance looking south KY 1325. School buses make left hand turn from Mar | 9 | East | 3.6243 | 0.68263 | 0 | 0.78593 | 2.1557 | 0 | 0 | 0 | 4
Y | 9 | FIVCO ADD | IP20140023 |  |  |  | Curve correction to improve horizontal alignment which will include a bridge replacement. | Reconstruction | Carter | 022-KY-0174 -000 | 6.56 | 6.65 | 0.09 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 350000 |  | 400000 |  | 5000000 |  | 2015-04-09 13:13
Y | 9 | Buffalo Trace ADD | IP20140027 |  |  |  | Reconstruct KY 8 (Dugan's Curve) to improve safety and regional connectivity. | Reconstruction | Lewis | 068-KY-0008 -000 | 14.45 | 14.95 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1000000 |  | 750000 |  | 5000000 |  | 2017-03-08 09:38 | To improve safety | This curve has been the site of multiple accidents. The curve needs to be realigned | BUFFALO TRACE ADD | East | 24.8293 | 4.2156 | 10.3293 | 4.0868 | 1.4072 | 0 | 0 | 4.7904 | 25
Y | 9 | FIVCO ADD | IP20150016 |  |  |  | Reconstruct horizontal & vertical deficiencies on KY 706, near the intersection of Barker Road, from milepoints 9.5 to 9.8. | Reconstruction | Elliott | 032-KY-0706 -000 | 9.5 | 9.8 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 275000 |  | 150000 |  | 250000 |  | 1750000 |  | 2015-04-09 13:15
Y | 9 | Gateway ADD | IP20150060 |  |  |  | Improve safety and geometrics and add shoulders on US 60 between Milepoints 11.2 and 11.4 around the KY 965 intersection. | Reconstruction | Bath | 006-US-0060 -000 | 11.2 | 11.35 | 0.15 | Modernize Roadway-Rural | 26 |  | 100000 |  | 1000000 |  | 1500000 |  | 1000000 |  | 8000000 |  | 2015-03-27 14:35 | The purpose of this project is to: improve safety, improve geometrics, and add shoulders. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Horizontal/Vertical Alignment, 3) Improve Drainage, 4) Add Shoulders, 4) Address Steep Horizontal Curves, and 5) Improve Dropoffs and Inadequate Clear Zones. | 9 | East | 20.8323 | 4.6946 | 2.6946 | 1.5269 | 1.3174 | 7.485 | 0 | 3.1138 | 21
Y | 9 | Gateway ADD | IP20150068 |  |  |  | Improve safety on KY 36 from the intersection with 1-64 to the intersection of KY 965 (Hart Pike) including the curves known as Clear Creek Furnace and Thomas Hill. | Reconstruction | Bath | 006-KY-0036 -000 | 13.4 | 17.2 | 3.8 | Modernize Roadway-Rural | 26 |  | 200000 |  | 2500000 |  | 2500000 |  | 2000000 |  | 27000000 |  | 2017-05-01 08:26 | The purpose of this project is to improve safety. | The following need has been identified for this project: 1) Improve Roadway Safety. | 9 | East | 39.8503 | 4.5509 | 8.2635 | 9.4311 | 2.6347 | 7.5449 | 0 | 7.4251 | 40
Y | 9 | Gateway ADD | IP20150102 |  |  |  | Improve safety and operational efficiency on US 60 from the intersection of KY 32 to approximately 750 feet east of the intersection of KY 799. | Reconstruction | Rowan | 103-US-0060 -000 | 9.683 | 12.998 | 3.315 | Modernize Roadway-Rural | 26 |  | 200000 |  | 2500000 |  | 5000000 |  | 3000000 |  | 20000000 |  | 2015-03-16 11:12 | The purpose of this project is to improve safety and operational efficiency. | The following needs have been identified fort his project: 1) improve safety; and 2) improve operational efficiency.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150103 |  |  |  | Reconstruct KY 7 from its junction with KY 2 to the intersection of KY 827. | Reconstruction | Greenup | 045-KY-0007 -000 | 0 | 7.269 | 7.269 | Other Improvement Types | 0 |  | 250000 |  | 4000000 |  | 6000000 |  | 4000000 |  | 45000000 |  | 2015-04-09 11:23 | Reconstruct KY 7 from its junction with KY 2 to the intersection of KY 827. | Reconstruct KY 7 from its junction with KY 2 to the intersection of KY 827.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150104 |  |  |  | Reconstruct KY 7 from the intersection with KY 827 to its intersection with Rakes Mill Road. | Reconstruction | Greenup | 045-KY-0007 -000 | 7.269 | 13.03 | 5.761 | Other Improvement Types | 0 |  | 250000 |  | 3500000 |  | 3500000 |  | 3000000 |  | 37000000 |  | 2015-04-09 11:21 | Reconstruct KY 7 from the intersection with KY 827 to its intersection with Rakes Mill Road. | Reconstruct KY 7 from the intersection with KY 827 to its intersection with Rakes Mill Road.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150105 |  |  |  | Reconstruct KY 7 from its intersection with Rakes Mill Road to its intersection with US 23 in South Shore. | Reconstruction | Greenup | 045-KY-0007 -000 | 13.03 | 20.052 | 7.022 | Other Improvement Types | 0 |  | 250000 |  | 4000000 |  | 6000000 |  | 4000000 |  | 45000000 |  | 2015-04-09 11:17 | Reconstruct KY 7 from its intersection with Rakes Mill Road to its intersection with US 23 in South Shore. | Reconstruct KY 7 from its intersection with Rakes Mill Road to its intersection with US 23 in South Shore.
Y | 9 | Gateway ADD | IP20150106 |  |  |  | Provide a planning study to determine possible alternates and feasibility of extending KY 801 from its intersection with KY 158 at Sharkey to KY 32 near the Fleming/Rowan county line. | New Route | Rowan | 103-KY-0801 -000 | 15.61 | 17.011 | 1.401 | Transportation Studies | 0 |  | 350000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-05-01 14:45 | The purpose of this project is to complete a planning study for a new route. | The following need has been identified for this project: complete a planning study to determine alternates and feasibility of extending KY 801. | 9 | East | 17.735 | 5.4371 | 0 | 10.8907 | 1.4072 | 0 | 0 | 0 | 18
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150131 |  |  |  | Reconstruct the intersection of US 60 & "Old 13th Street" (CS 2232) to descrease the number/risk of rear-end crashes and backups. | Reconstruction | Boyd | 010-US-0060 -000 | 10.4 | 10.5 | 0.1 | Other Improvement Types | 0 | Y | 50000 |  | 100000 |  | 350000 |  | 50000 |  | 750000 |  | 2015-04-21 13:44 | Reconstruct the intersection of US 60 & "Old 13th Street" (CS 2232) | To decrease the number/risk of rear-end crashes and backups.
Y | 9 | Bluegrass ADD | IP20150147 | 9-205 |  | A | IMPROVE THE KY-36/KY-32 INTERSECTION NEAR THE NICHOLAS COUNTY SCHOOL PROPERTY. (12CCR)(16CCR) | SAFETY(P) | Nicholas | 091-KY-0036 -000 | 3.1 | 3.283 | 0.183 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1380000 | 2024 | 890000 | 2024 | 5130000 | 2025 | 2019-03-06 08:49 | Improve Safety and Mobility | The current intersection has an atypical alignment. This project will help relieve congestion and increase safety and mobility by eliminating the existing signalized intersection and constructing a roundabout to the west of the current intersection locat | 9 | East | 53.449 | 3.4371 | 4.9401 | 7.7246 | 1.4072 | 0 | 0 | 5.94 | 23 | 15 | 15
Y | 9 | Gateway ADD | IP20150162 |  |  |  | Construct new route on KY 965 from Kendall Springs Road to Bath County High School in Owingsville. | New Route | Bath | 006-KY-0965 -000 | 6.6 | 7.997 | 1.397 | Construct Road in New Location | 0 |  | 240000 |  | 1200000 |  | 0 |  | 0 |  | 0 |  | 2017-03-17 10:48 | The purpose of this project is to construct a new route. | The following need has been identified for this project: construct a new route.
Y | 9 | Bluegrass ADD | IP20150176 | 9-8811 |  | A | RECONSTRUCT KY 36/KY 928 INTERSECTION. (14CCN)(16CCR)(18CCN) | RECONSTRUCTION(O) | Nicholas | 091-KY-0036 -000 | 8 | 8.23 | 0.23 | Improve Intersection | 26 |  |  |  | 0 |  | 200000 | 2021 | 160000 | 2021 | 470000 | 2023 | 2019-03-06 08:54 | Improve sight distance and safety. | Currently KY 928 intersects KY 36 at a location with very poor sight distance. It is proposed that KY 928 will be realigned and the intersection at KY 36 will shifted to the north and reconstructed at the peak of the vertical curve to improve sight dista | 9 | East | 21.8623 | 2.7904 | 11.7665 | 1.7964 | 1.8563 | 0 | 0 | 3.6527 | 22
Y | 9 | Buffalo Trace ADD | IP20150186 |  |  |  | CONSTRUCT RIGHT TURN LANE (SB) INTO CLARKSON SHERMAN ROAD (LANDFILL, 4.740) TO PROVIDE SAFETY FOR MOTORISTS TRAVELING ALONG THE AA HIGHWAY. (MP 4.6 TO MP 4.9)(14CCN) Replaces 09 081 D0009 1.50 | Safety-Haz-Elm | Mason | 081-KY-0009 -000 | 4.6 | 4.9 | 0.3 | Modernize Roadway-Rural | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 300000 |  | 2017-03-17 11:57 | To improve safety and mobility. | TO PROVIDE SAFETY FOR MOTORISTS TRAVELING ALONG THE AA HIGHWAY.
Y | 9 | FIVCO ADD | IP20150245 | 9-8401 |  | A | RECONSTRUCT US-60 FROM WEST OF GLENWOOD HOLLOW ROAD TO EAST OF KY-3296. THE PROJECT SHALL INCLUDE 12' LANES, WIDE PAVED SHOULDERS, UNOBSTRUCTED CLEAR ZONES, FLATTER VERTICAL GRADES, AND GENTLY HORIZONTAL CURVES. (08CCN)(12CCR)(14CCR)(18CCN) | SAFETY(P) | Carter | 022-US-0060 -000 | 16 | 17.112 | 1.112 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1780000 | 2021 | 1630000 | 2022 | 11280000 | 2024 | 2019-02-25 08:10 |  |  | 9 | East | 36.5015 | 4.5629 | 8.3533 | 6.3997 | 2.1856 | 0 | 0 | 0 | 22 | 15
Y | 9 | FIVCO ADD | IP20150332 | 9-8802 |  | A | KY-32 FROM 9.2 MILE MARKER TO 10.2 MILE MARKER WIDENING. (14CCN)(16CCR)(18CCN) | MAJOR WIDENING(O) | Elliott | 032-KY-0032 -000 | 9.2 | 10.2 | 1 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2021 | 480000 | 2022 | 320000 | 2023 | 9335000 | 2024 | 2018-07-10 08:18 |  |  | FIVCO ADD | East | 26.5105 | 1.4731 | 4.0419 | 4.1991 | 4.5808 | 6.5868 | 0 | 5.6287 | 26
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150338 | 9-8509 |  | A | IMPROVE KY-207 FROM THE INDUSTRIAL PARKWAY TO THE KY-693 INTERSECTION IN FLATWOODS.(08CCN)(16CCR) | NEW ROUTE(O) | Greenup | 045-KY-0207 -000 | 10.932 | 15.88 | 4.948 | Modernize Roadway-Rural | 26 |  |  |  | 2000000 | 2024 | 9270000 | 2025 | 7310000 | 2025 | 30420000 | 2025 | 2018-07-10 08:18 | To improve connectivity for economic development and safety at KY-207 in Flatwoods and KY-693 and the Industrial Parkway Connector between I64 and US-60. | Construction of a new facility (Braidy Industries and subsidiaries) will require improvement and/or new construction of a roadway with access to EastPark to provide safety and adequate access for employees, to allow for movement of freight, and reduce tra | Huntington/KYOVA MPO | East | 72.0165 | 5.018 | 10.2395 | 13.765 | 3.8323 | 0 | 0 | 9.1617 | 42 | 15 | 15
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150377 |  |  |  | Complete construction to ultimate 4-lane facility of KY 67 from junction with Technology Drive (MP 1.4) to US 23 in Wurtland (MP 13.039), a total of 11.639 miles. | Major Widening | Greenup | 045-KY-0067 -000 | 1.4 | 13.039 | 11.639 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 1350000 |  | 0 |  | 500000 |  | 56160000 |  | 2017-04-13 11:51 | Construction on KY 67 from junction with Technology Drive (MP 1.4) to US 23 in Wurtland (MP 13.039), a total of 11.639 miles. | Complete construction to ultimate 4-lane facility of KY 67 from junction with Technology Drive (MP 1.4) to US 23 in Wurtland (MP 13.039), a total of 11.639 miles.
Y | 9 | Gateway ADD | IP20150401 |  |  |  | Improve safety, geometrics, and operational efficiency on KY 36 from the intersection of Old KY 11 (MP 1.0) to the intersection of KY 1325 (MP 7.0). | Reconstruction | Bath | 006-KY-0036 -000 | 1.004 | 6.97 | 5.966 | Modernize Roadway-Rural | 26 |  | 400000 |  | 2100000 |  | 2700000 |  | 1200000 |  | 40000000 |  | 2017-03-17 11:51 | The purpose of this project is to improve safety, geometrics, width, and operational efficiency. | The following needs have been identified for this project: 1) improve safety; 2) improve horizontal alignment; 3) widen roadway; and 4) improve operational efficiency.
Y | 9 | FIVCO ADD | IP20150409 | 9-192.01 |  | A | IMPROVE KY-32 FROM WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(06CCR) (08CCR) (10CCR)(12CCR)(14CCR)(16CCR)(18CCR) | RECONSTRUCTION(O) | Elliott | 032-KY-0032 -000 | 2 | 8.656 | 6.656 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2021 | 5000000 | 2022 | 46510000 | 2023 | 2018-07-10 08:18 |  |  | FIVCO ADD | East | 63.7964 | 0.38323 | 5.479 | 8.5329 | 3.9521 | 5.6886 | 0 | 9.7605 | 34 | 15 | 15
Y | 9 | Buffalo Trace ADD | IP20150416 |  |  |  | NEW FULLY CONTROLLED ACCESS ROUTE FROM US 68 NEAR WASHINGTON EAST TO KY 11 INCLUDING A NEW I-CHNG AT KY 11. (PRIORITY SECTION)(2004BOPC)(06CCR) | New Route | Mason | 081-KY-0009 -000 | 7.4 | 12.6 | 5.2 | Other Improvement Types | 0 | Y | 0 |  | 780000 |  | 1580000 |  | 1820000 |  | 32450000 |  | 2016-11-01 14:58 | To improve safety and mobility | Remediating congestion and providing a route for trucks to use instead of using the AA.
Y | 9 | Buffalo Trace ADD | IP20150419 |  |  |  | RECONSTRUCT US 62 GOING TO SARDIS BETWEEN KY 324 AND SARDIS (BETWEEN TWIN BRIDGES). (14CCN) | Reconstruction | Mason | 081-US-0062 -000 | 0.7 | 3.528 | 2.828 | Other Improvement Types | 0 |  | 300000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-03-08 14:13 | To improve safety and mobility | The road is very narrow and curvy and has had issue with road side slipping. The road needs to be reconstructed.
Y | 9 | Buffalo Trace ADD | IP20150420 |  |  |  | NEW FULLY CONTROLLED ACCESS ROUTE FROM KY 11 NORTHEAST TO KY 9 (AA HWY) INCLUDING NEW I-CHNG AT KY 9. (2004BOPC)(06CCR) | New Route | Mason | 081-KY-0011 -000 | 8 | 11 | 3 | Other Improvement Types | 0 |  | 0 |  | 780000 |  | 1580000 |  | 1820000 |  | 33750000 |  | 2016-11-01 15:00 | To improve safety and mobility | Remediating congestion and providing a route for trucks to use instead of using the AA through the Walmart/Lowes area.
Y | 9 | Bluegrass ADD | IP20150425 |  |  |  | SAFETY IMPROVEMENTS ALONG KY 32 FROM LAKE ROAD (MP 9.5) TO SCRUBGRASS CREEK (MP 12.5) TO CORRECT HORIZONTAL, VERTICAL, PAVEMENT WITH DEFICIENCIES. (14CCN) replaces 09 091 D0032 1.40 | Safety-Haz-Elm | Nicholas | 091-KY-0032 -000 | 9.5 | 12.5 | 3 | Modernize Roadway-Rural | 26 |  | 100000 |  | 2000000 |  | 2000000 |  | 1500000 |  | 0 |  | 2017-03-17 11:43 | Improve safety, mobility, and drainage. Roadway is currently not up to geometric standards. | The current roadway has many geometric deficiencies. This project will provide minor realignment and widening to improve safety along the corridor. Drainage will also be upgraded and slide areas will be reinforced to enhance the longevity of the roadway.
Y | 9 | Huntington-Ashland-Ironton MPO | IP20150434 |  |  |  | LEWIS-GREENUP CONNECTOR ROAD CONNECTING KY-8 TO KY-10 AT SCAFFOLD LICK ROAD. (14CCN) | New Route | Greenup | 045-CR-1023 -000 | 0 | 0.931 | 0.931 | Construct Road in New Location | 0 |  | 500000 |  | 1500000 |  | 0 |  | 0 |  | 0 |  | 2017-03-08 13:38 | To provide safe access between Lewis and Greenup counties | The current roadway requires improvement to accommodate safety and efficient travel between the counties of Lewis and Greenup.
Y | 9 | Buffalo Trace ADD | IP20150469 |  |  |  | Safety (or Spot) Improvements and Pavement Rehab from the east end of the Flemingsburg Bypass to 0.5 mile into Rowan County. | Reconstruction | Fleming | 035-KY-0032 -000 | 13 | 28.293 | 15.293 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 6000000 |  | 5000000 |  | 35000000 |  | 2015-07-02 17:29 | To improve safety and mobility. | Safety (or Spot) Improvements and Pavement Rehab from the east end of the Flemingsburg Bypass to 0.5 mile into Rowan County
Y | 9 | Huntington-Ashland-Ironton MPO | IP20160007 |  |  |  | Remove the existing raised median to create a center-turn lane on Greenup Avenue from the southern split with Winchester Avenue to the intersection of 20th Street. | Reconstruction | Boyd | 010-US-0023 -000 | 17.065 | 18.055 | 0.99 | Other Improvement Types | 0 | Y | 0 |  | 50000 |  | 0 |  | 0 |  | 700000 |  | 2017-05-26 16:22 | Remove the existing raised median to create a center-turn lane on Greenup Avenue from the southern split with Winchester Avenue to the intersection of 20th Street. | Remove the existing raised median to create a center-turn lane on Greenup Avenue from the southern split with Winchester Avenue to the intersection of 20th Street. | Huntington/KYOVA MPO | East | 24.5539 | 7.1138 | 0 | 11.5419 | 0.98802 | 0 | 4.9102 | 0 | 25
Y | 9 | Gateway ADD | IP20160013 |  |  |  | Complete planning/congestion mitigation study on KY 32 at the I 64 interchange. | Congestion Management | Rowan | 103-KY-0032 -000 | 3.9 | 6.4 | 2.5 | Transportation Studies | 0 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-08-24 14:00 | The purpose of this project is to complete a planning/congestion mitigation study. | The following needs have been identified for this project: 1) during peak traffic flow times there is significant congestion centered at the KY 32/ I 64 interchange; 2) the area is a well-developed comercial areas and receives school, recreational, and in
Y | 9 | Gateway ADD | IP20160094 |  |  |  | Construct new route on KY 36 from Kendall Springs road to Bath County High School in Owingsville. | New Route | Bath | 006-KY-0036 -000 | 11.85 | 12.7 | 0.85 | Construct Road in New Location | 0 |  | 240000 |  | 1200000 |  | 0 |  | 0 |  | 0 |  | 2017-03-17 10:46 | The purpose of this project is to construct a new route. | The following need has been identified for this project: construct a new route.
Y | 9 | FIVCO ADD | IP20160125 | 9-228 |  | A | IMPROVE KY-7 FROM SOUTH CITY LIMITS OF SANDY HOOK TOWARD WRIGLEY. (12CCR)(16CCR)(18CCR) | RECONSTRUCTION(O) | Elliott | 032-KY-0007 -000 | 0 | 6.956 | 6.956 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 | 2021 | 13230000 | 2022 | 6490000 | 2023 | 61660000 | 2024 | 2018-07-10 08:18 |  |  | FIVCO ADD | East | 73.7829 | 2.4431 | 6.1976 | 12.4177 | 3.6527 | 6.8862 | 3.2036 | 8.982 | 44 | 15 | 15
Y | 9 | FIVCO ADD | IP20160126 |  |  |  | RECONSTRUCT KY 7 FROM SOUTH CITY LIMITS OF SANDY HOOK TOWARD WRIGLEY. (12CCR) (16CCN). | Reconstruction | Elliott | 032-KY-0007 -000 | 0 | 6.956 | 6.956 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-03-14 16:06
Y | 9 | FIVCO ADD | IP20160127 |  |  |  | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND. (PRIORITY SECTION I)(16CCR) | Reconstruction | Elliott | 032-KY-0032 -000 | 2 | 8.656 | 6.656 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-03-14 15:53
Y | 9 | FIVCO ADD | IP20160128 |  |  |  | RECONSTRUCT KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO 0.408 MI WEST OF STEGALL COLD SPRING ROAD IN ELLIOTT COUNTY. (16CCN) | Reconstruction | Elliott | 032-KY-0032 -000 | 0 | 2 | 2 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-03-14 15:56
Y | 9 | Gateway ADD | IP20160138 |  |  |  | Improve safety on US 60 from approximately Milepoint 5.0 west of North Stepstone Rd to approximately Milepoint 6.4 between Malibu Dr and Mandy Ave in Owingsville. | Safety-Haz-Elm | Bath | 006-US-0060 -000 | 4.98 | 6.429 | 1.449 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-19 10:31 | The purpose of this project is to improve safety. | The following needs have been identified for this project: 1) Improve Roadway Safety; and 2) Install Guardrail).
Y | 9 | Gateway ADD | IP20160143 |  |  |  | Improve safety on KY 32 from 0.1 mile east of US 60 (approximately Milepoint 8.5) to Veterans Lane in Rowan County. | Reconstruction | Rowan | 103-KY-0032 -000 | 8.545 | 13.645 | 5.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-19 11:05 | The purpose of this project is to improve safety. | The following need has been identified for this project: perform low cost safety improvements.
Y | 9 | Gateway ADD | IP20160169 |  |  |  | Construct a new interchange to provide west turn lanes on US 60 at Sunnybrook, east of Morehead. | New Interchange | Rowan | 103-US-0060 -000 | 11.4 | 12.2 | 0.8 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-11-03 11:23 | The purpose of this project is to construct a new interchange. | The following need has been identified for this project: construct new turning lanes at Sunnybrook.
Y | 9 | Buffalo Trace ADD | IP20160180 | 9-8902 |  | A | IMPROVE ACCESS AND RESPONSE TIMES FOR THE FLEMINGSBURG FIRE DEPARTMENT TO THE BYPASS AT MP 11.574. (16CCN)(18CCN) | SAFETY(P) | Fleming | 035-KY-0011 -000 | 11.573 | 11.575 | 0.002 | Other Improvement Types | 0 | [9 empty] | 80000 | 2019 |  | To improve mobility. | IMPROVE ACCESS AND RESPONSE TIMES FOR THE FLEMINGSBURG FIRE DEPARTMENT TO THE BYPASS | BUFFALO TRACE ADD | East | 13.1796 | 8.5988 | 0 | 0 | 0 | 0 | 4.5808 | 0 | 13
Y | 9 | FIVCO ADD | IP20160289 |  |  |  | CW Stevens Boulevard (CS 1110) carries approximately 6,300 vpd, with notable congestion at KY 1. It lacks defined entrances, improved radii at KY 1, and sidewalks. The street is the largest and most recognized Grayson freight generator. This project woul | Minor Widening | Carter | 022-CS-1110 -000 | 0 | 0.427 | 0.427 | Local Roadway Improvements | 3 |  | 0 |  | 100000 |  | 100000 |  | 250000 |  | 1664000 |  | 2016-12-29 14:58 |  | CW Stevens Boulevard (CS 1110) carries approximately 6,300 vpd, with notable congestion at KY 1. It lacks defined entrances, improved radii at KY 1, and sidewalks. The largest and most recognized Grayson freight generator, other than the two truck stops a
Y | 9 | FIVCO ADD | IP20160291 |  |  |  | CW Stevens Boulevard (City Street [CS] 1110) carries approximately 6,300 vpd. Currently, motorists traveling westbound on CW Stevens Boulevard must negotiate the congested KY 1/CW Stevens Boulevard intersection to travel to and from KY 9 (AA Highway). Th | New Route | Carter | 022-KY-0001 -000 | 11.915 | 12.275 | 0.36 | Construct Road in New Location | 0 |  | 0 |  | 250000 |  | 500000 |  | 150000 |  | 2030000 |  | 2017-05-01 13:55 |  | CW Stevens Boulevard (City Street [CS] 1110) carries approximately 6,300 vpd. Currently, motorists traveling westbound on CW Stevens Boulevard must negotiate the congested KY 1/CW Stevens Boulevard intersection to travel to and from KY 9 (AA Highway). Amo | FIVCO ADD | East | 19.7021 | 4.5749 | 0 | 6.265 | 0 | 8.8623 | 0 | 0 | 20
Y | 9 | FIVCO ADD | IP20160294 |  |  |  | Carol Malone Boulevard (KY 1) is congested approaching the I-64 interchange area with six intersections operating at LOS D, E, or F. This section carries between 7,720 and 13,620 vpd. Moreover, congestion exists due to lack of an alternative north-south r | New Route | Carter | 022-KY-0001 -000 | 11.369 | 11.915 | 0.546 | Construct Road in New Location | 0 | Y | 0 |  | 560000 |  | 250000 |  | 3150000 |  | 5580000 |  | 2016-12-29 15:11 |  | Carol Malone Boulevard (KY 1) is congested approaching the I-64 interchange area with six intersections operating at LOS D, E, or F. This section carries between 7,720 and 13,620 vpd. Moreover, congestion exists due to lack of an alternative north-south r
Y | 9 | FIVCO ADD | IP20160295 |  |  |  | Carol Malone Boulevard (KY 1) is congested approaching the I-64 interchange area with six intersections operating at LOS D, E, or F. Moreover, congestion exists due to lack of an alternative north-south route and lack of an access road for new development | New Route | Carter | 022-KY-0001 -000 | 10.646 | 11.369 | 0.723 | Construct Road in New Location | 0 |  | 0 |  | 850000 |  | 500000 |  | 250000 |  | 6900000 |  | 2016-12-29 15:13 |  | As noted with Alternative BB, Carol Malone Boulevard (KY 1) is congested approaching the I-64 interchange area with six intersections operating at LOS D, E, or F. Moreover, congestion exists due to lack of an alternative north-south route and lack of an a
Y | 9 | Buffalo Trace ADD | IP20160296 |  |  |  | Project is for reconstruction of Springdale Road to a wider typical section with shoulders and a new cross country connection to KY 3161. Carmeuse representatives state the need for better access to the AA Highway (KY 10). Currently, this facility generat | Reconstruction | Mason | 081-CR-1012 -000 | 0 | 2.502 | 2.502 | Local Roadway Improvements | 3 |  | 0 |  | 1750000 |  | 1000000 |  | 1500000 |  | 15250000 |  | 2016-12-29 14:38 | To improve safety and mobility | Carmeuse Lime and Stone, located along the Ohio River on Springdale Road, produces high calcium and dolomitic lime, chemical grade limestone, and crushed limestone aggregate products. Large trucks heading to/from the facility follow Springdale Road (CR 10
Y | 9 | Buffalo Trace ADD | IP20160297 |  |  |  | This project would widen KY 2515 to three lanes from the Intermediate School to US 62 providing right- and left-turn lanes at US 62. The project also would widen the right-turn radius from US 62 to KY 2515 and KY 2515 to Martha Comer Drive. The road impro | Safety-Haz-Elm | Mason | 081-KY-2515 -000 | 1.391 | 1.7 | 0.309 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 75000 |  | 200000 |  | 980000 |  | 2016-12-29 14:45 | To improve safety and mobility. | The turning radii at KY 2515 (Clarks Run Road) intersections with US 62 and Martha Comer Drive are problematic for school buses according to local officials/stakeholders. KY 2515 has also seen an increase in school-related traffic due to two new schools o | 9 | East | 21.2246 | 7.497 | 6.2874 | 2.8293 | 0.77844 | 0 | 0 | 3.8323 | 21
Y | 9 | Buffalo Trace ADD | IP20160298 |  |  |  | This project would provide a 300 foot right turn lane to accommodate decelerating vehicles. A double 7’x16’ culvert would be widened due to additional fill needed to widen the roadway. An additional low cost option to this project would be to extend the 4 | Safety-Haz-Elm | Mason | 081-KY-0009 -000 | 10.6 | 10.9 | 0.3 | Improve Intersection | 26 | Y | 0 |  | 200000 |  | 50000 |  | 150000 |  | 787000 |  | 2017-05-01 14:32 | To provide safety and mobility. | The Meadowview Regional Medical Center is located on Kenton Station Drive off of KY 9 (AA Highway) (MP 10.861) about a half mile west of the KY 9 and US 62 Intersection. Local Officials/Stakeholders identified this location as the main entrance to the hos | 9 | East | 35.6886 | 7.1257 | 13.6527 | 4.9401 | 0 | 0 | 4.9401 | 5.0299 | 36
Y | 9 | Buffalo Trace ADD | IP20160299 |  |  |  | Alternative N would realign KY 10 east of the KY 1449 intersection to improve curves to 45 mph design speed, provide a longer tangent section between curves and improve sight distance. This section of KY 10 carries 1,120 vpd with 10% trucks and is a high | Safety-Haz-Elm | Mason | 081-KY-0010 -000 | 6.058 | 6.558 | 0.5 | Improve Intersection | 26 |  | 0 |  | 350000 |  | 200000 |  | 250000 |  | 1578000 |  | 2016-12-29 14:50 | To improve safety and mobility. | Alternative N would realign KY 10 east of the KY 1449 intersection to improve curves to 45 mph design speed, provide a longer tangent section between curves and improve sight distance. This section of KY 10 carries 1,120 vpd with 10% trucks and is a high
Y | 9 | Buffalo Trace ADD | IP20160300 |  |  |  | This section of KY 1236 between MPs 1.1 and 1.3 carries 1,640 vpd and is a high crash location. The existing speed limit of the corridor is 55 mph, however there is an advanced warning sign for 20 mph 90 degree curve to the right and then 90 degree curve | Safety-Haz-Elm | Mason | 081-KY-1236 -000 | 1 | 1.5 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 250000 |  | 300000 |  | 340000 |  | 2016-12-29 14:54 | To improve safety and mobility | This section of KY 1236 between MPs 1.1 and 1.3 carries 1,640 vpd and is a high crash location. The existing speed limit of the corridor is 55 mph, however there is an advanced warning sign for 20 mph 90 degree curve to the right and then 90 degree curve
Y | 9 | Buffalo Trace ADD | IP20160301 |  |  |  | Add right-turn land on KY 9 (AA) southbound at KY 11. The KY 9/KY 11 intersection currently operates and will operate in 2040 at LOS C, and was identified as a high crash location. On KY 9 at KY 11, 10 of 17 crashes (CCRF 1.84) were rear-end. This proj | Safety-Haz-Elm | Mason | 081-KY-0009 -000 | 7 | 7.8 | 0.8 | Improve Intersection | 26 | Y | 0 |  | 100000 |  | 350000 |  | 250000 |  | 325000 |  | 2017-03-17 14:47 | To improve safety and mobility. | The KY 9/KY 11 intersection currently operates and will operate in 2040 at LOS C, and was identified as a high crash location. On KY 9 at KY 11, 10 of 17 crashes (CCRF 1.84) were rear-end. This project also provides for an improvement just east of the i
Y | 9 | Buffalo Trace ADD | IP20170037 |  |  |  | This roadway serves as a shorter-route alternative for motorists traveling between US 68 at Washington and KY 11 at the KY 9 (AA) intersection. In light of the district's decision to proceed with a "No Build" FONSI for the once-proposed Maysville bypass | Reconstruction | Mason | 081-KY-1236 -000 | 0 | 1.725 | 1.725 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 4500000 |  | 4500000 |  | 18000000 |  | 2017-03-08 13:38 | To improve mobility. | This roadway serves as a shorter-route alternative for motorists traveling between US 68 at Washington and KY 11 at the KY 9 (AA) intersection. In light of the district's decision to proceed with a "No Build" FONSI for the once-proposed Maysville bypass
Y | 9 | Gateway ADD | IP20170051 |  |  |  | Widen KY 36 from north of Mariella Drive (MP 12.3) to the intersection of Old KY 36 (MP 13.0). | Major Widening | Bath | 006-KY-0036 -000 | 12.3 | 13 | 0.7 | Auxiliary Lanes or Operation Improvements | 11 |  | 0 |  | 200000 |  | 500000 |  | 500000 |  | 1000000 |  | 2017-03-15 16:49
Y | 9 | Buffalo Trace ADD | IP20170052 |  |  |  | Reconstruct KY 3056 (Jersey Ridge Road) from KY 8 to US 68. | Reconstruction | Mason | 081-KY-3056 -000 | 5.763 | 7.607 | 1.844 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 3500000 |  | 1500000 |  | 25000000 |  | 2017-03-15 17:15 | To improve safety and mobility | KY 3056 is a ridge road and has multiple slips. The road has fallen into disrepair over the years.
Y | 9 | Gateway ADD | IP20170053 | 9-192.03 |  | A | RECONSTRUCT KY-32 FROM 0.408 MILES WEST OF STEGALL COLD SPRING ROAD TO KY-7 NEAR NEWFOUNDLAND.(PRIORITY SECTION I). (10CCR)(16CCN)(18CCN) | RECONSTRUCTION(O) | Rowan | 103-KY-0032 -000 | 16.619 | 21.636 | 5.017 | Modernize Roadway-Rural | 26 |  |  |  | 3250000 | 2025 | 0 |  | 6490000 | 2025 | 66690000 | 2023 | 2018-07-10 08:18 |  |  | GATEWAY ADD | East | 54.3668 | 1.4251 | 6.6467 | 11.2949 | 4.1317 | 6.1677 | 0 | 9.7006 | 39 | 15
Y | 9 | Buffalo Trace ADD | IP20170079 |  |  |  | This project proposes to make SAFETY IMPROVEMENTS to the intersection of KY 9 (AA) and US 62 located in Maysville. This intersection is operating at a very low LOS. Delays and traffic backups are extensive especially during peak hours. Right of way is | Safety-Haz-Elm | Mason | 081-KY-0009 -000 | 10.256 | 10.398 | 0.142 | Improve Intersection | 26 | Y | 0 |  | 150000 |  | 500000 |  | 350000 |  | 1000000 |  | 2017-04-13 14:31 | To improve safety and mobility. | Delays and traffic backups are extensive especially during peak hours. | 9 | East | 60.4311 | 7.1377 | 11.6766 | 3.0539 | 0 | 0 | 4.9701 | 3.5928 | 30 | 15 | 15
Y | 9 | Gateway ADD | IP20180047 |  |  |  | Improve geometrics and intersection on KY 211 at the intersection of KY 3290 (Mudlick Road). | Reconstruction | Bath | 006-KY-0211 -000 | 5.389 | 5.489 | 0.1 | Improve Intersection | 26 |  | 0 |  | 0 |  | 210000 |  | 110000 |  | 2250000 |  | 2018-10-03 16:13 | The purpose of this project is to improve safety. | The following needs have been identified for this project: 1) Improve Roadway Safety, and 2) Improve Intersection.
Y | 9 | Gateway ADD | IP20180049 |  |  |  | Intersection improvements on US 60 and KY 519 in Morehead. | Spot Improvement | Rowan | 103-US-0060 -000 | 7.061 | 7.137 | 0.076 | [14 empty] | The purpose of this project is to complete intersection improvements. | The following needs have been identified for this project: 1) complete intersection improvements; and 2) install lighting.
Y | 9 | Gateway ADD | IP20180050 |  |  |  | Improve turning operations on US 60 for the new Rowan County Jail (approximately from Milepoint 9.1 to Milepoint 9.2). | Minor Widening | Rowan | 103-US-0060 -000 | 9.05 | 9.25 | 0.2
Y | 9 | Gateway ADD | IP20180051 |  |  |  | Straighten curves and geometrically improve the road. | Reconstruction | Bath | 006-KY-1944 -000 | 1.131 | 2.2 | 1.069 | [14 empty] | The purpose of this project is to: straighten and improve geometrics. | The following needs have been identified for this project: 1) Straighten Roadway, and 2) Improve Geometrics.
Y | 9 | Gateway ADD | IP20190033 |  |  |  | Congestion mitigation study in Morehead at the KY 32 / I-64 interchange area. The study will include an approximate one-mile length of KY 32 as well as considering an additional I-64 interchange east of Exit 137. | Transportation Study | Rowan | 103-KY-0032 -000 | 4.5 | 6.5 | 2 | Transportation Studies | 0 |  | 150000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-01 14:55 | Perform a planning study to evaluate alternatives to improve safety and mitigate congestion in Morehead in the area of the I-64 and KY 32 interchange. | During peak flow times, the commercial area near the I-64 and KY 32 interchange area in Morehead becomes very congested and traffic delays become significant. The congestion creates a difficulty for emergency vehicles to navigate through the area thereby
Y | 9 | Buffalo Trace ADD | IP20190041 |  |  |  | KY 801 Planning Study to determine purpose and need for any changes needed to the route to adequately serve industry and school traffic. Scope will include evaluating feasibility and potential benefit of extending, by new route, KY 801 from the KY 158 in | Transportation Study | Fleming | 035-KY-0801 -000 | 0.9 | 0.912 | 0.012
Y | 9 | Buffalo Trace ADD | IP20190043 |  |  |  | Restoration of the Dover Covered Bridge. In 2017, the bridge suffered significant flood damage and compromised the bridge's ability to support itself. Since, emergency repairs have been made as a temporary fix until a full restoration project could be d | Reconstruction | Mason | 081-KY-3113 -000 | 0 | 0.012 | 0.012 | Other Improvement Types | 0 |  | 0 |  | 75000 | 2021 | 5000 | 2021 | 0 |  | 1500000 | 2022 | 2019-02-15 13:57 | Restore the Dover Covered Bridge to its original design utilizing as much of the original material as possible, complying with applicable standards and procedures for the restoration of historic structures. | In 2017, a localized flood washed away (and rendered unusable by bending) retrofitted steel girders that served as the Dover Cover Bridge's primary support. The original covered bridge is believed to have been built around 1835 and was added to the Natio
Y | 9 | FIVCO ADD | IP20190048 |  |  |  | Improve geometry of KY 182 from Milepoint 10.7 to 11.8, which is near the Carter Caves State Resort Park main entrance. There is a particularly tight curve that causes trouble for larger vehicles, namely campers and motor homes visiting the park. | Spot Improvement | Carter | 022-KY-0182 -000 | 10.7 | 11.8 | 1.1 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 1500000 | 2021 | 400000 | 2022 | 500000 | 2022 | 7500000 | 2023 | 2019-03-15 09:01 | Realign a curvy section of roadway immediately east of the Carter Caves State Resort Park entrance. This realignment will likely require the construction of a new bridge over Tygarts Creek. | Motorists are required to navigate a very steep curve approximately 750 feet east of the Carter Caves SRP entrance. As this section of roadway serves as the primary route for park visitors from I-64 and has a relatively high amount of RV and camper traff
Y | 9 | Buffalo Trace ADD | IP20190068 |  |  |  | Intersection Improvement along KY 560 from MP 1.60 to the US 68 Intersection (MP 2.142). | Spot Improvement | Mason | 081-KY-0560 -000 | 1.6 | 2.142 | 0.542 | Improve Intersection | 26 |  | 0 |  | 300000 | 2021 | 100000 | 2022 | 100000 | 2022 | 3000000 | 2022 | 2019-02-25 16:48 | Improve intersection, roadway geometry and flatten curve along KY 560 between MP 1.60 - 2.142. | With the current alignment larger trucks can't make the turn in the curve at MP 1.77 without dropping trailer tires off the shoulder of the road.
Y | 9 | Buffalo Trace ADD | IP20190070 |  |  |  | Improve sight distance along KY 8 at the intersection at Lake Charles Road. | Spot Improvement | Mason | 081-KY-0008 -000 | 8.1 | 8.7 | 0.6 | [14 empty] | Improve sight distance at the intersection of KY 8 & Lake Charles Road. | There is currently a lot of truck traffic at this location. Large trucks, especially when loaded, need extra time to stop and/or accelerate at intersections. Increasing sight distance would greatly improve safety and mobility at this location.
Y | 9 | Buffalo Trace ADD | IP20190115 |  |  |  | Major Widening along KY 9 from 0.3 miles south of Knoweshaw Road to the KY 11 intersection. | Major Widening | Mason | 081-KY-0009 -000 | 5.6 | 7.56 | 1.96 | Major Widening-Rural Mutilane | 34 |  | 0 |  | 1150000 | 2021 | 1000000 | 2022 | 1500000 | 2022 | 10750000 | 2023 | 2019-03-15 08:58 | Widen KY 9 to 4 lanes from 0.3 miles south of Knoweshaw Road to the KY 11 Intersection. | This project will improve the operational efficiency and reduce congestion by increasing the carrying capacity from Knoweshaw Rd to KY 11.
Y | 9 | Gateway ADD | IP20190120 |  |  |  | Improve safety and operational efficiency on US 60 from the Bath County line (milepoint 0.000) to approximately Kentre Lane (milepoint 5.250). | Reconstruction | Rowan | 103-US-0060 -000 | 0 | 5.25 | 5.25 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 3150000 | 2021 | 3500000 | 2022 | 2625000 | 2023 | 31500000 | 2024 | 2019-02-27 13:15 | Modernize US 60 to improve safety, operational efficiently and connectivity from the Bath County Line to Kentre Lane near Morehead. It is anticipated that this would also increase the flow of lake traffic into the City of Morehead resulting in an economic | The current roadway has geometric deficiencies and virtually no useable shoulder.
Y | 9 | Gateway ADD | IP20190121 |  |  |  | KY 801 Planning Study to determine purpose and need for any improvements needed to adequately serve industry and school traffic. Scope will include evaluating feasibility and potential benefit of extending, by new route, KY 801 from the KY 158 intersectio | Transportation Study | Rowan | 103-KY-0801 -000 | 14.2 | 17.011 | 2.811 | Transportation Studies | 0 |  | 250000 | 2020 | 0 | 2021 | 0 | 2022 | 0 | 2022 | 0 | 2023 | 2019-03-08 16:40 | Widen KY 801 to a 4 lane facility from the I-64 Interchange (MP 14.2) to Industry Road (MP 15.610). | The MMRC Industrial Park is expected to a have a dramatic increase in growth within the coming year. Along with this growth will come an increase of both vehicular and truck traffic along the KY 801 corridor from I-64 to the Industrial Park entrance. Ad
Y | 9 | FIVCO ADD | IP20190158 |  |  |  | Improve intersection of US 60 and KY 854 near Rush. | Spot Improvement | Carter | 022-US-0060 -000 | 33.4 | 34.2 | 0.8 | Improve Intersection | 26 |  | 0 |  | 750000 | 2021 | 500000 | 2022 | 400000 | 2022 | 5000000 | 2023 | 2019-03-15 08:49 | Reconstruct intersection of US 60 and KY 854 near Rush to improve sight distance and roadway geometry to better accommodate pickup trucks pulling trailers. | There has been a major increase over the past few years of pickups pulling trailers to/from Rush Outdoors. This intersection becomes very congested during Rush Outdoor events.
Y | 9 | Gateway ADD | IP20190176 |  |  |  | Geometrically improve roadway at Elk Lick Curve on KY 36 (at Swartz Mowing maintenance facility). | Spot Improvement | Bath | 006-KY-0036 -000 | 18.6 | 18.9 | 0.3 | Local Roadway Improvements | 3 |  | 0 |  | 500000 | 2021 | 300000 | 2022 | 150000 | 2022 | 3000000 | 2023 | 2019-03-15 08:46 | REALIGN HORIZONTAL CURVE (LOCALLY KNOWN AS "ELK LICK CURVE") ON KY 36 | A QUICK ACCIDENT HISTORY CHECK SHOWS 7 ACCIDENTS OCCURRING ON KY 36 AROUND IN THIS CURVE AREA. THE CURVE IS GEOMETRICALLY SUBSTANDARD AND THIS PROJECT WOULD RECONSTRUCT IN ACCORDANCE WITH EXISTING KYTC GEOMETRIC STANDARDS.
Y | 9 | Bluegrass ADD | IP20190177 |  |  |  | Reconstruct West Main Street in downtown Carlisle. | Reconstruction | Nicholas | 091-KY-0032 -000 | 8.3 | 8.85 | 0.55 | Maintenance Improvement | 10 |  | 0 |  | 300000 | 2021 | 50000 | 2022 | 300000 | 2022 | 3000000 | 2023 | 2019-03-06 10:41 | RECONSTRUCT WEST MAIN STREET (KY 32/KY 36) IN DOWNTOWN CARLISLE. PROJECT MAY INCLUDE SIDEWALKS AND UTILITY RELOCATION. | MAIN STREET IN CARLISLE IS ASPHALT OVER CONCRETE PAVEMENT. EXTENSIVE REFLECTIVE CRACKING IS PRESENT AND THE DEPTH OF THE ASPHALT HAS BUILT UP OVER THE YEARS AND HAS COMPROMISED THE FUNCTIONALITY OF THE CURB AND GUTTER SYSTEM.
Y | 9 | Gateway ADD | IP20190182 |  |  |  | Correct geometric deficiencies on KY 965 from Blevins Valley Road (MP 6.3) to Mill Creek Bridge (MP 7.0). | Reconstruction | Bath | 006-KY-0965 -000 | 6.3 | 7 | 0.7 | Modernize Roadway-Rural | 26 |  | 0 |  | 490000 | 2021 | 300000 | 2022 | 350000 | 2022 | 4900000 | 2023 | 2019-03-15 08:40 | Reconstruct KY 965 (Preston Road) from Blevins Valley Road (MP 6.3) to Mill Creek Bridge (MP 7.0) to correct geometric deficiencies. | There are geometric deficiencies (both horizontal and vertical) in this segment of KY 965. The route has periods of high traffic during Preston Court Days. A five-year crash history check (2014-2018) yields 4 accidents (two injury, two property-only) ap
Y | 10 | Kentucky River ADD | IP20000074 |  |  |  | Relocation from Tenmile Creek Road in Perry County to Noble Road in Breathitt County. | Relocation | Breathitt | 013-KY-0015 -000 | 0 | 3 | 3 | Modernize Roadway-Rural | 26 | Y | 50000 |  | 8000000 |  | 10000000 |  | 8000000 |  | 170000000 |  | 2011-07-21 13:20 |  | This is the primary route through the entire KRADD Region. This is a coal haul route and an extremely busy freight transportation route.
Y | 10 | Gateway ADD | IP20000075 |  |  |  | Complete spot improvement to modernize the roadway on KY 713 in the Fagan area from approximately Milepoint 6.6 to approximately Milepoint 7.25. | Spot Improvement | Menifee | 083-KY-0713 -000 | 6.6 | 7.25 | 0.65 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 | 2019 | 350000 | 2019 | 200000 | 2019 | 2000000 | 2019 | 2019-03-07 10:59 | The purpose of this project is to: complete spot improvements and modernize the roadway. | The following needs have been identified for this project: 1) complete spot improvements, 2) improve local roadway conditions, 3) reconstruct road segment to current standards, and 4) provide modern roadway for motorists.
Y | 10 | Gateway ADD | IP20000076 |  |  |  | Promote economic development and correct geometrics on KY 1274 from the intersection of US 60 to Scranton (MP 6.5). | Reconstruction | Menifee | 083-KY-1274 -000 | 0 | 6.548 | 6.548 | Modernize Roadway-Rural | 26 |  | 100000 |  | 2850000 |  | 1945000 |  | 1840000 |  | 17100000 |  | 2010-02-25 16:51 | The purpose of this project is to promote economic development and tourism, and correct geometrics. | The following needs have been identified for this project: 1) promote economic development; 2) promote tourism; 3) correct horizontal deficiencies; and 4) correct width deficincies.
Y | 10 | Bluegrass ADD | IP20000079 |  |  |  | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 11 FROM KY 15 (MP 20.971) TO THE POWELL-MONTGOMERY CO. LINE (MP 25.039) IN POWELL COUNTY, KY. (2014BOP) | Spot Improvement | Powell | 099-KY-0011 -000 | 20.971 | 25.039 | 4.068 | Other Improvement Types | 0 |  | 710000 |  | 4290000 |  | 22195000 |  | 4770000 |  | 53700000 |  | 2016-11-02 10:57 | To complete low-cost, spot safety improvements on KY 11 from KY 15 (MP 20.971) to the Powell-Montgomery Co. line (MP 25.039) in Powell County, KY. (2014BOP) | Substandard curves, poor geometrics and steeps grade at various points along KY 11 from KY 15 in Powell County to the Mt. Sterling Bypass. Horizontal Alignment rating of 4 indicates several curves uncomfortable or unsafe when traveled at the prevailing sp
Y | 10 | Kentucky River ADD | IP20000080 |  |  |  | MINOR WIDENING FROM BREATHITT C/L TO STATE ROAD FORK BRIDGE NEAR THE MOUNTAIN PKY EXTENSION (KY 9009) AT HELECHAWA. SEE OPTION A IN MAY, 1999 SCOPING STUDY (DESIGN). | Minor Widening | Wolfe | 119-KY-0205 -000 | 0 | 6.394 | 6.394 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 16000000 |  | 2015-03-20 12:03 | MINOR WIDENING FROM BREATHITT C/L TO STATE ROAD FORK BRIDGE NEAR THE MOUNTAIN PKY EXTENSION (KY 9009) AT HELECHAWA. SEE OPTION A IN MAY, 1999 SCOPING STUDY (DESIGN). | This road is narrow in many locations. There are steep horizontal curves and limited visibility from side entrances. This road carries frieght traffic and connects KY 15 ( a moajor route) to the Mountain Parkway.
Y | 10 | Big Sandy ADD | IP20040032 |  |  |  | RECONSTRUCT FROM WILL BAILEY BRANCH ROAD TO KY 1090. | Reconstruction | Magoffin | 077-KY-0007 -000 | 22.5 | 23.8 | 1.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 | 2019 | 2000000 | 2019 | 1500000 | 2019 | 6000000 | 2019 | 2019-03-07 10:54 | Improve safety, travel time, reliability, and reduce congestion along KY-7 from Joseph Street to Salyersville by reconstructing curves. | ADT is 3,518, traveling on two 10-foot lanes. This road segment carries the highest traffic count on KY 7 in Magoffin County. The substandard alignments (horz. align of 3, vert.align. of 4), lack of right-hand shoulder width (2-foot right hand shoulders | BIG SANDY ADD | East | 56.9117 | 5.6766 | 9.8802 | 7.7919 | 2.3952 | 8.024 | 0 | 8.1437 | 42 |  | 15
Y | 10 | Big Sandy ADD | IP20040033 |  |  |  | To provide improved access from a local road with substandard geometrics to a regional corridor. | Safety-Haz-Elm | Magoffin | 077-KY-0030 -000 | 7.519 | 7.665 | 0.146 | Other Improvement Types | 0 |  | 5000 |  | 500000 |  | 50000 |  | 500000 |  | 2000000 |  | 2011-01-28 15:39 | Address safety and access issues along this segment of KY-30 by improving lane width and sight distance; improve local connectivity to the Mountain Parkway. | This project is needed due to substandard roadway features.
Y | 10 | Kentucky River ADD | IP20050019 |  |  |  | Major widening along KY 15 from 440' SE of Beech Point Rd (CR 1304) to new KY 15. | Major Widening | Breathitt | 013-KY-0015 -000 | 15.6 | 17.9 | 2.3 | Modernize Roadway-Rural | 26 | Y | 0 |  | 2000000 |  | 5459000 |  | 1030000 |  | 17066000 |  | 2015-06-29 14:09 |  | This section of KY 15 in Jackson is a busy shopping area with many restaurants and gas stations. The entrance to the hospital, elementary schools, nursing home, funeral home, and Highway District Office is also along this section. There is a great amoun
Y | 10 | Kentucky River ADD | IP20050020 |  |  |  | Reconstruction of KY 30 from the Owsley County line to 0.006 miles West of KY 3237. See KY 30 Planning Study September 2014 Alternate 2A | Reconstruction | Breathitt | 013-KY-0030 -000 | 0 | 4.778 | 4.778 | Modernize Roadway-Rural | 26 |  | 0 |  | 2100000 |  | 1900000 |  | 1700000 |  | 23200000 |  | 2015-03-10 12:04 |  | Substandard geometric features and four high crash spots.
Y | 10 | Big Sandy ADD | IP20050021 | 10-8901 |  | A | IMPROVE US-460 IN MAGOFFIN COUNTY AT IVY POINT HILL WEST OF SALYERSVILLE. (16CCN) | RECONSTRUCTION(O) | Magoffin | 077-US-0460 -000 | 10 | 10.7 | 0.7 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 830000 | 2022 | 440000 | 2022 | 8280000 | 2024 | 2019-03-06 14:30 | To replace an existing regional corridor with numerous maintenance issues and existing geometric deficiencies. | To replace an existing roadway with numerous geometric deficiencies. | BIG SANDY ADD | East | 54.8308 | 8.2515 | 5.5689 | 6.4895 | 4.9102 | 9.1018 | 0 | 5.509 | 40 |  | 15
Y | 10 | Big Sandy ADD | IP20050022 |  |  |  | To provide motorist with a convenient modern facility that accesses several schools and that connects US 460 to the Mountain Parkway Corridor. | Reconstruction | Magoffin | 077-KY-0007 -000 | 24.06 | 25.058 | 0.998 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 1250000 |  | 1250000 |  | 4000000 |  | 2013-08-12 08:50 | Address local and regional connectivity issues by improving capacity and geometrics along the KY-7 connection between US-460 and the Mountain Parkway. | To replace an existing corridor connection with maintenance issues and existing geometric deficiencies.
Y | 10 | Gateway ADD | IP20050023 |  |  |  | Improve safety and correct geometrics on KY 2498 approximately from Milepoint 2.0 to Milepoint 7.3 in West Liberty. | Reconstruction | Morgan | 088-KY-2498 -000 | 2.042 | 7.25 | 5.208 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 3500000 |  | 2280000 |  | 20000000 |  | 2015-02-26 12:42 | The purpose of this project is to improve safety and correct geometric deficiencies. | The following needs have been identified for this project: 1) improve safety; 2) correct geometric deficiencies; and 3) provide improved accessibility to recreational and healthcare facilities.
Y | 10 | Kentucky River ADD | IP20060259 |  |  |  | Reconstruction of KY 30 from 1.044 miles East of KY 2469 to KY 205. See KY 30 Planning Study September 2014 Alternate 3 C | Reconstruction | Breathitt | 013-KY-0030 -000 | 6.97 | 14.8 | 7.83 | Modernize Roadway-Rural | 26 |  | 0 |  | 3600000 |  | 2200000 |  | 1400000 |  | 40800000 |  | 2015-03-10 12:06 |  | Substandard geometric features and four high crash spots.
Y | 10 | Kentucky River ADD | IP20060260 | 10-375 |  | A | IMPROVE KY-205 FROM NORTH OF KY-1812 TO SOUTH OF PEGGS FORK RD. | MINOR WIDENING(O) | Breathitt | 013-KY-0205 -000 | 7.804 | 9.954 | 2.15 | Modernize Roadway-Rural | 26 |  |  |  | 1560000 | 2021 | 2900000 | 2023 |  |  |  |  | 2019-03-06 14:15 | Upgrade a substandard connection to the Mountain Parkway. | Upgrade a substandard connection to the Mountain Parkway. | KENTUCKY RIVER ADD | East | 53.4536 | 2.8024 | 3.8623 | 3.3458 | 3.4431 | 0 | 3.1138 | 6.8862 | 24 | 15 | 15
Y | 10 | Kentucky River ADD | IP20060261 |  |  |  | Reconstruction of KY 52 from 0.202 miles West of KY 498 to 0.093 miles East of Old KY HWY 52/Carlisle Ave. | Reconstruction | Lee | 065-KY-0052 -000 | 7.1 | 12.35 | 5.25 | Modernize Roadway-Rural | 26 |  | 237000 |  | 2840000 |  | 7995000 |  | 2163000 |  | 18932000 |  | 2010-02-25 16:51 |  | To replace an existing regional corridor with numerous substandard curves and narrow lanes.
Y | 10 | Kentucky River ADD | IP20060262 |  |  |  | Reconstruction of KY 498 from the intersection of KY 52 to the intersection of KY 11. | Reconstruction | Lee | 065-KY-0498 -000 | 0 | 2.464 | 2.464 | Modernize Roadway-Rural | 26 |  | 125000 |  | 750000 |  | 3250000 |  | 1125000 |  | 8750000 |  | 2010-02-25 16:51 | Reconstruction of KY 498 from the intersection of KY 52 to the intersection of KY 11. | To replace an existing system connector with numerous roadway deficiencies. | KENTUCKY RIVER ADD | East | 37.5374 | 2.0359 | 7.6347 | 8.2859 | 3.8922 | 7.1856 | 0 | 8.503 | 38
Y | 10 | Gateway ADD | IP20060263 |  |  |  | Improve safety, correct geometrics, and enhance regional connectivity on US 460 from the intersection of KY 713 to Rothwell (MP 4.8). | Reconstruction | Menifee | 083-US-0460 -000 | 0.101 | 4.8 | 4.699 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 | 2019 | 3500000 | 2019 | 2250000 | 2019 | 22000000 | 2019 | 2019-03-07 10:59 | The purpose of this project is to improve safety, correct geometrics, and enhance regional connectivity. | The following needs have been identified for this project: 1) improve safety; 2) correct substandard geometrics; and 3) enhance regional connectivity.
Y | 10 | Gateway ADD | IP20060264 |  |  |  | Improve safety, correct geometrics, and enhance regional connectivity on US 460 from the intersection of KY 1240 to 0.7 miles East of the Morgan County line. | Reconstruction | Menifee | 083-US-0460 -000 | 15.233 | 19.003 | 3.77 | Modernize Roadway-Rural | 26 |  | 15000 |  | 2640000 |  | 5060000 |  | 1463000 |  | 15875000 |  | 2013-11-04 15:34 | The purpose of this project is to improve safety, correct geometrics, and enhance regional connectivity. | The following needs have been identified for this project: 1) improve safety; 2) correct substandard geometrics; and 3) enhance regional connectivity.
Y | 10 | Gateway ADD | IP20060265 |  |  |  | Improve accessibility on US 460 from west of KY 205 (approximately Milepoint 12.7) to Hutchinson Road (approximately Milepoint 15.5). | Reconstruction | Morgan | 088-US-0460 -000 | 12.75 | 15.473 | 2.723 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 50000 |  | 0 |  | 0 |  | 2200000 |  | 2010-02-25 16:51 | The purpose of this project is to: improve accessibility, enhance operational efficiency, and create a three lane section (TWLTL). | The following needs have been identified for this project: 1) Improve Accessibility to Current and Future Developments on US 460; 2) Enhance Operational Efficiency; and 3) Create a Three Lane Section (TWLTL). | GATEWAY ADD | East | 52.1751 | 5.1018 | 14.1018 | 12.5524 | 1.1976 | 8.4431 | 3.5928 | 7.1856 | 52
Y | 10 | Gateway ADD | IP20060266 |  |  |  | Enhance the operational efficiency and improve congestion on US 460 from the intersection of KY 2498 to the intersection of Court Street in West Liberty. | Reconstruction | Morgan | 088-US-0460 -000 | 16.95 | 17.454 | 0.504 | Major Widening-Urban Streets | 25 |  | 0 |  | 1000000 | 2019 | 1250000 | 2019 | 1000000 | 2019 | 5000000 | 2019 | 2019-03-07 10:49 | The purpose of this project is to enhance operational efficiency and improve congestion. | The following needs have been identified for this project: 1) enhance operational efficiency; 2) improve congestion; and 3) improve accessibility to current and future developments.
Y | 10 | Gateway ADD | IP20060267 |  |  |  | Improve safety, correct geometrics, and enhance regional connectivity on US 460 from the Spaws Creek Bridge to the Magoffin County line. | Reconstruction | Morgan | 088-US-0460 -000 | 18.78 | 28.565 | 9.785 | Modernize Roadway-Rural | 26 |  | 500000 |  | 5000000 |  | 6610000 |  | 4145000 |  | 44343000 |  | 2010-02-25 16:51 | The purpose of this project is to improve safety, correct geometrics, and enhance regional connectivity. | The following needs have been identified for this project: 1) improve safety; 2) correct substandard geometrics; and 3) enhance regional connectivity.
Y | 10 | Gateway ADD | IP20060268 |  |  |  | Improve safety, correct geometrics, and enhance regional connectivity on KY 7 from the intersection of KY 711 to the Elliot County line. | Reconstruction | Morgan | 088-KY-0007 -000 | 7.887 | 11.121 | 3.234 | Modernize Roadway-Rural | 26 |  | 150000 |  | 1800000 |  | 4486000 |  | 1735000 |  | 11716000 |  | 2010-02-25 16:51 | The purpose of this project is to improve safety, correct geometric deficiencies, and enhance regional connectivity. | The following needs have been identified for this project: 1) improve safety; 2) correct substandard geometrics; and 3) enhance regional connectivity.
Y | 10 | Kentucky River ADD | IP20060269 |  |  |  | RELOCATION FROM US 421 AT TYNER IN JACKSON CO TO KY 11 AT LEVI. SEE CORRIDOR D-H IN MARCH 2004 SCOPING STUDY. Project includes MP 12.523-20.919 also. | Relocation | Owsley | 095-KY-0030 -000 | 10.281 | 11.121 | 0.84 | Modernize Roadway-Rural | 26 |  | 0 |  | 9000000 |  | 20000000 |  | 19000000 |  | 102300000 |  | 2010-08-18 10:29 |  | As per 1998 Planning Study latitudinal and longitudinal curve design is inadequate for volume, safety, and efficient traffic flow. This is a regional project. The road was not orginally designed as a regional primary access nor to carry the volume of tra
Y | 10 | Kentucky River ADD | IP20060270 |  |  |  | Reconstruction of KY 30 from KY 11 to 0.028 miles West of Smokey Ln. See KY 30 Planning Study September 2014 Alternate 1A | Reconstruction | Owsley | 095-KY-0030 -000 | 10.281 | 15.154 | 4.873 | Modernize Roadway-Rural | 26 |  | 0 |  | 1300000 |  | 1000000 |  | 1700000 |  | 14000000 |  | 2015-03-10 12:00 |  | Substandard geometric features and four high crash spots.
Y | 10 | Kentucky River ADD | IP20060271 |  |  |  | Major widening from KY 7 South of Hazard to Red Oak Branch near Carr Creek Lake. Line A described in December, 1996 Draft Scoping Study. See Knott & Letcher Co listing for continuation to Whitesburg. | Major Widening | Perry | 097-KY-0015 -000 | 0 | 5.961 | 5.961 | Modernize Roadway-Rural | 26 | Y | 298000 |  | 5961000 |  | 70376000 |  | 2064000 |  | 76060000 |  | 2010-02-25 16:51 |  | This segment carries a lot of local and interstate traffic through southeastern KY. It is a high volume, coal haul route. This project begins at the Knott-Perry County Line at Red Oak Branch and extends to KY 7.
Y | 10 | Kentucky River ADD | IP20060273 |  |  |  | Reconstruction from Locust St in Lothair to KY 15X in Hazard. | Reconstruction | Perry | 097-KY-0451 -000 | 1.891 | 3.47 | 1.579 | Modernize Roadway-Rural | 26 |  | 0 |  | 1545000 |  | 1590000 |  | 1060000 |  | 6492500 |  | 2016-11-02 11:50 |  | THis 1.200 mile segment of KY 451 extends from Moreland Avenue to Locust Street in downtown Hazard. This road links directly to KY 15. The road lies in the floodplain and is continously has rock slides and slips due to the steep terrain and flood water
Y | 10 | Kentucky River ADD | IP20060275 |  |  |  | Reconstruct curve and intersection at KY 3351 (Pigeon Roost Rd.) in Ary. | Reconstruction | Perry | 097-KY-0476 -000 | 11.283 | 11.783 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 530000 |  | 530000 |  | 106000 |  | 1113000 |  | 2015-06-29 17:05 |  | Improve safety and deficiencies along a local roadway system that links to a regional corridor.
Y | 10 | Kentucky River ADD | IP20060276 |  |  |  | Reconstruction of KY 476 at the intersection of KY 1146 at Hardburly. | Reconstruction | Perry | 097-KY-0476 -000 | 3.801 | 3.901 | 0.1 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 94000 |  | 2010-02-25 16:51 |  | To provide improved access from a local road to a regional corridor.
Y | 10 | Kentucky River ADD | IP20060277 |  |  |  | Reconstruct roadway to eliminate flooding beginning at the intersection with KY 550. | Reconstruction | Perry | 097-KY-1440 -000 | 2.761 | 2.961 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 50000 |  | 50000 |  | 658000 |  | 2010-02-25 16:51 |  | The road segment has a history of flooding.
Y | 10 | Kentucky River ADD | IP20060278 |  |  |  | Reconstruction of KY 191 from KY 746 to 0.378 miles East of Lackey Rd. | Reconstruction | Wolfe | 119-KY-0191 -000 | 1.45 | 2.4 | 0.95 | Modernize Roadway-Rural | 26 |  | 50000 |  | 300000 |  | 1150000 |  | 434000 |  | 4000000 |  | 2010-02-25 16:51 | Reconstruction of KY 191 from KY 746 to 0.378 miles East of Lackey Rd. | Elevation and curvature problems are the biggest issue in this .700 mile segment of KY 191 in Wolfe County. This road goes to KY 205 and the Parkway and Hazel Green. It is a main thoroughfare for folks traveling to the parkway or out of the region. The
Y | 10 | Kentucky River ADD | IP20060279 | 10-212 |  | A | IMPROVE THE KY-191 AND KY-1812 INTERSECTION. | RECONSTRUCTION(O) | Wolfe | 119-KY-0191 -000 | 3.036 | 6.854 | 3.818 | Modernize Roadway-Rural | 26 |  |  |  | 300000 | 2023 | 100000 | 2023 | 120000 | 2023 | 980000 | 2024 | 2019-02-26 15:38 | Reconstruct KY 191 from the Mountain Parkway Exit/Underpass to KY 3356. | This road has mixed horizontal and vertical curves and is just overall a bad road.
Y | 10 | Kentucky River ADD | IP20060280 |  |  |  | Reconstruct KY 191 from KY 3356 to KY 203 in Hazel Green. | Reconstruction | Wolfe | 119-KY-0191 -000 | 6.854 | 10.317 | 3.463 | Modernize Roadway-Rural | 26 |  | 150000 |  | 2100000 |  | 3421000 |  | 1668000 |  | 8658000 |  | 2010-02-25 16:51 | Reconstruct KY 191 from KY 3356 to KY 203 in Hazel Green. | This road has mixed horizontal and vertical curves and is just overall a bad road.
Y | 10 | Kentucky River ADD | IP20060281 |  |  |  | RECONSTRUCTION FROM KY 191 TO US 460 W OF WEST LIBERTY | Reconstruction | Wolfe | 119-KY-0205 -000 | 6.436 | 6.913 | 0.477 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 300000 |  | 250000 |  | 4000000 |  | 2015-02-11 13:54 | RECONSTRUCTION FROM KY 191 TO US 460 W OF WEST LIBERTY | This 7.238 mile segment of KY 205 actually involves 2 counties. The project starts at the intersection of KY 191 and KY 205 in Wolfe County and ends at US 460 in Morgan County. KY 205 has 2-12 ft lanes and 10 ft paved shoulders. This section DOES NOT ap
Y | 10 | Kentucky River ADD | IP20060283 |  |  |  | MOUNTAIN PKY EXTENSION - MAJOR WIDENING TO 4 LANES FROM KY 15 AT CAMPTON TO KY 1010. SEE SEGMENTS 1a THRU 1d IN AUGUST, 1998 ADVANCE PLANNING STUDY. ADDITIONAL FUNDS NEEDED IN ADDITION TO FUNDS SCHEDULED IN 6YP ITEM 10-139.00. | Major Widening | Wolfe | 119-KY-9009 -000 | 43.104 | 53.28 | 10.176 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 9676000 |  | 14264000 |  | 9676000 |  | 51056000 |  | 2010-02-25 16:51 |  | This 10.2 segment of the KY-9009 was re-paved last year. The guard rail is in good shape. There are centerline and edge rumble strips. The shoulders are 8-10 ft. wide. the horizonatal curvature is pretty good until you get closer to Campton KY. Then
Y | 10 | Kentucky River ADD | IP20060284 |  |  |  | MOUNTAIN PKY EXTENSION - MAJOR WIDENING TO 4 LANES FROM KY 1010 TO 0.45 MI W OF KY 134 @ INSKO. | Major Widening | Wolfe | 119-KY-9009 -000 | 53.28 | 57.681 | 4.401 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 220000 |  | 4401000 |  | 6602000 |  | 4401000 |  | 26406000 |  | 2010-02-25 16:51 |  | This 4.401 segment of KY-9009 has edgeline and centerline rumble strips, the shoulders range from 8-10 ft. Repaved in the last 2 years and new guardrail in place. Limited passing in this section - but not really bad. There are 2 lanes with a 3rd truck -
Y | 10 | Kentucky River ADD | IP20060285 |  |  |  | MOUNTAIN PKY EXTENSION - CONSTRUCT NEW INTERCHANGE AT KY 1419 | New Interchange | Wolfe | 119-KY-9009 -000 | 55.384 | 55.484 | 0.1 | Grade Separated to Interchange | 0 | Y | 100000 |  | 1500000 |  | 1300000 |  | 300000 |  | 4000000 |  | 2010-02-25 16:51 |  | The nearest access interchange is at MP 53. However, due to the currrent transportation system available - local citizens have to drive longer in order to reconnect with the roadways they need. This segment would intersect with KY 1419, which would pro
Y | 10 | Bluegrass ADD | IP20080562 |  |  |  | IMPROVE LEVEL OF SERVICE AND SAFETY FROM MP 22.269 IN MADISON COUNTY TO KY-449 IN ESTILL CO. | Major Widening | Estill | 033-KY-0052 -000 | 0 | 5.799 | 5.799 | Other Improvement Types | 0 |  | 320000 |  | 3840000 |  | 7205000 |  | 2457000 |  | 32000000 |  | 2010-02-25 16:51 | Improve level of service and safety from MP 22.269 in Madison County to KY-449 in Estill County. | Current and future traffic projection indicates need for additional capacity on route that is the connector to I-75 for Estill and Lee Counties. Critical Rate Factorindicates potential safety issues.
Y | 10 | Bluegrass ADD | IP20080563 |  |  |  | IMPROVE LEVEL OF SERVICE AND SAFETY FROM RIVER ROAD IN IRVINE TO LEE COUNTY LINE. | Reconstruction | Estill | 033-KY-0052 -000 | 9.48 | 21.04 | 11.56 | Other Improvement Types | 0 |  | 578000 |  | 5780000 |  | 8881000 |  | 3928000 |  | 69360000 |  | 2010-02-25 16:51 | Improve level of service and safety from River Road in Irvine to Lee County line. | Of the 5 segments of Adequacy Ratings for this 11.56 miles of highway on KY 52 from River Road (KY 1571) in Irvine to the Lee County line, 4 have a Horizontal Alignment rating of 4 and the other is rated as a 3, indicating serious geometric issues and saf
Y | 10 | Bluegrass ADD | IP20080564 |  |  |  | ADDRESS SAFETY AND CONNECTIVITY FROM KY-1571 IN RAVENNA TO THE MT. SINAI CHURCH. | Relocation | Estill | 033-KY-0052 -000 | 9.48 | 18.681 | 9.201 | Other Improvement Types | 0 |  | 279000 |  | 2790000 |  | 3908000 |  | 1729000 |  | 25110000 |  | 2010-02-25 16:51 | To address safety and connectivity from KY-1571 in Ravenna to the Mt. Sinai Church. | Horizontal Alignment is rated 1 and Vertical Alignment is 3. Narrow lanes, with little or no shoulders characterize the corridor and contribute to safety concerns. Route is the primary connector between Beattyville, Irvine and I-75 at Richmond.
Y | 10 | Bluegrass ADD | IP20080565 |  |  |  | ADDRESS SAFETY AND CONNECTIVITY BETWEEN THE MT SINAI CHURCH IN ESTILL TO SILVER CREEK IN BEATTYVILLE. | Reconstruction | Estill | 033-KY-0052 -000 | 18.681 | 21.04 | 2.359 | Other Improvement Types | 0 |  | 750000 |  | 7500000 |  | 6475000 |  | 4988000 |  | 67500000 |  | 2010-02-25 16:51 | To address safety and connectivity between the Mt. Sinai Church in Estill to Silver Creek in Beattyville. | IRI indicating pavement problems. Horizontal Alignment is rated 3, indicating infrequent curves uncomfortable or unsafe at the prevailing speed limit. Narrow lanes, with little or no shoulders characterize the corridor and contribute to safety concerns. R
Y | 10 | Bluegrass ADD | IP20080566 | 10-205 |  | A | IMPROVE LEVEL OF SERVICE, SAFETY, AND CONNECTIVITY ON KY-82 FROM KY-89 IN ESTILL CO. TO NEW CONSTRUCTION LOCATED NORTH OF HUDSON MILL ROAD IN ESTILL COUNTY. | RECONSTRUCTION(O) | Estill | 033-KY-0082 -000 | 0 | 4.1 | 4.1 | Modernize Roadway-Rural | 26 |  |  |  | 2820000 | 2023 | [6 empty] | 2019-03-06 13:19 | To improve level of service and provide connectivity from KY-89 in Estill County to new construction located 0.009 miles North of Hudson Mill Road in Estill County. | Project covers KY 82 in Estill County from the KY 89 junction at Hargett to the Mountain Parkway at Clay City. Vertical Alignment is 4 indicating frequent grades and vertical curves that impair sight distance. A portion of the project is in a low Percenti | BLUEGRASS ADD | East | 68.1871 | 7.0419 | 9.4311 | 12.4626 | 2.994 | 8.6228 | 3.8323 | 8.8024 | 53 |  | 15
Y | 10 | Bluegrass ADD | IP20080567 |  |  |  | IMPROVE SAFETY ON KY-52 IN ESTILL COUNTY FROM HARRIS FERRY ROAD TO THE CLARK CO LINE. | Spot Improvement | Estill | 033-KY-0089 -000 | 21.87 | 22.428 | 0.558 | Other Improvement Types | 0 |  | 0 |  | 2200000 |  | 3100000 |  | 1500000 |  | 14800000 |  | 2010-02-25 16:51 | To improve safety on KY-52 in Estill County frmo Harris Ferry Rd. to the Clark County line. | KY 52 in Estill County From Harris Ferry Road to the Clark County line serves as access for employees and trucks going to the Power Plant at Trapp in Clark County. Increased ADT is expected with the new additional power plant at Trapp that will be bringin
Y | 10 | Bluegrass ADD | IP20080568 |  |  |  | IMPROVE SAFETY AND LEVEL OF SERVICE FROM 1500 FEET NORTH OF LANDFILL ROAD (ACROSS FROM ESTILL COUNTY HIGH SCHOOL) TO TOWER LANE (NORTH) IN CLARK COUNTY. | Reconstruction | Estill | 033-KY-0089 -000 | 14.198 | 22.428 | 8.23 | Other Improvement Types | 0 |  | 631000 |  | 7572000 |  | 11911000 |  | 5692000 |  | 56790000 |  | 2010-02-25 16:51 | Reconstructing KY 89 from the Estill/Clark County Line to Tower Lane in Clark County. | KY 89 has considerable truck trffic with little or no shoulders and is a major connector between Irvine and Winchester. A segment of the corridor is in the low percentile, indicating that most similar roads are in better condition. Horizontal Alignment is
Y | 10 | Bluegrass ADD | IP20080569 |  |  |  | IMPROVE SAFETY AND LEVEL OF SERVICE FROM 1500 FEET NORTH OF LANDFILL ROAD (ACROSS FROM ESTILL COUNTY HIGH SCHOOL) TO 1250 FEET NORTH OF RAILROAD BRIDGE B00001. | Reconstruction | Estill | 033-KY-0089 -000 | 14.3 | 17.473 | 3.173 | Other Improvement Types | 0 |  | 0 |  | 1300000 |  | 1400000 |  | 650000 |  | 14000000 |  | 2016-12-09 16:19 |  | KY 89 with little or no shoulders and has a high truck volume is a major connector between Irvine and Winchester. A segment of the corridor is in the low percentile, indicating that most similar roads are in better condition. Horizontal Alignment is 4 an
Y | 10 | Bluegrass ADD | IP20080570 |  |  |  | IMPROVE SAFETY AND LEVEL OF SERVICE FROM 1250 FEET NORTH OF RAILROAD BRIDGE B00001 TO 3200 FEET NORTH OF KY 1886. TIES TO 10-8305.00 ON NORTH END. | Reconstruction | Estill | 033-KY-0089 -000 | 17.473 | 19.806 | 2.333 | Other Improvement Types | 0 |  | 0 |  | 1150000 |  | 1360000 |  | 550000 |  | 11400000 |  | 2016-12-09 16:20 |  | KY 89 has narrow 9' lanes with little or no shoulders and is a major connector between Irvine and Winchester. a segment of the corridor is in the low percentile, indicating that most similar roads are in better condition. Horizontal Alignment is 4 and V
Y | 10 | Bluegrass ADD | IP20080571 |  |  |  | IMPROVE SAFETY ISSUES ALONG KY-1182 IN ESTILL OC FROM KY 52 JUNCTION NORTHEAST FOR 0.945 MILES | Reconstruction | Estill | 033-KY-1182 -000 | 0 | 0.945 | 0.945 | Other Improvement Types | 0 |  | 50000 |  | 300000 |  | 200000 |  | 272000 |  | 1418000 |  | 2010-02-25 16:51 | To improve safety issues along KY-1182 in Estill Co. from KY 52 junction NE for 0.945 miles. | Steep grade, inadequate geometrics, poor sight distance and narrow 8'-9' lanes on Cobb Hill Road (KY 1182) east of Irvine in Estill County from KY 52 junction northeast for 0.945 miles. Additional Adequacy Rating information is not available for this Rura
Y | 10 | Bluegrass ADD | IP20080572 | 10-206 |  | A | IMPROVE SAFETY ON KY-2459 (CARHARTT AVE.) FROM KY-89 TO THE RAILROAD BRIDGE.(18CCR) | SPOT IMPROVEMENTS(O) | Estill | 033-KY-2459 -000 | 0 | 0.373 | 0.373 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2020 | 320000 | 2021 | 520000 | 2021 |  |  | 2019-03-06 13:41 | ADDRESS SAFETY CONCERNS ALONG CARHARTT AVE. | Adequacy Ratings and additional HIS data not available. There are no turn lanes onto Main Street (KY 89) at this downtown Irvine intersection. CRASH records indicate 5 collisions at the site in 2002 through 2004. Crash rate may appear lower as data along | BLUEGRASS ADD | East | 18.1737 | 2.9341 | 6.1078 | 0.80838 | 3.9521 | 0 | 0 | 4.3713 | 18
Y | 10 | Bluegrass ADD | IP20080573 |  |  |  | ADDRESS CONNECTIVITY AND SAFETY ISSUES REGARDING FLOODED ROADAY ON KY-3327 IN ESTILL CO KY-594 AND KY-52 | Spot Improvement | Estill | 033-KY-3327 -000 | 2.057 | 2.267 | 0.21 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 252000 |  | 2010-02-25 16:51 | To address connectivity and safety issues regarding flooded roadway on KY-3327 in Estill County KY-594 and KY-52. | Adequacy Rating currently unavailable. Road is narrow (9' lanes) with little or no shoulders and located in a floodplain. Infrequent flooding on this section of KY 3327 west of Irvine, in Estill County blocks access and connectivity to and from KY 52, res
Y | 10 | Gateway ADD | IP20080574 |  |  |  | Improve safety and substandard geometrics on US 460 from the Menifee County Line to approximately Milepoint 0.8. | Spot Improvement | Morgan | 088-US-0460 -000 | 0 | 0.8 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 475000 |  | 167000 |  | 5858000 |  | 2013-08-12 08:59 | The purpose of this project is to improve: safety and substandard geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Substandard Geometrics; and 3) Enhance Regional Connectivity.
Y | 10 | Gateway ADD | IP20080575 |  |  |  | Improve safety and substandard geometrics on US 460 from South Sawmill Road to KY 946. | Spot Improvement | Morgan | 088-US-0460 -000 | 2.2 | 5 | 2.8 | Modernize Roadway-Rural | 26 |  | 1030000 |  | 1060000 |  | 1325000 |  | 1060000 |  | 14840000 |  | 2015-06-29 16:22 | The purpose of this project is to improve: safety and substandard geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Substandard Geometrics; and 3) Enhance Regional Connectivity.
Y | 10 | Gateway ADD | IP20080576 |  |  |  | Improve safety and substandard geometrics on US 460 from Bobby Jones Road to Ellis Drive. | Spot Improvement | Morgan | 088-US-0460 -000 | 6.411 | 8.489 | 2.078 | Modernize Roadway-Rural | 26 |  | 0 |  | 1260000 |  | 3200000 |  | 827000 |  | 10500000 |  | 2010-02-25 16:51 | The purpose of this project is to improve: safety and substandard geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Substandard Geometrics; and 3) Enhance Regional Connectivity.
Y | 10 | Gateway ADD | IP20080577 |  |  |  | Improve safety and substandard geometrics on US 460 from Ellis Drive to east of Grassy Creek Road. | Spot Improvement | Morgan | 088-US-0460 -000 | 8.489 | 10.713 | 2.224 | Modernize Roadway-Rural | 26 |  | 0 |  | 1320000 |  | 2275000 |  | 923000 |  | 11000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve: safety and substandard geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Substandard Geometrics; and 3) Enhance Regional Connectivity.
Y | 10 | Gateway ADD | IP20080579 |  |  |  | Improve safety and correct geometric deficiencies on KY 191 approximately from Milepoint 10.7 to Milepoint 11.3. | Reconstruction | Morgan | 088-KY-0191 -000 | 10.7 | 11.3 | 0.6 | Modernize Roadway-Rural | 26 |  | 0 |  | 795000 |  | 424000 |  | 212000 |  | 4346000 |  | 2015-06-29 16:19 | The purpose of this project is to improve safety and correct geometric deficiencies. | The following needs have been identified for this project: 1) improve safety; 2) correct horizontal and vertical alignments; and 3) modernize the roadway.
Y | 10 | Gateway ADD | IP20080580 |  |  |  | Improve safety by correcting horizontal and width deficiencies. | Minor Widening | Morgan | 088-KY-0437 -000 | 0 | 6 | 6 | Modernize Roadway-Rural | 26 |  | 0 |  | 50000 |  | 50000 |  | 100000 |  | 1500000 |  | 2013-03-19 09:02 | The purpose of this project is to improve safety and correct geometric deficiencies. | The following needs have been identified for this project: 1) improve safety; 2) correct horizontal and vertical deficiencies; and 3) widen the roadway.
Y | 10 | Bluegrass ADD | IP20080581 |  |  |  | IMPROVE LEVEL OF SERVICE FROM BROWN ST. TO STONEGATE DR. IN STANTON. | Reconstruction | Powell | 099-KY-0011 -000 | 14 | 16.7 | 2.7 | Modernize Roadway-Urban | 16 |  | 0 |  | 1500000 | 2019 | 3500000 | 2019 | 2000000 | 2019 | 7500000 | 2019 | 2019-03-07 11:06 | To improve level of service from Brown St. to Stonegate Dr. in Stanton. | Future ADT is expected to increase causing increased congestion along KY 11, a main corridor through the center of Stanton. Existing road is 2 lane facility with no turn lanes or medians, thereby increasing potential for rear-end collisions. | BLUEGRASS ADD | East | 56.8653 | 6.1317 | 14.012 | 13.3383 | 2.515 | 9.6407 | 3.8623 | 7.3653 | 57
Y | 10 | Bluegrass ADD | IP20080582 |  |  |  | RECONSTRUCTION FROM KY 15 TO 2250 FEET NORTH OF TEASLEY ROAD TO IMPROVE SAFETY AND DRIVEABILITY FROM KY-15 TO THE MT STERLING BYPASS. | Reconstruction | Powell | 099-KY-0011 -000 | 20.971 | 23.5 | 2.529 | Other Improvement Types | 0 |  | 125000 |  | 750000 |  | 3000000 |  | 2045000 |  | 11250000 |  | 2011-10-14 09:42 |  | Substandard curves, poor geometrics and steeps grade at various points along KY 11 from KY 15 in Powell County to the Mt. Sterling Bypass. Horizontal Aligment rating of 4 indicates several curves uncomfortable or unsafe when traveled at the prevailing s
Y | 10 | Bluegrass ADD | IP20080583 |  |  |  | RECONSTRUCTION FROM 2250 FEET NORTH OF TEASLEY ROAD TO 400 FEET SOUTH OF OLD KY 11 TO IMPROVE SAFETY AND DRIVEABILITY FROM KY-15 TO THE MT STERLING BYPASS. | Reconstruction | Powell | 099-KY-0011 -000 | 23.5 | 25.039 | 1.539 | Other Improvement Types | 0 |  | 270000 |  | 1630000 |  | 7600000 |  | 1150000 |  | 19000000 |  | 2010-02-25 16:51 |  | Substandard curves, poor geometrics and steeps grade at various points along KY 11 from KY 15 in Powell County to the Mt. Sterling Bypass. Horizontal Aligment rating of 4 indicates several curves uncomfortable or unsafe when traveled at the prevailing s
Y | 10 | Bluegrass ADD | IP20080584 |  |  |  | INTERSECTION IMPROVEMENTS AT KY 15 AND KY 11 IN POWELL COUNTY LOCATED IN DISTRICT 10. (2014BOP). | Reconstruction | Powell | 099-KY-0015 -000 | 3.339 | 3.493 | 0.154 | Other Improvement Types | 0 |  | 50000 |  | 150000 |  | 200000 |  | 81000 |  | 150000 |  | 2016-11-02 11:03 | To add intersection improvements at KY 15 and KY 11 in Powell County located in district 10. (2014BOP). | At the intersection of KY 11 and KY 15 in Clay City, CRF on KY 15 indicates serious safety concerns are present.
Y | 10 | Bluegrass ADD | IP20080585 |  |  |  | ADDRESS SAFETY AND LEVEL OF SERVICE FROM KY 11 TO KY 3022 IN CLAY CITY. | Congestion Management | Powell | 099-KY-0015 -000 | 3.493 | 4.01 | 0.517 | Other Improvement Types | 0 |  | 0 |  | 824000 |  | 1590000 |  | 1060000 |  | 4240000 |  | 2015-06-29 15:29 | To address safety and level of service from KY 11 to KY 3022 in Clay City. | IRI indicates possible pavement issues. Congestion is occurring at peak hours and future congestion during other times of the day. This segment of KY 15 is adjacent to the Mountain Parkway and leads to the central business district of Clay City.
Y | 10 | Bluegrass ADD | IP20080586 |  |  |  | IMPROVE SAFETY FROM END OF 4 LANE AT WATSON RIDGE RD TO KY 1028 NEAR CLAY CITY. | Safety-Haz-Elm | Powell | 099-KY-0082 -000 | 1.536 | 1.856 | 0.32 | Other Improvement Types | 0 |  | 50000 |  | 300000 |  | 1025000 |  | 164000 |  | 480000 |  | 2010-02-25 16:51 | To improve safety from end of 4 lane at Watson Ridge Rd. to KY 1028 near Clay City. | Sight distance restrictions and poor geometrics combined with little shoulders present unsafe driving conditions ont his segment of highway On KY 82 at the end of the existing four lane segment at Watson Ridge Road to KY 1028 near Clay City leading to the
Y | 10 | Bluegrass ADD | IP20080587 | 10-210 |  | A | IMPROVE SAFETY AND LEVEL OF SERVICE ON KY-213 IN POWELL COUNTY FROM SONS ROAD TO REED COURT. | SAFETY-HAZARD ELIM(P) | Powell | 099-KY-0213 -000 | 6.371 | 6.897 | 0.526 | Install Two-way Left Turn Lane | 28 |  |  |  | 590000 | 2023 | [6 empty] | 2019-02-26 15:35 | Improve safety and level of service on KY 213 in Powell County from Sons Road (milepoint 6.371) to Reed Ct (milepoint 6.897). | Adequacy ratings indicate serious safety concerns with roadway. Critical Rate Factor and Composite rating ote significant safety issues on corridor leading to the Mountain Parkway and downtown Stanton. Several curves uncomfortable or unsafe when traveled | BLUEGRASS ADD | East | 43.2994 | 0.69461 | 12.2156 | 7.006 | 3.7725 | 0 | 0 | 4.6108 | 28 |  | 15
Y | 10 | Bluegrass ADD | IP20080588 |  |  |  | ADDRESS SAFETY BETWEEN MILEPOINTS 35 AND 38 IN POWELL AND WOLFE COUNTIES. | Reconstruction | Powell | 099-KY-9000 -000 | 35 | 36 | 1 | Other Improvement Types | 0 | Y | 0 |  | 450000 |  | 400000 |  | 337000 |  | 3000000 |  | 2010-02-25 16:51 | To address safety between mile-points 35 and 38 in Powell and Wolfe Counties. | Horizontal Alignment is rated at 3 in Powell County and 4 in Wolfe County indicating several unsafe curves when travelling the prevailing speed limit on the Bert T. Combs Mountain Parkway between mile-points 35.20 - 38.00. Curves are inconsistent with the
Y | 10 | Big Sandy ADD | IP20100013 |  |  |  | Improve alternate methods for connecting US 460 to KY 40 near KY 2020. | Bypass | Magoffin | 077-KY-0040 -000 | 0 | 1.11 | 1.11 | Other Improvement Types | 0 |  | 50000 |  | 750000 |  | 1500000 |  | 1000000 |  | 15000000 |  | 2011-07-21 13:06 | Address local and regional connectivity by providing an alternate connection between US-460 and KY-40, to facilitate access to the Mountain Parkway. | This project will address the need for a link between US 460 and KY 40 at Salyersville. Thru traffic coming from the communities of Oil Springs, Falcon and various others must currently pass through the city of Salyersville on KY 40 and Parkway Drive to
Y | 10 | Kentucky River ADD | IP20110007 |  |  |  | Improve safety and substandard geometrics for KY 30 in Breathitt County across Shoulderblade Hill. To improve roadway geometrics to enhance safety and local mobility between Jackson and Booneville and regional connectivity between the Hal Rogers Parkw | Reconstruction | Breathitt | 013-KY-0030 -000 | 7.481 | 8.876 | 1.395 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 | 2019 | 500000 | 2019 | 500000 | 2019 | 3250000 | 2019 | 2019-03-07 11:14 | Improve safety and substandard geometrics for KY 30 in Breathitt County across Shoulderblade Hill. To improve roadway geometrics to enhance safety and local mobility between Jackson and Booneville and regional connectivity between the Hal Rogers Parkw | Substandard geometric features and four high crash spots. | KENTUCKY RIVER ADD | East | 37.0449 | 3.9162 | 7.3653 | 8.0389 | 3.4132 | 7.6647 | 0 | 6.6467 | 37
Y | 10 | Kentucky River ADD | IP20110008 |  |  |  | Extend two way left turning lane (TWLTL) from 0.047 miles North of Lee County Senior Citizens Ctr to 0.103 miles South of Grand Ave. | Minor Widening | Lee | 065-KY-0011 -000 | 4.8 | 5.5 | 0.7 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 100000 | 2019 | 0 | 2019 | 100000 | 2019 | 500000 | 2019 | 2019-03-13 15:37 | Improve traffic flow through area. | The left turn lane needs to be extended to accomodate new business along KY 11. Congestion and safety are issues in this section.
Y | 10 | Kentucky River ADD | IP20110009 |  |  |  | Add turn lane at the intersection of KY 11 and KY 498. | Spot Improvement | Lee | 065-KY-0011 -000 | 9.323 | 9.523 | 0.2 | Improve Intersection | 26 |  | 0 |  | 100000 | 2019 | 0 | 2019 | 50000 | 2019 | 250000 | 2019 | 2019-03-13 15:36 | To ensure continuos flow of traffic through an intersection. | To ensure continuos flow of traffic through an intersection.
Y | 10 | Kentucky River ADD | IP20110010 |  |  |  | Curve revision on KY 52 at Horseshoe Bend ending 0.297 miles West of Hawes Rd. | Safety-Haz-Elm | Lee | 065-KY-0052 -000 | 18.7 | 19.5 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 | 2019 | 750000 | 2019 | 300000 | 2019 | 3500000 | 2019 | 2019-03-07 11:27 | Curve revision on KY 52 at Horseshoe Bend ending 0.297 miles West of Hawes Rd. | To replace an existing substandard curve along a regional corridor. | KENTUCKY RIVER ADD | East | 15.1617 | 1.9281 | 3.503 | 1.6168 | 4.4012 | 0 | 0 | 3.7126 | 15
Y | 10 | Kentucky River ADD | IP20110011 |  |  |  | Reconstruct KY 52 from the Estill County Line to 0.012 miles East of Crystal Creek Ln. | Safety-Haz-Elm | Lee | 065-KY-0052 -000 | 0 | 3.1 | 3.1 | Modernize Roadway-Rural | 26 |  | 5000 |  | 400000 |  | 1000000 |  | 500000 |  | 12000000 |  | 2011-02-01 08:35 |  | To replace an existing regional corridor with numerous substandard curves.
Y | 10 | Kentucky River ADD | IP20110013 |  |  |  | Reconstruct the intersection of KY 11 and KY 846. | Safety-Haz-Elm | Owsley | 095-KY-0011 -000 | 3.8 | 4.2 | 0.4 | Improve Intersection | 26 |  | 0 |  | 200000 | 2019 | 200000 | 2019 | 200000 | 2019 | 1500000 | 2019 | 2019-03-07 11:11 | Correct sight distance issues at junction KY 11 & KY 846 | Correct sight distance issues at junction KY 11 & KY 846 | KENTUCKY RIVER ADD | East | 16.6512 | 0.5509 | 6.018 | 4.244 | 1.9461 | 0 | 0 | 3.8922 | 17
Y | 10 | Kentucky River ADD | IP20110014 |  |  |  | Reconstruct KY 28 from 0.377 miles West of KY 2024 to Smith Cemetery Rd. | Reconstruction | Owsley | 095-KY-0028 -000 | 2.5 | 3.3 | 0.8 | Modernize Roadway-Rural | 26 |  | 5000 |  | 200000 |  | 300000 |  | 200000 |  | 1295000 |  | 2011-02-01 08:49 |  | Correct a continuous maintenance problem.
Y | 10 | Kentucky River ADD | IP20110015 |  |  |  | Improve safety and substandard geometrics from Baker St (milepoint 7.406) to KY 15 (milepoint 7.861) in Combs. | Reconstruction | Perry | 097-KY-0080 -000 | 7.368 | 7.823 | 0.455 | Modernize Roadway-Rural | 26 |  | 0 |  | 515000 |  | 318000 |  | 212000 |  | 1060000 |  | 2016-09-14 11:37 |  | To provide improved access from a local road to a regional corridor.
Y | 10 | Kentucky River ADD | IP20110016 |  |  |  | Reconstruct curve on KY 80 from 0.135 miles West of Mordust Run to 0.179 miles West of Fieldsville Ln Conn. in Avawam. | Reconstruction | Perry | 097-KY-0080 -000 | 2.7 | 3.1 | 0.4 | Modernize Roadway-Rural | 26 |  | 5000 |  | 200000 |  | 500000 |  | 200000 |  | 1000000 |  | 2011-02-01 08:53 |  | This project is needed due to safety issues and substandard roadway features.
Y | 10 | Kentucky River ADD | IP20110018 |  |  |  | Correct continuous maintenance issues at railroad tunnel in Leatherwood. | Reconstruction | Perry | 097-KY-0699 -000 | 3.7 | 3.8 | 0.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 200000 |  | 195000 |  | 1400000 |  | 2013-08-12 09:52 |  | This project is needed due to substandard roadway features.
Y | 10 | Kentucky River ADD | IP20110019 | 10-209 |  | A | IMPROVE KY-476 FROM KY-15X IN WALKERTOWN TO NORTH OF WALKER CORNETT ROAD IN WABACO. | RECONSTRUCTION(O) | Perry | 097-KY-0476 -000 | 0.9 | 1.2 | 0.3 | Modernize Roadway-Urban | 16 |  |  |  | 780000 | 2021 | [6 empty] | 2019-03-06 13:56 | Improve traffic and drainage along KY 476. | This project is needed due to safety issues and substandard roadway drainage features. | KENTUCKY RIVER ADD | East | 51.2605 | 8.0719 | 11.9461 | 12.6198 | 1.9162 | 9.1617 | 0 | 7.5449 | 51
Y | 10 | Kentucky River ADD | IP20110021 |  |  |  | Reconstruction of KY 191 & KY 1010 intersection | Reconstruction | Wolfe | 119-KY-0191 -000 | 9.604 | 9.804 | 0.2 | Improve Intersection | 26 |  | 0 |  | 257500 |  | 51500 |  | 103000 |  | 530000 |  | 2015-06-29 16:33 | Reconstruction of KY 191 & KY 1010 intersection | To provide improved access from a local road to a regional corridor.
Y | 10 | Kentucky River ADD | IP20110022 |  |  |  | Reconstruction of KY 191 & KY 1812 intersection | Reconstruction | Wolfe | 119-KY-0191 -000 | 4.765 | 4.965 | 0.2 | Improve Intersection | 26 |  | 0 |  | 257500 |  | 77250 |  | 103000 |  | 795000 |  | 2015-06-29 16:30 | Reconstruction of KY 191 & KY 1812 intersection | To provide improved access from a local road to a regional corridor.
Y | 10 | Kentucky River ADD | IP20110023 |  |  |  | Reconstruction of KY 715 & KY 2016 intersection | Reconstruction | Wolfe | 119-KY-0715 -000 | 2.548 | 2.748 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 50000 |  | 100000 |  | 300000 |  | 2015-03-20 12:04 | Reconstruction of KY 715 & KY 2016 intersection | To provide improved access from a local road to a regional corridor.
Y | 10 | Bluegrass ADD | IP20110036 |  |  |  | Reconstruct section of KY 52 in Estill County (MP 13.00 to MP 14.00) to current standards. | Reconstruction | Estill | 033-KY-0052 -000 | 13 | 14 | 1 | Other Improvement Types | 0 |  | 5000 |  | 500000 |  | 300000 |  | 500000 |  | 10000000 |  | 2011-02-10 14:34 |  | Safety concerns are present as indicated by narrow shoulders and poor Horizontal and Vertical Alignments on this segment of KY 52 in Estill County.
Y | 10 | Bluegrass ADD | IP20110037 |  |  |  | Reconstruct section of KY 52 in Estill County to current standards. | Reconstruction | Estill | 033-KY-0052 -000 | 16 | 17 | 1 | Other Improvement Types | 0 |  | 5000 |  | 500000 |  | 300000 |  | 500000 |  | 10000000 |  | 2011-02-10 14:36 |  | Safety concerns are present as indicated by narrow shoulders and poor Horizontal and Vertical Alignments on this segment of KY 52 in Estill County.
Y | 10 | Bluegrass ADD | IP20110039 |  |  |  | Construct curb and gutter section on KY 11 in Stanton in order to improve drainage along roadway. | Drainage Improvement | Powell | 099-KY-0011 -000 | 14 | 15 | 1 | Other Improvement Types | 0 |  | 5000 |  | 500000 |  | 700000 |  | 800000 |  | 5000000 |  | 2011-02-10 14:40 | Construct curb and gutter section on KY 11 in Stanton in order to improve drainage along roadway. | Future ADT is expected to increase causing increased congestion along KY 11, a main corridor through the center of Stanton. Existing road is 2 lane facility with drainage problems thereby increasing potential for rear-end collisions.
Y | 10 | Gateway ADD | IP20110053 |  |  |  | Improve safety and complete maintenance improvements to correct a rock fall issue on KY 1274 from approximately Milepoint 4.7 to approximately Milepoint 5.0 west of Scranton. | Reconstruction | Menifee | 083-KY-1274 -000 | 4.7 | 5 | 0.3 | Maintenance Improvement | 10 |  | 0 |  | 200000 |  | 200000 |  | 195000 |  | 1400000 |  | 2011-03-22 13:22 | The purpose of this project is to improve safety and correct a rock fall issue. | The following needs have been identified for this project: 1) improve safety; 2) correct a rock fall issue; and 3) widen the roadway.
Y | 10 | Gateway ADD | IP20110054 |  |  |  | Correct geometric deficiencies and enhance regional connectivity on US 460 from approximately Milepoint 24.6 to approximately Milepoint 26.1. | Reconstruction | Morgan | 088-US-0460 -000 | 24.6 | 26.1 | 1.5 | Realign Intersection | 26 |  | 5000 |  | 800000 |  | 1500000 |  | 800000 |  | 7000000 |  | 2011-02-18 16:18 | The purpose of this project is to correct geometric deficiencies. | The following needs have been identified for this project: 1) correct substandard geometrics; enhance regional connectivity; 3) realign roadway segment; and replace bridge.
Y | 10 | Gateway ADD | IP20110056 |  |  |  | Correct geometric deficiencies and enhance regional connectivity on US 460 from approximately Milepoint 24.1 to approximately Milepoint 24.6. | Reconstruction | Morgan | 088-US-0460 -000 | 24.1 | 24.6 | 0.5 | Realign Intersection | 26 |  | 5000 |  | 200000 |  | 300000 |  | 200000 |  | 1000000 |  | 2011-02-18 16:20 | The purpose of this project is to correct geometric deficiencies. | The following needs have been identified for this project: 1) correct substandard geometrics; enhance regional connectivity; and 3) realign roadway segment.
Y | 10 | Gateway ADD | IP20110057 |  |  |  | Correct geometric deficiencies on KY 191 at Adele Hill, approximately from Milepoint 2.3 to Milepoint 3.6. | Reconstruction | Morgan | 088-KY-0191 -000 | 2.3 | 3.6 | 1.3 | Modernize Roadway-Rural | 26 |  | 5000 |  | 700000 |  | 500000 |  | 500000 |  | 3000000 |  | 2011-02-18 16:21 | The purpose of this project is to correct geometric deficiencies. | The following needs have been identified for this project: 1) correct horizontal and vertical alignments; 2) widen the roadway; and 3) alleviate continuous maintenance issues along road segment.
Y | 10 | Kentucky River ADD | IP20110127 |  |  |  | Relocation of KY 15 from S of Noble RD to Dube RD. | Relocation | Breathitt | 013-KY-0015 -000 | 3 | 5.4 | 2.4 | Modernize Roadway-Rural | 26 | Y | 15000 |  | 1000000 |  | 1250000 |  | 1000000 |  | 70125000 |  | 2011-08-11 16:15 |  | This is the primary route through the entire KRADD Region. This is a coal haul route and an extremely busy freight transportation route.
Y | 10 | Kentucky River ADD | IP20110128 |  |  |  | Relocation of KY 15 Dube RD to KY 476/Marie Roberts Road. | Relocation | Breathitt | 013-KY-0015 -000 | 5.4 | 7.7 | 2.3 | Modernize Roadway-Rural | 26 | Y | 15000 |  | 2000000 |  | 2250000 |  | 2000000 |  | 82400000 |  | 2011-08-11 16:17 |  | This is the primary route through the entire KRADD Region. This is a coal haul route and an extremely busy freight transportation route.
Y | 10 | Kentucky River ADD | IP20110129 |  |  |  | Reconstruction of KY 52 from the intersection of KY 2453 to the intersection of KY 399. | Reconstruction | Lee | 065-KY-0052 -000 | 3.524 | 4.859 | 1.335 | Modernize Roadway-Rural | 26 |  | 5000 |  | 300000 |  | 75000 |  | 175000 |  | 2500000 |  | 2012-01-25 13:54 |  | To replace an existing regional corridor with numerous substandard curves along a vertical grade.
Y | 10 | Kentucky River ADD | IP20110130 |  |  |  | Curve revision on KY 52 from 0.013 miles East of Mooretown Hill to 0.074 West of KY 2016. | Reconstruction | Lee | 065-KY-0052 -000 | 15.889 | 16.889 | 1 | Modernize Roadway-Rural | 26 |  | 5000 |  | 250000 |  | 50000 |  | 125000 |  | 2000000 |  | 2012-01-25 13:50 |  | To replace an existing regional corridor that contains substandard curves and a narrow bridge.
Y | 10 | Kentucky River ADD | IP20110131 |  |  |  | Reconstruction of KY 11 from Lone Oak Industrial Rd. (CR 1503) to KY 30 in Booneville. | Reconstruction | Owsley | 095-KY-0011 -000 | 10.253 | 12.114 | 1.861 | Modernize Roadway-Rural | 26 |  | 0 |  | 1545000 |  | 530000 |  | 530000 |  | 6360000 |  | 2015-06-29 14:21 | Reconstruction of KY 11 from Lone Oak Industrial Rd. (CR 1503) to KY 30 in Booneville. | Upgrade the existing corridor to the industrial park.
Y | 10 | Kentucky River ADD | IP20110132 |  |  |  | Reconstruction of KY 191 from 0.870 miles East of KY 15 to Trace Fork Rd. in Campton. | Reconstruction | Wolfe | 119-KY-0191 -000 | 0.87 | 2.879 | 2.009 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 500000 |  | 750000 |  | 6000000 |  | 2013-08-12 09:21 | Reconstruction of KY 191 from 0.870 miles East of KY 15 to Trace Fork Rd. in Campton. | To replace an existing regional corridor with a modern safe route.
Y | 10 | Kentucky River ADD | IP20110133 |  |  |  | New and better access to Wendell Ford Airport | New Route | Perry | 097-CR-1365Q4-000 | 0 | 1 | 1 | Construct Road in New Location | 0 | Y | 0 |  | 1100000 | 2019 | 1250000 | 2019 | 250000 | 2019 | 11500000 | 2019 | 2019-03-07 11:03 | Improve access to the Wendell H. Ford Airport. | The need of this project is due to substandard conditions of the existing access road, including narrow lanes, little to no shoulders, steep grades, and slope failures.
Y | 10 | Kentucky River ADD | IP20110134 |  |  |  | Reconstruct KY 15 from Stidham Lane to Tenmile Creek Road. | Reconstruction | Perry | 097-KY-0015 -000 | 21.5 | 24.3 | 2.8 | Modernize Roadway-Rural | 26 | Y | 15000 |  | 1500000 |  | 2000000 |  | 2000000 |  | 57375000 |  | 2011-08-11 16:25 |  | This 2.800 mile segment of KY 15 is highly traveled by local, regional, and interstate traffic. KY 15 is a coal haul road.
Y | 10 | Kentucky River ADD | IP20110135 |  |  |  | Reconstruct KY 451 from KY 15 to 0.057 miles South of Gregory Branch Rd in Christopher. | Reconstruction | Perry | 097-KY-0451 -000 | 0 | 1.006 | 1.006 | Modernize Roadway-Rural | 26 |  | 50000 |  | 500000 |  | 750000 |  | 600000 |  | 2700000 |  | 2012-01-25 14:06 |  | This project is needed due to safety issues.
Y | 10 | Kentucky River ADD | IP20110136 |  |  |  | Reconstruction of KY 451 from 0.057 miles South of Gregory Branch Rd in Christopher to Locust St in Lothair. | Reconstruction | Perry | 097-KY-0451 -000 | 1.006 | 1.891 | 0.885 | Modernize Roadway-Rural | 26 |  | 75000 |  | 750000 |  | 1000000 |  | 800000 |  | 4000000 |  | 2012-01-25 14:08 |  | Improve a local roadway system that links to a regional corridor.
Y | 10 | Kentucky River ADD | IP20110137 |  |  |  | Reconstruction of KY 476 from KY 15X in Walkertown to 0.025 North of Walker Cornett Rd. in Wabaco. | Reconstruction | Perry | 097-KY-0476 -000 | 0 | 0.9 | 0.9 | Modernize Roadway-Rural | 26 |  | 100000 |  | 500000 |  | 1000000 |  | 1000000 |  | 5000000 |  | 2012-01-25 14:11 | Reconstruction of KY 476 from KY 15X in Walkertown to 0.025 North of Walker Cornett Rd. in Wabaco. | This project is needed due to safety issues and substandard roadway features.
Y | 10 | Kentucky River ADD | IP20110138 |  |  |  | Reconstruct KY 1146 (Bulan Hiner Rd.) from KY 476 to KY 80. | Reconstruction | Perry | 097-KY-1146 -000 | 2.712 | 3.962 | 1.25 | Modernize Roadway-Rural | 26 |  | 50000 |  | 500000 |  | 500000 |  | 500000 |  | 3000000 |  | 2012-01-25 14:17 |  | Improve safety and deficiencies along a local roadway system that links to a regional corridor.
Y | 10 | Kentucky River ADD | IP20110139 |  |  |  | Reconstruct KY 476 from KY 1146 near Bulan to 0.077 MI North of Francis Lane. | Reconstruction | Perry | 097-KY-0476 -000 | 3.851 | 4.851 | 1 | Modernize Roadway-Rural | 26 |  | 50000 |  | 500000 |  | 1000000 |  | 750000 |  | 5000000 |  | 2012-01-25 14:13 |  | Improve safety and deficiencies along a local roadway system that links to a regional corridor.
Y | 10 | Gateway ADD | IP20110209 |  |  |  | To construct a west bypass of West Liberty from the junction of US 460 and KY 2498 that will proceed north to the completed portion of KY 7. | Bypass | Morgan | 088-US-0460 -000 | 15.247 | 17.573 | 2.326 | Construct Road in New Location | 0 |  | 75000 |  | 1000000 |  | 1000000 |  | 500000 |  | 10000000 |  | 2011-11-03 16:04 | The purpose of this project is to improve safety and congestion. | The following needs have been identified for this project: 1) improve safety; and 2) alleviate traffic congestion through West Liberty.
Y | 10 | Kentucky River ADD | IP20120017 |  |  |  | Reconstruction of KY 30 from 0.006 miles West of KY 3237 to 1.044 miles East of KY 2469. See KY 30 Planning Study September 2014 Alternate 2A | Reconstruction | Breathitt | 013-KY-0030 -000 | 5.203 | 6.97 | 1.767 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 800000 |  | 700000 |  | 9300000 |  | 2015-03-10 12:02 |  | The need for reconstruction is expressed through above average crash rates and substandard geometric features.
Y | 10 | Kentucky River ADD | IP20120018 |  |  |  | Reconstruction on KY 1278 due to continuous reoccurring maintenance issues. SYP Item no. 10-367 – EMBANKMENT FAILURE AND SLIDE REPAIRS ALONG KY 1278 BETWEEN MP 2.0 AND MP 3.0 IN BREATHITT COUNTY, KY. (2014BOP) | Reconstruction | Breathitt | 013-KY-1278 -000 | 1.8 | 2.2 | 0.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 25000 |  | 25000 |  | 1650000 |  | 2016-12-09 14:56 |  | This projected is needed due to continous reoccuring maintenenace issues.
Y | 10 | Kentucky River ADD | IP20120020 |  |  |  | Reconstruct KY 7 from 0.266 miles North of KY 1165 to 0.225 miles South of KY 2447. | Reconstruction | Perry | 097-KY-0007 -000 | 2.8 | 7.2 | 4.4 | Modernize Roadway-Rural | 26 |  | 100000 |  | 2250000 |  | 4500000 |  | 1200000 |  | 20250000 |  | 2013-01-22 16:32 |  | KY 7 is a highly traveled road along the river. Truck traffic causes many breaks along the road. There are numerous sharp curves. KY 7 provides the only road connecting many communities in Perry and Letcher Counties.
Y | 10 | Kentucky River ADD | IP20120021 |  |  |  | Reconstruct KY 7 from 0.275 North of KY 2447 to 0.070 miles South of the Letcher County line. | Reconstruction | Perry | 097-KY-0007 -000 | 7.7 | 13.5 | 5.8 | Modernize Roadway-Rural | 26 |  | 100000 |  | 2900000 |  | 5800000 |  | 1300000 |  | 26100000 |  | 2013-01-22 16:35 |  | KY 7 is a highly traveled road along the river. Truck traffic causes many breaks along the road. There are numerous sharp curves. KY 7 provides the only road connecting many communities in Perry and Letcher Counties.
Y | 10 | Kentucky River ADD | IP20120022 |  |  |  | Reconstruct KY 80 from 0.022 miles East of KY 451 to 0.200 miles West of Hall Old Home Place just off of HR Parkway Exit 56. | Reconstruction | Perry | 097-KY-0080 -000 | 4.4 | 4.7 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 250000 |  | 500000 |  | 200000 |  | 1500000 |  | 2013-01-22 16:28 |  | This project is needed in order to correct inefficent sight distance issues at the intersection of KY 80 and KY 451.
Y | 10 | Bluegrass ADD | IP20120046 |  |  |  | Correct flooding issues on KY 613 at Bowen from KY 11 to Bridge over Red River in Powell County. | Spot Improvement | Powell | 099-KY-0613 -000 | 0 | 0.363 | 0.363 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 100000 |  | 50000 |  | 1000000 |  | 2015-06-29 15:16 | Correct flooding issues on KY 613 at Bowen from KY 11 to Bridge over Red River in Powell County. | To promote the safe and efficient movement of people, goods and services to benefit all of the residents of the region.
Y | 10 | Bluegrass ADD | IP20120047 |  |  |  | Correct flooding issues on KY 1184 at Rosslyn in Powell County. | Spot Improvement | Powell | 099-KY-1184 -000 | 0 | 0.2 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 424000 |  | 106000 |  | 53000 |  | 874500 |  | 2015-06-29 15:34
Y | 10 | Kentucky River ADD | IP20120058 |  |  |  | Reconstruction from KY 847 to Jackson County Line. | Reconstruction | Owsley | 095-KY-0030 -000 | 0 | 4.833 | 4.833 | Modernize Roadway-Rural | 26 |  | 0 |  | 1500000 |  | 5000000 |  | 500000 |  | 25000000 |  | 2016-11-02 12:53 |  | This section of KY 30 is part of the I-75 to Mountain Parkway Corridor and will enhance connectivity to the area once completed. This portion has geometric deficiencies that need to be upgraded.
Y | 10 | Kentucky River ADD | IP20130013 |  |  |  | Improve railroad crossing and approaches at M.P 3.61, M.P. 2.53 and M.P. 2.20. | Reconstruction | Perry | 097-KY-0015 -000 | 2.1 | 3.7 | 1.6 | Improve Railroad Crossing | 55 | Y | 0 |  | 100000 |  | 50000 |  | 145000 |  | 1700000 |  | 2015-06-29 18:57 |  | To correct a continuous maintenance and vehicular drivability issue.
Y | 10 | Kentucky River ADD | IP20130014 |  |  |  | Replace existing drainage structure and realign approaches beginning at 0.090 miles West of Steepfield Fork Rd. in Avawam. | Culvert Replacement | Perry | 097-KY-0080 -000 | 0.9 | 1.1 | 0.2 | Maintenance Improvement | 10 |  | 0 |  | 100000 |  | 50000 |  | 100000 |  | 350000 |  | 2013-02-14 16:31 |  | Replace a deficient structure. Improve safety. Correct alignment issues.
Y | 10 | Bluegrass ADD | IP20130015 |  |  |  | Reconstruct KY 1571 in Estill County from KY 52 (MP 0.00) to 5.580. | Reconstruction | Estill | 033-KY-1571 -000 | 0 | 5.58 | 5.58 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 2000000 |  | 1000000 |  | 43000000 |  | 2013-02-14 16:26 | Reconstruct KY 1571 in Estill County from KY 52 (MP 0.00) to 5.580. | To promote the safe and efficient movement of people, goods, and services to benefit all of the residents of the region.
Y | 10 | Bluegrass ADD | IP20130016 |  |  |  | Correct maintenance issues caused by flooding on KY 594 in Estill County from Locust Branch Road to just beyond KY 3328. | Spot Improvement | Estill | 033-KY-0594 -000 | 0.995 | 12 | 11.005 | Other Improvement Types | 0 |  | 0 |  | 530000 |  | 212000 |  | 265000 |  | 2120000 |  | 2015-06-29 14:04 | Correct maintenance issues caused by flooding on KY 594 in Estill County from Locust Branch Road to just beyond KY 3328. | Frequent flooding on the roadway impedes traffic flow and isolates residents on either side of the spot flooding.
Y | 10 | Bluegrass ADD | IP20130017 |  |  |  | Correct Flooding issues on KY 3328 in Estill County near the Crooked Creek Bridge. | Spot Improvement | Estill | 033-KY-3328 -000 | 0.4 | 0.8 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 100000 |  | 50000 |  | 700000 |  | 2015-06-29 14:01 | Correct Flooding issues on KY 3328 in Estill County near the Crooked Creek Bridge. | Frequent flooding on the roadway impedes traffic flow and isolates residents on either side of the spot flooding.
Y | 10 | Kentucky River ADD | IP20130026 |  |  |  | Minor widening along the Hal Rogers Parkway beginning 0.574 miles East of the Leslie County line. | Minor Widening | Perry | 097-HR-9006 -000 | 51.6 | 52.2 | 0.6 | Modernize Roadway-Rural | 26 | Y | 0 |  | 350000 |  | 150000 |  | 100000 |  | 1800000 |  | 2013-08-12 09:42 |  | The continous improvement of safety and traffic flow along one of the regions most important corridors.
Y | 10 | Gateway ADD | IP20130027 |  |  |  | Improve substandard geometrics for US 460. Reconstruct the intersection of KY 882/US 460 | Reconstruction | Morgan | 088-US-0460 -000 | 0.1 | 0.3 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 150000 |  | 100000 |  | 500000 |  | 2013-03-01 14:37
Y | 10 | Kentucky River ADD | IP20130039 |  |  |  | Curve revision on KY 28 from 0.040 miles West of Gloryland Way to 1.968 miles West of Keneva Rd. | Spot Improvement | Perry | 097-KY-0028 -000 | 8.85 | 9.3 | 0.45 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 150000 |  | 100000 |  | 4600000 |  | 2013-05-01 15:17 | Curve revision on KY 28 from 0.040 miles West of Gloryland Way to 1.968 miles West of Keneva Rd. | Maintainence has continually repaired a slip at this section of KY 28. KY 28 is highly traveled by trucks and local traffic. | KENTUCKY RIVER ADD | East | 28.1961 | 5.2695 | 8.8922 | 4.8728 | 4.9701 | 0 | 0 | 4.1916 | 28
Y | 10 | Kentucky River ADD | IP20130070 |  |  |  | Reduce congestion and improve safety at the intersection of KY 80 and Justice Drive (CR 1863) in Hazard. | Reconstruction | Perry | 097-KY-0080 -000 | 8.362 | 8.562 | 0.2 | Improve Intersection | 26 | Y | 0 |  | 100000 |  | 50000 |  | 100000 |  | 250000 |  | 2013-07-19 09:28 |  | This project is needed in order to improve System reliability and congestion management.
Y | 10 | Kentucky River ADD | IP20140008 |  |  |  | Reconstruct curve from East of Hurt Cemetery to West of Hurt Branch Road on KY 1088 (Lotts Creek Road). | Reconstruction | Perry | 097-KY-1088 -000 | 0.4 | 0.73 | 0.33 | Modernize Roadway-Rural | 26 |  | 0 |  | 795000 |  | 212000 |  | 53000 |  | 1378000 |  | 2016-11-02 11:55 |  | Improve roadway structure and thus system reliability. Correct geometric deficiencies.
Y | 10 | Bluegrass ADD | IP20140009 |  |  |  | Stabilize road cut between Hatton Creek Road and Transfer Station Road on KY 11 along the Red River. | Reconstruction | Powell | 099-KY-0011 -000 | 17.042 | 18.109 | 1.067 | Other Improvement Types | 0 |  | 0 |  | 1060000 |  | 212000 |  | 106000 |  | 6890000 |  | 2015-06-29 15:31 | Stabilize road cut between Hatton Creek Road and Transfer Station Road on KY 11 along the Red River. | This section requires frequent maintenance attention due to rockfall occurrences.
Y | 10 | Bluegrass ADD | IP20140032 |  |  |  | Minor widening to correct vertical and horizontal deficiencies. | Minor Widening | Powell | 099-KY-2026 -000 | 2.3 | 4.2 | 1.9 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 750000 |  | 750000 |  | 6500000 |  | 2015-03-26 09:22 | Minor widening to correct vertical and horizontal deficiencies. | Due to the narrowness of this roadway, this section contains numerous horizontal and vertical deficiencies.
Y | 10 | Kentucky River ADD | IP20140034 |  |  |  | Improve existing Railroad Crossings in Beattyville from East Main St to KY 52. | Spot Improvement | Lee | 065-KY-0011 -000 | 4.347 | 4.456 | 0.109 | Improve Railroad Crossing | 55 |  | 0 |  | 250000 |  | 50000 |  | 50000 |  | 1000000 |  | 2014-12-05 13:45 | Improve existing Railroad Crossings in Beattyville from East Main St to KY 52. | Improve existing Railroad Crossings in Beattyville from East Main St to KY 52. | KENTUCKY RIVER ADD | East | 35.9701 | 7.018 | 14.8204 | 8.982 | 0.80838 | 0 | 4.3413 | 0 | 36
Y | 10 | Kentucky River ADD | IP20150006 |  |  |  | Reconstruction of KY 30 from 0.028 miles West of Smokey Ln. to Breathitt County line. See KY 30 Planning Study September 2014 Alternate 1A | Reconstruction | Owsley | 095-KY-0030 -000 | 15.154 | 18.753 | 3.599 | Modernize Roadway-Rural | 26 |  | 0 |  | 900000 |  | 800000 |  | 1300000 |  | 10400000 |  | 2015-03-10 11:57
Y | 10 | Kentucky River ADD | IP20150007 |  |  |  | Reroute Booneville: Realign KY 30 around the west side of Booneville and connect to KY 11 west of town. To improve roadway geometrics to enhance safety and local mobility between Jackson and Booneville and regional connectivity between the Hal Rogers | Relocation | Owsley | 095-KY-0030 -000 | 10.314 | 10.604 | 0.29 | Construct Road in New Location | 0 |  | 0 |  | 800000 |  | 1500000 |  | 1000000 |  | 14300000 |  | 2015-03-10 11:59
Y | 10 | Kentucky River ADD | IP20150100 | 10-8903 |  | A | NEW INTERCHANGE OFF OF A NEW EXIT 55 HAL ROGERS PARKWAY. (16CCN)(18CCN) | NEW INTERCHANGE(O) | Perry | 097-HR-9006 -000 | 54.9 | 55.6 | 0.7 | Grade Separated to Interchange | 0 | Y |  |  | 0 |  | 1330000 | 2019 | 330000 | 2020 | 11250000 | 2021 | 2019-03-06 14:37 | Construct a new interchange off of the Hal Rogers Parkway at Briar Fork Circle Rd (CR 1300). Briar Fork Circle Rd can be accessed by using HR 9006 Exit 56. It is located 1.4 miles from Exit 56. | Construct a new interchange off of the Hal Rogers Parkway at Briar Fork Circle Rd (CR 1300). Briar Fork Circle Rd can be accessed by using HR 9006 Exit 56. It is located 1.4 miles from Exit 56. | KENTUCKY RIVER ADD | East | 36.6123 | 8.1916 | 0 | 8.0614 | 0.41916 | 9.3413 | 3.8922 | 6.7066 | 37
Y | 10 | Gateway ADD | IP20150208 | 10-8804 |  | A | IMPROVE KY-2498 FROM US-460 TO THE ARH HOSPITAL. (14CCN)(16CCN) | RECONSTRUCTION(O) | Morgan | 088-KY-2498 -000 | 7.2 | 7.719 | 0.519 | Construct Road in New Location | 0 |  |  |  | 0 |  | 2090000 | 2022 | 520000 | 2023 | 7140000 | 2024 | 2019-03-06 14:58 | The purpose of this project is to improve the intersection. | The following needs have been identified for this project: 1) Improve Intersection, and 2) Reconstruction. | GATEWAY ADD | East | 47.6737 | 2.0599 | 5.9281 | 5.2545 | 4.4311 | 0 | 0 | 0 | 18 | 15 | 15
Y | 10 | Kentucky River ADD | IP20150243 | 10-292.10 / 10-292.12 | 2020-07-15 | A | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM KY-30 AT LEVI IN OWSLEY COUNTY TO THE LEE COUNTY LINE. (SEE 10-292.10 FOR D,R,U PHASES)(2016BOP) | RECONSTRUCTION(O) | Owsley | 095-KY-0011 -000 | 14.343 | 17.494 | 3.151 | Modernize & Widen Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 22100000 | 2021 | 2019-03-11 10:41 | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM KY-30 AT LEVI IN OWSLEY COUNTY TO 0.5 MILE SOUTH OF KY-587 IN LEE COUNTY. (06CCR)(10CCR)(14CCR) | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM KY-30 AT LEVI IN OWSLEY COUNTY TO 0.5 MILE SOUTH OF KY-587 IN LEE COUNTY. (06CCR)(10CCR)(14CCR) | KENTUCKY RIVER ADD | East | 58.0614 | 4.1317 | 5.8383 | 10.3967 | 3.7126 | 7.9641 | 3.0539 | 7.9641 | 43 |  | 15
Y | 10 | Gateway ADD | IP20150284 |  |  |  | Spot improvements on KY 36 from 0.18 miles south of Stonequarry Rd (approximately Milepoint 2.5) to 0.60 miles north of Suiter Branch Rd (approximately Milepoint 3.9). (Priority Section B-F) | Spot Improvement | Menifee | 083-KY-0036 -000 | 2.444 | 3.881 | 1.437 | Modernize Roadway-Rural | 26 |  | 0 |  | 200000 |  | 250000 |  | 250000 |  | 2000000 |  | 2016-11-01 11:36 | The purpose of this project is to: complete spot improvements and modernize the roadway. | The following needs have been identified for this project: 1) complete spot improvements, 2) improve local roadway conditions, 3) reconstruct road segment to current standards, and 4) provide modern roadway for motorists.
Y | 10 | Kentucky River ADD | IP20150475 |  |  |  | Install curb and gutter with sidewalks along KY 15 from KY 15S/KY 191 to Campton Square Apartments. | Minor Widening | Wolfe | 119-KY-0015 -000 | 9.515 | 10.03 | 0.515 | Modernize Roadway-Urban | 16 |  | 0 |  | 350000 | 2019 | 300000 | 2019 | 250000 | 2019 | 2000000 | 2019 | 2019-03-07 16:11 | Install curb and gutter with sidewalks along KY 15 from KY 15S/KY 191 to Campton Square Apartments. | Install curb and gutter with sidewalks along KY 15 from KY 15S/KY 191 to Campton Square Apartments. | KENTUCKY RIVER ADD | East | 13.8009 | 1.2934 | 0 | 9.6332 | 2.8743 | 0 | 0 | 0 | 14
Y | 10 | Kentucky River ADD | IP20150476 |  |  |  | Construct new access from Hal Rogers Parkway to Beech Nut Lane. | New Interchange | Perry | 097-HR-9006 -000 | 52.6 | 53.1 | 0.5 | Grade Separated to Interchange | 0 | Y | 0 |  | 1000000 |  | 250000 |  | 250000 |  | 11082500 |  | 2016-11-02 11:59
Y | 10 | Kentucky River ADD | IP20160002 |  |  |  | Improve safety through management of multiple conflict points at the intersection of KY 550 at Smitty Drive (MP 1.304), Combs Lane (MP 1.349) and Grand Vue Plaza (MP 1.394) in Perry County. (Intersections #9, #11, and #27 in District 10 Intersections Stud | Reconstruction | Perry | 097-KY-0550 -000 | 1.28 | 1.45 | 0.17 | Improve Intersection | 26 |  | 0 |  | 275000 |  | 250000 |  | 200000 |  | 930000 |  | 2016-06-17 11:19
Y | 10 | Kentucky River ADD | IP20160003 |  |  |  | Improve safety through improved sight distance at the intersection of KY 15X at Turner Street (MP 1.593) and Elizabeth Drive (MP 1.637) in Perry County. (Intersections #17 and #43 in District 10 Intersections Study 2015) | Reconstruction | Perry | 097-KY-0015X -000 | 1.4 | 1.7 | 0.3 | Improve Intersection | 26 |  | 0 |  | 350000 |  | 200000 |  | 200000 |  | 1035000 |  | 2016-06-17 11:21
Y | 10 | Kentucky River ADD | IP20160004 |  |  |  | Improve safety and traffic movement circulation at the intersection of KY 15X (MP 0.937) at Newland Street in Perry County. (Intersection #19 in District 10 Intersections Study 2015) | Reconstruction | Perry | 097-KY-0015X -000 | 0.9 | 1.1 | 0.2 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 150000 |  | 100000 |  | 650000 |  | 2016-06-17 11:22
Y | 10 | Kentucky River ADD | IP20160005 |  |  |  | Improve safety and traffic flow at the intersection of KY 15 (MP 9.486) at KY 191/KY 15S in Wolfe County. (Intersection #16 in District 10 Intersections Study 2015) | Reconstruction | Wolfe | 119-KY-0015 -000 | 9.45 | 9.55 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 100000 |  | 50000 |  | 50000 |  | 425000 |  | 2016-06-15 10:41 | Improve safety and traffic flow at the intersection of KY 15 (MP 9.486) at KY 191/KY 15S in Wolfe County. (Intersection #16 in District 10 Intersections Study 2015) | Improve safety and traffic flow at the intersection of KY 15 (MP 9.486) at KY 191/KY 15S in Wolfe County. (Intersection #16 in District 10 Intersections Study 2015) | KENTUCKY RIVER ADD | East | 54.2246 | 3.7006 | 14.3713 | 11.4521 | 3.2335 | 0 | 3.7725 | 2.6946 | 39 |  | 15
Y | 10 | Kentucky River ADD | IP20160010 |  |  |  | Minor widening and reconstruction along KY 399 in Lee County. This project also includes a section that is a reoccurring maintenance issue. | Reconstruction | Lee | 065-KY-0399 -000 | 5.75 | 6.2 | 0.45 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 | 2019 | 200000 | 2019 | 100000 | 2019 | 1000000 | 2019 | 2019-03-07 11:26 | Minor widening and reconstruction along KY 399 in Lee County. This project also includes a section that is a reoccurring maintenance issue. | Minor widening and reconstruction along KY 399 in Lee County. This project also includes a section that is a reoccurring maintenance issue.
Y | 10 | Kentucky River ADD | IP20160116 | 10-292.11 |  | I | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM JUST NORTH OF OWSLEY COUNTY LINE (MP 0.47) TO 0.35 MILE NORTH OF KY-587 (MP 1.94) IN LEE COUNTY. (SEE 10-292.10 FOR D,R,U PHASES)(2016BOP) | RECONSTRUCTION(O) | Lee | 065-KY-0011 -000 | 0.47 | 1.94 | 1.47 | Modernize Roadway-Rural | 26 | [9 empty] | 0 | 2025 |  |  |  | 10 | East | 58.0614 | 4.1317 | 5.8383 | 10.3967 | 3.7126 | 7.9641 | 3.0539 | 7.9641 | 43 |  | 15
Y | 10 | Kentucky River ADD | IP20160117 |  |  |  | INTERSECTION IMPROVEMENTS AT KY 15 (MP 11.75-11.95) AND KY 451C IN PERRY COUNTY, KY. (2016BOP) | Safety-Haz-Elm | Perry | 097-KY-0015 -000 | 11.75 | 11.95 | 0.2 | Improve Intersection | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 12:42
Y | 10 | Kentucky River ADD | IP20160118 |  |  |  | INTERSECTION IMPROVEMENTS AT KY 451 AND ELM/LIBERTY STREET IN PERRY COUNTY LOCATED IN DISTRICT 10. (2014BOP) | Safety-Haz-Elm | Perry | 097-KY-0451 -000 | 3.242 | 3.47 | 0.228 | Improve Intersection | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 12:42
Y | 10 | Kentucky River ADD | IP20160120 |  |  |  | WIDEN ASPHALT SHOULDERS ON KY 3349 IN PERRY COUNTY. (2016BOP) | Safety-Haz-Elm | Perry | 097-KY-3349 -000 | 0 | 2.389 | 2.389 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 13:02
Y | 10 | Kentucky River ADD | IP20160121 |  |  |  | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM LESLIE/PERRY LINE TO HAZARD, INCLUDING INTERCHANGE IN HAZARD; MP 51.03 TO MP 59.09. (16CCN) | Major Widening | Perry | 097-HR-9006 -000 | 51.03 | 59.088 | 8.058 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 13:05
Y | 10 | Kentucky River ADD | IP20160122 |  |  |  | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (2012BOP)(14CCR)(16CCR) | Major Widening | Wolfe | 119-KY-9009 -000 | 56.8 | 57.72 | 0.92 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 13:08 | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (2012BOP)(14CCR)(16CCR) | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.45 MI W OF KY 205 (MP 56.8) TO CR 1226 PARKWAY ROAD TUNNEL (MP 59.30). (2012BOP)(14CCR)(16CCR)
Y | 10 | Big Sandy ADD | IP20160150 |  |  |  | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.4 MI E OF THE KY-134 JOHNSON CREEK BR TO 0.3 MI W OF KY 3047 - SECTION 5. (14CCR)(16CCR) | Major Widening | Magoffin | 077-KY-9009 -000 | 63.123 | 65 | 1.877 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-19 12:30
Y | 10 | Kentucky River ADD | IP20160279 |  |  |  | I-75 to Mountain Parkway; reconstruct KY-11 from KY-30 at Levi in Owsley County to 0.5 mile south of KY-587 in Lee County. | Reconstruction | Owsley | 095-KY-0011 -000 | 14.343 | 17.494 | 3.151 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18400000 |  | 2017-03-23 11:05 | I-75 to Mountain Parkway; reconstruct KY-11 from KY-30 at Levi in Owsley County to 0.5 mile south of KY-587 in Lee County. | I-75 to Mountain Parkway; reconstruct KY-11 from KY-30 at Levi in Owsley County to 0.5 mile south of KY-587 in Lee County.
Y | 10 | Bluegrass ADD | IP20160280 |  |  |  | To create a new route between CR 1016 and CR 1015 | New Route | Powell | 099-CR-1016 -000 | 0 | 1.212 | 1.212 | Construct Road in New Location | 0 |  | 0 |  | 800000 |  | 820000 |  | 400000 |  | 8000000 |  | 2016-12-09 16:23 | To create a new route between CR 1016 and CR 1015 | To provide a direct connection from Menifee County to the Mountain Parkway. This would promote tourism in the Red River Gorge Area.
Y | 10 | Gateway ADD | IP20160281 |  |  |  | Reconstruct Buck Evans Road from the intersection of Bays Bend Road to the intersection of KY 2498. | New Route | Morgan | 088-CR-1304 -000 | 0 | 0.717 | 0.717 | Construct Road in New Location | 0 |  | 0 |  | 365000 |  | 325000 |  | 100000 |  | 3650000 |  | 2016-12-09 13:40 | The purpose of this project is to reconstruct a modernized roadway. | The following need has been identified for this project: reconstruct a modernized roadway.
Y | 10 | Gateway ADD | IP20160282 |  |  |  | Reconstruct and modernize KY 36 from the Bath County line to Frenchburg. | Reconstruction | Menifee | 083-KY-0036 -000 | 0 | 6.081 | 6.081 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 2882000 |  | 2507500 |  | 27450000 |  | 2016-12-09 13:38 | The purpose of this project is to modernize the roadway. | The following need has been identified for this project: modernize the roadway.
Y | 10 | Gateway ADD | IP20160283 |  |  |  | Reconstruct CR 1208 with new modern roadway. | Reconstruction | Menifee | 083-CR-1208 -000 | 0 | 2 | 2 | Modernize Roadway-Rural | 26 |  | 0 |  | 650000 |  | 820000 |  | 400000 |  | 6500000 |  | 2016-12-09 13:35 | The purpose of this project is to reconstruct a modernized roadway. | The following need has been identified for this project: construct a modernized roadway.
Y | 10 | Bluegrass ADD | IP20160285 | 10-207 |  | A | IMPROVE GEOMETRICS ON KY-89 IN ESTILL COUNTY FROM KY-1886 TO THE ESTILL/CLARK COUNTY LINE. | MAJOR WIDENING(O) | Estill | 033-KY-0089 -000 | 19.806 | 22.428 | 2.622 | Modernize Roadway-Rural | 26 |  |  |  | 1560000 | 2021 | [6 empty] | 2019-03-06 13:50 | The purpose of this project is to improve mobility, connectivity and safety, as well as to address roadway deficiencies between I-75 and the Mountain Parkway. | Roadway Deficiencies – KY 89 has noted vertical and horizontal deficiencies. Travel Time Reliability – KY 89 is a two lane road with limited passing opportunities. Numerous deficient horizontal and vertical curves require drivers to slow down to negotia | BLUEGRASS ADD | East | 52.1108 | 1.1377 | 7.7246 | 9.8353 | 2.3653 | 6.6467 | 0 | 9.4012 | 37 | 15
Y | 10 | Kentucky River ADD | IP20160286 | 10-376 |  | A | IMPROVE KY-15 FROM THE INTERSECTION OF NEW KY-15/30 TO INTERSECTION OF KY-1812. | MAJOR WIDENING(O) | Breathitt | 013-KY-0015 -000 | 16.75 | 17.9 | 1.15 | Install Two-way Left Turn Lane | 28 | Y |  |  | 0 | 2019 | 3050000 | 2021 | 1560000 | 2022 | 20250000 | 2023 | 2019-03-06 14:23 | Widen and install TWLTL along KY 15 from intersection of new KY 15 to intersection of KY 1812. | Widen and install TWLTL along KY 15 from intersection of new KY 15 to intersection of KY 1812. | KENTUCKY RIVER ADD | East | 86.1377 | 7.7246 | 13.3832 | 13.2036 | 1.018 | 9.9401 | 4.4012 | 6.4671 | 56 | 15 | 15
Y | 10 | Kentucky River ADD | IP20160287 |  |  |  | Reconstruct KY 15 from 2 lanes to 4 lanes from the Knott County line to Scuddy Branch. | Reconstruction | Perry | 097-KY-0015 -000 | 0 | 2 | 2 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 2400000 |  | 1700000 |  | 1350000 |  | 24000000 |  | 2016-12-09 16:15
Y | 10 | Kentucky River ADD | IP20170068 |  |  |  | The I-66 Corridor has been studied and potential alignments drawn from the State of Missouri to London, KY and from Pikeville, KY to West Virginia. This study would look at the missing area between them. This is a Planning Study to identify alignments and | Transportation Study | Perry | 097-HR-9006 -000 | 51.026 | 59.088 | 8.062 | Transportation Studies | 0 | Y | 1000000 | 2019 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-13 15:21 | This is a Planning Study to identify alignments and obstacles they may be faced in the future if/when the corridor moves forward. This study would develop recommendations at a corridor level based on existing topography, environmental features, socioeconm | This is a Planning Study to identify alignments and obstacles they may be faced in the future if/when the corridor moves forward. This study would develop recommendations at a corridor level based on existing topography, environmental features, socioeconm | 10 | Statewide | 25.4626 | 6.696 | 0 | 10.3084 | 7.0485 | 0 | 1.4097 | 0
Y | 10 | Kentucky River ADD | IP20180019 |  |  |  | Reconstruct benches/ slope improvement along KY 15 to eliminate rockfall issues. | Safety-Haz-Elm | Breathitt | 013-KY-0015 -000 | 13.75 | 14.644 | 0.894 |  |  | Y
Y | 10 | Kentucky River ADD | IP20180020 | 10-212 |  | A | IMPROVE THE KY-191 AND KY-1812 INTERSECTION. | RECONSTRUCTION(O) | Wolfe | 119-KY-0191 -000 | 4.765 | 4.965 | 0.2 | Realign Intersection | 26 |  |  |  | 300000 | 2023 | 100000 | 2023 | 120000 | 2023 | 980000 | 2024 | 2019-02-26 15:38 | Reconstruction of KY 191 & KY 1812 intersection | Reconstruction of KY 191 & KY 1812 intersection
Y | 10 | Kentucky River ADD | IP20180021 | 10-209 |  | A | IMPROVE KY-476 FROM KY-15X IN WALKERTOWN TO NORTH OF WALKER CORNETT ROAD IN WABACO. | RECONSTRUCTION(O) | Perry | 097-KY-0476 -000 | 0 | 0.9 | 0.9 | Modernize Roadway-Rural | 26 |  |  |  | 780000 | 2021 | [6 empty] | 2019-03-06 13:56 | Reconstruction of KY 476 from KY 15X in Walkertown to 0.025 North of Walker Cornett Rd. in Wabaco. | Reconstruction of KY 476 from KY 15X in Walkertown to 0.025 North of Walker Cornett Rd. in Wabaco.
Y | 10 | Gateway ADD | IP20180052 |  |  |  | Widen and improve geometrics on US 460 from Lariat Road to the Morgan County line (approximately Milepoint 19). Completes US 460 upgrades in Menifee County between Frenchburg and Morgan County Line. (14CCN) | Reconstruction | Menifee | 083-US-0460 -000 | 13.964 | 19.003 | 5.039 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 3500000 |  | 2000000 |  | 30000000 |  | 2018-10-09 09:21 | The purpose of this project is to: widen the roadway and improve geometrics. | The following needs have been identified for this project: 1) widen the roadway and 2) improve geometrics.
Y | 10 | Gateway ADD | IP20190028 |  |  |  | Minor Widening and Geometric Improvements on KY 172 from Crockett to just south of KY 1715 at Moon. | Reconstruction | Morgan | 088-KY-0172 -000 | 13 | 16.4 | 3.4 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 1500000 | 2019 | 2000000 | 2019 | 1500000 | 2019 | 10250000 | 2019 | 2019-03-12 09:09 | To modernize a deficient roadway making travel safer and easier for motorist using the KY 172 corridor. | KY 172 connects West Liberty and Paintsville via a horizontally deficient roadway with little to no shoulders. Improvements need to be made to ensure motorist are using a modern and safe roadway in their daily lives.
Y | 10 | Gateway ADD | IP20190035 |  |  |  | Create a NEW Eastern ByPass of West Liberty. | Bypass | Morgan | 088-US-0460 -000 | 16.95 | 18.55 | 1.6 | Construct Road in New Location | 0 |  | 0 |  | 1500000 | 2019 | 3000000 | 2019 | 1000000 | 2019 | 17000000 | 2019 | 2019-03-07 10:48 | Create a NEW Eastern ByPass of West Liberty. | Create a NEW Eastern ByPass of West Liberty.
Y | 10 | Big Sandy ADD | IP20190097 |  |  |  | RECONSTRUCT KY 7 TO A MODERN TYPICAL SECTION TO ALLOW EASIER AND SAFER ACCESS FROM THE MOUNTAIN PARKWAY TO ROYALTON. | Reconstruction | Magoffin | 077-KY-0007 -000 | 19 | 22.5 | 3.5 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 1700000 | 2019 | 3000000 | 2019 | 3000000 | 2019 | 11000000 | 2019 | 2019-03-07 10:53 | RECONSTRUCT KY 7 TO A MODERN TYPICAL SECTION TO ALLOW EASIER AND SAFER ACCESS FROM THE MOUNTAIN PARKWAY TO ROYALTON. | RECONSTRUCT KY 7 TO A MODERN TYPICAL SECTION TO ALLOW EASIER AND SAFER ACCESS FROM THE MOUNTAIN PARKWAY TO ROYALTON.
Y | 10 | Bluegrass ADD | IP20190108 |  |  |  | Reconstruct roadway out of Floodway/Floodway in order to eliminate Mountain Parkway Access. | Reconstruction | Powell | 099-CR-1316 -000 | 0.075 | 0.575 | 0.5 | Local Roadway Improvements | 3 |  | 0 |  | 500000 | 2019 | 100000 | 2019 | 100000 | 2019 | 2800000 | 2019 | 2019-03-07 11:04 | Reconstruct roadway out of Floodway/Floodway in order to eliminate Mountain Parkway Access. | Reconstruct roadway out of Floodway/Floodway in order to eliminate Mountain Parkway Access.
Y | 10 | Big Sandy ADD | IP20190122 |  |  |  | Modernize roadway to include better drainage and proper bike/ped facilities. | Minor Widening | Magoffin | 077-KY-0040 -000 | 0 | 0.7 | 0.7 | Modernize Roadway-Urban | 16 |  | 0 |  | 1000000 | 2019 | 2000000 | 2019 | 1000000 | 2019 | 5000000 | 2019 | 2019-03-07 10:53 | Provide a modern travel way for various types of transportation. | Area is in the downtown section of Salyersville but has no shoulders nor bike/ped facilities.
Y | 10 | Kentucky River ADD | IP20190180 |  |  |  | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM 0.3 MILE North OF KY-587 TO WEST RIDGE ROAD. | Reconstruction | Lee | 065-KY-0011 -000 | 1.8 | 3.3 | 1.5 | Modernize & Widen Roadway-Rural | 26 |  | 0 | 2019 | 1000000 | 2019 | 2500000 | 2019 | 500000 | 2019 | 10000000 | 2019 | 2019-03-12 10:04 | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM 0.3 MILE North OF KY-587 TO WEST RIDGE ROAD. | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM 0.3 MILE North OF KY-587 TO WEST RIDGE ROAD.
Y | 10 | Gateway ADD | IP20190185 |  |  |  | Minor Widening and Geometric Improvements on KY 172 from West of KY 1614 to 0.3 miles into Johnson County. | Reconstruction | Morgan | 088-KY-0172 -000 | 20.4 | 21.169 | 0.769 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 900000 | 2019 | 700000 | 2019 | 500000 | 2019 | 5000000 | 2019 | 2019-03-12 10:52 | To modernize a deficient roadway making travel safer and easier for motorist using the KY 172 corridor. | KY 172 connects West Liberty and Paintsville via a horizontally deficient roadway with little to no shoulders. Improvements need to be made to ensure motorist are using a modern and safe roadway in their daily lives.
Y | 11 | Cumberland Valley ADD | IP20050024 |  |  |  | Reconstruction of US 421 from KY 89 to KY 587 | Reconstruction | Jackson | 055-US-0421 -000 | 10.802 | 14.808 | 4.006 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 1500000 |  | 500000 |  | 24000000 |  | 2012-04-16 13:49 | The purpose of this project is to reconstruct US 421 from KY 89 to KY 587. This project is to help improve a primary regional access corridor for Jackson County that traverses through the county seat of McKee, which serves as the center of commercial act | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility
Y | 11 | Cumberland Valley ADD | IP20050025 |  |  |  | Reconstruction of US 421 from KY 89 North to Sand Lick Road. (See Section 1 of Alternative 4 in January 2005 US 421 Alternatives Study.) | Reconstruction | Jackson | 055-US-0421 -000 | 14.797 | 16.891 | 2.094 | Modernize Roadway-Rural | 26 |  | 0 |  | 970000 |  | 1200000 |  | 520000 |  | 12260000 |  | 2016-10-07 10:52 | The purpose of this project is to reconstruct US 421 from KY 89 North to Sand Lick Road. (See Section 1 of Alternative 4 in January 2005 US 421 Alternatives Study.) It is part of an effort to improve a primary regional access corridor for Jackson Count | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Improve Mobility
Y | 11 | Cumberland Valley ADD | IP20050029 |  |  |  | Reconstruction of US 421 from Asbill Road to J.A. Farmer Road. (See Section 6 of Alternative 4 in January 2005 US 421 Alternatives Study.) | Relocation | Jackson | 055-US-0421 -000 | 25.366 | 27.184 | 1.818 | Modernize Roadway-Rural | 26 |  | 0 |  | 910000 |  | 1050000 |  | 450000 |  | 9740000 |  | 2016-10-07 10:55 | The purpose of this project is to reconstruct US 421 from Asbill Road to J.A. Farmer Road. (See Section 6 of Alternative 4 in January 2005 US 421 Alternatives Study.) This project is part of an effort to improve a primary regional access corridor for Jac | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20050030 |  |  |  | Reconstruction of US 421 from J.A. Farmer Road to just north of the Jackson County/Rockcastle County line. (See Section 7 of Alternative 4 in January 2005 US 421 Alternatives Study.) | Reconstruction | Jackson | 055-US-0421 -000 | 27.184 | 29.574 | 2.39 | Modernize Roadway-Rural | 26 |  | 0 |  | 990000 |  | 1420000 |  | 620000 |  | 13180000 |  | 2016-10-07 10:55 | The purpose of this project is to reconstruct US 421 from J.A. Farmer Road to just north of the Jackson County/Rockcastle County line. (See Section 7 of Alternative 4 in January 2005 US 421 Alternatives Study.) This project is part of an effort to impro | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060286 |  |  |  | Correct substandard roadway geometrics and address condition and safety issues on US 421 from US 119 to KY 221 | Reconstruction | Harlan | 048-US-0421 -000 | 17.107 | 24.203 | 7.096 | Modernize Roadway-Rural | 26 |  | 0 |  | 5720000 |  | 8320000 |  | 1872000 |  | 117936000 |  | 2010-02-25 16:51 | The purpose of this project is to correct substandard roadway geometrics and address condition and safety issues on US 421 from US 119 to KY 221. This project is part of an overall plan to improve the US 421 corridor in Harlan County from US 119 to the H | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060287 |  |  |  | Address sight distance and safety issues on US 421 at its intersection of KY 1912 in Morrill | Reconstruction | Jackson | 055-US-0421 -000 | 29.466 | 29.574 | 0.108 | Modernize Roadway-Rural | 26 |  | 0 |  | 31200 |  | 31200 |  | 31200 |  | 218400 |  | 2010-02-25 16:51 | The purpose of this project is to address sight distance and safety issues on US 421 at its intersection of KY 1912 in Morrill. This project was identified in a recently completed alternatives study (January 2005) for US 421 from KY 89 at the northern ci | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20060288 |  |  |  | Address access and safety issues at the intersection of US 421/KY 3446/School Road #2 | Safety-Haz-Elm | Jackson | 055-US-0421 -000 | 21.463 | 21.663 | 0.2 | Improve Intersection | 26 |  | 0 |  | 260000 |  | 104000 |  | 52000 |  | 520000 |  | 2010-02-25 16:51 | The purpose of this project is to improve an intersection (US 421/KY 3446/School Road #2) that provides access to Sand Gap Elementary School, Sand Gap Park recreation area, S-Tree Tower, and residences. Also, no turn lanes exist at the intersection. Co | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060289 |  |  |  | Address safety, surface condition, and congestion issues on I-75 from 0.2 miles north of the US-25 North Overpass to Rockcastle River Bridges. Included in the 1998 Planning Study. | Major Widening | Laurel | 063-I -0075 -000 | 46.101 | 48.031 | 1.93 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 1711000 |  | 244400 |  | 488800 |  | 13686400 |  | 2010-02-25 16:51 | The purpose of this project is to address safety, surface condition, and congestion issues on I-75 from 0.2 miles north of the US-25 North Overpass to Rockcastle River Bridges. Included in the 1998 Planning Study. This project is a part of an overall pla | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060290 |  |  |  | Address safety and congestion issues on US 25 from KY 1189 to KY 1006. | Major Widening | Laurel | 063-US-0025 -000 | 6.953 | 9.028 | 2.075 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 208000 |  | 1352000 |  | 3016000 |  | 1040000 |  | 8320000 |  | 2010-02-25 16:51 | The purpose of this project is to address safety and congestion issues on US 25 from KY 1189 to KY 1006. This project is a part of an overall plan to expand US 25 from US 25E near Corbin to KY 192 in London. Over the course of the past several years deve | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060291 |  |  |  | Address congestion, access management, and safety issues on US 25 North from Hal Rogers Parkway near KY State Police Post to KY 490. | Congestion Management | Laurel | 063-US-0025 -000 | 13.556 | 16.7 | 3.144 | Modernize Roadway-Rural | 26 |  | 0 |  | 1050000 |  | 3150000 |  | 1050000 |  | 10000000 |  | 2017-05-18 11:09 | The purpose of this project is to address congestion, access management, and safety issues on US 25 North from Hal Rogers Parkway near KY State Police Post to KY 490. The project area is primarily commercial and has a high ADT range on a two lane roadway | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 39.2512 | 7.2607 | 12.0853 | 11.9431 | 1.327 | 0 | 0 | 6.6351 | 39
Y | 11 | Cumberland Valley ADD | IP20060292 |  |  |  | Address horizontal/vertical alignment and safety issues on KY 192 from the Laurel County/Pulaski County line to I-75 in London | Spot Improvement | Laurel | 063-KY-0192 -000 | 0 | 18.243 | 18.243 | Modernize Roadway-Rural | 26 |  | 0 |  | 374400 |  | 390000 |  | 416000 |  | 3848000 |  | 2010-02-25 16:51 | The purpose of this project is to undertake spot improvements on KY 192 from the Pulaski County line to Interstate 75 in London. This section of KY 192 has several horizontal and vertical alignment issues with no available passing lanes. A high ADT, CRF, | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20060293 | 11-365 |  | A | REDUCE CONGESTION ON THE HAL ROGERS PARKWAY FROM RELOCATED KY-30 TO KY-192. (18CCR) | MAJOR WIDENING(O) | Laurel | 063-HR-9006 -000 | 1.089 | 3.877 | 2.788 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 1870000 | 2021 | 2080000 | 2022 | 1250000 | 2022 | 5080000 | 2023 | 2019-02-27 09:27 | The purpose of this project is to reduce congestion on the Hal Rogers Parkway (HR-9006) from relocated KY 30 to KY 192. The parkway is the major east-west corridor connecting I-75 to eastern Kentucky. Commercial truck traffic, in particular, relies heav | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 88.2453 | 7.7062 | 14.4313 | 12.814 | 1.327 | 8.8626 | 4.1943 | 8.91 | 58 | 15 | 15
Y | 11 | Cumberland Valley ADD | IP20060294 |  |  |  | Address congestion issues on I-75 from the Tennessee state line to KY 92 at Williamsburg | Major Widening | Whitley | 118-I -0075 -000 | 0 | 10.548 | 10.548 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 1575000 |  | 2940000 |  | 5880000 |  | 89658000 |  | 2010-02-25 16:51 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. ADT in the project area continu | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060295 |  |  |  | Address congestion issues on I-75 from KY 92 at Williamsburg to US 25W at Goldbug | Major Widening | Whitley | 118-I -0075 -000 | 10.548 | 15.456 | 4.908 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 700000 |  | 1365000 |  | 2730000 |  | 41718000 |  | 2010-02-25 16:51 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. ADT continues to rise throughout | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060296 |  |  |  | Address congestion issues on I-75 from US 25W at Goldbug to MP 20.2 near Tidal Wave Road overpass | Major Widening | Whitley | 118-I -0075 -000 | 15.456 | 20.2 | 4.744 | Add Lane to Full Control Facility | 25 | Y | 0 |  | 1175000 |  | 2100000 |  | 1470000 |  | 40324000 |  | 2010-02-25 16:51 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. ADT in the project area continue | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20060297 |  |  |  | Address condition, safety, and congestion issues on US 25W from 13th Street to 18th Street in Corbin | Reconstruction | Whitley | 118-US-0025W -000 | 32.098 | 32.41 | 0.312 | Modernize Roadway-Rural | 26 |  | 250000 |  | 945000 |  | 3150000 |  | 1050000 |  | 4305000 |  | 2017-05-18 11:48 | Address condition, safety, and congestion issues on US 25W from 13th Street to 18th Street in Corbin. This project has a high ADT of traffic on a two lane road that varies in width. The volume of traffic has increased the congestion therefore decreasing | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 63.5794 | 9.6872 | 11.3744 | 9.3661 | 0 | 9.9052 | 4.6445 | 3.6019 | 49 | 15
Y | 11 | Cumberland Valley ADD | IP20060298 |  |  |  | Address flooding and safety issues on KY 1804 from 0.2 miles west of the railroad crossing to the I-75 underpass | Reconstruction | Whitley | 118-KY-1804 -000 | 0 | 1.358 | 1.358 | Maintenance Improvement | 10 |  | 0 |  | 315000 |  | 210000 |  | 105000 |  | 945000 |  | 2010-02-25 16:51 | The purpose of this project is to raise sections of KY 1804 out of high water from 0.2 miles west of the railroad crossing to the I-75 underpass. Standing water exists at several locations during wet weather periods and is a safety issue. | The following needs have been identified for this project: 1) Improve Roadway Safety
Y | 11 | Cumberland Valley ADD | IP20070244 |  |  |  | Address capacity, access, surface condition, and safety issues along KY 160 from US 119 to KY 522. | Major Widening | Harlan | 048-KY-0160 -000 | 10.981 | 12.954 | 1.973 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 2000000 |  | 5000000 |  | 2000000 |  | 15800000 |  | 2017-05-18 09:37 | The purpose of this project is to address capacity, access, surface condition, and safety issues along KY 160 from US 119 to KY 522. | Project begins 0.5 mi. East of US 119, goes through downtown Cumberland, and terminates at KY 522. The purpose of this project is to expand KY 160 from US 119 to KY 522 in the City of Cumberland, Kentucky, in order to reduce congestion, improve access t | CUMBERLAND VALLEY ADD | South | 39.3135 | 4.1517 | 9.2417 | 9.2773 | 3.7204 | 6.6825 | 0 | 6.24 | 39
Y | 11 | Cumberland Valley ADD | IP20070245 |  |  |  | Address safety and congestion issues on US 25 from US 25E near Corbin to KY 1189 as per 2006 Scoping Study. | Major Widening | Laurel | 063-US-0025 -000 | 0 | 6.953 | 6.953 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 750000 |  | 3250000 |  | 5000000 |  | 3000000 |  | 23000000 |  | 2010-02-25 16:51 | The purpose of this project is to address safety and congestion issues on US 25 from US 25E near Corbin to KY 1189 as per 2006 Scoping Study. This project is a part of an overall plan to expand US 25 from US 25E At North Corbin to KY 192(London Bypass) i | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20070246 |  |  |  | Address congestion and access issues on US 25W from US 25E to Engineers Street in Corbin | Major Widening | Whitley | 118-US-0025W -000 | 33.578 | 33.748 | 0.17 | Modernize Roadway-Rural | 26 |  | 0 |  | 850000 |  | 2500000 |  | 1050000 |  | 5500000 |  | 2013-07-31 15:58 | The purpose of this project is to address congestion and improve access on US 25W from US 25E to Engineers Street in Corbin. A small portion of the project area is located in the City of Corbin (in Whitley County), with the remaining portion located in s | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20070247 |  |  |  | Address congestion and safety issues on US 25W from KY 296 (Main Street) to just south of KY 92 in Williamsburg. | Reconstruction | Whitley | 118-US-0025W -000 | 10.823 | 12.422 | 1.599 | Modernize Roadway-Rural | 26 |  | 100000 |  | 800000 |  | 2000000 |  | 1000000 |  | 4900000 |  | 2017-05-18 11:46 | The purpose of this project is to address congestion and safety issues on US 25W from KY 296 (Main Street) to just south of KY 92 in Williamsburg. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 85.2938 | 7.0237 | 13.436 | 12.7962 | 1.327 | 9.3365 | 3.6967 | 7.6777 | 55 | 15 | 15
Y | 11 | Cumberland Valley ADD | IP20070248 |  |  |  | Address access and safety issues on US 25W from I-75 near Corbin to KY 90 (Cumberland Falls State Park entrance) | Reconstruction | Whitley | 118-US-0025W -000 | 21.9 | 28.2 | 6.3 | Add Lane to Full Control Facility | 25 |  | 500000 |  | 4000000 |  | 5200000 |  | 4000000 |  | 38100000 |  | 2018-11-28 15:59 | The purpose of this project is to address access and safety issues on US 25W from I-75 near Corbin to KY 90 (Cumberland Falls State Park entrance) on a route heavily used by visitors during summer months. This project begins at KY 90 (Cumberland Falls St | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080590 |  |  |  | Address safety, capacity, surface condition, and access issues from KY 3560 (Fox Hollow Road) to KY-11 at Treadway (Laurel Creek) | Reconstruction | Clay | 026-US-0421 -000 | 20.213 | 24.016 | 3.803 | Modernize Roadway-Rural | 26 |  | 0 |  | 4500000 |  | 6000000 |  | 4000000 |  | 51500000 |  | 2010-02-25 16:51 | The purpose of this project from Fox Hollow Road north to KY 11 junction is to improve a primary regional access corridor for Clay County that will enhance safety, expand capacity, upgrade surface conditions, and improve access to businesses and schools. | The following needs have been identified for this project: 1) Improve Roadway Safety 2) Improve Access 3) Increase Capacity 4) Improve Mobility 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 51.8211 | 7.3555 | 8.673 | 11.6055 | 3.6019 | 8.8152 | 3.2701 | 8.5 | 52
Y | 11 | Cumberland Valley ADD | IP20080591 |  |  |  | Address horizontal alignment, safety, surface condition from KY-66 to KY-149 | Reconstruction | Clay | 026-US-0421 -000 | 1.825 | 13.692 | 11.867 | Modernize Roadway-Rural | 26 |  | 0 |  | 7000000 |  | 12000000 |  | 6000000 |  | 71200000 |  | 2010-02-25 16:51 | The purpose of the project is to improve this section of US 421 in Clay County to address horizontal alignment, enhance safety, upgrade surface conditions, and expand capacity. The project area has infrequent curves with design speeds less than the preva | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility
Y | 11 | Cumberland Valley ADD | IP20080592 |  |  |  | Address horizontal alignment, safety, surface condition, and capacity issues on US-421 from KY-11 at Treadway (Laurel Creek) to the Clay County/Jackson County Line. | Reconstruction | Clay | 026-US-0421 -000 | 24.016 | 32.824 | 8.808 | Modernize Roadway-Rural | 26 |  | 0 |  | 4000000 |  | 9000000 |  | 6000000 |  | 53000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve US 421 from KY 11 in Clay County to the Clay/Jackson County line in order to address horizontal alignment, enhance safety, upgrade surface conditions, and expand capacity. Numerous curves are found along this str | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility | CUMBERLAND VALLEY ADD | South | 51.2725 | 6.1422 | 8.0332 | 12.1919 | 4.3602 | 7.4408 | 3.2464 | 9.8578 | 51
Y | 11 | Cumberland Valley ADD | IP20080593 |  |  |  | Correct substandard roadway geometrics and address safety issues from the Clay/Knox County Line to Cottongin | Reconstruction | Clay | 026-KY-0011 -000 | 0 | 2.9 | 2.9 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 2000000 |  | 11000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on KY 11. | This project is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County) and was identified in a 1999 corridor feasibility study (see segment 4). Operational efficiency along the corridor is diminished as a res
Y | 11 | Cumberland Valley ADD | IP20080594 |  |  |  | Correct substandard roadway geometrics and address safety issues from Cottongin to the railroad crossing at milepoint 5.300 | Reconstruction | Clay | 026-KY-0011 -000 | 2.9 | 5.3 | 2.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 2500000 |  | 2000000 |  | 10000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on KY 11. | This project is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County) and was identified in a 1999 corridor feasibility study (see segment 5). Operational efficiency along the corridor is diminished as a res
Y | 11 | Cumberland Valley ADD | IP20080595 |  |  |  | Correct substandard roadway geometrics and address safety issues from railroad crossing at mile point 5.300 to Engine Branch Road. | Reconstruction | Clay | 026-KY-0011 -000 | 5.3 | 7.2 | 1.9 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 2000000 |  | 2000000 |  | 8500000 |  | 2010-02-25 16:51 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on KY 11. | This project is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County) and was identified in a 1999 corridor feasibility study (see segment 6). Operational efficiency along the corridor is diminished as a res
Y | 11 | Cumberland Valley ADD | IP20080597 |  |  |  | Correct substandard roadway geometrics and address safety issues from US-421 to Oneida. | Reconstruction | Clay | 026-KY-0011 -000 | 8.891 | 19.591 | 10.7 | Modernize Roadway-Rural | 26 |  | 600000 |  | 6400000 |  | 5000000 |  | 2000000 |  | 51000000 |  | 2017-05-18 10:01 | The purpose of this project is to improve access to US 421 for the community of Oneida. Safety concerns exist along this corridor due to the narrow lanes and lack of sufficient shoulders. There are also sections of broken pavement, steep drop-off points, | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | CUMBERLAND VALLEY ADD | South | 55.641 | 1.346 | 9.0995 | 11.1434 | 4.1232 | 5.2607 | 0 | 9.6682 | 41 |  | 15
Y | 11 | Cumberland Valley ADD | IP20080598 |  |  |  | Correct substandard roadway geometrics on US 421 from KY 221 to the Harlan County/Leslie County line | Reconstruction | Harlan | 048-US-0421 -000 | 24.203 | 26.888 | 2.685 | Modernize Roadway-Rural | 26 |  | 0 |  | 2000000 |  | 3250000 |  | 2700000 |  | 35000000 |  | 2010-02-25 16:51 | The purpose of this project is to correct substandard roadway geometrics on US 421 from KY 221 to the Harlan County/Leslie County line. This project is part of an overall plan to improve the US 421 corridor in Harlan County from US 119 to the Harlan/Lesli | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080600 |  |  |  | Address congestion/capacity issues on KY 72 from Liggett Church Road (CR 1223) to US 421 | Reconstruction | Harlan | 048-KY-0072 -000 | 4.671 | 10.902 | 6.231 | Modernize Roadway-Rural | 26 |  | 0 |  | 3000000 |  | 9000000 |  | 6000000 |  | 74000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve KY 72 to increase its capacity to support substantial traffic increases related to a new coal development and an increasing residential sector along the corridor. | The following needs have been identified for this project: 1) Improve Roadway Safety 2) Improve Access 3) Increase Capacity 4) Improve Mobility 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080601 |  |  |  | Address horizontal alignment and safety concerns on KY 179 from KY 38 to KY 2006 | Reconstruction | Harlan | 048-KY-0179 -000 | 0 | 7.58 | 7.58 | Modernize Roadway-Rural | 26 |  | 0 |  | 5000000 |  | 5000000 |  | 4000000 |  | 121000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve KY 179 from KY 38 near Louellen to KY 2006 at the Southeast Community College campus at Cumberland Ave. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion The existing roadway traverses Black Mountain in Harlan County and has several sha
Y | 11 | Cumberland Valley ADD | IP20080602 |  |  |  | Address access and safety issues on KY 990 from KY 3001 to Mary Hellen Methodist Road (CR 1289) | Reconstruction | Harlan | 048-KY-0990 -000 | 0 | 1 | 1 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1200000 |  | 600000 |  | 3000000 |  | 2010-02-25 16:51 | The purpose of this project is to address access and safety issues on KY 990 from US 421 to Mary Hellen Methodist Road. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Improve Mobility. The project area is primarily residential; however, the roadway is classified as a coal haul highway and there is a significant
Y | 11 | Cumberland Valley ADD | IP20080604 |  |  |  | Address horizontal alignment on US 421 north of KY 89 near the city of McKee | Reconstruction | Jackson | 055-US-0421 -000 | 14.7 | 15 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 500000 |  | 120000 |  | 1000000 |  | 2013-07-31 12:31 | The purpose of this project is to address horizontal alignment on US 421 north of KY 89 near the city of McKee. It was identified in the US 421 Alternatives Study Spot Improvement 1 of Alternative 2. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20080605 |  |  |  | Address substandard horizontal and vertical alignment of US 421 in the Clover Bottom Area near the stone quarry. | Reconstruction | Jackson | 055-US-0421 -000 | 26.5 | 27 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 275000 |  | 335000 |  | 305000 |  | 2130000 |  | 2017-05-18 09:23 | The purpose of this project is to address substandard horizontal and vertical alignment of US 421 in the Clover Bottom Area near the stone quarry. The project area is known as Clover Bottom and includes a couple of sharp curves and an elevation change nea | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility | CUMBERLAND VALLEY ADD | South | 38.9135 | 4.7488 | 10.1659 | 4.4254 | 4.5024 | 6.9668 | 2.9858 | 5.1185 | 39
Y | 11 | Cumberland Valley ADD | IP20080606 |  |  |  | Address access and safety issues on US 421 at KY 2004 in Sand Gap. | Safety-Haz-Elm | Jackson | 055-US-0421 -000 | 22.038 | 22.238 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 156000 |  | 156000 |  | 104000 |  | 624000 |  | 2010-02-25 16:51 | The purpose of this project is to address access and safety issues on US 421 at KY 2004 in Sand Gap to improve access and address safety issues. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20080607 |  |  |  | Correct substandard roadway geometrics and address safety issues from US 25E north of Barbourville to north of Girdler | Reconstruction | Knox | 061-KY-0011 -000 | 10.118 | 13.918 | 3.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 1144000 |  | 4056000 |  | 1040000 |  | 15912000 |  | 2015-07-06 11:10 | This project is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County). Operational efficiency along the corridor is diminished as a result of narrow roadway widths, a lack of passing zones, and the number of | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 57.8744 | 2.9573 | 10.8768 | 10.4858 | 4.6682 | 7.0616 | 0 | 6.8246 | 43 | 15
Y | 11 | Cumberland Valley ADD | IP20080608 |  |  |  | Correct substandard roadway geometrics and address safety issues from north of Girdler to Mills Cemetery. (Part of 1999 KY 11 Corridor Feasibility Study.) | Reconstruction | Knox | 061-KY-0011 -000 | 16.293 | 18.293 | 2 | Modernize Roadway-Rural | 26 |  | 0 |  | 520000 |  | 1664000 |  | 520000 |  | 7500000 |  | 2015-07-06 11:23 | This project is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County). Operational efficiency along the corridor is diminished as a result of narrow roadway widths, a lack of passing zones, and the number of | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 27.0142 | 2.6066 | 3.6967 | 3.6256 | 3.1517 | 5.6398 | 0 | 8.2938 | 27
Y | 11 | Cumberland Valley ADD | IP20080609 |  |  |  | Correct substandard roadway geometrics & address safety issues from Mills Cemetery to Knox County/Clay County Line. (Addressed in 1999 KY 11 Corridor Feasibility Study.) | Reconstruction | Knox | 061-KY-0011 -000 | 18.293 | 22.694 | 4.401 | Modernize Roadway-Rural | 26 |  | 0 |  | 2500000 |  | 5500000 |  | 4500000 |  | 22000000 |  | 2017-05-18 10:03 | This project from just North of Girdler to Mills Cemetery is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County). Operational efficiency along the corridor is diminished as a result of narrow roadway widths | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 33.9301 | 2.5498 | 6.3981 | 7.1623 | 3.0332 | 5.2133 | 0 | 9.5735 | 34
Y | 11 | Cumberland Valley ADD | IP20080610 |  |  |  | Correct flooding issues on KY 11 from KY 92 in Whitley County to Poplar Street in the city of Barbourville. | Safety-Haz-Elm | Knox | 061-KY-0011 -000 | 0 | 9.088 | 9.088 | Maintenance Improvement | 10 |  | 0 |  | 312000 |  | 312000 |  | 312000 |  | 1144000 |  | 2010-02-25 16:51 | The purpose of this project is to raise sections of KY 11 out of high water from KY 92 in Whitley County to Poplar Street in Barbourville. Standing water exists at several locations throughout the 11.7 mile segment during periods of heavy rain. | The following needs have been identified for this project: 1) Improve Roadway Safety
Y | 11 | Cumberland Valley ADD | IP20080611 |  |  |  | Address access and safety issues at the intersection of KY 225 and KY 2421 | Reconstruction | Knox | 061-KY-0225 -000 | 14.642 | 14.892 | 0.25 | Improve Intersection | 26 |  | 0 |  | 156000 |  | 312000 |  | 312000 |  | 416000 |  | 2010-02-25 16:51 | The purpose of this project is to address access and safety on KY 225 at its intersection with KY 2421 in Barbourville. The project area is primarily commercial and provides access to downtown Barbourville and US 25E for individuals residing in the sout | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080613 |  |  |  | Address access and capacity issues on KY 80 from KY 192 to KY 1561 | Minor Widening | Laurel | 063-KY-0080 -000 | 13.278 | 15.21 | 1.932 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 1000000 |  | 1500000 |  | 3500000 |  | 2010-02-25 16:51 | The purpose of this project is to address capacity, access, and safety issues on KY 80 from KY 192 at London to KY 1561. While the Hal Rogers Parkway carries the bulk of the east-west traffic, local traffic relies on KY 80 to provide access to residentia | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080614 |  |  |  | Address access and safety issues along KY-229 from Levi Jackson State Park Entrance to Conley Road. | Reconstruction | Laurel | 063-KY-0229 -000 | 8.837 | 9.85 | 1.013 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1200000 |  | 1000000 |  | 7000000 |  | 2017-05-18 09:39 | The purpose of this project is to address access and safety issues along KY-229 from Levi Jackson State Park Entrance to Conley Road. This project from Levi Jackson State Park entrance to KY 192 (London Bypass) was identified in the 2001 London-Laurel Co | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 25.9633 | 7.3555 | 4.9763 | 4.4609 | 2.7725 | 0 | 0 | 6.3981 | 26
Y | 11 | Cumberland Valley ADD | IP20080615 |  |  |  | Address access and safety issues along KY 229 from Conley Road to KY 192. | Reconstruction | Laurel | 063-KY-0229 -000 | 9.85 | 11.522 | 1.672 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3000000 |  | 2500000 |  | 11000000 |  | 2010-02-25 16:51 | The purpose of this project is to address access and safety issues along KY 229 from Conley Road to KY 192. This project from Levi Jackson State Park entrance to KY 192 (London Bypass) was identified in the 2001 London- Laurel County Transportation Stud | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080616 |  |  |  | Address horizontal alignment issues on KY 363 from KY 3429 (Philpot Road) to the roundabout at KY 1006 with a study on adding an on/off ramp to I-75 from KY 363. | Reconstruction | Laurel | 063-KY-0363 -000 | 8.2 | 9.205 | 1.005 | Modernize Roadway-Rural | 26 |  | 250000 |  | 600000 |  | 1500000 |  | 1000000 |  | 3000000 |  | 2017-05-18 11:42 | The purpose of this project is to address horizontal alignment issues on KY 363 from KY 3429 (Philpot Road) to the roundabout at KY 1006 with a study on adding an on/off ramp to I-75 from KY 363. This project from KY 3429 (Philpot Road) to KY 1006 was id | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 37.3649 | 9.1659 | 5.7583 | 5.7583 | 4.1706 | 7.2038 | 0 | 5.3081 | 37
Y | 11 | Cumberland Valley ADD | IP20080617 |  |  |  | Address horizontal alignment, access, capacity, and safety issues on KY 1006 from KY 192 to US 25 (Main Street) in London. Project was listed in 2001 Laurel County Transportation Study. | Reconstruction | Laurel | 063-KY-1006 -000 | 5.364 | 6.899 | 1.535 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1500000 |  | 600000 |  | 2500000 |  | 2015-07-06 10:17 | The purpose of this project is to address horizontal alignment, access, capacity, and safety issues on KY 1006 from KY 192 to US 25 (Main Street) in London. This project was identified in the 2001 London-Laurel County Transportation Study to address hori | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Kentucky River ADD | IP20080618 |  |  |  | Correct poor pavement, substandard curves, and inadequate lanes and shoulders in order to improve connectibility, mobility, and safety on US 421 from Trace Branch/Warbranch Road to Mozelle. | Relocation | Leslie | 066-US-0421 -000 | 4.588 | 7.195 | 2.607 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 3500000 |  | 2600000 |  | 22600000 |  | 2017-05-18 11:56 | Correct poor pavement, substandard curves, and inadequate lanes and shoulders in order to improve connectibility, mobility, and safety on US 421 from Trace Branch/Warbranch Road to Mozelle. | This 5.700 segment of US 421 has numerous horizontal curves that wind throughout Leslie County. US 421 is the primary means of transportation linkage for the citizens of Leslie and Harlan Counties to access other Primary arterials. This segment is just | KENTUCKY RIVER ADD | South | 54.7701 | 2.1991 | 3.91 | 3.0213 | 4.9052 | 0 | 2.5829 | 8.1517 | 25 | 15 | 15
Y | 11 | Kentucky River ADD | IP20080619 |  |  |  | Relocate from South of Hoskinston to near the Leslie High and Middle Schools. Eliminate inadequate curvature design for current traffic conditions and address a major slope failure site at Stinnett Mountain near mp 15.7. | Relocation | Leslie | 066-US-0421 -000 | 13.6 | 20 | 6.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 2700000 |  | 6800000 |  | 1400000 |  | 78000000 |  | 2015-07-06 11:13 |  | This 6.4 mile segment of US 421 has numerous horizontal and vertical curves that wind throughout Leslie County. There are several slips and slides locations causing unsafe shoulder widths. Narrow lanes for the curve design, heavy trucks and congestion a
Y | 11 | Kentucky River ADD | IP20080620 |  |  |  | NEW ACCESS ROAD TO BUCKHORN STATE PARK FROM HYDEN TO CONFLUENCE | New Route | Leslie | 066-KY-0257 -000 | 0 | 10.985 | 10.985 | Construct Road in New Location | 0 |  | 0 |  | 1000000 |  | 5500000 |  | 2750000 |  | 38500000 |  | 2010-02-25 16:51 |  | This segment is a proposed new access road to Buckhorn State Resort Park from downtown Hyden to Confluence.
Y | 11 | Cumberland Valley ADD | IP20080621 |  |  |  | Address horizontal alignment and safety issues on KY 92 from US 25W in Williamsburg to US 25E at Four Mile in Bell County | Transportation Study | Whitley | 118-KY-0092 -000 | 11.341 | 32.998 | 21.657 | Modernize Roadway-Rural | 26 |  | 2000000 | 2020 | 16000000 | 2022 | 33000000 | 2025 | 33000000 | 2025 | 116000000 | 2027 | 2019-03-13 09:20 | The purpose of this project is to address horizontal alignment and safety issues on KY 92 from US 25W in Williamsburg to US 25E in Four Mile at Bell County. The project area has narrow lanes and numerous sharp curves, which result in a horizontal alignme | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080622 |  |  |  | Address access and safety issues on KY 312 from the Laurel/Whitley County Line to North Main Street (US 25W north) in downtown Corbin | Reconstruction | Whitley | 118-KY-0312 -000 | 0 | 2.542 | 2.542 | Modernize Roadway-Rural | 26 |  | 0 |  | 1300000 |  | 3000000 |  | 3000000 |  | 11700000 |  | 2010-02-25 16:51 | The purpose of this project is to improve KY 312 from the Laurel/Whitley county line to Kentucky Avenue in downtown Corbin in order to address access and safety issues. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080623 |  |  |  | Address safety and surface condition issues on KY 727 (West 5th Street) from Poplar Street to West 4th Street in Corbin. | Reconstruction | Whitley | 118-KY-0727 -000 | 3.7 | 4.48 | 0.78 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 700000 |  | 700000 |  | 4500000 |  | 2017-05-18 11:52 | The purpose of this project is to address safety and surface condition on KY 727 (also known as West 4th Street) from Poplar Street to West 5th street in Corbin. This section of KY 727 is a one-way street in downtown Corbin that provides access to sever | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 34.3969 | 8.9289 | 7.4645 | 7.1979 | 0.85308 | 5.782 | 0 | 4.1706 | 34
Y | 11 | Cumberland Valley ADD | IP20080624 |  |  |  | Address safety issue on KY 779 0.5 miles east of KY 26 | Reconstruction | Whitley | 118-KY-0779 -000 | 0.25 | 0.75 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 75000 |  | 300000 |  | 50000 |  | 500000 |  | 2013-07-31 16:15 | The purpose of this project is to address safety issues on KY 779 from 0.5 miles East of KY 26. This section of KY 779 has been identified by local officials as a safety issue due to the existence of a sharp curve, narrow lanes, and inadequate shoulders. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20080625 |  |  |  | Address safety issue on KY 779 at its intersection with Maple Creek Road | Safety-Haz-Elm | Whitley | 118-KY-0779 -000 | 3.826 | 4.326 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 60000 |  | 60000 |  | 60000 |  | 350000 |  | 2010-02-25 16:51 | The purpose of this project is to address a safety issue at and near the intersection of KY 779 and Maple Creek Road. This section of KY 779 has been identified by local officials as a safety issue due to the existence of a sharp curve at the intersection | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20080626 |  |  |  | Address flooding and safety issues on KY 1804 from Cane Creek bridge to Clear Fork bridge | Reconstruction | Whitley | 118-KY-1804 -000 | 3.044 | 5.341 | 2.297 | Maintenance Improvement | 10 |  | 0 |  | 315000 |  | 210000 |  | 105000 |  | 945000 |  | 2013-07-31 16:16 | The purpose of this project is to raise sections of KY 1804 out of high water from Cane Creek bridge to Clear Fork Bridge. Standing water exists at several locations during wet weather periods and is a safety issue. Access by emergency vehicles is a str | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20110173 |  |  |  | Address congestion/capacity issues on US-119 near Clear Glass Road and Conley Loop. | Minor Widening | Harlan | 048-US-0119 -000 | 10.66 | 10.79 | 0.13 | Modernize Roadway-Rural | 26 | Y | 0 |  | 75000 |  | 15000 |  | 35000 |  | 900000 |  | 2011-11-17 22:21 | The purpose of this project is to address congestion/capacity issues on US-119 near Clear Glass Road and Conley Loop. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion This project is part of an overall plan to improve and expand the capacity of US 11
Y | 11 | Cumberland Valley ADD | IP20110181 |  |  |  | Address congestion/capacity issues on US 119 from Billy Lee Road to Tremont Drive | Minor Widening | Harlan | 048-US-0119 -000 | 6.5 | 7.5 | 1 | Modernize Roadway-Rural | 26 | Y | 0 |  | 150000 |  | 75000 |  | 100000 |  | 1570000 |  | 2011-11-17 22:28 | The purpose of this project is to address congestion/capacity issues on US 119 from Billy Lee Road to Tremont Drive. This project is part of an overall plan to improve and expand the capacity of US 119 from US 25E in Pineville to US 421 in Harlan. Expande | The following needs have been identified for this project: 1) Improve Roadway Safety 2) Improve Access 3) Increase Capacity 4) Improve Mobility 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20110198 |  |  |  | Improve approach of US 119 from KY 1084 to US 421 through a new intersection and new alignment for US 119. Project #H-6 in US-119 Corridor Study | Reconstruction | Harlan | 048-US-0119 -000 | 12.435 | 13.213 | 0.778 | Modernize Roadway-Rural | 26 | Y | 0 |  | 900000 |  | 550000 |  | 250000 |  | 18300000 |  | 2011-11-17 22:39 | The purpose of this project is to improve the approach of US 119 from KY 1084 to US 421 through a new intersection and new alignment for US 119. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Kentucky River ADD | IP20110205 |  |  |  | Reconstruct US 421 from the Leslie/Harlan County Line to MP 2.00. | Reconstruction | Leslie | 066-US-0421 -000 | 0 | 2 | 2 | Modernize Roadway-Rural | 26 |  | 0 |  | 1400000 |  | 2310000 |  | 490000 |  | 47390000 |  | 2017-05-18 11:54 | Reconstruct US 421 from the Leslie/Harlan County Line to MP 2.00. | US 421 has numerous horizontal and vertical curves that wind throughout Leslie County. There are several slips and slides locations causing unsafe shoulder widths. Narrow lanes for the curve design, heavy trucks and congestion are common. US 421 is the | KENTUCKY RIVER ADD | South | 26.7476 | 1.8483 | 4.1232 | 3.9988 | 3.5071 | 4.7867 | 2.6066 | 5.8768 | 27
Y | 11 | Kentucky River ADD | IP20110206 |  |  |  | Reconstruct US 421 from Rockhouse to the Leslie/Clay County Line. | Reconstruction | Leslie | 066-US-0421 -000 | 26 | 35.3 | 9.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 4712000 |  | 5728500 |  | 2831000 |  | 50360000 |  | 2012-06-29 13:21 |  | US 421 has numerous horizontal and vertical curves that wind throughout Leslie County. There are several slips and slides locations causing unsafe shoulder widths. Narrow lanes for the curve design, heavy trucks and congestion are common. US 421 is the
Y | 11 | Cumberland Valley ADD | IP20110220 |  |  |  | Address horizontal/vertical alignment and safety issues on KY 80 from KY 1803 (near Bush) to Laurel County/Clay County line. | Reconstruction | Laurel | 063-KY-0080 -000 | 21.442 | 23.843 | 2.401 | Modernize Roadway-Rural | 26 |  | 0 |  | 308000 |  | 262500 |  | 262500 |  | 8000000 |  | 2013-05-21 10:19 | Address horizontal/vertical alignment and safety issues on KY 80 from KY 1803 (near Bush) to Laurel County/Clay County line. There are several curves along this section of KY-80 and horizontal alignment is an issue. Safety and congestion are also issues f | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20110221 |  |  |  | Spot improvements to address flooding and safety issues along KY 11 from the Whitley County/Knox County Line to KY 1809. | Spot Improvement | Knox | 061-KY-0011 -000 | 0 | 3.272 | 3.272 | Maintenance Improvement | 10 |  | 0 |  | 132000 |  | 165000 |  | 165000 |  | 4290000 |  | 2013-05-21 10:01 | The purpose of this project is to raise sections of KY 11 out of high water from the Whitley- Knox County Line to KY 1809. Standing water exists at several locations during periods of heavy rain and is a safety issue. An extremely high IRI range illustra | The following needs have been identified for this project: 1) Improve Roadway Safety
Y | 11 | Cumberland Valley ADD | IP20110222 |  |  |  | Spot Improvements to address flooding and safety issues along KY 11 from KY 1809 to Tye Bend Road. | Spot Improvement | Knox | 061-KY-0011 -000 | 3.272 | 7.194 | 3.922 | Maintenance Improvement | 10 |  | 0 |  | 160000 |  | 200000 |  | 200000 |  | 5200000 |  | 2013-05-21 10:07 | The purpose of this project is to raise sections of KY 11 out of high water from KY 1809 to Tye Bend Road. Standing water exists at several locations during periods of heavy rain and is a safety issue. An extremely high IRI range illustrates that the sur | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20110223 |  |  |  | Spot improvements to address flooding and safety issues along KY 11 from Tye Bend Road to South Main Street. | Spot Improvement | Knox | 061-KY-0011 -000 | 7.194 | 9.809 | 2.615 | Maintenance Improvement | 10 |  | 0 |  | 80000 |  | 50000 |  | 50000 |  | 2600000 |  | 2013-05-21 09:52 | The purpose of this project is to raise sections of KY 11 out of high water from Tye Bend Road to South Main Street. Standing water exists at several locations during periods of heavy rain and is a safety issue. An extremely high IRI range illustrates tha | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20110226 |  |  |  | Reconstruct KY 472 from mile point 2.7 and create a connection with the Hal Rogers Parkway at KY 192 to improve congestion and safety near North Laurel Middle School. | Reconstruction | Laurel | 063-KY-0472 -000 | 0 | 2.7 | 2.7 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 1900000 |  | 890000 |  | 5800000 |  | 2012-02-21 10:45 | The purpose of this project is to improve congestion and safety by reconstructing KY 472 and create a connection with the Hal Rogers Parkway with KY 192. This section of KY 472 intersects with Old Kentucky 472 road. It is less than 3 miles north from Ha | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20110227 |  |  |  | Improve existing geometrics, access management, and improve safety of the approach to the US-421/KY-80 Intersection. | Safety-Haz-Elm | Clay | 026-KY-2076 -000 | 0 | 0.5 | 0.5 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 930000 |  | 100000 |  | 3500000 |  | 2017-05-18 11:12 | The purpose of this project is to provide access management for nearby shopping center, eating establishments, and other businesses. | This segment of KY-2076 intersects with US-421. Access management is needed as there are multiple entrances from nearby shopping center, as well as McDonalds fast food establishment. Currently, there are only two lanes to turn onto US 421 - a left turn | 11 | South | 22.5889 | 3.7915 | 10.4502 | 6.1671 | 2.1801 | 0 | 0 | 0 | 23
Y | 11 | Cumberland Valley ADD | IP20110228 |  |  |  | Minor widening - improve geometrics and safety and provide for left and right turn lanes for Manchester Memorial Hospital entrance. | Minor Widening | Clay | 026-KY-3472 -000 | 0.2 | 0.6 | 0.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 500000 |  | 250000 |  | 750000 |  | 2012-02-27 15:11 | The purpose of this project is to improve geometrics and safety for the Manchester Memorial Hospital entrance. | The intersection of KY-3479 and KY-3472 leads to the entrance of Manchester Memorial Hospital, a church, and several medical clinics. KY-3479 is a two lane road. With a CRF rating of 1.12, this indicates that there may be a crash problem. An IRI rating
Y | 11 | Cumberland Valley ADD | IP20110229 |  |  |  | Reconstruct the KY-1193/KY-3497 intersection to improve approach geometry and increase safety | Reconstruction | Laurel | 063-KY-1193 -000 | 2.75 | 3 | 0.25 | Modernize Roadway-Rural | 26 |  | 0 |  | 30000 |  | 250000 |  | 100000 |  | 500000 |  | 2012-02-27 15:14 | The purpose of this project is to improve the intersection of KY 1193 and KY 3947 in Keavy. Both 1193 and 3947 are two lane roads used frequently by those accessing Holly Bay Marina and Laurel Lake. An IRI of 245.31 indicates that the road is considered | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20130059 |  |  |  | Curb & Gutter Drainage Project for Winchester Avenue from 20th Street to 40th Street in Middlesboro | Drainage Improvement | Bell | 007-KY-2079 -000 | 0 | 1.698 | 1.698 | Maintenance Improvement | 10 |  | 0 |  | 200000 |  | 500000 |  | 50000 |  | 2000000 |  | 2013-05-30 09:29 | The purpose of this project is to address the flooding and congestion concerns on KY-2079 in the city of Middlesboro. | The project area would be a curb & gutter drainage project for Winchester Avenue from 20th Street to 40th Street. The project area is primarily residential with mixed businesses throughout the route. WIth a CRF over 1.0, there is indication of a crash p
Y | 11 | Cumberland Valley ADD | IP20130060 |  |  |  | Address congestion issues on US 119 from the US 119/KY 3452 intersection and US 119/KY 1084 intersection. | Congestion Management | Harlan | 048-US-0119 -000 | 11.479 | 12.435 | 0.956 | Improve Intersection | 26 | Y | 0 |  | 35000 |  | 25000 |  | 25000 |  | 650000 |  | 2013-05-30 09:39 | The purpose of this project is to address congestion issues on US 119 from the US 119/KY 3452 intersection and US 119/KY 1084 intersection. The project area is primarily farmland with scattered residences. Turning lanes are needed to improve through traf | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20130061 |  |  |  | Address congestion and safety issues on US 421 near its intersection with KY 587 by Jackson County Board of Education and Middle School. | Congestion Management | Jackson | 055-US-0421 -000 | 10.5 | 11.1 | 0.6 | Improve Intersection | 26 |  | 0 |  | 375000 |  | 150000 |  | 100000 |  | 650000 |  | 2017-05-18 09:26 | The purpose of this project is to address congestion and safety issues on US 421 with its intersection at KY 587. The Jackson County Board of Education and Jackson County Middle School are located at this intersection. There is a sharp curve within the i | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 26.1576 | 4.1611 | 6.0427 | 3.1813 | 5 | 0 | 3.0806 | 4.6919 | 26
Y | 11 | Cumberland Valley ADD | IP20130063 |  |  |  | Address realignment, safety, and congestion of Meyers-Baker Road from KY 1006 (5th Street) to KY 363 (Whitley Street). Address horizontal alignment and sight-distance issues of the intersection of Meyers-Baker Road with KY 363. | Reconstruction | Laurel | 063-CS-1156 -000 | 0 | 0.636 | 0.636 | Modernize Roadway-Rural | 26 |  | 0 |  | 75000 |  | 350000 |  | 250000 |  | 1800000 |  | 2017-05-18 11:58 | The purpose of this project is to address realignment, safety, and congestion of Meyers-Baker Road from KY 1006 (5th Street) to KY 363 (Whitley Street). Address horizontal alignment and sight-distance issues of the intersection of Meyers-Baker Road with | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 22.6576 | 8.1611 | 5.6872 | 5.1363 | 3.673 | 0 | 0 | 0 | 23
Y | 11 | Cumberland Valley ADD | IP20130064 |  |  |  | Address safety concerns at the intersection of KY 727 and KY 1259 in Scuffletown | Safety-Haz-Elm | Whitley | 118-KY-0727 -000 | 2.4 | 2.5 | 0.1 | Improve Intersection | 26 |  | 0 |  | 75000 |  | 75000 |  | 75000 |  | 400000 |  | 2017-05-18 11:51 | The purpose of this project is to address safety concerns at the intersection of KY 727 and KY 1259 in Scuffletown. The horizontal alignment and sight distance makes it hard to turn onto KY-727. With a CRF of 1.9860, it indicates that there is a crash pr | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 21.7488 | 6.2275 | 6.1137 | 3.4834 | 2.2275 | 0 | 0 | 3.6967 | 22
Y | 11 | Cumberland Valley ADD | IP20130072 |  |  |  | Construct left and right turn lanes onto the Bell County Garage/Veteran's Park Entrance Six Year Plan Project 2014 11-8805.00 | Spot Improvement | Bell | 007-US-0119 -000 | 4.01 | 4.28 | 0.27 | Improve Intersection | 26 | Y | 0 |  | 100000 |  | 25000 |  | 50000 |  | 1100000 |  | 2013-07-24 14:52 | The purpose of this project is to address the safety issues on US-119 between Pineville and Harlan. The project area is primarily farmland with scattered residences. Turning lanes going into the Bell County Transportation Cabinet Garage and Veteran's Pa | The following needs have been identified for this project: 1) improve roadway safety, 2) improve mobility and capacity and reduce congestion.
Y | 11 | Cumberland Valley ADD | IP20130073 |  |  |  | Address access issues along US-119 onto KY 1334 and KY 1534 | Congestion Management | Bell | 007-US-0119 -000 | 4.98 | 5.25 | 0.27 | Improve Intersection | 26 | Y | 0 |  | 125000 |  | 25000 |  | 75000 |  | 1300000 |  | 2013-07-24 15:22 | The purpose of this project is to address the safety issues on US-119 between Pineville and Harlan. | Turning lanes are needed to improve through traffic flow. The road is frequently used by tractor trailers as well as regular automotives.
Y | 11 | Cumberland Valley ADD | IP20130074 |  |  |  | Scoping Study - minor reconstruction to improve safety and enhance access on KY 2430 | Reconstruction | Harlan | 048-KY-2430 -000 | 0 | 1 | 1 | Transportation Studies | 0 |  | 0 |  | 100000 |  | 0 |  | 0 |  | 0 |  | 2013-07-24 15:29 | The purpose of this project is to improve safety and enhance access through minor reconstruction of KY 2430 in Harlan County. | The following needs have been identified for this project: 1) Improve Roadway Safety 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20130075 |  |  |  | Address congestion issues on US 119 near its intersection with KY 840 | Congestion Management | Harlan | 048-US-0119 -000 | 7.74 | 8.05 | 0.31 | Modernize Roadway-Rural | 26 | Y | 0 |  | 100000 |  | 25000 |  | 75000 |  | 1300000 |  | 2017-05-18 11:44 | The purpose of this project is to address congestion issues on US 119 near its intersection with KY 840. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, and 4) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 30.7263 | 4.4171 | 13.2227 | 5.8827 | 0 | 0 | 3.4123 | 3.7915 | 31
Y | 11 | Cumberland Valley ADD | IP20130076 |  |  |  | Address congestion issues from US 119 onto KY 3152 | Congestion Management | Harlan | 048-US-0119 -000 | 8.48 | 8.75 | 0.27 | Modernize Roadway-Rural | 26 | Y | 0 |  | 100000 |  | 25000 |  | 50000 |  | 1100000 |  | 2013-07-24 15:53 | The purpose of this project is to address the safety issues on US-119 between Pineville and Harlan. The project area is primarily farmland with scattered residences. Turning lanes are needed to improve through traffic flow. The road is frequently used | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, and 4) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20130077 |  |  |  | Flood mitigation on KY 11 from north of KY 3438 to north of C Mills Rd (CR 1090) | Drainage Improvement | Knox | 061-KY-0011 -000 | 14 | 15 | 1 | Modernize Roadway-Rural | 26 |  | 0 |  | 40000 |  | 25000 |  | 25000 |  | 1200000 |  | 2015-07-06 11:11 | The purpose of the project is for flood mitigation on KY 11 in this area. With an adequacy rating of 65.50 and CRF higher than 1.0, there is indication of a crash problem. The IRI over 130 indicates that the road is very rough, as well as a high average | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20130078 |  |  |  | Improve safety and address geometric deficiencies, as well as flood mitigation on KY 1487 from north of Minton Rd (CS-1044) in Barbourville to near US 25E. | Reconstruction | Knox | 061-KY-1487 -000 | 0.687 | 1.107 | 0.42 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 300000 |  | 750000 |  | 5200000 |  | 2017-05-18 11:17 | The purpose of this project is to help alleviate the flooding issues on KY 1487. There are currently two one lane tunnels that are along this route with an average daily traffic count of 3022. This route provides access to downtown Barbourville and to U | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | CUMBERLAND VALLEY ADD | South | 27.8436 | 5.5924 | 4.3365 | 3.91 | 3.5308 | 6.4455 | 0 | 4.0284 | 28
Y | 11 | Cumberland Valley ADD | IP20130079 |  |  |  | Reconstruction of US 25W from Town Hill to Cordell Rd to improve safety and address geometric deficiencies. | Reconstruction | Whitley | 118-US-0025W -000 | 13.335 | 14.635 | 1.3 | Construct Road in New Location | 0 |  | 0 |  | 850000 | 2020 | 950000 | 2020 | 700000 | 2020 | 6000000 | 2022 | 2019-03-11 14:47 | The purpose of this project is to address horizontal alignment and safety issues on US-25W from Town Hill to Cordell Road in Williamsburg. The project area is primarily residential and businesses with the University of the Cumberlands nearby. Operationa | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150019 |  |  |  | Address congestion and access concerns at the entrance into Jackson County High School on US-421 with its intersection with Educational Mountain Drive and McCammon Ridge Rd. | Congestion Management | Jackson | 055-US-0421 -000 | 13.69 | 13.7 | 0.01 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 30000 |  | 150000 |  | 630000 |  | 2017-05-18 09:21 | The purpose of this project is to address congestion and access concerns at the entrance into Jackson County High School on US-421 with its intersection with Educational Mountain Drive and McCammon Ridge Rd. There has been recent develop of the high scho | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 21.7725 | 5.327 | 3.981 | 3.2701 | 2.4882 | 0 | 3.436 | 3.2701 | 22
Y | 11 | Cumberland Valley ADD | IP20150020 |  |  |  | Address safety and horizontal alignment of the curve on US-421 with its intersection at KY-3443 | Safety-Haz-Elm | Jackson | 055-US-0421 -000 | 1.5 | 1.8 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 50000 |  | 450000 |  | 1380000 |  | 2017-05-18 09:19 | The purpose of this project is to address safety and horizontal alignment of the curve on US 421 with its intersection at KY 3443. This project is part of an effort to improve a primary regional access corridor for Jackson County that will support econom | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | CUMBERLAND VALLEY ADD | South | 21.0592 | 1.9716 | 4.6919 | 3.519 | 4.2654 | 0 | 2.6777 | 3.9336 | 21
Y | 11 | Cumberland Valley ADD | IP20150021 |  |  |  | Address safety concerns and horizontal alignment with curve 1/4 mile south of intersection of KY-6 | Safety-Haz-Elm | Whitley | 118-KY-1064 -000 | 16.4 | 16.6 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 60000 |  | 200000 |  | 290000 |  | 2015-03-26 14:05 | The purpose of this project is to address safety concerns and horizontal alignment with curve 1/4 mile south of intersection of KY-6. According to elected officials, this curve has had multiple wrecks with serious injuries over the years. With an IRI of | The following needs have been identified for this project: 1) Improve Roadway Safety
Y | 11 | Cumberland Valley ADD | IP20150022 |  |  |  | Address safety concerns and horizontal alignment with curve just passed Brush Arbor Road, as well as adding sidewalks to roadway | Reconstruction | Whitley | 118-KY-0296 -000 | 0 | 0.824 | 0.824 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 100000 |  | 250000 |  | 950000 |  | 2017-05-18 11:40 | The purpose of this project is reconstruction of curve on KY 296 to address vertical alignment and safety issues. Furthermore, sidewalks need to be constructed to connect to KY 92 to provide safe and reliable access for those living near Brush Arbor Road | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility | CUMBERLAND VALLEY ADD | South | 33.5746 | 2.7393 | 13.6493 | 7.3045 | 3.8626 | 0 | 0 | 6.019 | 34
Y | 11 | Cumberland Valley ADD | IP20150024 |  |  |  | Address access and safety concerns on 20th Street near Corbin High School in Corbin. | Minor Widening | Whitley | 118-CS-2010 -000 | 0 | 0.498 | 0.498 | Local Roadway Improvements | 3 |  | 0 |  | 250000 |  | 60000 |  | 60000 |  | 120000 |  | 2017-05-18 11:26 | The purpose of this project is to address access and safety concerns on 20th Street near Corbin High School in Corbin. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 5.9656 | 0.23697 | 0 | 2.7903 | 2.9384 | 0 | 0 | 0 | 6
Y | 11 | Cumberland Valley ADD | IP20150025 |  |  |  | Minor widening of Corbin Bypass (KY-3041) | Minor Widening | Whitley | 118-KY-3041 -000 | 0 | 1.79 | 1.79 | Modernize Roadway-Rural | 26 | Y | 0 |  | 1000000 |  | 100000 |  | 500000 |  | 9000000 |  | 2015-03-26 14:03 | The purpose of this project is to provide minor widening of Corbin Bypass (KY-3041) | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150062 |  |  |  | Address access, safety, and surface condition on KY 3431 from US 25E to Tyler Trail | Transportation Study | Laurel | 063-KY-3431 -000 | 0.65 | 1.581 | 0.931 | Transportation Studies | 0 |  | 750000 | 2019 | 500000 |  | 700000 |  | 950000 |  | 2200000 |  | 2019-03-15 08:17 | The purpose of this project is to address access, safety, and surface condition on KY 3431 from US 25E to Tyler Trail. This section of KY 3431 provides direct access to several commercial entities, low income residences, and industrial building. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150063 |  |  |  | Address access, safety, sidewalk improvements on KY 1223 from KY 3431 (American Greeting Card Road) to North Stewart Road | Minor Widening | Laurel | 063-KY-1223 -000 | 1.139 | 1.666 | 0.527 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 300000 |  | 500000 |  | 1100000 |  | 2015-03-13 12:56 | The purpose of this project is to address access, safety, and sidewalk improvements on KY 1223 from KY-3431 to Appaloosa Trail Road. This section of KY-1223 provides direct access to several commercial entities, and low income residences. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150066 |  |  |  | Address congestion, safety, and access management of 2nd Street (CS-1132) in Williamsburg. | Reconstruction | Whitley | 118-CS-1132 -000 | 0 | 1.317 | 1.317 | Local Roadway Improvements | 3 |  | 0 |  | 1000000 |  | 1700000 |  | 2000000 |  | 3411000 |  | 2015-03-26 14:14 | The purpose of this project is to address congestion, safety, and access management on 2nd Street in Williamsburg. Cumberland College has built new sport facilities along this route. Tractor Trailers use this route for delivery of goods to businesses. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150097 |  |  |  | Address congestion on Add Hollow Road onto US 421 by redirecting onto KY 80. | New Route | Clay | 026-US-0421 -000 | 15.5 | 17 | 1.5 | Construct Road in New Location | 0 |  | 0 |  | 500000 |  | 200000 |  | 150000 |  | 1514408 |  | 2017-05-18 14:11 | This project is to provide easier access to coal tipple, health department, correctional facility, and county extension office. | The following needs have been identified for this project: 1) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 29.9882 | 8.5782 | 0 | 10.9123 | 1.2085 | 9.2891 | 0 | 0 | 30
Y | 11 | Cumberland Valley ADD | IP20150098 |  |  |  | Address safety issues with vertical & horizontal alignment on US-421 from milepoint 11.600, east of Pilgrims Rest Rd (CR-1007), to 12.600, west of Ranger Station Rd (FD-289). | Reconstruction | Jackson | 055-US-0421 -000 | 11.6 | 12.6 | 1 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 650000 |  | 550000 |  | 3300000 |  | 2015-03-26 13:47 | The purpose of this project is to address safety issues with vertical & horizontal alignment on US 421. This project is part of an effort to improve a primary regional access corridor for Jackson County that will support economic development in this low-i | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 39.4526 | 4.3223 | 10.3081 | 4.9408 | 4.9763 | 6.7299 | 3.0569 | 5.1185 | 40
Y | 11 | Cumberland Valley ADD | IP20150101 |  |  |  | Address intersection approach grade of KY 578 onto KY 290 | Safety-Haz-Elm | Jackson | 055-KY-0578 -000 | 7 | 7.202 | 0.202 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 25000 |  | 125000 |  | 1275000 |  | 2015-03-26 13:50 | The purpose of this project is to address intersection approach grade of KY 578 onto KY 290. The approach of KY 578 into this intersection is very steep and has had several accidents within close proximity. The plan is to reduce the grade into the inte | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150107 |  |  |  | Address safety issues with vertical curve alignment at the intersection of US-25W with Hightop Road | Safety-Haz-Elm | Whitley | 118-US-0025W -000 | 27.2 | 27.4 | 0.2 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 890000 |  | 250000 |  | 500000 |  | 2015-03-26 13:55 | The purose of this project is to address the steep vertical curve alignment on US-25W near Hightop Road. The current alignment makes it hard for travelers leaving Hightop Road to be able to see oncoming traffic, as well as making those traveling on US-25 | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20150108 |  |  |  | Address safety issues with vertical curve alignment at the intersection of US-25W with Angel Road | Safety-Haz-Elm | Whitley | 118-US-0025W -000 | 19.65 | 19.85 | 0.2 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 1100000 |  | 250000 |  | 1000000 |  | 2015-03-26 13:53 | This project is to address the steep vertical curve alignment on US-25W near Angel Road. The current alignment makes it hard for travelers leaving Angel Road to be able to see oncoming traffic, as well as making those traveling on US-25W make quick stop | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20150109 |  |  |  | Improve safety and address geometric deficiencies of intersection of US 25E and KY 2420. | Minor Widening | Knox | 061-US-0025E -010 | 10.83 | 11.034 | 0.204 | Improve Intersection | 26 | Y | 0 |  | 300000 |  | 700000 |  | 100000 |  | 135000 |  | 2015-03-26 14:27 | The purpose of this project is to improve safety and address geometric deficiencies of intersection of US-25E and KY-2420. This is a congested area with a V/SF over .80. It is a major traffic route along US-25E that connects Barbourville to Pineville/Mi | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150112 |  |  |  | Improve safety, address geometric deficiencies, reduce congestion and improve mobility on KY 727 from US 25W to KY 3421. | Reconstruction | Whitley | 118-KY-0727 -000 | 0 | 1.539 | 1.539 | Modernize Roadway-Rural | 26 |  | 0 |  | 700000 |  | 1130000 |  | 1550000 |  | 1900000 |  | 2015-06-25 13:09 | The purpose of this project is to improve safety, address geometric deficiencies, reduce congestion and improve mobility on KY 727 from US 25W to KY 3421. This project will improve the safety, reduce congestion, and improve mobility through subdivisions | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150115 |  |  |  | Improve safety, address geometric deficiencies, reduce congestion and improve mobility on KY 1487 from US 25E to downtown Barbourville, Knox Central Middle School, Barbourville City Schools and Union College. | Minor Widening | Knox | 061-KY-1487 -000 | 0.369 | 0.687 | 0.318 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 592500 |  | 255000 |  | 1035375 |  | 2018-11-28 10:09 | Improve safety, address geometric deficiencies, reduce congestion and improve mobility on KY 1487 from US 25E to downtown Barbourville, Knox Central Middle School, Barbourville City Schools and Union College. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20150194 | 11-8861 |  | A | IMPROVE SAFETY AND SIGHT DISTANCE ALONG KY 638 (MP 6.7 TO MP 7.1) AND ITS INTERSECTION WITH KY 3476. (14CCN)(18CCN) | SAFETY(P) | Clay | 026-KY-0638 -000 | 6.7 | 7.1 | 0.4 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2020 | 0 | 2020 | 2000000 | 2021 | 2019-03-08 14:38 | The purpose of this project is to improve safety and sight distance along KY 638. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | 11 | South | 21.3495 | 2.1137 | 11.5166 | 3.2879 | 4.4313 | 0 | 0 | 0 | 21
Y | 11 | Kentucky River ADD | IP20150234 | 11-8516 |  | A | CONSTRUCT A NEW APPROACH FROM KY-1482 ONTO THE HAL ROGERS PARKWAY AT MP 39. (08CCN)(10CCR)(2011BOPP)(18CCN) | NEW ROUTE(O) | Leslie | 066-KY-1482 -000 | 0.09 | 0.19 | 0.1 | Construct Road in New Location | 0 |  |  |  | 260000 | 2021 | 1020000 | 2022 | 460000 | 2022 | 6860000 | 2023 | 2019-03-08 08:15 |  |  | 11 | South | 7.9858 | 0.52133 | 0 | 0 | 3.1043 | 4.3602 | 0 | 0 | 8
Y | 11 | Cumberland Valley ADD | IP20150251 | 11-186 / 11-186.01 |  | A | IMPROVE FREIGHT MOBILITY AND REDUCE CONGESTION ON US-25W FROM KY-727 TO KY-3041. (12CCR)(16CCR) | MAJOR WIDENING(O) | Whitley | 118-US-0025W -000 | 28.1 | 30.425 | 2.325 | Arterial to Partial Control | 23 |  |  |  | 0 |  | 5820000 | 2021 | 8660000 | 2021 | 26000000 | 2022 | 2019-03-08 07:50 | The purpose of this project is to improve freight mobility and reduct congestion on US 25W from KY 727 to KY 3041. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 91.7488 | 9.1659 | 14.3602 | 12.7962 | 2.7488 | 9.5735 | 4.0995 | 9.0047 | 62 | 15 | 15
Y | 11 | Cumberland Valley ADD | IP20150348 | 11-8515 / 11-8515 |  | A | IMPROVE CONNECTIVITY BETWEEN CORBIN AND LONDON FROM KY-1006 TO US-25E. (08CCN) | DESIGN ENGINEERING(O) | Laurel | 063-US-0025 -000 | 0 | 10.475 | 10.475 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  | 2020 | 0 | 2022 | 78720000 | 2025 | 6420000 | 2025 | 141140000 | 2025 | 2019-03-08 08:03 | The purpose of this project is to improve connectivity between London and Corbin from KY 1006 to US 25E. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 90.5995 | 8.7393 | 13.0095 | 13.9692 | 1.327 | 9.0521 | 4.5498 | 9.9526 | 61 | 15 | 15
Y | 11 | Cumberland Valley ADD | IP20150430 | 11-8864 |  | A | IMPROVE GEOMETRICS ALONG URBAN CREEK ROAD (CR 1286) AND, INCLUDING INTERSECTIONS AT HAL ROGERS PARKWAY AND KY 687. (14CCN)(18CCN) | SAFETY(P) | Clay | 026-CR-1286 -000 | 0 | 3.067 | 3.067 | Local Roadway Improvements | 3 |  |  |  | 0 |  | 0 |  | 0 |  | 6600000 | 2021 | 2018-09-27 11:39 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on CR 1286. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | 11 | South | 19.0462 | 0.028436 | 0 | 5.0652 | 4.9526 | 0 | 0 | 9 | 19
Y | 11 | Cumberland Valley ADD | IP20160055 | 11-8910 |  | A | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM CLAY/LAUREL LINE TO MANCHESTER (JUST PAST EXIT 20 AT BRIDGE OVER KY 80/US 421), MP 10.593 TO MP 21.498 (SEGMENT 7). (16CCN)(18CCN) | MAJOR WIDENING(O) | Clay | 026-HR-9006 -000 | 10.593 | 21.498 | 10.905 | Full Control to Interstate | 10 | Y |  |  | 1000000 | 2021 | 15000000 | 2022 | 11000000 | 2023 | 98000000 | 2024 | 2018-07-10 08:18 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on Hal Rogers Parkway. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | Statewide | 45.0549 | 7.3304 | 5.4626 | 8.4251 | 7.0485 | 0 | 2.5551 | 14.2333
Y | 11 | Cumberland Valley ADD | IP20160056 | 11-8911 |  | A | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM MANCHESTER TO CLAY/LESLIE LINE; MP 21.498 TO MP 35.929 (SEGMENT 8) (16CCN)(18CCN) | MAJOR WIDENING(O) | Clay | 026-HR-9006 -000 | 21.498 | 35.929 | 14.431 | Full Control to Interstate | 10 | Y |  |  | 1000000 | 2021 | 18000000 | 2022 | 13000000 | 2023 | 99000000 | 2024 | 2018-07-10 08:18 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on Hal Rogers Parkway. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | Statewide | 39.5044 | 5.8678 | 3.8767 | 6.6079 | 7.0485 | 0 | 1.1454 | 14.9582
Y | 11 | Cumberland Valley ADD | IP20160058 |  |  |  | Reconstruct and improve existing alignments, with shoulders, of KY 11 from US 25E to the Knox/Clay County Line (16CCN) | Transportation Study | Knox | 061-KY-0011 -000 | 10.108 | 22.694 | 12.586 | Modernize Roadway-Rural | 26 |  | 1000000 | 2021 | 6200000 | 2022 | 14800000 | 2023 | 7000000 | 2023 | 57500000 | 2024 | 2019-03-07 13:13 | The purpose of this project is to reconstruct and improve existing alignments, with shoulders, of KY 11 from US 25E to the Knox/Clay County Line. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20160061 |  |  |  | Improve safety and provide access to Thunder Gap Horse Racing Track by widening Allison Boulevard (CS-1107) (16CCN) | Minor Widening | Knox | 061-CS-2053 -000 | 0 | 0.318 | 0.318 | Local Roadway Improvements | 3 |  | 0 |  | 150000 |  | 150000 |  | 75000 |  | 1650000 |  | 2016-11-30 12:34 | The purpose of this project is to improve safety and provide access to Thunder Gap Horse Racing Track by widening Allison Boulevard (CS-1107) (16CCN). | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20160062 |  |  |  | Enhancing Cumberland Avenue from US 25E to 18th Street with street improvements for vehicle and pedestrians, as well as storm water management to improve safety, congestion, and environmental impact. | Congestion Management | Bell | 007-KY-0074 -000 | 15.19 | 16.753 | 1.563 | Modernize Roadway-Rural | 26 |  | 500000 |  | 1750000 |  | 500000 |  | 2250000 |  | 7000000 |  | 2019-03-05 10:03 | The City of Middlesboro desires to attract visitors and residents to the city by enhancing the Cumberland Avenue gateway into downtown from US 25E to 18th Street, as well as making improvements to the intersection of US 25E/Cumberland Avenue and managemen | This project with proposed complete streets and intersection improvements will revitalize economic development, as well as improve safety, congestion, and environmental impact of the Cumberland Avenue/US 25E intersection and Cumberland Avenue Right of Way
Y | 11 | Kentucky River ADD | IP20160107 | 11-8951 |  | A | CONSTRUCT RIGHT TURN LANE ON US 421 AT INTERSECTION WITH KY 80. (16CCN)(18CCN) | CONGESTION MITIGTN(O) | Leslie | 066-US-0421 -000 | 21.236 | 21.736 | 0.5 | Improve Intersection | 26 |  |  |  | 520000 | 2021 | 120000 | 2022 | 280000 | 2022 | 1300000 | 2023 | 2019-03-06 09:54 | CONSTRUCT RIGHT TURN LANE ON US 421 AT INTERSECTION WITH KY 80. (16CCN) | CONSTRUCT RIGHT TURN LANE ON US 421 AT INTERSECTION WITH KY 80. (16CCN) | KENTUCKY RIVER ADD | South | 22.404 | 5.0521 | 5.9005 | 1.9017 | 2.109 | 0 | 3.4597 | 3.981 | 22
Y | 11 | Kentucky River ADD | IP20160109 |  |  |  | CONSTRUCT A NEW APPROACH FROM KY-3424 ONTO THE HAL ROGERS PARKWAY. | New Interchange | Leslie | 066-KY-3424 -000 | 2.521 | 3.121 | 0.6 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 11:32
Y | 11 | Kentucky River ADD | IP20160110 |  |  |  | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM CLAY/LESLIE LINE TO HYDEN SPUR, MP 35.929 TO MP 44.188 (SEGMENT 9). (16CCN) | Reconstruction | Leslie | 066-HR-9006 -000 | 35.929 | 44.188 | 8.259 | Modernize Roadway-Rural | 26 | Y | 0 |  | 1000000 |  | 12000000 |  | 9000000 |  | 94400000 |  | 2016-11-30 12:27
Y | 11 | Kentucky River ADD | IP20160111 |  |  |  | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: 4 LANE FROM HYDEN SPUR TO LESLIE/PERRY LINE (SEGMENT 10). (16CCN) | Reconstruction | Leslie | 066-HR-9006 -000 | 44.188 | 51.026 | 6.838 | Modernize Roadway-Rural | 26 | Y | 0 |  | 1000000 |  | 10000000 |  | 7000000 |  | 79600000 |  | 2016-11-30 12:28
Y | 11 | Cumberland Valley ADD | IP20160142 | 11-8909 |  | A | IMPROVE THE HAL ROGERS PARKWAY TO INTERSTATE STANDARDS FROM 4.0 MI EAST OF KY 192 TO LAUREL/CLAY CO. LINE. (I-75 TO HAZARD) (16CCN)(18CCR) | RECONSTRUCTION(O) | Laurel | 063-HR-9006 -000 | 7.877 | 10.593 | 2.716 | Arterial to Full Control | 36 | Y |  |  | 1000000 | 2021 | 2200000 | 2022 | 1000000 | 2023 | 27000000 | 2024 | 2018-07-10 08:18 | The purpose of this project is to upgrade Hal Rogers Parkway (KY 80) from Somerset to Hazard to interstate standards. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | Statewide | 34.1207 | 5.6035 | 5.9912 | 3.2544 | 6.7401 | 0 | 2.7313 | 9.8002
Y | 11 | Cumberland Valley ADD | IP20160264 |  |  |  | Construct a new entrance to the University of the Cumberlands from South 2nd Street up the hill to tie into Hutton Way (16CCN) | New Route | Whitley | 118-CS-1121 -000 | 0 | 0.149 | 0.149 | Construct Road in New Location | 0 |  | 0 |  | 300000 |  | 50000 |  | 0 |  | 1600000 |  | 2016-11-30 12:31 | The purpose of this project is to construct a new entrance to the University of the Cumberlands from South 2nd Street up the hill to tie into Hutton Way (16CCN) | The following needs have been identified for this project: 1) Improve Access, 2) Improve Mobility
Y | 11 | Cumberland Valley ADD | IP20170086 |  |  |  | Construction of I 75 Frontage Road from KY 3432 to 5th Street (SEE 8-8514.10 AND 8-8514.00 FOR ADDITIONAL SECTIONS) (08CCN) | New Route | Laurel | 063-KY-1006 -000 | 5.6 | 5.8 | 0.2 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 3130000 |  | 275000 |  | 7500000 |  | 2017-05-18 11:19 | The purpose of this project is to provide construction of I 75 Frontage Road from KY 3432 to 5th Street. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility
Y | 11 | Cumberland Valley ADD | IP20180074 |  |  |  | Reconstruct US 421 from Clover Bottom Creek Road to 0.11 mile south of Asbill Road. (2006BOPC) | Reconstruction | Jackson | 055-US-0421 -000 | 23.51 | 25.37 | 1.86 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 | 2020 | 1500000 | 2021 | 640000 | 2021 | 13750000 | 2022 | 2019-03-07 11:23 | The purpose of this project is to reconstruct US 421 from Clover Bottom Creek Road to 0.11 mile south of Asbill Road. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access
Y | 11 | Cumberland Valley ADD | IP20180075 |  |  |  | Construct a new route to address access issue on KY 72 from Alva/Black Star near Harlan/Bell County line to Liggett, which is west of the city of Harlan | New Route | Harlan | 048-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 1000000 | 2020 | 2000000 | 2021 | 1000000 | 2022 | 500000 | 2022 | 24000000 | 2023 | 2019-03-07 10:47 | The purpose of this project is to address acess issues on KY 72 from Alva/Black Star near Harlan/Bell County Line to Liggett, which is west of the city of Harlan. Currently there is no route to connect the communities. A major landslide in February 2019 | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility. According to Google, it’s 19 miles between Liggett and Pineville, but it’s 38 miles of driving distance. I
Y | 11 | Cumberland Valley ADD | IP20190030 |  |  |  | Explore access management opportunities, as well as increase safety and mobility in this heavily congested area on US-25E in Barbourville. | Congestion Management | Knox | 061-US-0025E -000 | 8 | 12 | 4 | Transportation Studies | 0 |  | 1000000 | 2020 | 0 |  | 0 |  | 0 |  | 0 |  | 2019-03-07 10:58 | The purpose of this project is to explore access management opportunities, as well as increase safety and mobility in this heavily congested area on US-25E in Barbourville. | The following needs have been identified for this project: 1) Improve roadway safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, and 5) Reduce Congestion
Y | 11 | Cumberland Valley ADD | IP20190184 |  |  |  | Improve safety and connectivity with interchange improvements on I-75 at Exit 15 Goldbug/Williamsburg. | Reconstruction | Whitley | 118-I -0075 -000 | 15 | 15.8 | 0.8 | Interchange Safety Improvements | 35 |  | 0 |  | 1000000 | 2021 | 1000000 | 2022 | 1000000 | 2022 | 8250000 | 2023 | 2019-03-11 11:03 | This Interchange Safety Project will improve safety and traffic operations within and near the US 25W interchange with I-75 in Whitley County, Exit 15. | Improve safety and traffic operations within and near the US 25W interchange with I-75 in Whitley County, Exit 15.
Y | 12 | Kentucky River ADD | IP20000084 |  |  |  | PINE MOUNTAIN - RELOCATION WITH TUNNEL FROM KY 932 TO KY 15 AT WHITESBURG. ADDITIONAL FUNDS NEEDED IN ADDITION TO FUNDS SCHEDULED IN 6YP ITEMS 12-314.00 THRU 314.30. | Relocation | Letcher | 067-US-0119 -000 | 8.832 | 16.075 | 7.243 | Construct Road in New Location | 0 | Y | 0 |  | 10500000 |  | 19500000 |  | 6000000 |  | 114000000 |  | 2010-12-01 10:21 |  | This road is a highly traveled road that connects Cumberland to Whitesburg. There is a high percentage of truck traffic.
Y | 12 | Big Sandy ADD | IP20000089 |  |  |  | Improve geometrics/pavement condition and safety concerns from the junction of KY 122 and KY 610 to the junction of KY 122 and KY 2167. | Reconstruction | Pike | 098-KY-0122 -000 | 5.2 | 10.37 | 5.17 | Other Improvement Types | 0 |  | 0 |  | 4200000 |  | 5600000 |  | 2800000 |  | 34400000 |  | 2010-12-03 14:39 | Address safety and reliability on this segment of KY-122 by improving geometrics and increasing lane and shoulder width. | The problems on this portion of road is that the road has poor horizontal and vertical deficiences (steep grade, steep curves, no shoulder, deep ditches, etc). This route has some coal haul from various mines. Minimal lane width (9 feet) and rough pavem
Y | 12 | Big Sandy ADD | IP20020005 |  |  |  | Create alternate route(s) entering and exiting Mayo Shopping Plaza to relieve congestion on KY 321. | New Route | Johnson | 058-KY-0321 -000 | 8.3 | 8.6 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 500000 |  | 110000 |  | 2300000 |  | 2011-01-11 14:57 | Address safety and access issues, relieve congestion, and facilitate economic development by creating an alternate access to the Mayo Shopping Plaza to relieve congestion on KY-321. | KY 321, serving the major traffic generator of Mayo Plaza in Paintsville is currently one of the worst bottlenecks for traffic congestion in the entire region, especially during times when there is new construction and development going on in the area,
Y | 12 | Kentucky River ADD | IP20070250 |  |  |  | Provide a new connector on US 119 in Jenkins to the Gateway Industrial Park | New Route | Letcher | 067-US-0119 -000 | 26.023 | 26.374 | 0.351 | Construct Road in New Location | 0 | Y | 0 |  | 400000 |  | 650000 |  | 150000 |  | 1500000 |  | 2010-10-11 16:05 |  | This project is to provide a new connector on US 119 to the Gateway Industrial Park in Jenkins. A second access route to the park is needed. There are three businesses and an emergency helapad located at the Industrial Park. The connector will be essen
Y | 12 | Big Sandy ADD | IP20080627 |  |  |  | Address the issue of incidents occuring between vehicles entering US 23 S from KY 1428, and vehicles traveling on US 23 N. Improve the flow of traffic through this intersection, and improve the junctions of KY 1427 and US 23, and KY 1428 and US 23. | New Interchange | Floyd | 036-US-0023 -000 | 17.7 | 17.9 | 0.2 | Other Improvement Types | 0 | Y | 0 |  | 500000 |  | 600000 |  | 330000 |  | 13800000 |  | 2010-02-25 16:51 | Improve safety and access and reduce congestion by reconstructing the intersection between US-23 and KY-1428. | ADT at this location is 18200 v.p.d., on four 12-foot lanes. It incurs truck traffic of 11% and is also a heavily-used coal haul route. This intersection of US 23 and KY 1428 has a rising CRF, and this project is intended to prevent future crashes which
Y | 12 | Big Sandy ADD | IP20080629 | 12-8703 | 2021-01-15 | A | IMPROVE ACCESS TO KY 80 AT GARRETT EASTBOUND AND ELIMINATE NECESSITY FOR CROSSING WESTBOUND LANES TO MERGE INTO EASTBOUND LANES. MP 1.527 TO MP 1.827 (12CCN)(18CCN) | CONGESTION MITIGTN(O) | Floyd | 036-KY-0080 -000 | 1.527 | 1.827 | 0.3 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 | 2021 | 0 |  | 3120000 | 2022 | 2018-07-10 08:18 | Improve safety and access to KY-80 at Garrett eastbound by eliminating the necessity for eastbound traffic to cross westbound lanes to merge. | ADT of 11800 v.p.d. includes very heavy truck traffic (18.0%) and coal haul activity. This project is access- and mobility-driven. Currently, the only access from KY 7 N/S onto KY 80 E is to traverse both westbound lanes of KY 80 W before turning left o | BIG SANDY ADD | East | 23.6317 | 4.6946 | 4.5808 | 5.2545 | 0.41916 | 0 | 4.6108 | 4.0719 | 24
Y | 12 | Big Sandy ADD | IP20080630 |  |  |  | Improve alignment/lane width/shoulder width issues; improve site distance issues; improve opportunities for passing slower traffic, i.e. coal trucks, from the junction of KY 122 and KY 80 to the Floyd-Pike County line. | Reconstruction | Floyd | 036-KY-0122 -000 | 8.52 | 34.191 | 25.671 | Other Improvement Types | 0 |  | 0 |  | 11900000 |  | 18700000 |  | 8500000 |  | 130900000 |  | 2010-12-01 11:00 | Improve safety, reliability, and mobility along this section of KY-122. | A high CRF and the Horz. Align. Adeq. of 3 (75% of the curves on this section of road are substandard), expresses the alignment problems on this 22.3 mile section of KY 122. It is called the Left Beaver Creek Road, and serves more than half the total po
Y | 12 | Big Sandy ADD | IP20080631 |  |  |  | Address traffic congestion, flow and mobility issues, and safety concerns, on KY 122, from .5 miles before Creekside Lane to Doty Branch. | Major Widening | Floyd | 036-KY-0122 -000 | 17.8 | 18.409 | 0.609 | Modernize Roadway-Rural | 26 |  | 0 |  | 500000 |  | 1500000 |  | 538000 |  | 3230000 |  | 2015-07-06 09:44 | Address congestion, flow, mobility, and pedestrian safety issues on KY-122 from 0.5 miles before Creekside to Doty Branch. | ADT at this location is 5,885 v.p.d., on two 10-foot lanes. Though the truck traffic data shows it as 4.3%, this is in reality a much heavier-used coal haul route than that number suggests. This location is in a very congested area caused by a build-up of | BIG SANDY ADD | East | 46.262 | 4.3234 | 12.8443 | 9.274 | 1.6467 | 9.2216 | 3.6228 | 5.3293 | 46
Y | 12 | Big Sandy ADD | IP20080632 |  |  |  | Address sight distance issues and substandard geometrics of this curve, from Hamilton's Mobile Home Park to .3 miles before Nancy Road. | Spot Improvement | Floyd | 036-KY-0122 -000 | 24.6 | 25 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1300000 |  | 360000 |  | 4330000 |  | 2015-07-06 09:46 | Improve safety, reliability, and mobility along this section of KY-122 by realigning the curve near Price. | ADT of 3,185 v.p.d. travel on two 10-foot lanes. Though no truck traffic data is available, this is a heavily-used coal haul route. The issues resulting in a high CRF of 1.04 include a geometrically-deficient horizontal curve near Price which causes ina
Y | 12 | Big Sandy ADD | IP20080633 |  |  |  | Address sight distance issues and substandard geometrics of this curve, from .3 miles before Nancy Road to .5 miles past Creekside Drive. | Spot Improvement | Floyd | 036-KY-0122 -000 | 25.2 | 25.5 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 1500000 |  | 330000 |  | 2300000 |  | 2010-02-25 16:51 | Address safety, reliability, and mobility along this section of KY-122 by improving sight distance and geometric deficiencies. | ADT of 3,190 v.p.d. travel on two 10-foot lanes. Though no truck traffic data is available, this is a heavily-used coal haul route. The issues resulting in a high CRF include a geometrically-deficient horizontal curve near Price which causes inadequate
Y | 12 | Big Sandy ADD | IP20080634 |  |  |  | Reconstruct KY 122 and raise above high water at Bucks Branch, between Stafford Lane and Flanery Cemetary Road. | Safety-Haz-Elm | Floyd | 036-KY-0122 -000 | 7.736 | 7.954 | 0.218 | Other Improvement Types | 0 |  | 0 |  | 50000 |  | 300000 |  | 75000 |  | 650000 |  | 2015-08-04 08:36 | Improve safety and reliability along this section of KY-122 by raising the roadway above high water at Bucks Branch between Stafford Lane and Flannery Cemetery Road. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Reliability.
Y | 12 | Big Sandy ADD | IP20080635 |  |  |  | KY 122 in Floyd County would be widened to a two-lane highway with 8 foot DGA shoulders and passing lanes a various locations. This new 2-lane road would have 12 foot width lanes. The road could be separated into various segments which would serve the m | Minor Widening | Floyd | 036-KY-0122 -000 | 8.146 | 8.496 | 0.35 | Other Improvement Types | 0 |  | 0 |  | 1600000 |  | 2800000 |  | 1200000 |  | 14400000 |  | 2010-12-01 10:58 | Improve safety, mobility, and reliability of this section of KY-122 by widening the lanes and shoulders. | KY 122 in Floyd Co. is currently a rural two-lane road constructed in the 1930's. The average shoulder with is 2 feet. There are many substandard curves and many hidden entrances with severe site distance problems. This section of Left Beaver Creek Road
Y | 12 | Big Sandy ADD | IP20080636 |  |  |  | Reconstruct curve and intersection at junction of KY 3385 and KY 194. | Safety-Haz-Elm | Floyd | 036-KY-0194 -000 | 5.317 | 5.93 | 0.613 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 150000 |  | 55000 |  | 920000 |  | 2010-02-25 16:51 | Address safety and access issues at the intersection of KY-194 and KY 3385 by correcting curve geometry and improving sight distance. | The purpose of this project is to correct the curve geometry at the intersection of KY 194 and KY 3385. Both the horizontal and vertical aspects of this intersection play a factor in the increased danger of collision as well as creating difficult condit
Y | 12 | Big Sandy ADD | IP20080637 |  |  |  | Improve site distance/lane width/shoulder width issues. Improve entrances onto roadway. | Reconstruction | Floyd | 036-KY-1427 -000 | 4.58 | 9.082 | 4.502 | Modernize Roadway-Rural | 26 |  | 500000 |  | 900000 |  | 1950000 |  | 800000 |  | 12300000 |  | 2015-08-05 11:20 | Improve safety, reliability, and mobility along KY-1427 by improving sight distance, lane width, and shoulder width deficiencies and improving entrances onto the roadway. | The Abbott Creek Road (no ADEQ Rating information available) provides access to what has quickly become one of the City of Prestonsburg's major residential areas. The availability of flat land on this long section of rural highway is quickly giving way to | BIG SANDY ADD | East | 59.8174 | 1.4491 | 11.4072 | 11.991 | 4.4611 | 6.8263 | 0 | 8.6826 | 45 | 15
Y | 12 | Big Sandy ADD | IP20080638 |  |  |  | Curve improvement at Cane Branch Rd | Safety-Haz-Elm | Floyd | 036-KY-1427 -000 | 1.2 | 1.45 | 0.25 | Other Improvement Types | 0 |  | 0 |  | 46000 |  | 120000 |  | 37000 |  | 717000 |  | 2010-12-01 10:51 | Address safety issues on KY-1427 by improving the geometrics of the curve at Cane Branch Road. | The following needs have been identified for this project: 1) Improve Roadway Safety.
Y | 12 | Big Sandy ADD | IP20080641 |  |  |  | Improve lane and shoulder width issues, and increase pedestrian safety | Spot Improvement | Floyd | 036-KY-1428 -000 | 12.373 | 14.75 | 2.377 | Other Improvement Types | 0 |  | 0 |  | 30000 |  | 60000 |  | 18000 |  | 492000 |  | 2010-12-01 10:47 | Address safety issues for both motorists and pedestrians along this section of KY-1428 by increasing lane and shoulder width. | CRF and IRI both show the safety and condition issues that exist on this stretch of roadway. There are also 1 foot shoulders, and 11 feet lane widths, making this a dangerous road for travel, on foot or by car. Little to no out of lane recovery room is
Y | 12 | Big Sandy ADD | IP20080642 |  |  |  | Improve site distance/lane width/shoulder width issues along this section, from the junction of KY 1428 and Long Branch Road to the junction of KY 1428 and Cow Creek. | Spot Improvement | Floyd | 036-KY-1428 -000 | 8.4 | 8.7 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 30000 |  | 60000 |  | 18000 |  | 492000 |  | 2010-12-01 10:45 | Address safety and access issues along this section of KY-1428 by improving sight distance, lane width, and shoulder width. | In this location there are virtually no shoulders (1 foot shoulder widths) to speak of. This is a potentially high crash location and the site distance at this location for motorist trying to enter KY 1428 is almost non-existent, due to a highwall on t
Y | 12 | Big Sandy ADD | IP20080643 |  |  |  | Improve safety for motorists at this curve from Canner Hunter Road to Hunter Road. | Safety-Haz-Elm | Floyd | 036-KY-2030 -000 | 4.8 | 5.1 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 300000 |  | 165000 |  | 1350000 |  | 2015-01-08 13:25 | Improve safety and access issues on this section of KY-2030 by reconstructing the curve at Canner Hunter Road. | No HIS/adeq data is available for this project. This curve is a 90-degree curve, and sits at the intersection of a county road and Little Mud Road. It sustains extremely heavy coal haul activities, which deposits mud on the road from the trucks, in turn c
Y | 12 | Big Sandy ADD | IP20080644 |  |  |  | CURVE REVISION AT FROG BRANCH COUNTY RD | Safety-Haz-Elm | Floyd | 036-KY-2030 -000 | 7 | 7.4 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 300000 |  | 220000 |  | 1380000 |  | 2010-02-25 16:51 | Address safety and access issues along this section of KY-2030 by reconstructing the curve at Frog Branch Road to improve sight distance. | The purpose of this project is to correct a curve on KY 2030 at Frog Branch RD. KY 2030 has an ADT of 1189. The geometry of this curve which includes the intersection(s) of Frog Branch and Clark's Place limits sight distance of approaching traffic to th
Y | 12 | Big Sandy ADD | IP20080646 |  |  |  | Address geometric and safety issues on KY 3384, from the junction of US 23 and KY 3384 to Town Branch Bridge. | Reconstruction | Floyd | 036-KY-3384 -000 | 0 | 1.822 | 1.822 | Modernize Roadway-Rural | 26 |  | 0 |  | 1400000 |  | 2600000 |  | 1940000 |  | 17200000 |  | 2015-07-06 10:00 | Address safety and connectivity issues by correcting geometric deficiencies and widening lane and shoulder widths on this roadway between US-23 and KY-1428. | No data is available via HIS to adequately express the need for this project. This road serves as a direct connection between US 23 and KY 1428 (South Lake Drive/Main Street) in Prestonsburg. This road carries heavy vehicle traffic, partuclarly in morning
Y | 12 | Big Sandy ADD | IP20080647 |  |  |  | Address alignment and safety issues on KY 3384, from Town Branch Bridge to the junction of KY 3384 and KY 1428. | Minor Widening | Floyd | 036-KY-3384 -000 | 1.922 | 2.047 | 0.125 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 1000000 |  | 1000000 |  | 800000 |  | 2010-02-25 16:51 | Improve safety and connectivity by widening this section of KY-3384 from Town Branch Bridge to KY-1428. | No data available to adequately express the need for this project. This road, a connector between Town Branch Bridge, from US 23, to KY 1428 (South Lake Drive/Main Street) in Prestonsburg is a heavily-traveled (particularly in monrings and afternoons) n
Y | 12 | Big Sandy ADD | IP20080648 |  |  |  | Improve/upgrade existing roadway from Johnson-Magoffin County line to the US 23 overpass, to increase traffic flow and efficiency. | Major Widening | Johnson | 058-US-0460 -000 | 0 | 7.745 | 7.745 | Other Improvement Types | 0 | Y | 0 |  | 3000000 |  | 7000000 |  | 5000000 |  | 32000000 |  | 2010-02-25 16:51 | Improve regional connectivity and safety by widening this section of US-460 from the Johnson/Magoffin County line to US-23 in Paintsville, improving access to the Mountain Parkway. | US 460 is a Major Connector Access from the Mountain Parkway to US 23 at Paintsville. Motorists from Johnson, Martin, Lawrence, and points east utilize this route as access to Central Kentucky and the Mountain Parkway.
Y | 12 | Big Sandy ADD | IP20080649 |  |  |  | Improve the sight distance issues and the grade on the inside of the curve, under the railroad overpass, to decrease flooding, improve truck clearance and sight distance. | Spot Improvement | Johnson | 058-KY-0040 -000 | 11.762 | 11.843 | 0.081 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 200000 |  | 180000 |  | 1240000 |  | 2015-07-06 09:54 | Address safety and reliability issues by mitigating flooding and increasing truck clearance at overpass at this spot on KY-40. | ADT is 11,206v.p.d. at this location, on two 12-foot lanes. There is a railroad underpass present, with insufficient grading on the approaches, to handle rain run-off. This causes standing water in the underpass up to 2-feet in depth during heavy rains, d
Y | 12 | Big Sandy ADD | IP20080650 |  |  |  | Address alignment, congestion and safety issues on this curve, from BMP 10.290, 4/10 of a mile east of the intersection of Third and West, to the intersection of Third Street (KY 40) and West Street. | Safety-Haz-Elm | Johnson | 058-KY-0040 -000 | 10.29 | 10.697 | 0.407 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 1600000 |  | 425000 |  | 2500000 |  | 2010-02-25 16:51 | Address safety and access issues along KY-40 from MP 10.290 to the intersection of West Street. | ADT at this location is 6,689 v.p.d., traveling on two 10 -foot lanes. This segment of KY 40 also carries moderate to heavy truck traffic, in the form of commercial haulers accessing the city and east Paintsville. This project is safety based, as eviden
Y | 12 | Big Sandy ADD | IP20080651 |  |  |  | Perform spot improvements at various locations and segments of KY 172 to better accommodate trucks and farm vehicles. | Spot Improvement | Johnson | 058-KY-0172 -000 | 0 | 12.37 | 12.37 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 1500000 |  | 650000 |  | 4300000 |  | 2015-01-08 14:18 | Address safety and mitigate congestion by making spot improvements along this section of KY-172. | The land use adjacent to KY 172 in Johnson County is mostly for agricultural use. This is one of the last significant areas in the BSADD region for farming communities. KY 172 is the sole access route for the "stock yard" (a flea market which acts as a m
Y | 12 | Big Sandy ADD | IP20080652 |  |  |  | Address safety, bridge and approach condition issues, and correct rock-fall safety hazard at Mud Lick Creek Bridge | Minor Widening | Johnson | 058-KY-0172 -000 | 11.8 | 12.1 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 350000 |  | 110000 |  | 2070000 |  | 2010-02-25 16:51 | Improve safety and reliability by increasing lane and shoulder widths, improving sight distances, and eliminating rockfall hazards on this section of KY-172. | ADT is 3,714 v.p.d, on two 9-foot lanes. Narrow, high-wall vertical cuts are close to the east end of Mud Lick Creek Bridge, creating a stretch of roadway with no shoulders on the roadway or bridge. Pavement deterioration is present. Two private entrance
Y | 12 | Big Sandy ADD | IP20080654 |  |  |  | Address congestion and crash issues on KY 321, from 6th Street to the Junction of KY 321 and KY 40. | Congestion Management | Johnson | 058-KY-0321 -000 | 7.07 | 8.791 | 1.721 | Modernize Roadway-Rural | 26 |  | 300000 |  | 1275000 |  | 4250000 |  | 2200000 |  | 23900000 |  | 2015-01-08 12:15 | Address safety and reliability and mitigate congestion on this segment of KY-321. | ADT is 15,970 v.p.d., on two lanes, ranging from 11-feet to 12-feet in width. Extremely high CRF exhibits the serious hazardous and substandard conditions present on this section of roadway. A high school, a middle school, a Post Office, many banks, resta
Y | 12 | Big Sandy ADD | IP20080655 |  |  |  | Address severe congestion, mobility, collision, and pedestrian accessibility issues along KY 321, from the 11th Street turnoff to the entrance of Mill Branch Road (Southside Drive). | Congestion Management | Johnson | 058-KY-0321 -000 | 6.647 | 7.35 | 0.703 | Other Improvement Types | 0 |  | 0 |  | 175000 |  | 0 |  | 110000 |  | 1035000 |  | 2010-02-25 16:51 | Improve safety and reliability and mitigation congestion on this segment of KY-321. | This project has been segmented from its parent project. ADT is 12,583 v.p.d., on two 10- to 11-foot lanes. A high CRF adequately expresses the urgent need for improving/enhancing this segment of KY 321. Efficient and safe traffic flow is impeded along
Y | 12 | Big Sandy ADD | IP20080656 |  |  |  | Improve geometrics from KY 40 to 1.0 mile N of KY 40 | Reconstruction | Johnson | 058-KY-0581 -000 | 0 | 1 | 1 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 1500000 |  | 690000 |  | 8310000 |  | 2010-12-01 11:40 | Address safety and connectivity issues along this segment of KY-581 by improving lane width and roadway geometrics in several locations. | The purpose of this project is to address roadway width and curvature issues, as well as a hazardous railroad crossing on KY 581, from KY 40 to the one mile point. KY 581 is the primary route linking the communities of Thealka and River to Paintsville a
Y | 12 | Big Sandy ADD | IP20080657 |  |  |  | CURVE IMPROVEMENTS BETWEEN KY 302 AND KY 40 | Safety-Haz-Elm | Johnson | 058-KY-1107 -000 | 1.2 | 1.5 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 450000 |  | 200000 |  | 275000 |  | 2300000 |  | 2010-02-25 16:51 | Improve safety, reliability, and access issues along this segment of KY-1107 by improving sight distance and roadway geometrics. | The purpose of this project is to address curvature issues on a segment of KY 1107 from KY 302 to KY 40, a length of about 0.3 miles. KY 1107 is a secondary route linking the communities of West Van Lear to Paintsville . This section follows the curvatu
Y | 12 | Big Sandy ADD | IP20080659 |  |  |  | Improve alignment and geometrics of KY 2040 from KY 40 to end of state maintenance. | Reconstruction | Johnson | 058-KY-2040 -000 | 0 | 3.06 | 3.06 | Other Improvement Types | 0 |  | 0 |  | 1500000 |  | 5000000 |  | 3500000 |  | 15000000 |  | 2012-01-30 13:21 | Address safety, access, and connectivity issues along this segment of KY-2040 by improving roadway alignment and geometrics. | The purpose of this project is to address curvature and roadway width on KY 2040 from KY 40 to the end of state maintenance at the intersection of Pricetown RD and Banjer BR, a length of 3.1 miles. KY 2040 is a primary route linking the communities of O
Y | 12 | Kentucky River ADD | IP20080660 |  |  |  | Safety improvements while maintaining or improving traffic flow on KY 15 at the intersection of KY 160 near Carr Fork Lake. | Safety-Haz-Elm | Knott | 060-KY-0015 -000 | 3.8 | 4.1 | 0.3 | Improve Intersection | 26 | Y | 0 |  | 200000 |  | 250000 |  | 220000 |  | 1600000 |  | 2015-01-08 13:15 | Safety improvements while maintaining or improving traffic flow on KY 15 at the intersection of KY 160 near Carr Fork Lake. | Many collisions have occured at this location. Types of collisions are: right angle, southbound rear end and southbound side swipes. This intersection is one of two major routes into Hindman. Currently neither KY 15 nor KY 160 has left turn lanes creat | KENTUCKY RIVER ADD | East | 39.522 | 7.7605 | 13.5629 | 8.488 | 0.41916 | 0 | 4.2515 | 5.04 | 40
Y | 12 | Kentucky River ADD | IP20080661 |  |  |  | To combine the 1997 Scoping Study and other previous studies into one comprehensive programming document for further consideration. To be combined with 12-067-D0015-85.10 for study purposes. Initial scope included Relocation south of Carr Fork Lake from | Relocation | Knott | 060-KY-0015 -000 | 0 | 8.9 | 8.9 | Transportation Studies | 0 | Y | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2015-06-22 14:01 | To combine the 1997 Scoping Study and other previous studies into one comprehensive programming document for further consideration. To be combined with 12-067-D0015-85.10 for study purposes. Initial scope included Relocation south of Carr Fork Lake from | The existing KY 15 is a high speed, heavily congested roadway and a heavy coal haul road. It is primary arterial route connecting this Eastern region of KY with the rest of the state as well as Virginia and Tennessee. There was a scoping study completed | KENTUCKY RIVER ADD | East | 26.7889 | 7.3054 | 0 | 13.9446 | 1.2275 | 0 | 4.3114 | 0 | 27
Y | 12 | Kentucky River ADD | IP20080662 |  |  |  | Improve safety and substandard geometrics with a new facility that meets current standards from KY 899 to KY 3391. | Reconstruction | Knott | 060-KY-0160 -000 | 8.198 | 9.42 | 1.222 | Modernize Roadway-Rural | 26 |  | 0 |  | 1000000 |  | 6000000 |  | 2200000 |  | 18500000 |  | 2015-01-08 13:42 | Improve safety and substandard geometrics with a new facility that meets current standards from KY 899 to KY 3391. | The problem with the existing roadway is that it is a substandard, geometrically deficient roadway that is forced to serve as a major collector from KY 80 to KY 15 through Hindman. | KENTUCKY RIVER ADD | East | 67.1901 | 9.0539 | 9.7904 | 10.8009 | 3.0838 | 9.521 | 4.012 | 5.9281 | 52 |  | 15
Y | 12 | Kentucky River ADD | IP20080663 |  |  |  | Provide a better transition at this curve, from the new section to the old section at the bottom of the hill at Short Branch near Pippa Passes. | Safety-Haz-Elm | Knott | 060-KY-0899 -000 | 3.7 | 4.2 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 300000 |  | 330000 |  | 4410000 |  | 2015-01-08 12:12 | Provide a better transition at this curve, from the new section to the old section at the bottom of the hill at Short Branch near Pippa Passes. | The problem is the very steep horizontal and vertical curve located at the bottom of a hill just north of a previous reconstruction of this road. The problems of this project were increased by the reconstruction of the adjoining segment because driver ex | KENTUCKY RIVER ADD | East | 24.6617 | 3.7485 | 5.6587 | 6.2425 | 2.9042 | 0 | 0 | 6.1078 | 25
Y | 12 | Kentucky River ADD | IP20080664 |  |  |  | Construct a Pedestrian bridge on KY 899 at the entrance to Alice Lloyd College in order to separate pedestrian and vehicles, improve safety by seperating transportation systems of highway and pedestrian traffic. 6YHP # 12-8802 C-2015 SPP FUNDING | Safety-Haz-Elm | Knott | 060-KY-0899 -000 | 5.9 | 6 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 100000 |  | 100000 |  | 500000 |  | 2010-02-25 16:51 |  | The problem with this segment of KY 899 is at the entrance to Alice Lloyd College. Student parking for the college on one side of KY 899 and the college campus is on the other side, creating pedestrian traffic at the bottom of a verticle curve in the mid
Y | 12 | FIVCO ADD | IP20080665 |  |  |  | Improve KY-1 from the Johnson C/L to KY-3 to eliminate dangerous curves and address safety. | Major Widening | Lawrence | 064-KY-0001 -000 | 0 | 14.14 | 14.14 | Other Improvement Types | 0 |  | 0 |  | 8000000 |  | 13000000 |  | 3000000 |  | 76000000 |  | 2010-11-30 14:14 |  | This project had an IRI of 163 in 2003 and is now rated at 147 in 2005, indicating a serious problem. The road is narrow with 9' lane width (3'shoulders) and has steep curves. The last actual ADT was taken in 2001-2004 ranged between 413 to 1042. The l
Y | 12 | FIVCO ADD | IP20080666 |  |  |  | Reconstruct to accommodate recreational vehicles in this region of rural Kentucky at mountain crossing between US 23 and KY 1185. | Major Widening | Lawrence | 064-KY-0003 -000 | 17.1 | 19.627 | 2.527 | Modernize Roadway-Rural | 26 |  | 0 |  | 1250000 |  | 1875000 |  | 1375000 |  | 13800000 |  | 2015-01-08 13:51 |  | This road along KY3 from US23 to KY1185 (2.5 miles)leading to Yatesville Lake Marina is a narrow 2-10 feet lanes with very little to no shoulder. It has steep curves and a steep hill to traverse. This is the main connection to the Yatesville Lake Marina | FIVCO ADD | East | 57.0254 | 3.3054 | 9.521 | 9.1392 | 3.9521 | 8.2036 | 0 | 7.9042 | 42 |  | 15
Y | 12 | FIVCO ADD | IP20080667 |  |  |  | Improve KY-32 from Elliott C/L to Yatesville Lake reconstruction section for better access to Yatesville Lake and to improve safety. See Elliott County listing for continuation of project to KY-7 @ Sandy Hook. | Spot Improvement | Lawrence | 064-KY-0032 -000 | 0 | 23.586 | 23.586 | Local Roadway Improvements | 3 |  | 0 |  | 1500000 |  | 2500000 |  | 1500000 |  | 9000000 |  | 2019-03-11 13:21 | To improve safety, increase capacity, and allow for longer vehicles. | KY32 had A/R rating of 84.6 now 75.9 and an IRI of 139 now 127 indicating a possible need to improve for safety concerns. Currently the roadway is not sufficient to handle traffic and provides poor access to Yatesville Lake. Vehicles hauling boats and c
Y | 12 | FIVCO ADD | IP20080668 |  |  |  | Correct substandard roadway geometricts and address safefy issues on KY-201/KY-32 from Johnson C/L to KY-1 for safety. | New Route | Lawrence | 064-KY-0201 -000 | 0 | 4.99 | 4.99 | Other Improvement Types | 0 |  | 0 |  | 7000000 |  | 12000000 |  | 6000000 |  | 75000000 |  | 2010-11-30 14:17 |  | This project involves two routes in a rural area: KY201 from mp0.0 to mp 18.16 and a small part of KY32, which runs concurrently for a distance of .191 miles (MP 10.756 to MP 10.965) is a narrow winding road with lane widths of 9' to 10' and narrow should
Y | 12 | FIVCO ADD | IP20080669 |  |  |  | Extend KY-645 from US-23 @ Ulysses to I-64 somewhere between Morehead in Rowan County to KY-67 (Industrial Parkway in Carter) for connectivity to promote tourism, economic development, and provide access to medical centers and higher learning facilities. | Major Widening | Lawrence | 064-KY-0645 -000 | 0.01 | 5.205 | 5.195 | Other Improvement Types | 0 |  | 0 |  | 24000000 |  | 39000000 |  | 12000000 |  | 225000000 |  | 2010-11-30 14:19 |  | To provide connectivity to under served areas while providing a more efficient connection between the NORTH EASTERN REGION of KY and the CENTRAL REGION, to promote tourism, economic development and to provide access to major medical facilities and higher
Y | 12 | FIVCO ADD | IP20080670 |  |  |  | Reconstruct the access into this area along existing KY 707 in order to upgrade this road facility to current standards. KY 707 MP 0 - 8.16 from KY 3 to KY 1937. | Major Widening | Lawrence | 064-KY-0707 -000 | 0 | 8.16 | 8.16 | Modernize Roadway-Rural | 26 |  | 0 |  | 4100000 |  | 9000000 |  | 8200000 |  | 36900000 |  | 2010-02-25 16:51 |  | KY707 is a narrow winding one to two lane road. There are no guard rails along areas with 6 to 20 feet vertical drops next to two to four for shoulders. Slips are evident in at least one blind curve after cresting a hill. The current 55 mph speed limit | FIVCO ADD | East | 21.8603 | 0.16766 | 2.6048 | 6.3323 | 4.7006 | 5.5689 | 0 | 2.486 | 22
Y | 12 | FIVCO ADD | IP20080671 |  |  |  | Reconstruct the access into this area along existing KY 707 in order to upgrade this road facility to current standards. KY707 MP 8.16 to 9.69 from KY 1937 to US 23 at Buchanan. | Major Widening | Lawrence | 064-KY-0707 -000 | 8.16 | 9.69 | 1.53 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 1500000 |  | 1200000 |  | 6400000 |  | 2015-01-08 13:56 |  | KY707 is a narrow winding one to two lane road. There are no guard rails along areas with 6 to 20 feet vertical drops next to two to four for shoulders. Slips are evident in at least one blind curve after cresting a hill. The current 55 mph speed limit | FIVCO ADD | East | 16.7051 | 0.21557 | 2.8743 | 3.3458 | 4.3413 | 5.9281 | 0 | 0 | 17
Y | 12 | FIVCO ADD | IP20080672 |  |  |  | To upgrade the access to the marina from KY 3 in order to better accommodate recreational traffic using the road. KY 1185 MP 0.00 to 2.232 at Yatesville Lake | Major Widening | Lawrence | 064-KY-1185 -000 | 0 | 2.232 | 2.232 | Modernize Roadway-Rural | 26 |  | 0 |  | 1100000 |  | 2500000 |  | 2420000 |  | 10800000 |  | 2015-01-08 14:22 |  | The current access to the Yatesville Lake and marina is along this existing narrow, winding two lane road with 9' lanes and 3' shoulders. This access to the marina for unfamiliar drivers does not provide safe or sufficient width for boats on trailers to p | FIVCO ADD | East | 32.5464 | 0.56287 | 6.7365 | 5.8159 | 4.2216 | 5.988 | 0 | 9.2216 | 32
Y | 12 | FIVCO ADD | IP20080673 |  |  |  | Redesign this intersection to have a single connection to KY2565 and move the intersection East of its current position, thus improving the sight distance problem. 6YHP # 12-193 R/U-2014, C-2015 SPP FUNDING | Reconstruction | Lawrence | 064-KY-2565 -000 | 3.081 | 3.231 | 0.15 | Realign Intersection | 26 |  | 0 |  | 200000 |  | 100000 |  | 110000 |  | 1265000 |  | 2015-03-17 14:39 |  | This section of road on KY2565 has a very steep horizontal curve and has been the site of several crashes and fatalities. There is a sight distance issue in this curve where traffic exits from both east and west on separate but merging roads called Elois
Y | 12 | FIVCO ADD | IP20080674 |  |  |  | Improve/widen KY-3398 from KY-3 @ Fallsburg to US-23 @ Fullers to improve safety and to accommodate residential growth and recreational vehicles in this area. | Major Widening | Lawrence | 064-KY-3398 -000 | 0 | 2.289 | 2.289 | Modernize Roadway-Rural | 26 |  | 0 |  | 800000 |  | 1200000 |  | 1650000 |  | 10580000 |  | 2010-02-25 16:51 |  | This roadway is a mountainous region of Lawrence County. The road has both steep grades and sharp horizontal curves (or, both poor vertical and horizontal roadway deficiencies). The intersection of this road at KY3 is at a camp ground, therefore this rou | FIVCO ADD | East | 36.8847 | 2.1317 | 8.5329 | 5.8608 | 4.7305 | 7.2455 | 0 | 8.3832 | 37
Y | 12 | Kentucky River ADD | IP20080676 |  |  |  | Provide a new connector at MP 12.672 on KY 805 in Jenkins to US 23. | New Route | Letcher | 067-US-0023 -000 | 0 | 4.5 | 4.5 | Construct Road in New Location | 0 | Y | 0 |  | 1015000 |  | 2436000 |  | 2230000 |  | 11670000 |  | 2010-02-25 16:51 |  | This project is to provide a new connector from MP 16.672 McPeeks Branch on KY 805 to US 23 in Jenkins. THe new route will eliminate through traffic in Jenkins, truck traffic around Burdine Elementary in Jenkins and Dorton Grade School in Pike County,m p
Y | 12 | Kentucky River ADD | IP20080677 |  |  |  | Relocation of KY 15 0.086 South of KY 15C to the Knott County Line. | Relocation | Letcher | 067-KY-0015 -000 | 1.475 | 9.216 | 7.741 | Modernize Roadway-Rural | 26 | Y | 0 |  | 16100000 |  | 24100000 |  | 12000000 |  | 148800000 |  | 2010-12-01 10:11 |  | This 9.200 mile segment of KY 15 in Letcher County is a project from the 1996 draft scoping study to widen or relocate the existing KY 15 to a four lane facility. This road was not orginally designed to carry the traffic volume that it carries today. Th
Y | 12 | Kentucky River ADD | IP20080678 |  |  |  | Correct insufficient turning radius at intersection KY 160 and KY-588 for continuous flow of traffic and freight movement. | Reconstruction | Letcher | 067-KY-0160 -000 | 15.3 | 15.6 | 0.3 | Improve Intersection | 26 |  | 0 |  | 300000 |  | 200000 |  | 100000 |  | 1200000 |  | 2010-02-25 16:51 |  | This .300 mile segment is an intersection at KY 588. This intersection handles a large volume of truck/freight movement. It has an indaquate turning radius to the point that all traffic stops when a tractor trailor approaches to make a turn. Trucks stop
Y | 12 | Kentucky River ADD | IP20080680 |  |  |  | Improve this road segment in order to eliminate the substandard curvature while improve the the roadway lane width and shoulder width. Between Cambden and Joes Branch KY 805. | Safety-Haz-Elm | Letcher | 067-KY-0805 -000 | 10.3 | 11 | 0.7 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 600000 |  | 300000 |  | 2500000 |  | 2010-02-25 16:51 |  | The problem at this segment of road is the steep horizontal curvature. This curve is much steeper than prior curves leading drivers not to expect the characteristics in this curve.
Y | 12 | Kentucky River ADD | IP20080681 |  |  |  | To alleviate the congestion along this segment of roadway to better accommodate motorist and shoppers in this area or entering into the entrances of the various businesses. As well as to reduce the occurrence of crashes. Walmart shopping area. | Congestion Management | Letcher | 067-KY-2034 -000 | 0 | 0.8 | 0.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 500000 |  | 950000 |  | 2970000 |  | 2015-07-06 09:33 | To alleviate the congestion along this segment of roadway to better accommodate motorist and shoppers in this area or entering into the entrances of the various businesses. As well as to reduce the occurrence of crashes. Walmart shopping area. | The problem is the traffic congestion resulting from a shopping area including Wal-Mart. As a result there are many low speed rear-end and right angle collisions at the entrances along this route. | KENTUCKY RIVER ADD | East | 31.2605 | 9.4491 | 11.5868 | 7.6796 | 2.5449 | 0 | 0 | 0 | 31
Y | 12 | Big Sandy ADD | IP20080682 |  |  |  | CURVE REVISION W OF THE KY 40 INTERSECTION | Spot Improvement | Martin | 080-KY-0003 -000 | 11.8 | 12.1 | 0.3 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 200000 |  | 275000 |  | 2300000 |  | 2010-02-25 16:51 | Improve safety, mobility, and reliability along KY-3 by correcting the curve west of the KY-40 intersection. | The purpose of this project is to correct a curve on KY 3, west of the KY 40 Intersection. This segment of KY 3 has an ADT of 2043. | BIG SANDY ADD | East | 25.7201 | 1.4012 | 12.0359 | 3.8398 | 4.6707 | 0 | 0 | 3.7725 | 26
Y | 12 | Big Sandy ADD | IP20080683 |  |  |  | Improve roadway alignment and geometrics from Johnson County line to junction of KY 40 and KY 645 near Inez. | Reconstruction | Martin | 080-KY-0040 -000 | 0 | 9.148 | 9.148 | Other Improvement Types | 0 |  | 0 |  | 2500000 |  | 6500000 |  | 2000000 |  | 39000000 |  | 2010-11-30 14:03 | Address safety, access, and connectivity issues on this segment of KY-40 by improving roadway alignment and geometrics. | The purpose of this project is to address the curvature, shoulder width and pavement width issues on KY 40 from the Johnson County line to KY 645 near Inez. This route is a primary link between Paintsville and Inez as reflected by the ADT of 5740. This
Y | 12 | Big Sandy ADD | IP20080684 |  |  |  | Spot improvements to curve geometrics near intersection with KY 1884. Replaces 12 080 D0040 938.00 | Safety-Haz-Elm | Martin | 080-KY-0040 -000 | 6.9 | 7.1 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 150000 |  | 110000 |  | 1470000 |  | 2015-01-08 13:06 | Improve safety, reliability, and connectivity on KY-40 between Paintsville and Inez by reconstructing the curve near the intersection with KY-1884. | The purpose of this project is a spot improvment on KY 40 from mile point 6.9 to mile point 7.1. This route is a primary link between Paintsville and Inez. | BIG SANDY ADD | East | 20.9102 | 1.3293 | 4.2216 | 1.8862 | 3.4731 | 0 | 0 | 10 | 21
Y | 12 | Big Sandy ADD | IP20080685 |  |  |  | Improve site distance/alignment and access/exit hazards from this section of KY 40, from the junction of KY 40 and KY 2032 to just past the junction of Ky 40 and Albert Pinson Road. | Spot Improvement | Martin | 080-KY-0040 -000 | 15.2 | 15.7 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 150000 |  | 240000 |  | 3100000 |  | 2015-07-06 09:45 | Improve safety and access issues along this segment of KY-40 by improving curve geometrics and sight distance. | Adequacy data indicates growing safety and condition concerns. This intersection (junction of KY 40 and KY 2032) is currently located in a very substandard curve with poor sight distance. There are no left or right turn lanes in either direction. Also, sl
Y | 12 | Big Sandy ADD | IP20080686 |  |  |  | CURVE REVISION NEAR WARFIELD | Reconstruction | Martin | 080-KY-0040 -000 | 18.8 | 19 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 100000 |  | 110000 |  | 1725000 |  | 2010-02-25 16:51 |  | The purpose of this project is a curve revision on KY 40 near the town of Warfield, KY. This curve traverses hilly terrain and limits sight distance of school buses entering and leaving Warfield Middle School.
Y | 12 | Big Sandy ADD | IP20080687 |  |  |  | Improve roadway's ability to handle truck and commuter traffic. Improve alignment/site distance/lane and shoulder width issues, from the Martin-Pike County line to the junction of KY 1439 and KY 2032. | Reconstruction | Martin | 080-KY-1439 -000 | 0 | 10.733 | 10.733 | Other Improvement Types | 0 |  | 0 |  | 5000000 |  | 8000000 |  | 4000000 |  | 48000000 |  | 2010-02-25 16:51 | Address roadway safety and increase capacity on this section of KY-1439 by improving alignment, increasing lane and shoulder width, and addressing sight distance issues. | This road is known locally as Wolfe Creek Road. It serves the major coal-producing area of Martin County. Martiki Coal, Pontiki Coal and Martin County Coal use this coal-haul road extensively. It is a winding, narrow, 2 lane rural road with less than 1
Y | 12 | Big Sandy ADD | IP20080688 |  |  |  | Improve condition/alignment and safety concerns on KY 2032 from the junction of KY 2032 and KY 1439 to the junction of KY 2032 and KY 40. | Reconstruction | Martin | 080-KY-2032 -000 | 0 | 4.04 | 4.04 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 4300000 |  | 2000000 |  | 16200000 |  | 2010-02-25 16:51 | Address safety and increase capacity on this section of KY-2032 by improving alignment and addressing sight distance issues. | This section of KY 2032 serves as an extension to the KY 1439 major coal haul route from the Wolfe Creek area in Martin County. It is a narrow, 2-lane (18ft) road with shoulder width one foot or less, winding curves and blind entrances. School buses, co
Y | 12 | Big Sandy ADD | IP20080689 |  |  |  | Address substandard roadway geometrics and pavement condition on this segment of KY 2032, from .5 miles past Ralph Moore Lane to 1.3 miles past Thickety Fork Road. | Minor Widening | Martin | 080-KY-2032 -000 | 1.9 | 3 | 1.1 | Modernize Roadway-Rural | 26 |  | 0 |  | 750000 |  | 650000 |  | 908000 |  | 6900000 |  | 2010-02-25 16:51 | Address safety and mobility issues by improving lane width, improving roadway geometrics, and improving pavement condition on KY-2032 from 0.5 miles past Ralph Moore Lane to 1.3 miles past Thickety Fork Road. | ADT on this segment of KY 2032 is 1,671 v.p.d., on two 9-foot lanes. Though not reflected in the numbers, this is a steep hill with many tight and narrow curves. There are several roadway breaks on this section of 9-foot lanes and no shoulders in many pl | BIG SANDY ADD | East | 28.229 | 2.1437 | 5.3892 | 8.241 | 4.3713 | 0 | 0 | 8.0838 | 28
Y | 12 | Big Sandy ADD | IP20080690 |  |  |  | Curve revisions at two locations near KY 40. | Safety-Haz-Elm | Martin | 080-KY-2032 -000 | 3.3 | 3.8 | 0.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 400000 |  | 200000 |  | 330000 |  | 3000000 |  | 2015-01-08 14:20 | Improve safety, mobility, and capacity along KY-2032 between mp 3.3 and 3.8 by reconstructing curves to improve sight distance and lane width. | The purpose of this project is two curve revisions on KY 2032, between mile points 3.3 and 3.8, near the intersection of KY 40. This road traverses hilly terrain and limits sight distance. This, in combination with narrow lanes and limited shoulders, make | BIG SANDY ADD | East | 19.262 | 2.1437 | 4.1317 | 3.256 | 3.3832 | 0 | 0 | 6.3473 | 19
Y | 12 | Big Sandy ADD | IP20080691 |  |  |  | Improve the access of Keyser Heights onto US 23 as discussed in the 1999 Pikeville Urban Transportation Study as a Long Range Recommended Project. MP 24.9 - 25.0. | Spot Improvement | Pike | 098-US-0023 -000 | 25.3 | 25.5 | 0.2 | Other Improvement Types | 0 | Y | 0 |  | 10000 |  | 24000 |  | 6000 |  | 160000 |  | 2010-11-30 14:27 | Address safety and mobility and mitigate congestion on this segment of US-23 by improving the access from Keyser Heights. | The entrance and exit for Keyser Heights subdivision is situated at a high-volume stretch of US 23 in Pikeville. Some delays are experienced before turning onto US 23, and rarely can the southbound lane be turned onto or from safely.
Y | 12 | Big Sandy ADD | IP20080692 |  |  |  | Spot Safety and Access Improvement project for 2.2 miles South of KY 1426 at Island Creek. This project is also identified in the 1999 Pikeville Urban Transportation Study. MP 20.741 -22.941. | Spot Improvement | Pike | 098-US-0023 -000 | 20.741 | 22.941 | 2.2 | Other Improvement Types | 0 | Y | 0 |  | 3400000 |  | 6300000 |  | 2875000 |  | 44925000 |  | 2010-11-30 14:30 | Address safety and mobility and mitigate congestion along this segment of US-23 by improving access. | Issues along this stretch of roadway are numerous entrances and heavy traffic volume in a high speed curb and gutter section of US 23 south of Pikeville. There have been many crashes and fatalities over the last several years along this portion of US 23
Y | 12 | Big Sandy ADD | IP20080693 |  |  |  | Improvements to improve safety and to realign the intersections of KY 3495 and Ratliff's Creek Road in order to better accommodate turning movements with a traffic signal. | Safety-Haz-Elm | Pike | 098-US-0023 -000 | 25.5 | 26 | 0.5 | Other Improvement Types | 0 | Y | 0 |  | 150000 |  | 700000 |  | 138000 |  | 1525000 |  | 2010-02-25 16:51 |  | This portion of US 23 allows left and right turns onto US 23. These turns and a high ADT results in many conflicts. This portion does not include barrier walls to keep traffic from turning or making U-turns anywhere along the road. Two intersections, KY
Y | 12 | Big Sandy ADD | IP20080694 |  |  |  | Reconstruct this intersection of US 119 and US 23 in order to better accommodate the flow of traffic through this portion of US 23. Identified in the 1999 Urban Transportation Study. MP 26.184 - 26.384. | New Interchange | Pike | 098-US-0023 -000 | 26.184 | 26.384 | 0.2 | Improve Intersection | 26 | Y | 0 |  | 3500000 |  | 8600000 |  | 2875000 |  | 42525000 |  | 2010-11-30 14:32 | Improve safety and access and reduce congestion in this high-traffic intersection between Thompson Road and US-23/US-460. | The problem is that this is the intersection of US 119 (Four Lane Facility) with US 23, and also with Thompson Road, which is the major shopping area in Pikeville. This location is mostly the busiest intersection on US 23 in District #12 and experiences | BIG SANDY ADD | East | 43.1108 | 9.4731 | 8.4431 | 14.8653 | 0 | 0 | 4.7605 | 5.5689 | 43
Y | 12 | Big Sandy ADD | IP20080695 |  |  |  | Improve the intersection/signal layout and entry/exit points for Thompson and Stonecoal Roads/US 23 junction and car dealership, to improve traffic flow, efficiency and safety. | New Interchange | Pike | 098-US-0023 -000 | 27.2 | 27.5 | 0.3 | Other Improvement Types | 0 | Y | 0 |  | 250000 |  | 250000 |  | 275000 |  | 2012000 |  | 2010-02-25 16:51 | Address safety, reliability, and mobility, and mitigate congestion by reconstructing this intersection between Thompson Road, Stonecoal Road, and US-23. | High ADT on this segment, on six-lanes, 12-feet in width. Truck traffic is between 10.9%. Two heavilytraveled roads,Thompson Road to the west (1 of 2 entrances to Super Wal Mart), and Stonecoal Road to the east, sit approximately 100 feet apart. This cr
Y | 12 | Big Sandy ADD | IP20080696 |  |  |  | Improve safety and traffic flow on US 460 from MP 4.1 to MP 4.4 near Sutton. | Spot Improvement | Pike | 098-US-0460 -000 | 4.1 | 4.4 | 0.3 | Other Improvement Types | 0 | Y | 0 |  | 150000 |  | 450000 |  | 470000 |  | 1610000 |  | 2015-07-06 09:52 | Address safety, mobility, and capacity along this segment of US-460. | The intersection of KY 3226 with US 460 has an increasing CRF and is identified in the August 2003 KY Transportation Report, Crash Rates at Intersections. Request for traffic signals have been made several times, but the intersection characteristics do no
Y | 12 | Big Sandy ADD | IP20080697 | 12-346 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION AT THE US-460 AND KY-1460 INTERSECTION. | MINOR WIDENING(O) | Pike | 098-US-0460 -000 | 2.57 | 2.77 | 0.2 | Improve Intersection | 26 | Y |  |  | 240000 | 2021 | 400000 | 2022 | 160000 | 2022 | 1470000 | 2024 | 2018-07-10 08:17 | Improve roadway safety and minimize congestion by constructing a left turn lane at the intersection of US-460 and KY-1460. | The problem at this US 460-KY 1460 intersection at Justiceville in Pike County, is heavy congestion due to backups created with the traffic signal and delays resulting from left turns being made only on a permissive phase in between gaps. In the meantime, | BIG SANDY ADD | East | 60.0509 | 8.5389 | 14.2814 | 13.518 | 1.6467 | 0 | 4.1317 | 2.9341 | 45 | 15
Y | 12 | Big Sandy ADD | IP20080698 |  |  |  | Correct substandard roadway geometrics to address safety and sight distance issues from .5 miles past Biggs Branch to .1 miles past Winston Branch, at the entrance to Millard Grade School. | Spot Improvement | Pike | 098-US-0460 -000 | 6.993 | 7.98 | 0.987 | Other Improvement Types | 0 | Y | 0 |  | 750000 |  | 900000 |  | 550000 |  | 5750000 |  | 2015-03-20 10:01 | Address roadway safety on this segment of US-460 by improving roadway geometrics and sight distance. | Rising ADT on this segment of US 460, with increasing truck traffic at, traveling on two 11-foot lanes. CRF indicates existing and potential safety issues on this highway segment. IRI score shows pavement deterioration. In addition, the entrance to Mill
Y | 12 | Big Sandy ADD | IP20080699 |  |  |  | Improve connectivity for motorists to access new US 460 from old US 460. | Reconstruction | Pike | 098-KY-0080 -000 | 0 | 1.5 | 1.5 | Other Improvement Types | 0 | Y | 0 |  | 500000 |  | 1000000 |  | 880000 |  | 12305000 |  | 2010-02-25 16:51 | Address safety and reliability of this segment of KY-80 and improve access to US-460 by correcting roadway geometrics and increasing lane width. | The current connector between the new US 460 and old US 460 at Belcher, along KY 80, has several deficient geometric features, including narrow lanes, poor shoulders and some unstable areas along the Russell Fork. IRI of 114 indicates increasing pavemen
Y | 12 | Big Sandy ADD | IP20080700 |  |  |  | Improve the geometrics of this roadway with spot improvments in order to allow motorists to safely travel this roadway from the Floyd County Line to the bottom of Abner Mountain. | Reconstruction | Pike | 098-KY-0122 -000 | 0.5 | 1.5 | 1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 600000 |  | 550000 |  | 9900000 |  | 2010-02-25 16:51 | Address safety and reliability on this segment of KY-122 by improving roadway geometrics and increasing lane width. | ADEQ Rating, CRF and IRI all indicate growing safety and condition concerns. The problems on this portion of road is that the road has poor horizontal and vertical deficiences (steep grade, steep curves, no shoulder, deep ditches, etc), as evidenced by
Y | 12 | Big Sandy ADD | IP20080701 |  |  |  | Improve the geometrics of this roadway with spot improvments in order to allow motorists to safely travel this roadway. MP 1.94 - 5.20. | Reconstruction | Pike | 098-KY-0122 -000 | 1.944 | 5.2 | 3.256 | Other Improvement Types | 0 |  | 0 |  | 1000000 |  | 5500000 |  | 1700000 |  | 20000000 |  | 2010-02-25 16:51 | Address safety and reliability of this segment of KY-122 by improving geometrics and increasing lane and shoulder width. | The problems on this portion of road is that the road has poor roadway features (steep curves, no shoulder, high drop-off's in creek, and several embankment failures along creek bank). This is evidenced by the ADEQ Rating and ADEQ Percentile. This route
Y | 12 | Big Sandy ADD | IP20080702 | 12-198 |  | A | IMPROVE KY 194 FROM US 119 RAMP NEAR SMITH FARMS BOTTOM (CR 1458) TO NEAR DESKINS BRANCH CULVERT. (18CCR) | RECONSTRUCTION(O) | Pike | 098-KY-0194 -000 | 17.951 | 21 | 3.049 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 4200000 | 2021 | 3120000 | 2021 | 21840000 | 2023 | 2019-03-11 16:41 | Improve safety and reliability on this segment of KY-194 by improving alignment, improving sight distance, and increasing lane and shoulder width. | This portion of KY 194 is the most heavily-traveled portion, including trucks from various mines and the cookie factory. This road is narrow with two lanes, virtually no shoulder and deep ditches. It has very sharp curves at several locations. The ADEQ | 12 | East | 86.4521 | 6.4072 | 12.3054 | 12.7096 | 3.5928 | 8.5629 | 3.7725 | 9.1018 | 56 | 15 | 15
Y | 12 | Big Sandy ADD | IP20080705 |  |  |  | This project addresses safety concerns and substandard roadway geometrics along KY 194, from the railroad crossing .15 miles before Hurricane Creek to .5 miles past the junction of KY 194 and KY 632. | Minor Widening | Pike | 098-KY-0194 -000 | 26.131 | 27.131 | 1 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 700000 |  | 550000 |  | 2650000 |  | 2016-10-31 16:16 | Address safety and reliability of this segment of KY-194 by improving geometrics and increasing lane and shoulder width. | Though no data was available, this is a heavy coal haul route. There are safety concerns on this stretch of highway and the IRI score reflects the substandard pavement condition. All these factors, along with substandard geometrics (horz. alignment of 3,
Y | 12 | Big Sandy ADD | IP20080707 |  |  |  | Ugrade this portion of roadway from Martin County Line to US 119. | Reconstruction | Pike | 098-KY-0292 -000 | 5.058 | 12.78 | 7.722 | Other Improvement Types | 0 |  | 0 |  | 5000000 |  | 7000000 |  | 2000000 |  | 36000000 |  | 2010-11-30 14:51 | Address safety and reliability of this segment of KY-292 by increasing lane and shoulder width. | This route has narrow lanes, 0-2 foot shoulders and many curves (horz. alignments of 3). This is the primary coal haul route from this part of Pike County into Martin County, and vice versa. The road is always in poor condition (high CRF and IRI).
Y | 12 | Big Sandy ADD | IP20080708 |  |  |  | Improve commuter safety on this portion of roadway over Hardy Mountain, from Blackberry Creek to Turkeytoe Branch. | Reconstruction | Pike | 098-KY-0319 -000 | 0.35 | 2.35 | 2 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 500000 |  | 550000 |  | 9800000 |  | 2010-02-25 16:51 | Improve safety and reliability on this segment of KY-319 by improving roadway geometrics and alignment and increasing lane and shoulder width. | This route has a high CRF, on a road with narrow lanes (9 feet) , steep grade (vert.alignment of 4) and 0-2 foot shoulders. Coal haul activ ity makes this a hazardous section of roadway due to poor geometrics.
Y | 12 | Big Sandy ADD | IP20080709 |  |  |  | Improve the safety at this intersection by improving geometrics of curve. | Spot Improvement | Pike | 098-KY-0468 -000 | 6.2 | 6.7 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 250000 |  | 110000 |  | 4025000 |  | 2010-02-25 16:51 | Address roadway safety at this intersection by improving the curve and increasing sight distance. | The following needs have been identified for this project: 1) Improve Roadway Safety.
Y | 12 | Big Sandy ADD | IP20080710 |  |  |  | Eliminate both the sight distance deficiencies caused by the vertical curve and the low underpasses in order to improve the flow of traffic without interruption. | Spot Improvement | Pike | 098-KY-0805 -000 | 0.45 | 0.85 | 0.4 | Other Improvement Types | 0 |  | 10000 |  | 190000 |  | 200000 |  | 220000 |  | 2875000 |  | 2010-02-25 16:51 | Improve roadway safety and mobility by addressing sight distance limitations and overpass clearance on this segment of KY-805. | CRF of and IRI indicate a potential for safety and condition concerns. This portion of road (Old US 23) includes two railroad overpasses with very restricted vertical clearances. Many times trucks delivering goods or equipment to the Elkhorn and Shelby
Y | 12 | Big Sandy ADD | IP20080711 |  |  |  | Eliminate both the sight distance dificiencies caused by the vertical curve and the safety problem created by both the bridge headwall and the steep curve. | Spot Improvement | Pike | 098-KY-0805 -000 | 1.2 | 1.5 | 0.3 | Other Improvement Types | 0 |  | 10000 |  | 150000 |  | 150000 |  | 110000 |  | 1725000 |  | 2010-02-25 16:51 | Address safety and reliability on this segment of KY-805 by increasing lane width and improving curve geometrics. | CRF and IRI indicate growing safety and condition concerns. This portion of road (Old US 23) includes walls for one former railroad overpasses in the middle of a very steep horizontal curve (horz. alignment of 3), with no shoulders and a deep ditch. Thi
Y | 12 | Big Sandy ADD | IP20080713 |  |  |  | Improve flow and efficiency, as well as eliminate flooding issues at this location on Hurricane Creek @ the Church. | Spot Improvement | Pike | 098-KY-1384 -000 | 1.5 | 2 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 200000 |  | 330000 |  | 1470000 |  | 2015-01-08 12:21 | Improve safety and reliability of this segment of KY-1384 by elevating the roadway above high water. | KY 1384 is used as a detour for US 23 when US 23 has crashes or other major slowdowns. This location is very low-lying and often subject to flood conditions.
Y | 12 | Big Sandy ADD | IP20080714 |  |  |  | Improve this curve on KY 1384 from 1/2 mile before Dog Fork to Dog Fork in order to reduce collisions and improve safety. | Spot Improvement | Pike | 098-KY-1384 -000 | 3.2 | 3.7 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 300000 |  | 220000 |  | 4600000 |  | 2010-02-25 16:51 | Improve roadway safety and reliability by improving the curve from 0.5 miles before Dog Fork to Dog Fork. | This location on KY 1384 near mile point 3.2 on KY 1384 near Hurricane Creek is in a very steep horizontal curve. This route is often used as a bypass for Pikeville when a crash stops traffic on US 23. KY 1384 is mostly a one lane road with very little
Y | 12 | Big Sandy ADD | IP20080715 |  |  |  | Improve flow and efficiency while controlling motorist's speed through this section of roadway. | Minor Widening | Pike | 098-KY-1384 -000 | 5.798 | 6.787 | 0.989 | Other Improvement Types | 0 |  | 0 |  | 70000 |  | 150000 |  | 46000 |  | 884000 |  | 2010-11-30 15:00 | Improve roadway safety and capacity along this segment of KY-1384 by widening the lanes. | This portion of experiences frequently heavy congestion. High IRI indicates pavement condition concerns. This route is through a very upscale subdivision and is often used as a detour for traffic from US 23. The thru-traffic in this route tends to travel
Y | 12 | Big Sandy ADD | IP20080716 |  |  |  | Improve this roadway in order to improve safety from junction of KY 1426 and KY 3417 to six-tenths of a mile past Coon Branch junction, as recommended in the 1999 Pikeville Urban Study. | Reconstruction | Pike | 098-KY-1426 -000 | 2 | 3.334 | 1.334 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 1000000 |  | 400000 |  | 7800000 |  | 2010-11-30 15:02 | Address safety and reliability of this segment of KY-1426 by increasing lane and shoulder width and improving sight distance. | Narrow two-lane roadway, with no shoulders and immediate drop-off's into the creek. Some sharp curves with poor sight distance. Identified in the 1999 Pikeville Urban Study.
Y | 12 | Big Sandy ADD | IP20080717 |  |  |  | Upgrade this route from junction of KY 1426 and KY 3416 to junction of KY 1426 and US 23, as identified in the 1999 Pikeville Urban Trnapsortation Study. | Reconstruction | Pike | 098-KY-1426 -000 | 3.334 | 4.889 | 1.555 | Other Improvement Types | 0 |  | 0 |  | 1240000 |  | 1650000 |  | 414000 |  | 10496000 |  | 2010-11-30 15:04 | Improve safety and reliability of this segment of KY-1426 by increasing lane and shoulder widths. | This route is narrow and has no shoulders. It has a UPS hub along the route. It is also a major coal route. Pavement along this road is very rough and detriorated (high IRI). Identified in the 1999 Pikeville Urban Study.
Y | 12 | Big Sandy ADD | IP20080718 |  |  |  | Mitigate or eliminate rockfall hazards and improve roadway for better flow and efficiency in order to handle the expected congestion arising from events at the Expo Center. Identified in the 1999 Pikeville Urban Study, from Baird to Huffman. | Minor Widening | Pike | 098-KY-1426 -000 | 5.467 | 6.187 | 0.72 | Other Improvement Types | 0 |  | 0 |  | 280000 |  | 450000 |  | 201000 |  | 3094000 |  | 2010-11-30 15:05 | Address safety and reliability on this segment of 1426 by mitigating rockfall hazards. | Identified in the 1999 Pikeville Urban Study as in need of widening and highwall stablization. This location is a continuous problem with rock falls because of the unstable vertical rock wall. As well, widening is needed for this location in order to ac
Y | 12 | Big Sandy ADD | IP20080719 |  |  |  | Mitigate or eliminate rockfall hazards and improve roadway for better flow and efficiency in order to handle the expected congestion arising from events at the Expo Center. Identified in the 1999 Pikeville Urban Study, from Baird to Huffman. | Minor Widening | Pike | 098-KY-1426 -000 | 6.187 | 7.528 | 1.341 | Other Improvement Types | 0 |  | 0 |  | 201000 |  | 375000 |  | 86000 |  | 2213000 |  | 2010-11-30 15:07 | Address safety and reliability of this segment of KY-1426 my mitigating rockfall hazards. | CRF and IRI both evidences need for safety/condition improvements. Identified in the 1999 Pikeville Urban Study as in need of widening and highwall stablization. This location is a continuous problem with rock falls because of the unstable vertical rock
Y | 12 | Big Sandy ADD | IP20080720 |  |  |  | Mitigate or eliminate rockfall hazards and improve roadway for better flow and efficiency in order to handle the expected congestion arising from events at the Expo Center. Identified in the 1999 Pikeville Urban Study, from Bill King Rd. to US 119. | Reconstruction | Pike | 098-KY-1426 -000 | 7.528 | 9.638 | 2.11 | Other Improvement Types | 0 |  | 0 |  | 1600000 |  | 2400000 |  | 800000 |  | 15200000 |  | 2010-11-30 15:09 | Address safety and reliability on this segment of KY-1426 by mitigating rockfall hazards. | CRF and IRI indicate safety and condition concerns. Identified in the 1999 Pikeville Urban Study as in need of reconstruction. This location is a continuous problem with rock falls, a steep grade and several sharp curves. This route will also be used by
Y | 12 | Big Sandy ADD | IP20080721 |  |  |  | Address alignment, safety and geometric concerns of KY 1460 at mountain crossing in Pikeville. | Reconstruction | Pike | 098-KY-1460 -000 | 2.5 | 3.3 | 0.8 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 500000 |  | 360000 |  | 4820000 |  | 2015-07-06 09:51 | Address safety and reliability of this segment of KY-1460 by improving roadway alignment and geometrics. | The purpose of this project is to address the the safety issue of the mountain crossing on KY 1460 between Upper Chloe Rd and Fife Fork Rd, a primary link between US 119 and the City of Pikeville. This section of roadway presents various safety issues
Y | 12 | Big Sandy ADD | IP20080722 |  |  |  | Reconstruct and raise roadway above high water from Walters Road to KY 1426 in Pikeville. | Reconstruction | Pike | 098-KY-1460 -000 | 3.801 | 5.07 | 1.269 | Other Improvement Types | 0 |  | 0 |  | 920000 |  | 1270000 |  | 460000 |  | 9500000 |  | 2015-01-08 13:31 | Address safety and reliability on this segment of KY-1460 by elevating the roadway above high water. | This project will address the flooding problem on KY 1460 between milepoint 3.801 (Walters Road) and mile point 5.070 (KY 1426 :Town Mountain Road). The high CRF indicates that crashes are occurring at a high rate along this narrow, curvy road with no sh
Y | 12 | Big Sandy ADD | IP20080723 |  |  |  | Widen this curve on KY 1460 in order to improve sight distance and to improve superelevation in order to reduce crashes. | Spot Improvement | Pike | 098-KY-1460 -000 | 4.2 | 4.5 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 50000 |  | 55000 |  | 1670000 |  | 2010-02-25 16:51 | Address safety, reliability, and mobility along this segment of KY-1460 by widening the curve and improving sight distance. | This location on KY 1460 is a narrow 2 lane road with 10 foot lanes and and no shoulder. Chloe Creek is immediately on the right and a steep rock mountain is on the left. This location is a very steep curve with no superelevation and inadaquate sight di
Y | 12 | Big Sandy ADD | IP20080724 |  |  |  | Improve substandard geometrics in the curve near Marshall Branch. | Safety-Haz-Elm | Pike | 098-KY-1469 -000 | 4.9 | 5.199 | 0.299 | Other Improvement Types | 0 |  | 0 |  | 97000 |  | 180000 |  | 55000 |  | 1120000 |  | 2015-01-08 13:46 | Address safety, reliability, and mobility on this segment of KY 1469 by correcting the curve alignment and increasing lane and shoulder width. | This project will correct a hazardous curve on KY 1469 near Long Fork of Marshall Branch, at mile point 5.0 to mile point 5.1. This road is restricted by both the 8 foot lane widths and 2 foot shoulders.
Y | 12 | Big Sandy ADD | IP20080725 |  |  |  | RELOCATION BEGINNING APPROX. 0.2 MI E OF KY 194 NEAR WOODMAN | Relocation | Pike | 098-KY-2059 -000 | 0.2 | 0.5 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 150000 |  | 100000 |  | 650000 |  | 2012-01-30 13:35 | Address safety and access issues on this segment of KY-2059 by improving sight distance and increasing lane and shoulder width. | This project will address the need to relocate a section of KY 2059 near the community of Woodman.
Y | 12 | Big Sandy ADD | IP20080726 |  |  |  | Improve geometrics and alignment of curve, from two-tenths of mile before Johns Creek Bridge to junction of KY 2061 and KY 194 on Lower Johns Creek. | Spot Improvement | Pike | 098-KY-2061 -000 | 6.937 | 7.14 | 0.203 | Other Improvement Types | 0 |  | 0 |  | 130000 |  | 305000 |  | 109000 |  | 1641000 |  | 2010-11-30 15:17 | Address safety and reliability of this segment of KY-2061 by improving curve geometrics. | The problem at this location is the sharp S-Curve connecting to the deficient one-lane bridge at the intersection with KY 194. This route has 0-2 foot shoulders. It is the main access to the only public Golf Course in Pike County as well as the headwater
Y | 12 | Big Sandy ADD | IP20080727 |  |  |  | Address alignment, safety and geometric issues from KY 194 at Jamboree to KY 194 at Stopover. | Reconstruction | Pike | 098-KY-2062 -000 | 0 | 3.132 | 3.132 | Other Improvement Types | 0 |  | 0 |  | 2850000 |  | 4600000 |  | 2140000 |  | 26060000 |  | 2010-11-30 15:19 | Improve the safety and reliability of this segment of KY-2062 by improving roadway geometrics and increasing lane and shoulder width. | This project will address the need to reconstruct a section of KY 2059 from KY 194 near Jamboree to KY 194 at Stopover. Various issues with sharp curves and steep grades, combined with the narrow 9 foot lanes and 2 foot shoulders, create hazards for mot
Y | 12 | Big Sandy ADD | IP20080728 |  |  |  | Address access issues from KY 3414 to US 23 at Beef hide, allowing for safer movement of coal and better conectivity for locals. | New Route | Pike | 098-KY-3414 -000 | 1.718 | 3.406 | 1.688 | Other Improvement Types | 0 |  | 0 |  | 1210000 |  | 2070000 |  | 860000 |  | 13110000 |  | 2010-11-30 15:20 | Address roadway safety and increase capacity by increasing lane and shoulder width and addressing access issues on this segment of KY-3414. | KY 3414 (Petty Fork) that connects with KY 1469 (Long Fork) both experience heavy mining activity. The current route is back to KY 610 then to the coal processing facility near US 23. This one and two lane facility does not adaquately accommodate trucks
Y | 12 | Big Sandy ADD | IP20080729 |  |  |  | Address alignment and geometric concerns from KY 1426 to KY 1384 in Pikeville. See 1999 Pikeville Urban Transportation Study. | Reconstruction | Pike | 098-KY-3417 -000 | 0 | 1.104 | 1.104 | Other Improvement Types | 0 |  | 0 |  | 610000 |  | 840000 |  | 304000 |  | 5846000 |  | 2010-11-30 15:29 | Address safety and reliability of this segment of KY-3417 by improving alignment and increasing lane and shoulder width. | This project will address various issues with curvature, lane width, pavement deterioration and shoulders along KY 3417.
Y | 12 | Big Sandy ADD | IP20080730 |  |  |  | RELOCATION TO PROVIDE IMPROVED ACCESS TO FISHTRAP LAKE FROM KY 194 TO KY 1441 | Reconstruction | Pike | 098-KY-3418 -000 | 0 | 10 | 10 | Other Improvement Types | 0 |  | 0 |  | 6900000 |  | 12070000 |  | 4300000 |  | 62930000 |  | 2010-11-30 15:31 | Address safety, reliability, and mobility of this segment of KY-3418 by improving alignment and increasing lane and shoulder width. | This project will address various issues with curvature, lane width, pavement deterioration and shoulder conditions along KY 3418, from KY 194 to KY 1441.
Y | 12 | Big Sandy ADD | IP20080731 |  |  |  | Reduce congestion, improve condition and increase motorist safety on this segment of KY 3495, from the temination of the US 23/KY 3495 exit ramp north 0.3 miles on KY 3495 to just past Pikeville High School. | Safety-Haz-Elm | Pike | 098-KY-3495 -000 | 0 | 0.3 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 220000 |  | 253000 |  | 490000 |  | 2015-01-08 14:11 | Address safety and reliability and mitigate congestion on this segment of KY-3495 by increasing lane and shoulder widths and adding a left turn lane for school traffic. | This segment suffers extreme congestion in the morning and afternoon hours, as this is the only access route to and from Pikeville High School. Lack of a left-hand turn lane further aggravates the congestion issue during these hours. This heavy cyclical t
Y | 12 | Big Sandy ADD | IP20080750 |  |  |  | Add new system mileage in the form of a connector link between Big Sandy Regional Airport and the Honey Branch Industrial park, utilizing reclaimed strip-mined ridgetop. | New Route | Martin | 080-CR-1237 -000 | 1.155 | 2.968 | 1.813 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 250000 |  | 50000 |  | 2000000 |  | 2011-01-11 14:50 | Improve safety and mobility by constructing a connector between the Big Sandy Regional Airport and the Eastern Kentucky Business Park. | This project would add new system mileage by establishing a link between the Big Sandy Regional Airport and the Eastern Kentucky Business Park in Martin County, improving economic development opportunities. It would also create a more efficient route be
Y | 12 | Big Sandy ADD | IP20100014 |  |  |  | Provide a new connector from KY 122 at Minnie to KY 979 near Harold. Section 2 is one section of three for this total project. | New Route | Floyd | 036-KY-0979 -000 | 11.421 | 14.081 | 2.66 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 2750000 |  | 605000 |  | 32200000 |  | 2011-01-11 15:06 |  | This is one section of a new connector from KY 122 at Minnie to KY 979 at Harold. Presently, this traffic uses KY 979 and KY 680 which is a rural two lane route with many substandard curves and mountain crossings. The new route will be much less distanc
Y | 12 | Big Sandy ADD | IP20100016 |  |  |  | Address alignment and geomtrics concerns from new US 23 to new US 460. | Reconstruction | Pike | 098-KY-0122 -000 | 10.9 | 12 | 1.1 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 800000 |  | 400000 |  | 4800000 |  | 2010-12-03 14:41 | Address safety and mobility by reconstructing KY-122 from US-23 to new US-460. | The purpose of this project is to address the reconstruction of KY 122 from new US 23 to new US 460. KY 122 is a primary link between Cardinal East and Cardinal North principle arterial highways. This segment of KY 122 is characterized by sharp curves,
Y | 12 | Big Sandy ADD | IP20110001 |  |  |  | Improve roadway geometrics from mp 9.15 to mp 10.68. | Reconstruction | Johnson | 058-KY-0040 -000 | 9.15 | 9.155 | 0.005 | Other Improvement Types | 0 |  | 0 |  | 1200000 |  | 3300000 |  | 4000000 |  | 11300000 |  | 2011-01-11 15:53 | Address safety and access issues and mitigate congestion along this section of KY-40. | This project will mitigate certain substandard roadway geometrics between mps 9.15 and 10.68, as well as provide easier access/egress to the City of Paintsville, Paintsville Independent Schools, Johnson Central Middle and High Schools and Paul B. Hall Med
Y | 12 | Big Sandy ADD | IP20110002 |  |  |  | Provide alternate means to access/egress the Johnson Central Middle and High Schools campus. | New Route | Johnson | 058-KY-0321 -000 | 7.893 | 8.231 | 0.338 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 200000 |  | 510000 |  | 3700000 |  | 2011-01-11 15:48 | Address safety and access issues, mitigate congestion, and facilitate economic development by constructing an alternate access to the high and middle school campuses, relieving congestion on KY-321. | This project is to construct a new bridge connecting the Johnson Middle and High School campus, and KY 321, to KY 40. This will provide congestion relief to KY 321 as well as provide alternate means of entering and exiting the school campus.
Y | 12 | Kentucky River ADD | IP20110062 |  |  |  | Reconstruct section with sharp curve at KY 463 intersection with KY 510. | Safety-Haz-Elm | Letcher | 067-KY-0463 -000 | 0.537 | 0.737 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 200000 |  | 200000 |  | 300000 |  | 700000 |  | 2011-09-15 12:27 |  | Correct safety issues at the intersection of KY 462 and KY 510.
Y | 12 | Kentucky River ADD | IP20110150 |  |  |  | Eliminate rockfall hazards 0.2 mile west of Intersection of KY 1087 & KY 80. | Safety-Haz-Elm | Knott | 060-KY-0080 -000 | 11.62 | 11.74 | 0.12 | Maintenance Improvement | 10 | Y | 0 |  | 100000 |  | 100000 |  | 100000 |  | 600000 |  | 2011-09-14 15:12 |  | This location experiences numerous rockfall incidents of varying severity, especially during heavy rain or freeze/thaw cycles.
Y | 12 | Kentucky River ADD | IP20110151 |  |  |  | Eliminate rockfall hazards from kY 2029 to Rock Fork Road. | Safety-Haz-Elm | Knott | 060-KY-0080 -000 | 14.69 | 16 | 1.31 | Maintenance Improvement | 10 | Y | 0 |  | 200000 |  | 500000 |  | 600000 |  | 5200000 |  | 2011-09-15 10:23 |  | This location suffers numerous rockfall incidents of varying severity, especially during heavy rain or freeze/thaw cycles.
Y | 12 | Kentucky River ADD | IP20110152 |  |  |  | Curve revision 3.654 miles east of intersection of KY 3209 & KY 1087. | Safety-Haz-Elm | Knott | 060-KY-1087 -000 | 5.05 | 5.25 | 0.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 100000 |  | 200000 |  | 100000 |  | 800000 |  | 2011-09-15 10:46 |  | This location is characterized by a hazardous curve with substandard geometrics and poor sight distance.
Y | 12 | Kentucky River ADD | IP20110153 |  |  |  | Curve revisions at three locations between Eagle Road and Cookville Road. | Safety-Haz-Elm | Letcher | 067-KY-0931 -000 | 14.5 | 16 | 1.5 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 400000 |  | 300000 |  | 2900000 |  | 2015-01-08 13:58 | Curve revisions at three locations between Eagle Road and Cookville Road. | These three locations are characterized by hazardous curves with substandard geometrics and poor sight distance. | KENTUCKY RIVER ADD | East | 32.8877 | 4.1677 | 10.509 | 6.9835 | 4.8802 | 0 | 0 | 6.3473 | 33
Y | 12 | Big Sandy ADD | IP20110154 |  |  |  | Curve revision at Coal Hollow Rd. intersection. | Safety-Haz-Elm | Pike | 098-KY-0194 -000 | 13.711 | 14.089 | 0.378 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 200000 |  | 200000 |  | 1350000 |  | 2015-01-08 14:03 | Address safety and reliability of this segment of KY-194 by revising the curve at Coal Hollow Road intersection. | This location is characterized by a hazardous curve with substandard geometrics and poor sight distance.
Y | 12 | Big Sandy ADD | IP20110158 |  |  |  | Improve safety and curve geometrics at the Midas curve 0.6 miles south of KY 850. | Safety-Haz-Elm | Floyd | 036-KY-0550 -000 | 1.35 | 1.55 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 200000 |  | 300000 |  | 750000 |  | 2015-01-08 12:58 | Address safety and reliability on this section of KY-550 by improving curve geometrics and sight distance at the Midas Curve 0.6 miles south of KY-850. | This location is characterized by a hazardous curve with substandard geometrics and poor sight distance.
Y | 12 | Big Sandy ADD | IP20110159 |  |  |  | Reconstruct this section of KY 195 characterized by a sharp curve and dropoff to creek level. | Safety-Haz-Elm | Pike | 098-KY-0195 -000 | 10.65 | 10.89 | 0.24 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 200000 |  | 300000 |  | 960000 |  | 2015-01-08 13:17 | Address safety on this segment of KY-195 by improving curve alignment and increasing shoulder width. | This location has a bad curve with substandard geometrics, and little to no recovery room, due to dropoff to creek level.
Y | 12 | Big Sandy ADD | IP20110160 |  |  |  | Reconstruct to improve sight distance at US 23/Daniels Creek Road intersection. | Safety-Haz-Elm | Floyd | 036-US-0023 -000 | 8.662 | 8.859 | 0.197 | Modernize Roadway-Rural | 26 | Y | 0 |  | 200000 |  | 400000 |  | 400000 |  | 1750000 |  | 2015-01-08 13:27 | Address safety and access issues by improving sight distance at the US 23 and Daniels Creek Road intersection. | This location has a hidden entrance to NB traffic on US 23 at the Daniels Creek Road intersection. NB traffic suffers from minimal site distance to slow-moving traffic entering US 23 NB or crossing their lanes to US 23 SB. Traffic entering from Daniels | BIG SANDY ADD | East | 26.3323 | 8.024 | 5.1198 | 3.0988 | 0.41916 | 0 | 4.8204 | 4.8503 | 26
Y | 12 | FIVCO ADD | IP20120001 |  |  |  | Provide a connection over the Big Sandy River to KY 52 in WV north of Louisa in order to alleviate the congestion problem caused by trucks in downtown Louisa. | New Route | Lawrence | 064-KY-0003S -000 | 0 | 0.135 | 0.135 | Other Improvement Types | 0 |  | 0 |  | 800000 |  | 200000 |  | 220000 |  | 5865000 |  | 2012-03-07 09:30 |  | Traffic, especially coal trucks coming from WV, currently enter and leave KY va KY 3 through Lousia creating congestion in downtown.
Y | 12 | Big Sandy ADD | IP20120009 |  |  |  | Improve the access/egress, and provide a secondary entrance/exit to and from the community of Auxier through the construction of a new bridge over the Levisa Fork of the Big Sandy River; and relocation of an approximately 1 1/2-mile stretch of existing KY | Relocation | Floyd | 036-KY-3051 -000 | 0.775 | 2.2 | 1.425 | Other Improvement Types | 0 |  | 0 |  | 600000 |  | 600000 |  | 250000 |  | 3000000 |  | 2013-01-28 13:44 | Improve connectivity and reliability by constructing an additional access bridge between KY-3/KY-321 and KY-3051 to Auxier. | The community of Auxier presently only has one access/egress, which is over an old, inadequate bridge to KY 321, which also is the site of one of the state's higher-rated rockfall hazards. This hazardous for the residents of Auxier in that, should a ship
Y | 12 | Kentucky River ADD | IP20120023 |  |  |  | Reconstruct intersection with KY 3401 and add turn lane for Parkway Inn Motel access. | Reconstruction | Letcher | 067-KY-0015 -000 | 3.621 | 4.018 | 0.397 | Improve Intersection | 26 | Y | 0 |  | 250000 |  | 275000 |  | 275000 |  | 1300000 |  | 2015-01-08 13:54 | Reconstruct intersection with KY 3401 and add turn lane for Parkway Inn Motel access. | Correct sight distance issues at the intersection of KY 15 and KY 3401. Provide a safe lane for motorists turning into the Parkway Inn. | KENTUCKY RIVER ADD | East | 57.2754 | 9.5808 | 14.1916 | 8.8922 | 0.41916 | 0 | 4.521 | 4.6707 | 42 | 15
Y | 12 | Kentucky River ADD | IP20120024 |  |  |  | Reconstruct intersection with KY 15 at Isom. | Reconstruction | Letcher | 067-KY-0007 -000 | 13.397 | 14.257 | 0.86 | Modernize Roadway-Rural | 26 | Y | 0 |  | 300000 |  | 300000 |  | 300000 |  | 1300000 |  | 2015-01-08 13:59 |  | Correct sight distance and safety issues at both intersections of KY 7 and KY 15 in Isom. There have been fatalities at the north intersection.
Y | 12 | Big Sandy ADD | IP20150001 |  |  |  | Make safety spot improvements at this high crash location. Priority 7 of 8 of recommended spot improvement in referenced study. | Reconstruction | Pike | 098-KY-0632 -000 | 0.1 | 0.6 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 400000 |  | 300000 |  | 5186000 |  | 2016-11-01 09:21 | Address safety and improve mobility in this segment of KY-632 by reconstructing the curve from MP 0.1 to 0.6. | Spot 6—(MP 0.1 to MP 0.6). The Spot 6 improvement consists of a 0.5-mile- long curve reconstruction with a cost estimate of approximately $6.3 million (nearly 50% for earthwork).
Y | 12 | Big Sandy ADD | IP20150002 |  |  |  | Make safety spot improvements at this high crash location. Priority 4 of 8 of recommended spot improvement in referenced study. Spot 7, Section 3. | Spot Improvement | Pike | 098-KY-0632 -000 | 1.38 | 1.91 | 0.53 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 450000 |  | 350000 |  | 2924000 |  | 2016-11-01 09:29 | Address safety and mobility on this segment of KY-632 by revising two curves between MP 0.21 to MP 4.0. | Spot 7—(MP 1.4 to MP 1.9). Spot 7 improves two curves near the Huff Processing Plant and their coal stock pile location. This proposed alignment widens to the north for about 0.5 mile. The cost estimate is over $4.0 million (35% earthwork).
Y | 12 | Big Sandy ADD | IP20150003 |  |  |  | Make safety spot improvements at this high crash location. Priority 1 of 8 of recommended spot improvement in referenced study. Spot 8, Section 3. | Spot Improvement | Pike | 098-KY-0632 -000 | 2.6 | 3.2 | 0.6 | Modernize Roadway-Rural | 26 |  | 0 |  | 350000 |  | 440000 |  | 330000 |  | 4734000 |  | 2017-05-17 12:43 | Improve roadway safety, improve access, and increase capacity along this section of KY-194/KY-632 by eliminating a reverse curve. | Spot 8—(MP 2.7 to MP 3.2). Spot 8 removes a reverse curve. The existing westbound approach to this spot location has a passing lane that ends in a curve, just before a rock wall. This spot location has been mentioned by multiple stakeholders as a problem | BIG SANDY ADD | East | 40.5284 | 4.4431 | 12.5749 | 10.1272 | 4.1916 | 0 | 3.4431 | 5.7485 | 40
Y | 12 | Big Sandy ADD | IP20150004 |  |  |  | Make safety spot improvements at this high crash location. Priority 2 of 8 of recommended spot improvement in referenced study. Spot 9, Section 4. | Spot Improvement | Pike | 098-KY-0632 -000 | 5.3 | 5.7 | 0.4 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 400000 |  | 300000 |  | 1520000 |  | 2016-11-01 09:32 | Address safety, reliability, and mobility on this segment of KY-632 by widening the lane and shoulder through the reverse curve. | Spot 9—(MP 5.3 to MP 5.7). This improvement would widen KY 632 through a reverse curve. The widening would be to the north to minimize impacts to the stream. The cost estimate is $2.37 million (21% earthwork).
Y | 12 | Big Sandy ADD | IP20150005 |  |  |  | Make safety spot improvements at this high crash location. Priority 3 of 8 of recommended spot improvement in referenced study. Spot 10, Section 5. | Spot Improvement | Pike | 098-KY-0632 -000 | 11.5 | 12 | 0.5 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 400000 |  | 300000 |  | 2913000 |  | 2016-11-01 09:34 | Address the safety, reliability, and mobility of KY-632 by increasing lane and shoulder width and adding turn lanes for the school. | Spot 10—(MP 11.5 to MP 12.0). This spot improvement is located at the Phelps school complex. The proposed spot improvement uses the existing KY 632 alignment and introduces turning lanes (left and right) at the high school and the elementary school. The t
Y | 12 | Big Sandy ADD | IP20150356 | 12-8705 / 12-8705 |  | A | IMPROVE CONNECTIVITY BETWEEN THOMPSON ROAD AND US-23 AT STONECOAL.(12CCN)(14CCR)(16CCR) | NEW ROUTE(O) | Pike | 098-US-0023 -000 | 26.5 | 28.5 | 2 | Realign Intersection | 26 | Y |  |  | 0 |  | 5000000 |  | 1460000 | 2024 | 13920000 | 2024 | 2019-03-06 08:26 | To reduce congestion, improve safety and increase access to the local shopping and housing locations on Thompson Road. | Decrease crashes and relieve local traffic congestion and wait times to at the double traffic signals at US 23, Stone Coal and Thompson Roads. | 12 | East | 67.6332 | 8.8383 | 0 | 13.9446 | 0 | 10 | 4.8503 | 0 | 38 | 15 | 15
Y | 12 | Big Sandy ADD | IP20150357 |  |  |  | PIKEVILLE TO VA STATE LINE; US 460/KY 80; MAINLINE BRIDGES OVER KY 195 @ MARROWBONE CREEK. (SECTION 5B) (2014BOP) | Relocation | Pike | 098-US-0460 -000 | 0 | 1 | 1 | Construct Road in New Location | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 15000000 |  | 2016-10-31 15:41 | Improve regional connectivity and increase capacity by relocating this segment of US-460. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 12 | Big Sandy ADD | IP20150429 | 12-198 |  | A | IMPROVE KY 194 FROM US 119 RAMP NEAR SMITH FARMS BOTTOM (CR 1458) TO NEAR DESKINS BRANCH CULVERT. (18CCR) | RECONSTRUCTION(O) | Pike | 098-KY-0194 -000 | 17.951 | 21 | 3.049 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 4200000 | 2021 | 3120000 | 2021 | 21840000 | 2023 | 2019-03-11 16:41 | Address safety, reliability, and mobility on this segment of KY-194 by improving geometrics, increasing sight distance, and improvement pavement at various locations. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 12 | Big Sandy ADD | IP20160155 |  |  |  | BRIDGE OFF OF KY-1428 ACROSS LEVISA FORK TO SERVE BIG SANDY WASTEWATER TREATMENT PLANT. (14CCN) | Economic Development | Floyd | 036-KY-1428 -000 | 1.032 | 1.129 | 0.097 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-19 15:46 | Facilitate infrastructure and economic development by constructing a new bridge to serve the Big Sandy Wastewater Treatment Plant. | Construction of the Big Sandy Wastewater plant at this location is contingent on providing an access bridge.
Y | 12 | Big Sandy ADD | IP20160161 |  |  |  | PIKEVILLE TO VA. STATE LINE; US460/KY80 FROM KY-195 TO EAST OF POND CREEK - SECTION 6A-2 BRIDGE AT POND CREEK.(14CCR) | Relocation | Pike | 098-US-0460 -000 | 0 | 25.325 | 25.325 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-20 09:20 | Improve regional connectivity and mobility by relocating this segment of US-460. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 12 | Big Sandy ADD | IP20160163 |  |  |  | PIKEVILLE TO VA. STATE LINE; US 460/KY 80 AT BEAVER CREEK NEAR BEAVER BOTTOM (SECTION 7A-2), RAMP 2, GRADE, DRAIN AND SURFACING.(14CCR)(16CCR) | Relocation | Pike | 098-US-0460 -000 | 0 | 25.325 | 25.325 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-20 09:27 | Improve regional connectivity and mobility by relocating this segment of US-460. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 12 | Big Sandy ADD | IP20160164 |  |  |  | PIKEVILLE TO VA. STATE LINE; US460/KY80 IN VIRGINIA FROM VIRGINIA STATE LINE TO BREAKS INTERSTATE PARK (SECTION 9V). (KYTC SHARE) (GRADE & DRAIN ONLY) | Relocation | Pike | 098-US-0460 -000 | 0 | 25.325 | 25.325 | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-20 09:30 | Improve regional connectivity and reliability by relocating this segment of US-460. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity.
Y | 12 | Big Sandy ADD | IP20180040 | 12-80000 |  | A | CONSTRUCT NEW INTERSECTION ON US-23 AT THE ENTRANCE TO BETSY LANE HIGH SCHOOL(18CCN) | SAFETY(P) | Floyd | 036-US-0023 -000 | 3.1 | 3.2 | 0.1 | Improve Intersection | 26 | Y |  |  | 250000 | 2020 | [6 empty] | 2018-07-10 08:18 | To increase safety at the intersection of US 23 and the Betsy Layne High School access road. | The lack of horizontal sight distance to the south and the high speed of traffic on US 23 has caused concern with in the local community. | General Assembly | East | 18.9172 | 6.9941 | 0 | 3.6391 | 0 | 0 | 4.7929 | 3.4911 | 19
Y | 12 | Kentucky River ADD | IP20180085 |  |  |  | Road improvements on KY 588 from Tolson Branch to the intersection of KY 588 and KY 160 in the Roxana community. A federal prison is planned to be built in this area. | Spot Improvement | Letcher | 067-KY-0588 -000 | 4 | 5.009 | 1.009 | [14 empty] | Road improvements on KY 588 from Tolson Branch to the intersection of KY 588 and KY 160 in the Roxana community. A federal prison is planned to be built in this area. | Road improvements on KY 588 from Tolson Branch to the intersection of KY 588 and KY 160 in the Roxana community. A federal prison is planned to be built in this area.
Y | 12 | FIVCO ADD | IP20190039 |  |  |  | New route to extend Chapman Street (CR 1112) at York Hollow Road to Walbridge Road (CR 1110). 1.52 miles | New Route | Lawrence | 064-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 300000 |  | 75000 |  | 75000 |  | 750000 |  | 2019-02-15 13:32 | Improve connectivity, and decrease travel time of Lawrence County Road system. | Connect the existing road system at the York Hollow and Old Walbridge and decrease emergency vehicle travel time, and establish a through route.
Y | 12 | FIVCO ADD | IP20190045 |  |  |  | New Route KY 645 from existing US 23, KY 645 at Ulysses to the Industrial Park Road east of Grayson using KY 201 and KY 1. 33 miles | New Route | Lawrence | 064-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 41250000 |  | 16500000 |  | 16500000 |  | 660000000 |  | 2019-02-15 13:02 | To improve connectivity, promote tourism, stimulate economic development, and provide access to medical centers and higher learning facilities. | Improved direct connection between areas of Lawrence and Martin Counties to the Industrial Parkway KY 67 in Carter County.
Y | 12 | FIVCO ADD | IP20190046 |  |  |  | Construct extension of KY 1185 from Boy Scout Road at Yatesville Lake to around the headwaters of the lake to KY 3215. 4.23 miles | New Route | Lawrence | 064-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 500000 |  | 50000 |  | 100000 |  | 13000000 |  | 2019-02-28 13:46 | Increase connectivity between KY-3215 and KY-1185 at Yatesville Lake. | Decrease travel time between the lake marina and the State Park area.
Y | 12 | Big Sandy ADD | IP20190074 |  |  |  | New Route. Construct new connectivity from KY-321 at MP 8.18 to KY-40 at MP 9.75 at the mouth of Garbage Hollow. | New Route | Johnson | 058-KY-0321 -000 | 8.18 | 8.2 | 0.02 | Construct Road in New Location | 0 |  | 0 |  | 750000 |  | 300000 |  | 750000 |  | 5000000 |  | 2019-02-28 10:50 | Increase capacity, safety, and connectivity between KY-321 near the school to KY-40 near Garbage Hollow with new route. | Improve connectivity and reduce travel time between KY-321 at school to downtown Paintsville.
Y | 12 | Big Sandy ADD | IP20190076 |  |  |  | Improve roadway geometrics and capacity on KY-40 from KY-321 to Garbage Hollow. | Reconstruction | Johnson | 058-KY-0040 -000 | 9.15 | 9.8 | 0.65 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 750000 |  | 500000 |  | 750000 |  | 6000000 |  | 2019-02-28 10:06 | Increase capacity, safety, and connectivity between KY-321 on KY-40 past Tays Branch to Garbage Hollow. | Improve roadway geometrics and safety of the KY-40
Y | 12 | Big Sandy ADD | IP20190077 |  |  |  | Improve roadway geometrics and capacity from Garbage Hollow to East of Mill Street. | Reconstruction | Johnson | 058-KY-0040 -000 | 9.8 | 10.7 | 0.9 | Modernize Roadway-Urban | 16 |  | 0 |  | 800000 |  | 2500000 |  | 3000000 |  | 7000000 |  | 2019-02-28 10:31 | Increase capacity, safety, and connectivity between Garbage Hollow area on KY-40 to Third Street past Mill Street in Paintsville. | Improve geometrics and safety of KY-40 west of Paintsville.
Y | 12 | Big Sandy ADD | IP20190147 |  |  |  | Address safety concerns, substandard roadway geometrics, and pavement conditions on KY-908 from Reservoir Road to Helen Mills Road. 1.5 miles | Spot Improvement | Martin | 080-KY-0908 -000 | 6.7 | 8.2 | 1.5 | Local Roadway Improvements | 3 |  | 0 |  | 250000 |  | 75000 |  | 100000 |  | 750000 |  | 2019-02-28 15:04 | Increase safety, and improve alignment at various locations. | Improve roadway safety and improve geometry to allow for larger vehicles to travel roadway.
N; Mega | 1 | Purchase ADD | IP20150296 | 1-25 |  | A | IMPROVE THE PURCHASE PARKWAY AT THE KENTUCKY/TENNESSEE LINE TO SOUTHWEST OF THE US-51 INTERCHANGE.(I-69 CORRIDOR IMPROVEMENT)(2012BOP) | RECONSTRUCTION(O) | Fulton | 038-JC-9003 -000 | 0 | 1.66 | 1.66 | Full Control to Interstate | 10 | Y | 0 |  | 2500000 |  | 2320000 | 2024 | 1130000 | 2025 | 23400000 | 2025 | 2018-07-10 08:18 |  |  | 1 | Statewide | 33.3667 | 1.4802 | 4.9339 | 3.5518 | 5.859 | 0 | 6.696 | 10.8457
N; Mega | 1 | Purchase ADD | IP20150376 | 1-26 |  | A | IMPROVE THE PURCHASE PARKWAY FROM SOUTHWEST OF THE US-51 INTERCHANGE TO CARDINAL ROAD NEAR MAYFIELD INCLUDING THE KY-339 INTERCHANGE IN WINGO, KY. (I-69 CORRIDOR IMPROVEMENT) (2012BOP) | RECONSTRUCTION(O) | Graves | 042-JC-9003 -000 | 8.352 | 20 | 11.648 | Full Control to Interstate | 10 | Y |  |  | 0 |  | 830000 | 2023 | 500000 | 2023 | 17550000 | 2025 | 2018-07-10 08:18 | RECONSTRUCT ELEMENTS OF THE EXISTING PURCHASE PARKWAY BETWEEN MP 1 AND MP 20 INCLUDING THE RECONSTRUCTION OF THE KY339 INTERCHANGE IN WINGO, KY. (I-69 CORRIDOR IMPROVEMENT) (2012BOP) | Upgrade Purchase Parkway to interstate standards. Remove former toll booth interchage at Wingo and replace with interstate standard on / off ramps. | 1 | Statewide | 47.3748 | 2.0969 | 12.7753 | 9.0198 | 1.8062 | 0 | 7.1366 | 14.54
N; Mega | 2 | Evansville-Henderson MPO | IP20150240 | 2-1088.10 |  | A | DEVELOP ALIGNMENT FOR I-69 HENDERSON/EVANSVILLE OHIO RIVER CROSSING (TO BE DEVELOPED IN CONCERT WITH 2-1088.00).(16CCR)(C-COST=$1.0 BILLION; KYTC SHARE $600 MILLION) | NEW ROUTE(O) | Henderson | 051-US-0041 -000 | 19.179 | 20.207 | 1.028 | Transportation Studies | 0 | Y |  |  | 0 | 2019 | 20000000 | 2021 | 15000000 | 2022 | 99999999 | 2025 | 2018-07-10 08:18 | To improve mobility access and safety | To provide a connection across the river for I-69. | 2 | Statewide | 35.9119 | 12.1233 | 0 | 7.533 | 0 | 7.3128 | 8.9427 | 0
N; Let/Awarded | 1 | Purchase ADD | IP20150198 | 1-154 | 2019-01-25 | A | CONSTRUCT A DOUBLE-CROSSOVER DIAMOND INTERCHANGE ON US-60 AT THE I-24 INTERCHANGE NEAR KENTUCKY OAKS MALL. | I-CHANGE RECONST(O) | McCracken | 073-US-0060 -000 | 10.484 | 10.891 | 0.407 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 |  | 0 |  | 0 | 2019 | 2019-02-25 14:43 | The purpose of this project is to use innovative construction techniques to improve traffic flow, reduce congestion and crashes near, at, and through the US 60 and I-24 interchange. | US 60 carries 3 lanes in each direction through the I-24 interchange. Congestion issues are a result of close intersection spacing and short interior left turn lanes. An innovative, cost-effective solution to easing the congestion bottleneck is a Double | 1 | West | 78.793 | 8.8316 | 13.7113 | 14.6521 | 0 | 0 | 4.5533 | 7.0447 | 49 | 15 | 15
N; Let/Awarded | 2 | Pennyrile ADD | IP20000004 | 2-137.01 / 2-137.02 / 2-137.04 / 2-137.10 / 2-137.20 | 2017-12-08 | A | US 41A PHASE II DESIGN AND RIGHT-OF-WAY. (2005HPP-KY135)(SEE 2-137.01 FOR "STP" COMPONENT) | MAJOR WIDENING(O) | Hopkins | 054-US-0041A -000 | 0 | 3.426 | 3.426 | Arterial to Partial Control | 23 |  |  |  | 0 |  | 3200000 |  | 0 |  | 47949680 | 2017 | 2017-05-18 10:39 |  | Improve congestion | 2 | West | 89.3359 | 9.7182 | 10.7732 | 13.4665 | 1.9588 | 9.7595 | 4.0378 | 9.622 | 59 | 15 | 15
N; Let/Awarded | 2 | Owensboro MPO | IP20160031 | 2-2092.10 | 2018-06-07 | I | I-65 SPUR CORRIDOR; MODERNIZATION OF EXISTING NATCHER PARKWAY FROM THE OHIO-BUTLER COUNTY LINE (MP 37.143) TO THE US-60 INTERCHANGE (MP 72.264) IN OWENSBORO. (2016BOP) | RECONSTRUCTION(O) | Daviess | 030-WN-9007 -000 | 61.553 | 72.264 | 10.711 | Full Control to Interstate | 10 | Y |  |  | 0 |  | 200000 | 2018 |  |  | 0 | 2020 | 2018-07-10 08:18 | To bring the William Natcher Parkway up to interstate standards | To allow the conversion of the Parkway to Interstate
N; Let/Awarded | 2 | Owensboro MPO | IP20160032 | 2-2092 / 2-2092.10 | 2018-06-07 | I | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO.(SEE 2-2092.10) | RECONSTRUCTION(O) | Daviess | 030-WN-9007 -000 | 61.553 | 72.264 | 10.711 | Full Control to Interstate | 10 | Y |  |  | 0 |  | 200000 | 2018 |  |  | 0 | 2018 | 2018-07-10 08:18 | The purpose of this project is to improve safety, reliability and mobility along the William Natcher Parkway (WN 9007), better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 2 | Statewide | 46.6891 | 2.0969 | 13.304 | 8.4747 | 1.8062 | 0 | 6.0352 | 14.9721
N; Let/Awarded | 2 | Evansville-Henderson MPO | IP20160037 | 2-2092.10 | 2018-06-07 | I | I-65 SPUR CORRIDOR; MODERNIZATION OF EXISTING NATCHER PARKWAY FROM THE OHIO-BUTLER COUNTY LINE (MP 37.143) TO THE US-60 INTERCHANGE (MP 72.264) IN OWENSBORO. (2016BOP) | RECONSTRUCTION(O) | Henderson | 051-US-0041 -000 | 19.14 | 20.168 | 1.028 | Maintenance Improvement | 10 | Y |  |  | 0 |  | 200000 | 2018 |  |  | 0 | 2020 | 2018-07-10 08:18 | ? | ?
N; Let/Awarded | 2 | Owensboro MPO | IP20160256 | 2-2092.10 | 2018-06-07 | I | I-65 SPUR CORRIDOR; MODERNIZATION OF EXISTING NATCHER PARKWAY FROM THE OHIO-BUTLER COUNTY LINE (MP 37.143) TO THE US-60 INTERCHANGE (MP 72.264) IN OWENSBORO. (2016BOP) | RECONSTRUCTION(O) | Daviess | 030-WN-9007 -000 | 61.553 | 72.264 | 10.711 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 200000 | 2018 |  |  | 0 | 2020 | 2018-07-10 08:18 | The purpose of this project is to improve safety, reliability and mobility along WN 9007 (William Natcher Parkway), better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
N; Let/Awarded | 3 | Bowling Green MPO | IP20060212 | 3-202 / 3-2042.11 / 3-2042.20 | 2018-11-16 | A | I-65 SPUR CORRIDOR SIGNING; EXISTING NATCHER PARKWAY FROM I-65 INTERCHANGE (EXIT 2) IN WARREN CO. EXTENDING NORTH TO THE US 60 INTERCHANGE IN DAVIESS CO. TO MEET INTERSTATE STANDARDS. (2016BOP) | SIGNING(P) | Warren | 114-PF-9999 - |  |  |  | Innovative Interchange | 40 | Y |  |  | 1250000 | 2017 | 0 |  | 0 |  | 8060000 | 2019 | 2017-09-15 13:42 | Improve safety and mobility to meet interstate compliancy. | The removal of toll booths on the Natcher Parkway at Exit 7 (US 231) has created a congestion and safety problem at this cloverleaf interchange. The existence of the toll booths provided a control of traffic entering and exiting the Natcher Parkway. The r | 3 | Statewide | 30.5368 | 3.859 | 4.141 | 6.0132 | 4.4053 | 0 | 5.859 | 6.2593
N; Let/Awarded | 3 | Barren River ADD | IP20150096 | 3-2042.03 / 3-2042.10 / 3-2042.30 | 2018-06-07 | A | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 36). (2016BOP) | I-CHANGE RECONST(O) | Butler | 016-WN-9007 -000 | 20.246 | 37.143 | 16.897 | Full Control to Interstate | 10 | Y |  |  | 0 |  | 200000 |  | 0 |  | 6460000 | 2019 | 2018-09-20 11:01 | Upgrade and modernize. | Upgrading and modernizing the roadway is needed to increase economic development throughout the region. | 3 | Statewide | 46.0191 | 2.837 | 10.9251 | 9.9119 | 1.8062 | 0 | 5.5947 | 14.9442
N; Let/Awarded | 5 | KIPDA ADD | IP20150209 | 5-159 | 2018-05-04 | I | IMPROVE RAMP CAPACITY OF THE I-64 WESTBOUND RAMP TO I-264 WESTBOUND FROM ONE TO TWO LANES FOR ENTIRE LENGTH AND OTHER NEEDED IMPROVEMENTS TO ADDRESS WEAVE ISSUES AT MERGE ON I-264. (2006BOPP)(12CCR) | RECONSTRUCTION(O) | Jefferson | 056-I -0064 -000 | 12 | 12.5 | 0.5 | Auxiliary Lanes or Operation Improvements | 11 | Y |  |  |  |  | 0 |  | 0 |  | 0 | 2019 | 2018-12-10 09:06 |  |  | 5 | Statewide | 55.1044 | 19.2775 | 7.4009 | 4.6421 | 7.3128 | 0 | 6.4758 | 9.9954
N; Let/Awarded | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160210 | 5-527 / 5-538 | 2018-10-26 | I | CONSTRUCT NEW I-65 INTERCHANGE BETWEEN KY-480 AND KY-245. | NEW INTERCHANGE(O) | Bullitt | 015-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 8610000 |  | 1280000 |  | 18720000 | 2018 | 2017-12-07 13:28 | Improve access and mobility between I-65 and the rapidly growing commercial development to the south of KY 480 (Cedar Grove Road). | This project is needed because the I-65/KY 480 interchange is projected to operate at LOS F in the PM peak period for both southbound and northbound ramp intersections and in the AM the southbound ramp intersection is projected to operate at LOS D while t | 5 | Statewide | 35.7687 | 17.4978 | 0 | 6.9053 | 1.8062 | 0 | 9.5595 | 0
N; Let/Awarded | 6 | Northern Kentucky ADD | IP20110126 | 6-367 | 2018-06-07 | I | IMPROVE MOBILITY AT THE INTERSECTION OF KY-842 AND US-42. (12CCR)(16CCN) | SAFETY(P) | Boone | 008-US-0042 -000 | 12.803 | 13.066 | 0.263 | Improve Intersection | 26 | Y |  |  | 0 |  | 0 |  | 0 |  | 0 | 2018 | 2018-11-28 11:28 |  | Relieve congestion | 6 | Statewide | 71.8278 | 14.6608 | 18.0617 | 10.2919 | 5.9031 | 8.6564 | 7.8414 | 6.4126
N; Let/Awarded | 6 | Northern Kentucky ADD | IP20150431 | 6-8001.21 | 2018-10-05 | I | IMPROVE KY-237 FROM VALLEY VIEW DRIVE TO ROGERS LANE. (14CCR) | RECONSTRUCTION(O) | Boone | 008-KY-0237 -000 | 2.251 | 5.37 | 3.119 | Modernize Roadway-Rural | 26 | Y |  |  |  |  | 0 |  | 0 |  | 0 | 2018 | 2019-02-05 09:09 |  |  | 6 | Statewide | 67.0058 | 11.3656 | 13.2159 | 9.8954 | 9.5154 | 7.5991 | 4.0529 | 11.3615
N; Let/Awarded | 6 | Northern Kentucky ADD | IP20160045 | 6-351.45 | 2018-08-02 | I | MINOR WIDENING AND CONSTRUCT A SOUTHBOUND LEFT TURN LANE ON US-25 (DRY RIDGE-FLORENCE ROAD) AT MUBEA. | MINOR WIDENING(O) | Boone | 008-US-0025 -000 | 8.468 | 8.842 | 0.374 | Modernize Roadway-Rural | 26 |  |  |  | 100000 |  | 0 |  | 0 |  | 0 | 2019 | 2019-01-22 09:54 |  |  | 6 | North | 60.1092 | 5.1631 | 10.6615 | 4.0385 | 1.5231 | 0 | 3.7077 | 5.0154 | 30 | 15 | 15
N; Let/Awarded | 6 | Northern Kentucky ADD | IP20160170 | 6-3019.10 | 2018-04-03 | I | PHASE II: IMPROVE INTERSECTION OPERATIONS AT THE INTERSECTIONS OF IDLEWILD RD. (KY-338)/JEFFERSON ST./TEMPERATE ST. AND IMPROVE PEDESTRIAN SAFETY ALONG IDLEWILD RD. AND JEFFERSON ST. (AS PER AGREEMENT WITH COUNTY) (SEE 6-3019.00 PHASE I) (2012BOP) | TRANSP ENHANCEMENT(P) | Boone | 008-KY-0338 -000 | 26.661 | 26.85 | 0.189 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 2018 | 2018-11-28 11:32 |  |  | 6 | North | 36.4692 | 8.2154 | 13.2923 | 3.3923 | 4.1077 | 0 | 2.4154 | 5.0462 | 36
N; Let/Awarded | 8 | Lake Cumberland ADD | IP20070237 | 8-8502 | 2018-04-03 | I | CONSTRUCT A NEW INTERCHANGE AT THE CUMBERLAND PARKWAY INTERSECTION WITH KY-910 AT WINDSOR. (08CCN)(10CCR) | NEW INTERCHANGE(O) | Russell | 104-LN-9008 -000 | 70.5 | 70.9 | 0.4 | Construct Road in New Location | 0 | Y |  |  | 0 |  | 0 |  | 0 |  | 0 | 2018 | 2018-12-10 09:15 |  | The only access point to the Louie B Nunn Cumberland Parkway in Russell Co. is located at US 127 in Russell Springs. Business development patterns have created a need for increased highway access in the eastern part of the county. This new interchange w | 8 | Statewide | 7.4031 | 1.3568 | 0 | 0.49559 | 1.8062 | 0 | 3.7445 | 0
N; Let/Awarded | 8 | Lake Cumberland ADD | IP20150378 | 11-184.10 / 11-184.10 | 2018-08-31 | I | RECONSTRUCT KY-92 FROM 500 FT WEST OF THE WHITLEY/MCCREARY COUNTY LINE TO 1200 FT EAST OF OLD JELLICO CREEK ROAD. (SECTION 1)(14CCR) | RELOCATION(O) | McCreary | 074-KY-0092 -000 | 20.335 | 24.835 | 4.5 | Construct Road in New Location | 0 | [7 empty] | 40000 |  | 0 | 2019 | 2018-11-08 14:35 | This project is needed because the geometrics along KY 92 between 1450 ft West of KY 592 and 350 ft East of Whitley/McCreary Co Line are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 37.9396 | 2.0569 | 2.2038 | 7.8021 | 3.0095 | 5.3081 | 2.5592 | 0 | 23 | 15
N; Let/Awarded | 8 | Cumberland Valley ADD | IP20150380 | 8-6.10 | 2018-02-05 | I | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 6 LANES FROM 1MI N SAND HILL ROAD UNDERPASS N TO 1.1 MILES N OF THE US-25 I-CHNG AT MT. VERNON. (16CCR) | MAJOR WIDENING(O) | Rockcastle | 102-I -0075 -000 | 55.745 | 60.1 | 4.355 | Add Lane to Full Control Facility | 25 | Y |  |  | 1500000 |  | 750000 |  | 0 |  | 0 | 2018 | 2018-12-10 13:35 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on I-75. | This project is part of an overall plan to widen I-75 from the Tennessee State line to Lexington. The project will serve to upgrade the existing system and provide congestion relief and improve roadway conditions. | 8 | Statewide | 59.4939 | 16.511 | 10.3965 | 10.0606 | 1.8062 | 0 | 8.0617 | 12.658
N; Let/Awarded | 9 | Gateway ADD | IP20110059 | 9-227 | 2018-12-07 | I | CONSTRUCT TURN LANES INTO LAKESIDE CHRISTIAN ACADEMY TO IMPROVE SAFETY.(12CCR) | SAFETY(P) | Rowan | 103-US-0060 -000 | 5.25 | 5.55 | 0.3 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-01-03 08:24 | The purpose of this project is to improve safety. | The following needs have been identified for the project: 1) Improve Roadway Safety, and 2) Improve Intersection. | 9 | East | 47.6243 | 5.8802 | 15 | 6.0853 | 1.1078 | 0 | 0 | 4.5509 | 33 | 15
N; Let/Awarded | 10 | Kentucky River ADD | IP20150274 | 10-158 | 2018-02-05 | I | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY-15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY-15 BYPASS | RECONSTRUCTION(O) | Perry | 097-KY-0015 -000 | 13.269 | 14.512 | 1.243 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 5370000 |  | 0 |  | 0 | 2018 | 2019-01-24 10:01 | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY 15 BYPASS | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 15 IN PERRY COUNTY FROM MORTON BOULEVARD TO KY 15 BYPASS | KENTUCKY RIVER ADD | Statewide | 57.4142 | 12.2115 | 9.7797 | 9.4989 | 6.9163 | 9.0308 | 1.0132 | 8.9638
N; Let/Awarded | 10 | Gateway ADD | IP20150470 | 10-293.10 | 2017-12-21 | I | RECONSTRUCT/WIDENING OF MAIN ST (KY 7) IN WEST LIBERTY BEGINNING AT RIVERSIDE DR. (CS 1058) AND EXTENDING NORTH TO 0.159 MILES NORTH OF INTERSECTION WITH CEDAR RD (CS 1053). (2014BOP)(D,R,U COMPLETED UNDER 10-293)(CONSTRUCTION SEQ 2)(16CCR) | RECONSTRUCTION(O) | Morgan | 088-KY-0007 -000 | 0.134 | 0.5 | 0.366 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  |  |  | 0 | 2018 |  | The purpose of this project is to: improve mobility and widen the roadway. | The following needs have been identified for this project: 1) Improve Mobility, and 2) Minor Widening Through Commercial Area of West Libety to Enhance Economic Growth. | 10 | East | 39.9177 | 4.6108 | 8.7126 | 7.9716 | 2.4551 | 8.0838 | 3.3533 | 4.7305 | 40
N; Let/Awarded | 11 | Cumberland Valley ADD | IP20150315 | 11-188 | 2018-06-28 | I | IMPROVE SAFETY AND ACCESS MANAGEMENT, AND REDUCE CONGESTION ON US-25E FROM CORBIN BYPASS TO KNOX/LAUREL COUNTY LINE.(12CCR) | MAJOR WIDENING(O) | Knox | 061-US-0025E -000 | 24.222 | 26.197 | 1.975 | Arterial to Partial Control | 23 | Y |  |  | 0 |  | 0 |  | 0 |  | 0 | 2020 | 2018-12-07 14:13 | The purpose of this project is to address safety and capacity on US 25E from Corbin Bypass to Knox/Laurel County Line. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 86.6908 | 7.2891 | 14.5024 | 12.4585 | 0 | 9.9526 | 4.7156 | 7.7725 | 57 | 15 | 15
N; Let/Awarded | 12 | FIVCO ADD | IP20160146 | 12-196.10 | 2018-07-27 | I | RECONSTRUCT KY 2565 FROM APPROX. 550' NW OF CR 1529/KY2565/KY2563 INTERSECTION TO APPROX. 1150' SE OF THE INTERSECTION (SECTION 2). (2014BOP) | RECONSTRUCTION(O) | Lawrence | 064-KY-2565 -000 | 1.915 | 2.234 | 0.319 | Modernize Roadway-Rural | 26 | [9 empty] | 0 |  |  |  |  | 12 | East | 73.7141 | 9.6048 | 9.6108 | 6.7141 | 0 | 9.7605 | 4.5509 | 3.4731 | 44 | 15 | 15
N; Let/Awarded | 12 | FIVCO ADD | IP20160147 | 12-196.10 | 2018-07-27 | I | RECONSTRUCT KY 2565 FROM APPROX. 550' NW OF CR 1529/KY2565/KY2563 INTERSECTION TO APPROX. 1150' SE OF THE INTERSECTION (SECTION 2). (2014BOP) | RECONSTRUCTION(O) | Lawrence | 064-CR-1529 -000 | 0.206 | 0.726 | 0.52 | Modernize Roadway-Rural | 26 | [9 empty] | 0
N; Committed | 1 | Purchase ADD | IP19990004 | 1-181.50 | 2019-03-22 | A | MURRAY-MAYFIELD RD; EXTEND MAYFIELD SOUTHERN BYPASS FROM KY-303 SOUTH OF MAYFIELD, NORTHWEST TO JULIAN M. CARROLL PARKWAY (PURCHASE PARKWAY). (EXTENSION OF 1-181.30)(00CCR)(12CCR)(14CCR)(18CCR) | NEW ROUTE(O) | Graves | 042-PF-9999 - |  |  |  | Construct Road in New Location | 0 | [9 empty] | 29120000 | 2020 | 2018-11-14 12:44 | Final link of 4 Lane KY 80 from Bowling Green to Mayfield - Section from KY 303 to Purchase Parkway (Future I-69) in Mayfield. (Six Year Plan Item No. 181.50). Note: Construction funding is all that is needed to complete this project. | This is the final piece of the KY 80 four lane project connecting from Bowling Green to Mayfield. This project creates a southern bypass around the City of Mayfield, creating a link to I-69. | 1 | West | 58.683 | 9.134 | 2.2165 | 7.3325 | 2.3024 | 7.6976 | 0 | 0 | 29 | 15 | 15
N; Committed | 1 | Purchase ADD | IP20000001 | 1-115 |  | A | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM STAFFORD ROAD TO BETHEL CHURCH ROAD (INCLUDES KEVIL BYPASS)(TO BE LET WITH 1-115.10) (06CCR)(12CCR)(14CCR)(18CCR). | MAJOR WIDENING(O) | Ballard | 004-US-0060 -000 | 13.62 | 16.937 | 3.317 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  |  |  | 7350000 | 2020 | 5200000 | 2021 | 10130000 | 2025 | 2018-07-10 08:18 | Address condition, safety, congestion and future capacity issues from proposed 1.0 miles east of Denis Jones Road to Bethel Church Road. (See December 2001 KYTC Intermediate Planning Study.) | This project is part of an overall plan to widen US 60 west of Paducah. Capacity is expected to become an issue in the near future as traffic growth continues to increase. This project will serve to upgrade the existing system. US 60 serves as a regional | 1 | West | 88.7363 | 7.6495 | 12.8866 | 11.8943 | 4.0206 | 8.6254 | 4.0722 | 9.5876 | 59 | 15 | 15
N; Committed | 1 | Purchase ADD | IP20150158 | 1-152 | 2020-07-15 | A | MAJOR WIDENING OF US-62 FROM KY-998 TO PADUCAH INFORMATION AGE PARK. (12CCR) | MAJOR WIDENING(O) | McCracken | 073-US-0062 -000 | 7.59 | 8.808 | 1.218 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 0 |  | 0 |  | 0 | 2019 | 5740000 | 2021 | 2018-07-10 08:18 | The purpose of this project is to continue system continuity and improve traffic flow to the Paducah Commerce Park. | It would be appropriate to extend the 5 lane section of US 62 to accommodate the increase in traffic from development occurring at the Paducah Commerce Park. Due to the opening of McCracken County High School, this route is also used to access the back e | 1 | West | 81.0146 | 7.5052 | 13.4536 | 9.884 | 2.3024 | 8.6598 | 3.5395 | 5.6701 | 51 | 15 | 15
N; Committed | 1 | Purchase ADD | IP20150167 | 1-314.10 | 2019-07-26 | A | MAJOR WIDENING FROM TENN. STATE LINE TO MURRAY PRIORITY SECTION 1; FROM CLARKS RIVER BRIDGE, NORTH 1.0 MILE TO EXISTING 4-LANE.(SEE 1-8852.00)(12CCR) | MAJOR WIDENING(O) | Calloway | 018-US-0641 -000 | 5.666 | 6.666 | 1 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | [6 empty] | 0 |  | 6040000 | 2018 | 2018-07-10 08:18 | MAJOR WIDENING FROM TENN. STATE LINE TO MURRAY PRIORITY SECTION 1; FROM CLARKS RIVER BRIDGE, NORTH 1.0 MILE TO EXISTING 4-LANE.(SEE 1-8852.00)(12CCR) | 1-314.10 | 1 | Statewide | 52.3367 | 6.5551 | 14.0969 | 7.2687 | 8.5903 | 4.8238 | 1.9824 | 9.0195
N; Committed | 1 | Purchase ADD | IP20150291 | 1-115.10 |  | A | PADUCAH-WICKLIFFE RD: IMPROVE US-60 FROM BETHEL CHURCH ROAD TO KY-1154 (MARTIN MARIETTA) (04CCR) (TO BE LET WITH 1-115.00).(10CCR)(12CCR)(18CCR) | MAJOR WIDENING(O) | McCracken | 073-US-0060 -000 | 0.4 | 1.968 | 1.568 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  |  |  | 5260000 | 2019 | 5420000 | 2022 | 16880000 |  | 2018-07-10 08:18 | Address condition, safety, congestion and future capacity issues from Bethel Church Road to KY-1154 | This project is part of an overall plan to widen US 60 west of Paducah. Capacity is expected to become an issue in the near future as traffic growth continues to increase. This project will serve to upgrade the existing system. US 60 serves as a regional | 1 | West | 79.7569 | 7.0722 | 12.8351 | 8.3892 | 1.3058 | 9.0722 | 4.4845 | 6.5979 | 50 | 15 | 15
N; Committed | 1 | Purchase ADD | IP20150304 | 1-118 |  | A | IMPROVE US-60 FROM PROPOSED SOUTHERN BYPASS OF LA CENTER TO EAST OF DENIS JONES ROAD. (02CCR) | MAJOR WIDENING(O) | Ballard | 004-US-0060 -000 | 11.815 | 13.615 | 1.8 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  |  |  | 2370000 | 2024 | 1900000 | 2024 | 9850000 | 2025 | 2018-07-10 08:18 | Address condition, safety, congestion and future capacity issues from proposed southern bypass of LaCenter to 1.0 miles east of Denis Jones Road. | This project is part of an overall plan to widen US 60 west of Paducah. Capacity is expected to become an issue in the near future as traffic growth continues to increase. This project will serve to upgrade the existing system. US 60 serves as a regional | 1 | West | 77.549 | 7.622 | 7.7835 | 8.5696 | 1.9416 | 8.5567 | 4.0034 | 9.0722 | 48 | 15 | 15
N; Committed | 1 | Purchase ADD | IP20150398 | 1-314.20 |  | A | IMPROVE US-641 FROM THE TENNESSEE STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | MAJOR WIDENING(O) | Calloway | 018-US-0641 -000 | 0 | 5.666 | 5.666 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 4000000 | 2018 | 6620000 | 2019 | 9000000 | 2019 | 58500000 | 2021 | 2018-07-10 08:18 | MAJOR WIDENING FROM TENN. STATE LINE TO MURRAY PRIORITY SECTION 2; FROM TENN. STATE LINE TO CLARKS RIVER BRIDGE.(SEE 1-8852.00) | 1-8852 | 1 | West | 90.1667 | 5.9313 | 14.1237 | 13.3763 | 4.9485 | 8.5911 | 3.7801 | 9.4158 | 60 | 15 | 15
N; Committed | 1 | Purchase ADD | IP20150418 | 1-153 |  | A | IMPROVE KY-1286 (FRIENDSHIP ROAD) FROM MP 3.6 TO MP 6.4 IN PADUCAH. (PRELIMINARY ENGINEERING) (12CCR)(14CCR)(16CCN)(18CCR) | RECONSTRUCTION(O) | McCracken | 073-KY-1286 -000 | 3.623 | 6.423 | 2.8 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 | 2019 | 4970000 | 2020 | 4620000 | 2024 | 17550000 | 2024 | 2018-07-10 08:18 | UPGRADE KY 1286 (FRIENDSHIP ROAD) FROM MP 3.6 TO MP 6.4 IN PADUCAH. (PRELIMINARY ENGINEERING) (12CCR)(14CCR) | KY1286 is a vital collector RT between the major arterial RTs of US45, US60, US62. It serves as an alternative connector RT roughly paralleling I-24 from southern McCracken to near the heavy commercial growth area along Hinkleville RD (US60) and serves he | 1 | West | 84.9716 | 8.4811 | 10.9794 | 14.1366 | 4.5704 | 8.9691 | 0 | 7.8351 | 55 | 15 | 15
N; Committed | 1 | Pennyrile ADD | IP20160235 | 1-187.50 |  | A | RELOCATE US-641 FROM US-62 NEAR EDDYVILLE TO SOUTH OF THE LYON/CALDWELL COUNTY LINE. | RELOCATION(O) | Lyon | 072-US-0641 -000 | 0 | 5.715 | 5.715 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 10920000 | 2019 | 13230000 | 2020 | 3270000 | 2020 | 54000000 | 2022 | 2018-07-10 08:18 | To improve safety and truck access to the City of Marion. | There are no existing highway routes into Crittenden County that are approved for 102 inch wide truck trailers. | 1 | West | 80.6435 | 4.8316 | 11.3918 | 10.7603 | 3.9863 | 6.7698 | 3.0756 | 9.8282 | 51 | 15 | 15
N; Committed | 1 | Pennyrile ADD | IP20160236 | 1-187.60 |  | A | RELOCATE US-641 FROM SOUTH OF THE LYON/CALDWELL COUNTY LINE TO FREDONIA, 4.5 MILES. | RELOCATION(O) | Lyon | 072-US-0641 -000 | 0 | 5.715 | 5.715 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 7800000 | 2019 | 13230000 | 2020 | 4890000 | 2020 | 67500000 | 2022 | 2018-07-10 08:18 | To improve safety and truck access to the City of Marion | There are no existing highway routes into the City of Marion that can support 102 inch wide truck trailers. The relocated US 641 is needed to support truck access. | 1 | West | 79.6641 | 4.8316 | 10.4124 | 10.7603 | 3.9863 | 6.7698 | 3.0756 | 9.8282 | 50 | 15 | 15
N; Committed | 2 | Clarksville-Oak Grove MPO | IP20060084 | 2-180 | 2019-12-13 | A | IMPROVE KY-911 FROM US-41A TO OAK GROVE.(12CCR). | MAJOR WIDENING(O) | Christian | 024-KY-0911 -000 | 0 | 1.7 | 1.7 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 15600000 | 2020 | 2019-03-08 10:54 | The purpose of this project is to improve: safety, reliability and mobility along KY 911, better access control, and reduce congestion. | This project is needed because the capacity of KY 911 does not meet the current and future traffic volumes that are generated by Fort Campbell, resulting in congestion and decreased mobility. | 2 | West | 80.3213 | 8.5086 | 11.0825 | 11.6237 | 2.2337 | 8.866 | 0 | 8.0069 | 50 | 15 | 15
N; Committed | 2 | Evansville-Henderson MPO | IP20080099 | 2-383 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON CS-1372 (WATSON LANE). (18CCR) | RECONSTRUCTION(O) | Henderson | 051-CS-1372 -000 | 0.309 | 1.395 | 1.086 | Modernize Roadway-Urban | 16 |  |  |  | 0 | 2019 | 1550000 | 2020 | 1460000 | 2021 | 5630000 | 2022 | 2019-03-11 08:37 | Improve traffic flow and safety. | WATSON LN FROM GREEN RIVER RD TO SUNSET LN IN HENDERSON IS A HIGHLY TRAVELED CONNECTOR TO US 41. THIS ROUTE IS NARROW AND NEEDS TO BE RECONSTRUCTED TO PROVIDE A MORE EFFICEINT AND SAFE ROUTE. | Evansville/Henderson MPO | West | 68.6306 | 8.3299 | 6.701 | 10.7474 | 4.5361 | 8.3162 | 0 | 0 | 39 | 15 | 15
N; Committed | 2 | Pennyrile ADD | IP20080107 | 2-8506 | 2019-06-21 | A | WIDEN US-62 FROM WAL-MART TO US-431. (08CCN)(10CCR)(12CCR)(14CCR)(INCLUDES 2-8301) | MAJOR WIDENING(O) | Muhlenberg | 089-US-0062 -000 | 16.471 | 17.93 | 1.459 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 8000000 | 2018 | 2019-03-11 09:26 |  | This route has a high ADT and CRF. The route has strip commercial development and left turning vehicles block traffic and create congestion. | 2 | West | 85.3746 | 8.5361 | 12.268 | 12.5773 | 0.94502 | 9.1409 | 3.7629 | 8.1443 | 55 | 15 | 15
N; Committed | 2 | Green River ADD | IP20150406 | 2-226 | 2022-01-15 | A | IMPROVE THE WESTBOUND LANES OF US-60 FROM KY-1957 TO 0.2 MILE WEST OF KY-6106. (12CCR)(14CCR)(18CCR) | MINOR WIDENING(O) | Hancock | 046-US-0060 -000 | 1.933 | 8.5 | 6.567 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 80000 | 2019 | 820000 | 2020 | 5200000 | 2021 | 2019-03-08 10:50 | Address safety issues and reduce hazards along US 60 WB lanes. | The following need has been identified for this project: 1) Improve Roadway Safety. | 2 | West | 75.4734 | 4.4811 | 13.6598 | 12.4871 | 0 | 0 | 4.9141 | 9.9313 | 46 | 15 | 15
N; Committed | 2 | Owensboro MPO | IP20150444 | 2-8300 / 2-8300.01 |  | A | IMPROVE KY-54 FROM WEST OF THE US-60 BYPASS TO CR-1021 (JACK HINTON ROAD). (06CCN)(10CCR)(12CCR)(14CCR)(16CCR) | MAJOR WIDENING(O) | Daviess | 030-KY-0054 -000 | 2.47 | 8.003 | 5.533 | Arterial to Partial Control | 23 |  |  |  | 0 |  | 30100000 | 2019 | 43140000 | 2022 | 70200000 | 2024 | 2019-03-11 09:05 | The purpose of this project is to improve safety, reliability and mobility along KY 54, better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 2 | West | 90.4261 | 8.6392 | 13.4021 | 14.9485 | 0.94502 | 9.0378 | 4.3471 | 9.1065 | 60 | 15 | 15
N; Committed | 2 | Green River ADD | IP20160025 | 2-2092.20 | 2020-07-15 | A | I-65 SPUR CORRIDOR; RECONSTRUCT THE EXISTING NATCHER PARKWAY/KY-69 INTERCHANGE (EXIT 50) IN OHIO COUNTY. (2016BOP) | I-CHANGE RECONST(O) | Ohio | 092-WN-9007 -000 | 49.7 | 50.1 | 0.4 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 | 2019 | 0 | 2019 | 9030000 | 2021 | 2018-07-10 08:18 | Address safety and access issues at the WN 9007 (Future I-165) and WK 9004 interchange. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access. | 2 | Statewide | 28.0459 | 3.1894 | 5.1101 | 3.2874 | 1.8062 | 0 | 7.1806 | 7.4721
N; Committed | 3 | Bowling Green MPO | IP20000009 | 3-110 / 3-110.01 |  | A | IMPROVE KY-185 FROM NORTH OF THE JUNCTION WITH KY-263 NEAR RICHARDSVILLE TO THE BUTLER COUNTY LINE. (02CCR)(04CCR)(06CCR)(10CCR)(14CCR)(18CCR) | RECONSTRUCTION(O) | Warren | 114-KY-0185 -000 | 6.29 | 11.913 | 5.623 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 2460000 |  | 29700000 | 2020 | 2019-03-05 09:23 | Increase safety and mobility. | This corridor has been identified as a safety concern, so modernization is needed to improve safety. | 3 | West | 75.9201 | 4.1031 | 10.4639 | 12.3325 | 4.244 | 5.7388 | 0 | 9.0378 | 46 | 15 | 15
N; Committed | 3 | Bowling Green MPO | IP20060200 | 3-199 / 3-199.01 / 3-199.99 | 2020-09-15 | A | IMPROVE US-31W FROM SOUTH OF KY-242 TO DILLARD ROAD.(12CCR) | PREFINANCD CONVRSN(O) | Warren | 114-US-0031W -000 | 4.1 | 6.7 | 2.6 | Major Widening-Rural Mutilane | 34 |  |  |  | 10000 | 2022 | 0 |  | 0 |  | 23820000 | 2022 | 2019-03-05 09:43 | Reduce congestion and increase mobility. | US 31W between a point 0.3 mile south of KY 242 and the Dillard Road is a two lane facilty. Turning lanes exist only at the intersection with KY 242 and are the result of a safety (HES) project. US 31W is one of the major non-interstate, north-south rout | 3 | West | 76.8574 | 8.4811 | 12.4742 | 12.3454 | 0.84192 | 0 | 4.8454 | 7.8694 | 47 | 15 | 15
N; Committed | 3 | Bowling Green MPO | IP20060203 | 3-8905 |  | A | IMPROVE MOBILITY AND REDUCE CONGESTION ON US-31W FROM US-68 TO MIZPAH. (16CCN) | RECONSTRUCTION(O) | Warren | 114-US-0031W -000 | 21.148 | 22.49 | 1.342 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 0 | 2020 | 1000000 | 2020 | 450000 | 2020 | 3280000 | 2022 | 2019-03-05 09:52 | Improve mobility. | US 31W between US 68 and Mizpah Road is primarily a two lane road. A high volume of traffic is encountered along this highway and is rapidly increasing due to industrial expansion. The entrance to the Multimodal Transpark in Warren County is located along | 3 | West | 77.7311 | 6.9622 | 14.4845 | 8.1057 | 0.94502 | 7.2852 | 3.6942 | 6.2543 | 48 | 15 | 15
N; Committed | 3 | Bowling Green MPO | IP20150160 | 3-8702 / 3-8702.01 | 2020-01-15 | A | IMPROVE US-231 FROM PASCOE BLVD. TO NORTH OF CAVE MILL ROAD. (12CCN) | PREFINANCD CONVRSN(O) | Warren | 114-US-0231 -000 | 9.455 | 10.453 | 0.998 | Improve Intersection | 26 | Y | 0 |  | 0 |  | 0 |  | 0 | 2018 | 7820000 | 2019 | 2019-02-28 10:07 | Improve mobility and safety. | With the growing population of Bowling Green, especially in the Cave Mill area, the congestion issue in this corridor needs to be addressed. | 3 | West | 51.323 | 9.5533 | 15 | 14.7423 | 0 | 0 | 4.6048 | 7.4227 | 51
N; Committed | 3 | Barren River ADD | IP20150189 | 3-8305 | 2019-04-26 | A | IMPROVE KY-100 (OLD GALLATIN ROAD) FROM SOUTH OF KY-2160 TO KY-980. (06CCN) | RECONSTRUCTION(O) | Allen | 002-KY-0100 -000 | 14.1 | 14.441 | 0.341 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 1330000 | 2018 | 2019-02-28 10:01 | Improve safety and mobility. | Congestion occurs from the signal at KY-980 to KY-2160 from traffic trying to turn left to go to the Police Department/Detention Center, the Minit Mart gas station, Pizza Hut, and KY-2160. | 3 | West | 78.543 | 6.5842 | 12.0103 | 9.1753 | 1.323 | 9.4158 | 4.1237 | 5.9107 | 48 | 15 | 15
N; Committed | 3 | Barren River ADD | IP20150352 | 3-7020 / 3-7020 / 3-7020.01 / 3-7020.01 / 3-7020.17 / 3-7020.18 | 2017-09-29 | A | CONSTRUCT NEW ROUTE FOR THE EAST TOMPKINSVILLE BYPASS "GRADE & DRAIN ONLY". (98CCN)(02CCR) (2002BOPC)(DESIGN "STP" FUNDING SHALL BE SUPPLEMENTAL TO THE AUTHORIZED AMOUNT ALREADY EXPENDED ON THIS PROJECT). (08CCR)(10CCR) | NEW ROUTE(O) | Monroe | 086-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 15820000 | 2017 | 2003-11-21 11:09 | Improve mobility. | A new bypass would alleviate some of the truck volume that goes through the city of Tompkinsville to improve their mobility as well as the mobility of other vehicles. | 3 | West | 42.7826 | 6.2749 | 7.5773 | 12.4356 | 3.1787 | 9.2096 | 4.1065 | 0 | 43
N; Committed | 3 | Barren River ADD | IP20160167 | 3-108.50 / 3-108.51 | 2020-07-15 | A | PRIORITY SECTION 3: IMPROVE KY-90 EAST OF GLASGOW FROM BRIDGE OVER FALLEN TIMBER CREEK TO THE METCALFE COUNTY LINE. (2002BOPC)(08CCR)(10CCR)(12CCR) | PREFINANCD CONVRSN(P) | Barren | 005-KY-0090 -000 | 17.758 | 21.975 | 4.217 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 15400000 | 2022 | 2019-02-28 08:55 | Improve safety and mobility. | A high number of crashes has created the need to reconstruct this section of KY-90, particularly straightening out the S-curve, to improve safety and mobility. | 3 | West | 83.4828 | 5.1753 | 12.0619 | 10.9536 | 4.2096 | 8.0069 | 3.5911 | 9.4845 | 54 | 15 | 15
N; Committed | 3 | Barren River ADD | IP20160172 | 3-2042.30 | 2020-07-15 | A | I-65 SPUR CORRIDOR: IMPROVE THE NATCHER PARKWAY/US-231 INTERCHANGE (EXIT 36). (2016BOP) | I-CHANGE RECONST(O) | Butler | 016-WN-9007 -000 | 20.246 | 37.143 | 16.897 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 |  | 0 |  | 6460000 | 2021 | 2018-09-20 11:01 | Upgrade and modernize. | Upgrading and modernizing the roadway is needed to increase economic development throughout the region.
N; Committed | 3 | Bowling Green MPO | IP20160173 | 3-322 | 2019-07-26 | A | IMPROVE KY-526 FROM NEAR KY-2630 TO US-31W. (2014BOP) | MINOR WIDENING(O) | Warren | 114-KY-0526 -000 | 6.205 | 6.388 | 0.183 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2019 | 0 | 2019 | 250000 | 2020 | 2019-02-28 09:31 | Improve safety and mobility. | Widening is needed for this corridor due to congestion from school traffic at peak times. | 3 | West | 54.5412 | 8.7766 | 14.9485 | 9.4588 | 2.3024 | 0 | 0 | 4.055 | 40 | 15
N; Committed | 3 | Bowling Green MPO | IP20170078 | 3-80000 |  | A | SOUTHWEST PARKWAY - NEW CONSTRUCTION FROM US-68 TO A CONNECTION AT KOBE WAY IN BOWLING GREEN(18CCN) | NEW ROUTE(O) | Warren | 114-PF-9999 - |  |  |  | Construct Road in New Location | 0 | Y |  |  | 0 | 2019 | 0 | 2019 | 0 | 2019 | 3870000 | 2019 | 2018-11-14 12:48 | Increase mobility. | Traffic along the US 68 West (Russellville Road) Corridor and US 31W South (Nashville Road) Corridor have experienced a high amount of stress due to congestion. A major mixed-use development has been proposed in cooperation with the city and local plann | Bowling Green MPO | West | 76.0052 | 8.0756 | 14.5876 | 9.1495 | 0 | 9.4845 | 4.7079 | 0 | 46 | 15 | 15
N; Committed | 4 | Barren River ADD | IP20060226 | 4-441 |  | A | IMPROVE MOBILITY, CONNECTIVITY AND SAFETY BY ADDRESSING COMMERCIAL AND INDUSTRIAL TRAFFIC MOVEMENT FROM US-31W SOUTH OF KY-218 TO I-65. (16CCR)(18CCR) | ECONOMIC DEVEL(O) | Hart | 050-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 750000 |  | 2120000 | 2020 | 1510000 | 2021 | 7380000 |  | 2018-08-22 13:11 | Improve mobility and connectivity by addressing commercial and industrial traffic between I-65 and Horse Cave's industrial areas to the south along US 31W | KY 335 is a two lane facility with narrow lanes in this area. This road in conjunction with a city street, makes a south western bypass for Horse Cave and is being used as such. Large vehicles, as well as, other vehicles are using this route to avoid goin | BARREN RIVER ADD | South | 52.404 | 6 | 0 | 3.1102 | 1.8246 | 7.9147 | 3.5545 | 0 | 22 | 15 | 15
N; Committed | 4 | Lake Cumberland ADD | IP20060237 | 4-8920 | 2019-07-26 | A | HEARTLAND PARKWAY: IMPROVE MOBILITY ON KY-55 FROM SOUTH OF THE TAYLOR/ADAIR COUNTY LINE TO THE CAMPBELLSVILLE BYPASS. (16CCN) | RECONSTRUCTION(O) | Taylor | 109-KY-0055 -000 | 0 | 8.7 | 8.7 | Modernize & Widen Roadway-Rural | 26 | Y |  |  | 0 |  | 0 | 2019 | 0 | 2019 | 19600000 | 2020 | 2019-02-01 08:14 | Improve mobility on KY 55 from south of the Taylor/Adair County line to the Campbellsville Bypass | Upgrade KY 55 from the Adair County line to the proposed Campbellsville Bypass. The US 68/KY 55/555 corridor links the cities of Columbia, Campbellsville, Lebanon and Springfield to both the Louie B. Nunn/Cumberland Parkway and the Martha Layne Collins/Bl | 4 | South | 85.8424 | 6.7014 | 14.0047 | 13.3116 | 0.47393 | 7.8199 | 4.1469 | 9.3839 | 56 | 15 | 15
N; Committed | 4 | Lincoln Trail ADD | IP20120062 | 4-8803 | 2019-04-26 | A | IMPROVE SAFETY, MOBILITY AND GEOMETRICS ON KY-49 NEAR SOUTHERN KY-52 INTERSECTION. (14CCN)(18CCR) | SPOT IMPROVEMENTS(O) | Marion | 078-KY-0049 -000 | 23.35 | 24.98 | 1.63 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 3000000 | 2020 | 2018-07-10 08:18 | Improve safety, mobility and geometrics on KY 49 near southern KY 52 intersection | KY 49 is the main route between Loretto and Lebanon. The road has numerous horizontal and vertical curves creating safety hazards. The curve at mile point 24.5 alone had 5 accidents between 2009 and 2011. | LINCOLN TRAIL ADD | South | 61.5095 | 3.2038 | 11.872 | 7.5711 | 3.4123 | 0 | 0 | 5.4502 | 32 | 15 | 15
N; Committed | 4 | Elizabethtown-Radcliff MPO | IP20150172 | 4-7020 | 2019-05-24 | A | RELOCATE INTERSECTION OF WOODLAND DRIVE AT US-31W. (98CCN)(06CCR)(REMAINING FUNDS FOR AGREEMENT)(12CCR)(LET BY KYTC) | SAFETY(P) | Hardin | 047-KY-0361 -000 | 0 | 0.5 | 0.5 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 2300000 | 2020 | 2018-09-12 17:07 | Address safety and geometrics at the intersection of KY 1600 (Now KY 361) and US 31W | KY 1600 (Now KY 361) meets US 31W at an angle or Y and creates a hazardous situation | Radcliff/Elizabethtown MPO | South | 33.6481 | 2.7773 | 13.1517 | 9.4017 | 3.4834 | 0 | 0 | 4.8341 | 34
N; Committed | 4 | Lincoln Trail ADD | IP20150212 | 4-8309.10 | 2020-05-15 | A | IMPROVE US-150 FROM WEST OF KY-245 THROUGH THE BLUEGRASS PARKWAY INTERCHANGE TO EAST OF LESLIE BALLARD LN (CR 1110). (06CCN)(2006BOPC)(12CCR)(14CCR)(16CCR)(18CCR) | MAJOR WIDENING(O) | Nelson | 090-US-0150 -000 | 1.697 | 2.285 | 0.588 | Innovative Interchange | 40 |  |  |  | 0 |  | 0 |  | 1000000 | 2019 | 12000000 | 2020 | 2019-02-13 08:06 | Address congestion and safety along US 150 from near KY 245 through the Bluegrass Parkway Interchange to just past Leslie Ballard Road | US 150 is only 2 lanes with significant commercial and passenger traffic. Traffic backs up on the ramps from the Bluegrass Parkway waiting to turn onto US 150 which is in part due to traffic on US 150 stopping traffic in order to turn left onto the Blueg | LINCOLN TRAIL ADD | South | 70.9597 | 9.7156 | 9.8104 | 12.0498 | 0 | 0 | 4.7393 | 4.6445 | 41 | 15 | 15
N; Committed | 4 | Lake Cumberland ADD | IP20150235 | 4-142.30 |  | A | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-70 TO US-68 EAST OF CAMPBELLSVILLE. SECTION 2. (2010BOP)(16CCR) | NEW ROUTE(O) | Taylor | 109-PF-9999 - |  |  |  | Construct Road in New Location | 0 | [5 empty] | 0 |  | 1300000 | 2019 | 12100000 | 2025 | 2019-03-14 15:42 | Address safety, congestion, and mobility along US 68 in Campbellsville. | US 68 is congested and has numerous accidents. There is no other safe route between the east side of Campbellsville and KY 55 south of Campbellsville. This is a recommendation from the 2005 Heartland Parkway Study. | 4 | South | 70.4609 | 8.3223 | 2.6303 | 14.4846 | 1.327 | 9.1943 | 4.5024 | 0 | 40 | 15 | 15
N; Committed | 4 | Lake Cumberland ADD | IP20150236 | 4-142.20 | 2019-09-20 | A | HEARTLAND PARKWAY: IMPROVE MOBILITY AND CONNECTIVITY VIA NEW CAMPBELLSVILLE BYPASS FROM KY-55 SOUTH OF CAMPBELLSVILLE TO KY-70. SECTION 1. (2010BOP)(14CCR)(16CCR) | NEW ROUTE(O) | Taylor | 109-PF-9999 - |  |  |  | Construct Road in New Location | 0 | [5 empty] | 0 |  | 0 |  | 30400000 | 2022 | 2018-07-10 08:18 | Address safety, congestion, and mobility along US 68 in Campbellsville. | US 68 is congested and has numerous accidents. There is no other safe way to get traffic including trucks from the east side of Campbellsville to the south side on KY 55. This is part of the Heartland Parkway and a recommended improvement from the study. | 4 | South | 70.8934 | 8.7962 | 2.8436 | 13.5427 | 1.327 | 9.5261 | 4.8578 | 0 | 41 | 15 | 15
N; Committed | 4 | Lincoln Trail ADD | IP20150265 | 4-8502.10 | 2019-05-24 | A | IMPROVE US 62 FROM LEITCHFIELD BYPASS (KY 3155) TO JUST EAST OF BEEHIVE CURVE. CONSTRUCTION SEGMENT 1. | MINOR WIDENING(O) | Grayson | 043-US-0062 -000 | 23 | 24.5 | 1.5 | Modernize Roadway-Rural | 26 | [9 empty] | 4000000 | 2020 |  | Address safety, geometric deficiencies, and congestion along US 62 between Leitchfield and Clarkson. | US 62 is a 2 lane route with a lot of traffic connecting Leitchfield and Clarkson. Many trucks use this corridor and there have been numerous accidents. | LINCOLN TRAIL ADD | South | 72.9242 | 8.3981 | 12.5829 | 11.6588 | 2.2275 | 0 | 0 | 8.0569 | 43 | 15 | 15
N; Committed | 4 | Elizabethtown-Radcliff MPO | IP20150297 | 4-8801 |  | A | IMPROVE SAFETY, GEOMETRICS, DRAINAGE AND MAINTENANCE ISSUES ALONG KY-1357 (ST. JOHNS RD) FROM US-31W BYPASS TO KY-3005 (RING ROAD). (14CCN) | SAFETY(P) | Hardin | 047-KY-1357 -000 | 14.614 | 16.292 | 1.678 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 3000000 | 2020 | 3500000 | 2021 | 8000000 | 2024 | 2019-02-28 12:24 | Address safety, geometric deficiencies, and maintenance issues along KY 1357 between US 31WBypass and KY 3005 (Ring Road) | KY 1357 provides access to local residential areas and is a direct link between KY 3005 (Ring Road), the US 31W Bypass, and US 31W on the west side of Elizabethtown. It serves as a minor arterial route between these three major arterials. KY 1357 betwee | Radcliff/Elizabethtown MPO | South | 73.3637 | 9.1754 | 10.5213 | 9.9704 | 2.2275 | 5.6872 | 0 | 5.782 | 43 | 15 | 15
N; Committed | 5 | KIPDA ADD | IP20060242 | 5-8300 | 2022-06-15 | A | MAJOR RECONSTRUCTION OF KY-146 BETWEEN NEW CASTLE AT US-421 AND PENDLETON AT KY-153. SEGMENT 1: PENDLETON ROAD (KY 153) TO LOST CREEK (1/2 MILE EAST OF SAFETY KLEEN ENTRANCE). MILE POINT 2.1 TO MILE POINT 6.8. (06CCN)(08CCR)(10CCR)(12CCR)(14CCR)(18CCR) | RECONSTRUCTION(O) | Henry | 052-KY-0146 -000 | 2.169 | 6.8 | 4.631 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 32000000 | 2019 | 2019-03-06 11:49 | Improve safety with maintaining the efficiency of KY 146 from KY 153 near the I-71 interchange to US 421 at New Castle. Segment 1: KY 153 to Lost Creek (1/2 mile east of Safety Kleen entrance). | This project is needed due to a steep grade at the western end of the project ("Pendleton Hill"), and improperly banked curve at "Baxter Curve" near Dawkins Lane, poor sight distance at the KY 1606 intersection, several blind entrances to local roads and | 5 | North | 69.6785 | 2.1785 | 10.4769 | 7.8692 | 3.2154 | 7.0154 | 0 | 8.9231 | 40 | 15 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110064 | 5-549 | 2020-09-15 | A | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. (2016BOP) | I-CHANGE RECONST(O) | Jefferson | 056-I -0265 -000 | 25.215 | 25.746 | 0.531 | Innovative Interchange | 40 | Y |  |  | 0 | 2018 | 1250000 | 2019 | 1270000 | 2019 | 39740000 | 2020 | 2019-03-07 12:57 | The purpose of the Gene Snyder Interchange Project is to enhance the operation and improve the safety of the I-265/I-64 Interchange. | The present operation and safety of the I-265/I-64 interchange is considered deficient based on a poorly linked, congested, and functionally obsolete transportation network. With a current Average Daily Traffic (ADT) count of 76,700, the current Level of
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20130147 | 5-808 | 2020-02-15 | A | SAFETY PROJECT FOR RECONSTRUCTION OF TAYLORSVILLE ROAD AND SOUTH POPE LICK ROAD INTERSECTION AND BRIDGE OVER POPE LICK CREEK. (2016BOP) | DESIGN ENGINEERING(O) | Jefferson | 056-KY-0155 -000 | 4.4 | 5 | 0.6 | Improve Intersection | 26 |  |  |  | 0 |  | 620000 | 2019 | 240000 | 2019 | 5000000 | 2019 | 2019-03-08 07:42 | Improve intersection safety and maintain continuity for roadway users, park users, and local residents at and near the KY 155/South Pope Lick Road intersection in eastern Jefferson County. | This project is needed because traffic has increased significantly with recent developments in the area including the new 4,000 acre Parklands of Floyds Fork recreational area making it difficult for vehicles to turn onto KY 155 from the approach roads at | 5 | North | 57.4727 | 8.8554 | 14.2615 | 7.2808 | 2.3846 | 0 | 3.6154 | 6.075 | 42 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150183 | 5-21.10 / 5-549 / 5-549.01 | 2020-09-15 | A | SNYDER FREEWAY: RECONSTRUCT I-64 EB TO I-265 RAMPS WITH POSSIBLE AUXILIARY LANES ON I-64 EB FROM KY 913 TO I-265. (2006BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0064 -000 | 18.446 | 19.525 | 1.079 | Innovative Interchange | 40 | Y |  |  | 1450000 | 2018 | 7540000 | 2019 | 11140000 | 2019 | 102780000 | 2020 | 2016-05-24 07:22 | The purpose of this project is to improve traffic operations and safety in the I-265 (Gene Snyder Freeway)/I-64 interchange area. | This project is needed because of vehicular delay and queuing experienced during the peak hours and a high volume of crashes within the I-265 (Gene Snyder Freeway)/I-64 interchange and area of influence. Insufficient capacity within the existing interchan
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150184 | 5-549 | 2020-09-15 | A | RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE. (2016BOP) | I-CHANGE RECONST(O) | Jefferson | 056-PF-9999 - |  |  |  | Innovative Interchange | 40 | Y |  |  | 0 | 2018 | 1250000 | 2019 | 1270000 | 2019 | 39740000 | 2020 | 2019-03-07 12:57 | The purpose of this project is to improve traffic operations and safety in the interchange area. | The need for this project is based on vehicular delay and queuing experienced during the peak hours and a high volume of crashes within the interchange and area of influence. Insufficient capacity within the existing interchange configuration and heavy w | 5 | Statewide | 63.9193 | 19.0837 | 9.2511 | 12.6872 | 4.4053 | 0 | 6.7401 | 11.7519
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150195 | 5-371.13 | 2019-06-21 | A | RECONSTRUCT KY-22 AT GOOSE CREEK ROAD. (06CCN) (2004BOPC)(14CCR)(18CCR) | SAFETY(P) | Jefferson | 056-KY-0022 -000 | 2.537 | 2.937 | 0.4 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 870000 | 2020 | 2019-03-07 16:01 | Improve safety and traffic operations at the KY 22/Goose Creek Road intersection. | This project is needed because KY 22 near the Goose Creek Road intersection has a critical crash rate factor greater than that of similar roads in the state. There is also an inadequate capacity to handle turning movements at the intersection. | 5 | North | 46.1823 | 6.2092 | 10.3846 | 4.2346 | 1.5231 | 0 | 2.7077 | 6.1231 | 31 | 15
N; Committed | 5 | KIPDA ADD | IP20150314 | 5-8511 | 2020-04-15 | A | WIDEN KY-53 TO FOUR LANES FROM I-64 TO US-60.(08CCN)(10CCN) (12CCR)(14CCR)(16CCR)(18CCR) | RECONSTRUCTION(O) | Shelby | 106-KY-0053 -000 | 6.064 | 8.006 | 1.942 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 0 |  | 0 |  | 0 |  | 22580000 | 2019 | 2019-03-07 15:04 | The purpose of the KY 53 Widening Project is to promote better connectivity, improve safety, and reduce congestion on KY 53 between I-64 and US 60. | This project would provide an improved connection between I-64 and Shelbyville's downtown and commercially growing east side. KY 53 is a 2 lane facility with a 2017 ADT of 17,762 and a 2028 projected ADT of 30,200. The route currently suffers from recurri | 5 | North | 85.7338 | 7.6185 | 13.7077 | 12.7615 | 0 | 9.1385 | 4.2 | 8.3077 | 56 | 15 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150450 | 5-483 | 2019-10-25 | A | SIX LANE PRIORITY SECTION OF I-71 BETWEEN I-265 AND KY-329.(16CCR) | MAJOR WIDENING(O) | Oldham | 093-I -0071 -000 | 11.315 | 14.1 | 2.785 | Add Lane to Full Control Facility | 25 | Y |  |  | 0 |  | 1500000 | 2018 | 1500000 | 2018 | 180000000 | 2019 | 2018-07-10 08:18 | The Purpose of the I-71 widening and reconstruction is to address the capacity deficiencies and operational issues that currently characterize the existing corridor and provide increased efficiency and safety for the traveling public. It will serve thro | The Needs being addressed by the proposed I-71 project are based on the following facts: • Increasing traffic volumes have resulted in traffic congestion and poor traffic flow characteristics. In 2009, the Average Daily Traffic was 56,600 vehicles per d | 5 | Statewide | 73.8296 | 17.1806 | 10.5727 | 10.1927 | 4.4053 | 8.7004 | 9.3392 | 13.4387
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160177 | 5-371.10 | 2020-07-15 | A | RECONSTRUCT KY-22 AT SPRINGCREST DRIVE. (06CCN) (2004BOPC)(14CCR)(EMERGENCY CULVERT REPLACEMENT AWARDED UNDER 5-371.12) | SAFETY(P) | Jefferson | 056-KY-0022 -000 | 1.432 | 1.789 | 0.357 | Improve Intersection | 26 | [9 empty] | 2020000 | 2022 |  | The purpose of this project is to provide better turning movements and improve safety on KY 22 at the intersection with Springcrest Drive, thereby improving the existing corridor and supporting the overall quality of life of the roadway users. | For the three-year period from 2001-2003, there were thirty crashes on the section of roadway between Greenlawn and Brownhurst Cove Rd. The Springcrest interesection is within this section. The project is needed because twelve of these crashes were rear-e | 5 | North | 51.1092 | 6.2092 | 11.1692 | 6.8077 | 3.3385 | 0 | 2.7077 | 5.8769 | 36 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160186 | 5-323.01 | 2022-01-15 | A | WIDEN GREENWOOD ROAD FROM GREENBELT HWY TO DIXIE HWY (US-31W) (3-LANE IMPROVEMENT) FROM MP 0.54 TO MP 3.148. (98CCR)(R-04DEOB)(04CCR)(BOP2006P)(10CCR)(12CCR) | MAJOR WIDENING(O) | Jefferson | 056-KY-1931 -000 | 0.54 | 3.148 | 2.608 | Install Two-way Left Turn Lane | 28 | [5 empty] | 0 |  | 9840000 |  | 19420000 | 2022 | 2018-07-10 08:18 | Improve safety and mobility on Greenwood Road (KY 1931) between Greenbelt Highway (KY 1934) and Dixie Highway (US- 31W) by providing operational improvements and safety countermeasures for vehicles, pedestrians and bicyclists. | Accident data for the last five years show that there have been close to 300 accidents, with an additional 95 accidents involving injuries. Cyclists and pedestrians have few accommodations. | 5 | North | 85.1238 | 7.8892 | 13.7538 | 13.7423 | 2.5692 | 8.8923 | 0 | 8.2769 | 55 | 15 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160190 | 5-247.10 | 2020-04-15 | A | WIDEN BLUE LICK ROAD FROM SNYDER FREEWAY NORTH TO KY-61 (LOU T.I.P.) (SECTION 2) (RU-04DEOB)(08CCR)(12CCR)(16CCR) | MAJOR WIDENING(O) | Jefferson | 056-KY-1450 -000 | 1.873 | 3.542 | 1.669 | Install Two-way Left Turn Lane | 28 | [5 empty] | 0 |  | 0 |  | 20980000 | 2020 | 2019-03-07 16:05 | The purpose of this project is to improve safety and relieve congestion while accommodating pedestrian traffic. | Blue Lick Road (KY 1450) from I-265 to Preston Highway is currently a two lane road with narrow driving lanes, no shoulders, and steep roadside ditches. The crash rate in the project area is approximately double the statewide average for similar facilitie | 5 | North | 71.1254 | 7.8831 | 11.6308 | 12.1962 | 3.6462 | 8.4615 | 3.3077 | 9 | 56 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160217 | 5-391.20 | 2020-07-15 | A | WIDEN CEDAR GROVE ROAD (KY-480) FROM CEDAR GROVE ELEMENTARY SCHOOL TO VALLEY VIEW DRIVE. (12CCR)(14CCR) (SEE 5-391.3 FOR INTERCHANGE IMPROVEMENTS) | RECONSTRUCTION(O) | Bullitt | 015-KY-0480 -000 | 1.698 | 2.84 | 1.142 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 7900000 | 2022 | 2019-03-01 14:13 | Improve capacity and safety on KY 480 (Cedar Grove Road) from Omega Parkway to Valley View Drive. | The project is needed because the capacity of KY 480 (Cedar Grove Road) from Omega Parkway to Valley View Drive is inadequate to meet current and future traffic volumes, resulting in congestion. Current level of service and projected level of service in | 5 | North | 67.8938 | 3.8092 | 8.4 | 5.8846 | 2.5692 | 7.6308 | 2.7385 | 6.8615 | 38 | 15 | 15
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160234 | 5-539 | 2019-10-25 | A | PROVIDE COLLECTOR-DISTRIBUTOR LANE ON SOUTHBOUND I-71 TO FACILITATE RAMP MOVEMENTS TO AND FROM I-265. | RECONSTRUCTION(O) | Jefferson | 056-I -0071 -000 | 8.5 | 10 | 1.5 | Auxiliary Lanes or Operation Improvements | 11 | Y |  |  | 0 | [5 empty] | 4400000 | 2019 | 2018-07-10 08:18 | The purpose of the proposed project is to facilitate traffic flow on I-71 and improve ramp movement efficiency to and from I-265. | I-71, I-265, and the interchange between these facilities carry high traffic volumes, particularly during peak travel periods. Capacity analysis using the HCS7 Freeways module indicates the weaving segment (between the I-71 southbound loop ramps) is over | 5 | Statewide | 78.863 | 17.8502 | 17.7974 | 11.4317 | 4.4053 | 7.7974 | 9.2511 | 10.3299
N; Committed | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20190047 | 5-483.30 | 2020-06-15 | A | CONSTRUCT NEW I-71 INTERCHANGE BETWEEN KY-393 AND KY-53 TO RELIEVE CONGESTION IN LAGRANGE. | NEW INTERCHANGE(O) | Oldham | 093-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 |  |  |  | 3000000 | 2018 | 6000000 | 2019 | 3800000 | 2019 | 24960000 | 2020 | 2019-03-06 10:32 | The purpose of the project is to provide connectivity to the surrounding development/community that is already experiencing growth today. | The need is that the existing KY 53 Interchange experiences congestion today.
N; Committed | 6 | Northern Kentucky ADD | IP20000015 | 6-78 |  | A | IMPROVE FREIGHT MOBILITY AT I-275 AND GRAVES ROAD (CONTINUATION OF 6-8953: INTERCHANGE JUSTIFICATION STUDY ON I-275/GRAVES RD).(18CCR) | NEW INTERCHANGE(O) | Boone | 008-I -0275 -000 | 7.2 | 8.9 | 1.7 | Construct Road in New Location | 0 | Y |  |  | 12000000 | 2019 | 51520000 | 2020 | 8800000 | 2020 | 100000000 | 2020 | 2018-12-14 09:09 |  | Increased freight and residential traffic has occurred along/near KY 237 & Worldwide Blvd. such that traffic queues on mainline I-275 and takes 30 minutes to exit and get north of Worldwide. Worldwide is connected to Graves Rd. to the west. Freight woul | 6 | Statewide | 56.8899 | 14.1145 | 14.3612 | 7.4009 | 1.8062 | 9.9119 | 9.2952 | 0
N; Committed | 6 | Northern Kentucky ADD | IP20070208 | 6-449 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-17 AT THE I-275 INTERCHANGE. (18CCR) | CONGESTION MITIGTN(O) | Kenton | 059-KY-0017 -000 | 18.15 | 18.65 | 0.5 | Innovative Interchange | 40 |  |  |  | 0 | 2019 | 200000 | 2020 | 350000 | 2020 |  |  | 2018-07-10 08:17 |  | The current conditions of KY 17 does not supply sufficient capacity and extensive growth is planned for the southern portion of the county. ADD ADDITIONAL CAPACITY ON KY-17 FROM HOLDS BRANCH TO I-275 | 6 | North | 73.7546 | 9.3046 | 13.0154 | 11.4346 | 0 | 0 | 4.0923 | 5.9077 | 44 | 15 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20080361 | 6-450 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | CONGESTION MITIGTN(O) | Kenton | 059-KY-1303 -000 | 5.01 | 6.248 | 1.238 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2019 | 2000000 | 2019 | 1000000 | 2020 |  |  | 2018-07-10 08:17 |  | Improve travel safety, accessibility and mobility options for people and goods. Enhance the integration and connectivity of the transportation system and support economic vitality. This corridor serves access to Crestview Hills Mall, a medical office par | Cincinnati/Northern Kentucky MPO | North | 78.6423 | 7.0154 | 13.1077 | 13.4885 | 3.1385 | 0 | 4.3538 | 7.5385 | 49 | 15 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20130051 | 6-450 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | CONGESTION MITIGTN(O) | Kenton | 059-KY-1303 -000 | 5.39 | 5.5 | 0.11 | Realign Intersection | 26 |  |  |  | 0 | 2019 | 2000000 | 2019 | 1000000 | 2020 |  |  | 2018-07-10 08:17 |  | Reduce congestion, improve safety and support economic vitality of the area. The area provides access to I-275, Crestview Hills Mall, a medical office park, St. Elizabeth Hospital and Thomas More College. The project needs to address multi-modal needs o | 6 | North | 37.3169 | 7.0092 | 8.5385 | 11.8154 | 1.5231 | 0 | 4.3385 | 4.0923 | 37
N; Committed | 6 | Northern Kentucky ADD | IP20150217 | 6-14 | 2019-05-24 | A | IMPROVE THE KY-536 (MT. ZION ROAD) INTERCHANGE. (14CCR)(16CCR)(18CCR) | I-CHANGE RECONST(O) | Boone | 008-I -0075 -000 | 177.659 | 178.345 | 0.686 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 |  | 5430000 | 2018 | 17000000 | 2021 | 2019-03-11 11:17 |  |  | 6 | Statewide | 54.2044 | 17.815 | 5.5507 | 7.3348 | 4.4053 | 0 | 9.9119 | 9.1868
N; Committed | 6 | Northern Kentucky ADD | IP20150241 | 6-8307.10 | 2019-09-20 | A | IMPROVE HANDS PIKE (KY-1501) FROM KY-17 TO CRYSTAL LAKE DRIVE.(12CCR)(14CCR)(16CCR) | RECONSTRUCTION(O) | Kenton | 059-KY-1501 -000 | 0 | 1.032 | 1.032 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 760000 |  | 0 |  | 8010000 | 2019 | 2018-07-10 08:18 |  | The existing KY 1501 (Hands Pike) provides a vital east-west connection in this fast growing area of Kenton County. The sharp curves and steep grades of Hands Pike make this road unsafe with the high existing and future traffic volume. ADT on existing K | 6 | North | 75.5346 | 6.9538 | 10.9385 | 9.0115 | 3.9231 | 7.3538 | 0 | 7.3538 | 46 | 15 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20150242 | 6-162.20 | 2020-06-15 | A | IMPROVE SAFETY AND REDUCE CONGESTION ON KY-536 FROM THE WEST END OF THE NS RAILROAD BRIDGE (B91) TO KY-1303 (PRIORITY SECTION 1). DESIGN PHASE UNDER PARENT NO. 6-162.01. (16CCN)(18CCR) | RECONSTRUCTION(O) | Kenton | 059-KY-0536 -000 | 0 | 1.061 | 1.061 | Arterial to Partial Control | 23 | [5 empty] | 0 |  | 0 | 2019 | 21640000 | 2020 | 2018-12-04 09:59 |  |  | 6 | North | 73.3669 | 4.5785 | 9.3692 | 7.7885 | 4.8462 | 7.4462 | 2.8462 | 6.4923 | 43 | 15 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20150285 | 6-8706 | 2019-07-26 | A | IMPROVE SAFETY ON US-27 FROM BUTLER IN PENDLETON COUNTY TO SOUTH OF KY-154 IN CAMPBELL COUNTY.(12CCN)(14CCR) | MAJOR WIDENING(O) | Campbell | 019-US-0027 -000 | 0 | 1.9 | 1.9 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 5000000 | 2020 | 2018-09-27 10:33 |  | 1. In Campbell County the intersection of US 27/North Short Fairlane Road/Plum Creek Road/ Green Acres Bar. This area has a high accident rate and could use some access management and left turn lanes: i. Right of Way $500,000 ii. Utilities | Cincinnati/Northern Kentucky MPO | North | 52.3738 | 4.7508 | 5.8154 | 6.6692 | 1.3538 | 7.7846 | 3.7692 | 7.2308 | 37 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20150323 | 6-14.50 | 2019-01-25 | A | ADD AUXILIARY LANES ON I-71/75 FROM KY-536 TO US-42 (NB & SB) AS PER THE INTERCHANGE JUSTIFICATION STUDY (IJS).(10CCR)(12CCR)(LET W/ 6-20002.10) | MINOR WIDENING(O) | Boone | 008-I -0075 -000 | 178.039 | 180.106 | 2.067 | Auxiliary Lanes or Operation Improvements | 11 | Y |  |  | 0 |  | 4300000 |  | 0 | 2018 | 20000000 | 2024 | 2018-07-10 08:18 |  |  | 6 | Statewide | 69.8226 | 18.7665 | 12.8634 | 11.0848 | 4.4053 | 0 | 9.7797 | 12.9229
N; Committed | 6 | Northern Kentucky ADD | IP20150387 | 6-198 / 6-198.01 | 2019-12-13 | A | IMPROVE SAFETY ON KY-22 FROM KY-227 TO KY-845. (06CCR)(08CCN)(12CCR)(14CCR) | PREFINANCD CONVRSN(P) | Owen | 094-KY-0022 -000 | 11.315 | 16.057 | 4.742 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 1000000 |  | 13500000 | 2020 | 2018-10-23 12:06 | RECONSTRUCT KY-22 AT KY-227 AT END OF NEW CONSTRUCTION TO 0.4 MILE EAST OF KY 845 SOUTH TO BRING GEOMETRIC DEFICIENCIES UP TO MODERN STANDARDS. (06CCR)(08CCN)(12CCR)(14CCR) | KY 22 is a major east-west corridor that is a primary focus in the rural NKY region. This is a small part of the larger KY 22 project that connects 3 counties to each other and the I 75 corridor. | 6 | North | 63.7092 | 1.04 | 6.4154 | 6.0231 | 4.6923 | 6.0308 | 0 | 9.5077 | 34 | 15 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20160009 | 6-450 |  | A | IMPROVE SAFETY AND REDUCE CONGESTION ALONG KY-1303 (TURKEYFOOT RD) FROM DUDLEY RD TO US-25 (DIXIE HWY). (18CCR) | CONGESTION MITIGTN(O) | Kenton | 059-KY-1303 -000 | 5.285 | 5.396 | 0.111 | Other Improvement Types | 0 |  |  |  | 0 | 2019 | 2000000 | 2019 | 1000000 | 2020 |  |  | 2018-07-10 08:17 |  | The large number of NB KY 1303 peak hour vehicles needing to make right turns on to Thomas More Parkway is limited by the larger volume of thru traffic who are in a dedicated lane to access EB I-275 further downstream. Safety: From 2011 thru 2015 there
N; Committed | 6 | Northern Kentucky ADD | IP20160288 | 6-18 | 2019-08-23 | A | RECONSTRUCT THE KY-338 (RICHWOOD ROAD) INTERCHANGE. (FUNDING FOR IMR SHOWN UNDER 6-14.01) (10CCR)(12CCR)(14CCR)(16CCR) | I-CHANGE RECONST(O) | Boone | 008-I -0075 -000 | 175.217 | 175.622 | 0.405 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 | 2019 | 14000000 | 2020 | 125900000 | 2021 | 2017-03-31 15:35 |  | Interchange provides residential access to west and significant industrial/distribution warehouses to the east. Improvements will address safety and congestion. Improvements to eliminate to at-grade crossings with NS RR. | 6 | North | 65.0777 | 9.12 | 3.8769 | 10.1423 | 1.1231 | 0 | 5 | 5.8154 | 35 | 15 | 15
N; Committed | 6 | Northern Kentucky ADD | IP20190183 | 6-937 |  | A | SPOT IMPROVEMENTS AND CONGESTION MITIGATION IN BOONE COUNTY FOR AMAZON DEVELOPMENT. (18CCR) | SAFETY(P) | Boone | 008-PF-9999 - | [14 empty] | 8000000 | 2018
N; Committed | 7 | Lexington MPO | IP20070218 | 7-915 | 2019-12-13 | A | IMPROVE INTERSECTION OF KY-29 NORTH OF WILMORE.(16CCR)(18CCR) | SAFETY(P) | Jessamine | 057-US-0068 -000 | 4.1 | 4.8 | 0.7 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 650000 | 2019 | 1600000 | 2020 | 2019-03-04 17:51 | Improve safety and mobility, and roadway geometrics at the intersection at KY 29 North of Wilmore. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Roadway Geometrics, 3) Improve Mobility. | Lexington MPO | North | 67.1169 | 5.1323 | 13.2 | 7.2 | 2.9846 | 0 | 2.8154 | 5.7846 | 37 | 15 | 15
N; Committed | 7 | Bluegrass ADD | IP20150427 | 7-235 |  | A | IMPROVE KY-52 FROM WALLACE MILL ROAD TO INTERSTATE 75 AT THE DUNCANNON ROAD INTERCHANGE. (02CCR)(12CCN)(14CCR) (DESIGN/BUILD)(16CCR)(18CCR) | RECONSTRUCTION(O) | Madison | 076-KY-0052 -000 | 1.17 | 4.019 | 2.849 | Modernize Roadway-Rural | 26 | [5 empty] | 0 | 2019 | 3930000 | 2020 | 22490000 | 2020 | 2019-03-12 11:33 | Improve safety and mobility on KY-52 from Wallace Mill Rd. to I-75 at the Duncannon Rd. interchange. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility. | 7 | North | 65.1746 | 1.5631 | 4.9385 | 7.95 | 3.4769 | 5.6923 | 2.0154 | 9.5385 | 35 | 15 | 15
N; Committed | 7 | Bluegrass ADD | IP20160208 | 7-251.40 | 2022-07-15 | A | PRIORITY SECTION II & III: WIDEN US-25 FROM US-421 TO PUMPKIN RUN.(SEE 7-251.10 FOR SEC III UTIL & CONST) (2006BOPC)(08CCR)(10CCR)(12CCR)(14CCR) | MAJOR WIDENING(O) | Madison | 076-US-0025 -000 | 11.903 | 14.883 | 2.98 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 13390000 | 2024 | 2019-03-08 09:56 | Improve safety and mobility and reduce congestion on US-25 from US 421 to Pumpkin Run. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility, 3) Reduce Congestion. | BLUEGRASS ADD | North | 82.7477 | 8.6092 | 11.4 | 9.5538 | 1.5231 | 9.2923 | 4.2154 | 8.1538 | 53 | 15 | 15
N; Committed | 7 | Bluegrass ADD | IP20160222 | 7-8403 | 2019-02-22 | A | IMPROVE SAFETY AND REDUCE CONGESTION AT THE KY-627 BRIDGE OVER I-75. (INCLUDES 7-8400) (B40)(08CCN)(10CCR)(14CCR)(16CCR)(18CCR) | MAJOR WIDENING(O) | Madison | 076-KY-0627 -000 | 0.073 | 0.193 | 0.12 | Innovative Interchange | 40 | Y |  |  | 0 |  | 0 |  | 0 |  | 0 | 2018 | 2019-02-05 08:41 | Reduce traffic congestion and improve mobility on the KY-627 bridge over I-75. | The following needs have been identified on this project: 1) Reduce Congestion, 2) Improve Mobility. | 7 | North | 58.4431 | 6.8492 | 4.0615 | 7.1077 | 1 | 0 | 3.7846 | 5.64 | 28 | 15 | 15
N; Committed | 8 | Lake Cumberland ADD | IP20070234 | 8-59.25 |  | A | IMPROVE KY-461 FROM KY-80 TO BUCK CREEK BRIDGE, INCLUDING INTERCHANGE AT KY-80. (18CCR) | MAJOR WIDENING(O) | Pulaski | 100-KY-0461 -000 | 0 | 3.879 | 3.879 | Modernize Roadway-Rural | 26 | Y | 1000000 |  |  |  | 12000000 | 2019 | 6000000 | 2020 | 26000000 | 2021 | 2018-07-10 08:18 | This project is needed because the capacity of KY 461 between KY 80 and Buck Creek Bridge, including the interchange at KY 80, is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues and reduced mobility on this st | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 77.0628 | 7.6967 | 8.1043 | 10.077 | 1.019 | 8.1043 | 4.6682 | 7.3934 | 47 | 15 | 15
N; Committed | 8 | Bluegrass ADD | IP20150148 | 8-196 | 2020-02-15 | A | IMPROVE US-27 FROM KY-590 TO BELL STREET IN STANFORD. (INCLUDES NEW GOSHEN CUT-OFF ROAD)(2005HPP-KY115)(18CCR) | MAJOR WIDENING(O) | Lincoln | 069-US-0027 -000 | 18.2 | 18.9 | 0.7 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 2800000 | 2019 | 2200000 | 2019 | 13000000 | 2020 | 2018-07-10 08:18 | Widen US-27 From KY-590 To Bell Street In Stanford (Mp 18.2 To Mp 18.9). (Includes New Goshen Cut-Off Road)(2005Hpp-KY115) | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | 8 | South | 75.7275 | 5.7156 | 12.8673 | 9.3483 | 0.78199 | 9.1469 | 3.3649 | 4.5024 | 46 | 15 | 15
N; Committed | 8 | Lake Cumberland ADD | IP20150306 | 8-109.10 | 2020-06-15 | A | IMPROVE KY-90 FROM OLD MILL SPRINGS ROAD TO THE BRIDGE AT MP 19.5. (12CCR)(16CCR)(18CCR) | SAFETY(P) | Wayne | 116-KY-0090 -000 | 17.691 | 19.5 | 1.809 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 8440000 | 2020 | 2018-07-10 08:18 | This project is needed because the geometrics along KY 90 between Old Mill Springs Road and the bridge at MP 19.5 are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 46.5225 | 7.4882 | 7.109 | 6.096 | 0.92417 | 0 | 4.218 | 5.6872 | 32 | 15
N; Committed | 8 | Lake Cumberland ADD | IP20150372 | 8-8601.21 / 8-8601.26 | 2019-08-23 | A | RELOCATE US-127 FROM EAST OF THE KY-1730 AND MANNTOWN RD INTERSECTION, AND EXTENDING NORTHERLY TO NORTH BANK OF CUMBERLAND RIVER (SEE 8-108&8-115 FOR PE/PH.2)(12CCR)(14CCR) | RELOCATION(O) | Russell | 104-US-0127 -000 | 0 | 2.5 | 2.5 | Construct Road in New Location | 0 | Y |  |  | 0 |  | 0 |  | 0 |  | 180240000 | 2019 | 2018-07-10 08:18 |  | This section of the US 127 corridor provides very limited passing opportunities for more than 9.9 miles, causing congestion and interrupting the natural traffic flow. | 8 | Statewide | 14.3833 | 0 | 0 | 4.2952 | 9.9119 | 0 | 0.17621 | 0
N; Committed | 9 | FIVCO ADD | IP20150210 | 9-144 | 2019-05-24 | A | IMPROVE KY-7/KY-1 (CAROL MALONE BLVD.) FROM LITTLE SANDY RIVER BRIDGE TO ACADEMIC PARKWAY. (08CCR)(12CCR)(16CCR) | MAJOR WIDENING(O) | Carter | 022-KY-0007 -000 | 10.318 | 10.865 | 0.547 | Modernize Roadway-Rural | 26 | [9 empty] | 0 | 2021 | 2018-09-25 13:20 |  |  | FIVCO ADD | East | 86.0853 | 7.8443 | 13.8323 | 13.5404 | 1.6467 | 9.7006 | 4.0719 | 5.4491 | 56 | 15 | 15
N; Committed | 9 | Gateway ADD | IP20150311 | 9-204 |  | A | IMPROVE KY-32 FROM PARK HILLS DRIVE TO VIKING DRIVE NORTH. (12CCR)(18CCR) | RECONSTRUCTION(O) | Rowan | 103-KY-0032 -000 | 2.235 | 4.157 | 1.922 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 11040000 | 2020 | 8420000 | 2021 | 42200000 | 2021 | 2018-07-10 08:18 |  |  | GATEWAY ADD | East | 83.3802 | 9.1138 | 9.7006 | 12.979 | 1.1078 | 9.2814 | 4.4311 | 6.7665 | 53 | 15 | 15
N; Committed | 9 | Gateway ADD | IP20150366 | 9-8406 |  | A | IMPROVE SAFETY AND CONNECTIVITY AND REDUCE CONGESTION ON KY-377 FROM KY-32 TO NORTH OF KY-799. (08CCN)(10CCR)(16CCR)(18CCR) | RECONSTRUCTION(O) | Rowan | 103-KY-0377 -000 | 0 | 8.2 | 8.2 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 5210000 | 2020 | 7700000 | 2021 | 54750000 | 2022 | 2018-07-10 08:18 | The purpose of this project is to improve: safety, capacity, and connectivity. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Increase Capacity, and 3) Improve Connectivity. | GATEWAY ADD | East | 76.232 | 3.3653 | 9.2515 | 13.5853 | 2.2455 | 7.7844 | 0 | 10 | 46 | 15 | 15
N; Committed | 9 | FIVCO ADD | IP20160292 | 9-62 |  | A | IMPROVE MOBILITY AND REDUCE CONGESTION AT THE KY 1/I-64 WESTBOUND OFF-RAMP INTERSECTION. | CONGESTION MITIGTN(O) | Carter | 022-I -0064 -000 | 171.6 | 171.8 | 0.2 | Improve Intersection | 26 | Y |  |  | 0 | 2019 | 80000 | 2019 | 80000 | 2019 | 500000 | 2019 | 2018-07-10 08:17 |  | The KY 1/I-64 westbound ramp intersection currently operates at LOS C in the PM peak hour; however, the westbound left turns operate at LOS F with 89.4 seconds/vehicle in delay. In the 2040 No-Build design year, although the overall intersection drops to | 9 | East | 58.012 | 9.6287 | 14.9102 | 7.9042 | 0.41916 | 0 | 5 | 5.1497 | 43 | 15
N; Committed | 9 | FIVCO ADD | IP20190159 | 9-397 / 9-397.01 / 9-397.02 |  | A | SAFETY, SPOT IMPROVEMENTS AND CONGESTION MITIGATION FOR INDUSTRIAL PARKWAY (KY 67) IN CARTER, BOYD, AND GREENUP COUNTIES FOR BRAIDY INDUSTRIES ALUMINUM PLANT DEVELOPMENT. | SAFETY(P) | Carter | 022-KY-0067 -000 | 0 | 0.335 | 0.335 | Major Widening-Rural Mutilane | 34 |  |  |  | 0 | 2018 | 5260000 | 2019 | 5000000 | 2019 | 35360000 | 2020 | 2019-03-13 14:37 | Widen KY 67 (Industrial Parkway) to 4 lanes from I-64 in Carter County to Technology Drive in Greenup County to improve safety and congestion of anticipated traffic generated by Braidy Industries. | Braidy Industries, a prospective aluminum producer, is planning to locate an aluminum mill that is expected to employee 550+ jobs at full production. With the employee traffic and projected freight traffic, it is proposed to widen the current two-lane ro
N; Committed | 10 | Big Sandy ADD | IP20040034 | 10-126.40 | 2019-08-23 | A | MOUNTAIN PARKWAY CORRIDOR: WIDEN THE MOUNTAIN PARKWAY TO 4 LANES FROM 0.3MI W OF KY 3047 (65.0) TO 0.7 MI W OF MIDDLE FORK LICKING RIVER BRIDGE (69.6). (2012BOP)(14CCR)(16CCR) | MAJOR WIDENING(O) | Magoffin | 077-KY-9009 -000 | 65 | 69.531 | 4.531 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 0 |  | 0 |  | 3400000 |  | 320000000 | 2019 | 2018-07-10 08:18 |  |  | BIG SANDY ADD | Statewide | 42.9124 | 4.37 | 7.8414 | 4.8238 | 8.8546 | 0 | 2.7753 | 14.2472
N; Committed | 10 | Kentucky River ADD | IP20060272 | 10-8906 |  | A | SAFETY IMPROVEMENTS ON KY-80 FROM LESLIE COUNTY LINE TO KY-451. (16CCN) | SAFETY(P) | Perry | 097-KY-0080 -000 | 0 | 4.6 | 4.6 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2019 | 350000 | 2020 | 280000 | 2020 | 5620000 | 2022 | 2019-03-06 14:41 |  | To replace an existing local corridor with numerous maintenance and safety issues. | 10 | East | 60.1153 | 6.2754 | 13.7425 | 13.0015 | 3.5329 | 0 | 0 | 8.5629 | 45 |  | 15
N; Committed | 10 | Bluegrass ADD | IP20150125 | 10-211 | 2020-03-15 | A | CORRECT FLOODING ISSUES ON KY-2026 FROM KY-11 TO THE RED RIVER IN CLAY CITY. | RECONSTRUCTION(O) | Powell | 099-KY-2026 -000 | 0.045 | 0.381 | 0.336 | Maintenance Improvement | 10 |  |  |  | 0 | 2019 | 200000 | 2020 | 150000 | 2020 | 1150000 | 2021 | 2019-02-25 09:37 | Correct flooding issues on KY 2026 at Clay City in Powell County. | This section is closed multiple times each year due to flooded roadway. | BLUEGRASS ADD | East | 3.3743 | 0.87425 | 0 | 0.22455 | 2.2754 | 0 | 0 | 0 | 3
N; Committed | 10 | Gateway ADD | IP20150253 | 10-8802 | 2020-07-15 | A | IMPROVE SAFETY AND GEOMETRICS ON US-460 FROM THE END OF ROTHWELL HILL IMPROVEMENTS TO THE BRIDGE OVER BEAVER CREEK. (14CCN)(16CCR)(18CCR) | SAFETY(P) | Menifee | 083-US-0460 -000 | 6.2 | 8.5 | 2.3 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2020 | 0 | 2020 | 27060000 | 2021 | 2018-12-10 16:08 | The purpose of this project is to improve: safety and geometrics. | The following needs have been identified for this project: 1) Improve Roadway Safety, and 2) Improve Substandard Geometrics. | GATEWAY ADD | East | 65.5195 | 5.9162 | 7.1856 | 8.0165 | 3.3533 | 0 | 3.5629 | 7.485 | 36 | 15 | 15
N; Committed | 10 | Kentucky River ADD | IP20150394 | 10-279.60 / 10-279.61 | 2019-08-23 | A | IMPROVE KY-30 FROM KY-847 IN OWSLEY COUNTY TO JACKSON COUNTY LINE.(LET W/ JACKSON CO. SECTION UNDER 11-278.30)(SEE 10-279.60 FOR PE & ENVIR)(AR/W)(14CCR)(16CCR)(18CCR) | RECONSTRUCTION(O) | Owsley | 095-KY-0030 -000 | 0 | 5.166 | 5.166 | Modernize Roadway-Rural | 26 |  | 0 |  | 0 |  | 0 |  | 0 |  | 229000000 | 2019 | 2014-07-24 07:59 | RECONSTRUCT KY 30 FROM KY 847 TO THE JACKSON COUNTY LINE.(14CCR)(SEE 10-279.60 FOR PE & ENVIR) | RECONSTRUCT KY 30 FROM KY 847 TO THE JACKSON COUNTY LINE.(14CCR)(SEE 10-279.60 FOR PE & ENVIR) | KENTUCKY RIVER ADD | East | 55.6766 | 1.0659 | 5.7485 | 10.4192 | 4.491 | 6.4072 | 3.024 | 9.521 | 41 |  | 15
N; Committed | 10 | Bluegrass ADD | IP20170014 | 10-208 | 2020-01-15 | A | IMPROVE SAFETY AND MOBILITY ON KY-1645 (KIRKLAND AVE) NEAR CR-1087 (LOCK 12 ROAD). | RECONSTRUCTION(O) | Estill | 033-KY-1645 -000 | 1.7 | 2.1 | 0.4 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2019 | 100000 | 2020 | 50000 | 2020 | 340000 | 2020 | 2019-02-25 09:25 | Reconstruction of KY 1645 between mile points 1.7 and 2.1 to more safely move people, goods, and services. | This section contains two horizontally deficient curves that hinders the travel flow. | BLUEGRASS ADD | East | 55.8204 | 0.37126 | 7.9042 | 3.2335 | 4.5509 | 5.8683 | 0 | 3.8922 | 26 | 15 | 15
N; Committed | 11 | Cumberland Valley ADD | IP20000082 | 11-9.10 / 11-9.14 / 11-9.15 / 11-9.16 | 2019-03-22 | A | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | PREFINANCD CONVRSN(O) | Laurel | 063-I -0075 -000 | 28.85 | 33.062 | 4.212 | Add Lane to Full Control Facility | 25 | Y |  |  |  |  | 280000 | 2019 | 200000 | 2019 | 0 | 2020 | 2019-03-06 09:43 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Laurel County. This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. Safety has become an issue as t | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
N; Committed | 11 | Cumberland Valley ADD | IP20000083 | 11-14.80 / 11-14.81 / 11-14.83 / 11-14.84 |  | A | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN. (18CCR) | PREFINANCD CONVRSN(O) | Whitley | 118-I -0075 -000 | 20.2 | 27.943 | 7.743 | Add Lane to Full Control Facility | 25 | Y |  |  |  |  | 530000 | 2019 | 520000 | 2019 | 85170000 | 2020 | 2007-11-15 13:03 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. ADT in the projectarea continue | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
N; Committed | 11 | Cumberland Valley ADD | IP20090005 | 11-187 / 11-187.01 | 2020-07-15 | A | IMPROVE SAFETY, ACCESS MANAGEMENT, AND FREIGHT MOBILITY; AND REDUCE CONGESTION ON KY-192 NEAR KY-1006 TO US-25 IN LONDON. (12CCR) | PREFINANCD CONVRSN(O) | Laurel | 063-KY-0192 -000 | 18.505 | 20.07 | 1.565 | Arterial to Partial Control | 23 | Y |  |  | 0 |  | 0 | 2018 | 0 | 2018 | 37440000 | 2022 | 2019-02-27 09:02 | The purpose of this project is to improve safety, access management, and freight mobility; and reduce congestion on KY 192 near KY 1006 to US 25 in London (12CCR). KY 192 has been the recent growth corridor for the London/Laurel County area. The roads rad | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 90.3768 | 9.2038 | 14.1469 | 14.3246 | 0 | 9.6682 | 4.8341 | 8.1991 | 60 | 15 | 15
N; Committed | 11 | Cumberland Valley ADD | IP20150321 | 11-185 / 11-185.01 | 2019-08-23 | A | IMPROVE SAFETY, IMPROVE ACCESS MANAGEMENT, AND REDUCE CONGESTION ON US-25E FROM THE KNOX/LAUREL COUNTY LINE TO KY-770 (12CCR)(16CCR) | PREFINANCD CONVRSN(O) | Laurel | 063-US-0025E -000 | 0 | 2.024 | 2.024 | Arterial to Partial Control | 23 | Y |  |  | 0 |  | 0 |  | 0 |  | 29960000 | 2020 | 2018-08-30 08:59 | The purpose of this project is to improve safety, improve access management, and reduce congestion on US 25E from the Knox/Laurel County Line to KY 770. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 89.6043 | 9.3081 | 14.7156 | 14.1114 | 1.1848 | 9.6682 | 4.8815 | 5.7346 | 60 | 15 | 15
N; Committed | 11 | Cumberland Valley ADD | IP20150367 | 11-278.30 |  | A | IMPROVE KY-30 FROM US-421 TO THE OWSLEY COUNTY LINE. (14CCR)(SEE 10-279.60 FOR PE & ENVIR)(16CCR)(TO BE LET WITH 10-279.61) | RECONSTRUCTION(O) | Jackson | 055-KY-0030 -000 | 9.121 | 17.517 | 8.396 | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 2019 | 2019-01-11 14:09 | The purpose of this project is to reconstruct KY 30 from US 421 to the Owsley County Line as part of the overall reconstruction of KY 30 from Hal Rogers Parkway in Laurel County to Mountain Parkway in Owsley County. This will help provide a safe and secu | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 36.763 | 0.43602 | 0 | 9.8104 | 4.8104 | 4.218 | 2.4882 | 0 | 22 |  | 15
N; Committed | 11 | Cumberland Valley ADD | IP20150379 | 11-9.10 | 2019-03-22 | A | IMPROVE I-75 FROM US-25E TO THE LITTLE LAUREL RIVER (16CCR) | MAJOR WIDENING(O) | Laurel | 063-I -0075 -000 | 28.85 | 33.162 | 4.312 | Add Lane to Full Control Facility | 25 | Y |  |  |  |  | 280000 | 2019 | 200000 | 2019 | 0 | 2020 | 2019-03-06 09:43 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I 75 in Laurel County. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | Statewide | 59.9149 | 17.3216 | 8.9868 | 8.7225 | 1.8062 | 0 | 9.207 | 13.8708
N; Committed | 11 | Cumberland Valley ADD | IP20150412 | 11-14.80 |  | A | TENN. STATE LINE-LEXINGTON; WIDEN I-75 TO 8 LANES FROM MP 20.2 IN WHITLEY COUNTY TO MP 28.85, US-25E NORTH OF CORBIN. (C-COST=$87,500,000)(18CCR) | MAJOR WIDENING(O) | Whitley | 118-I -0075 -000 | 20.2 | 27.943 | 7.743 | Add Lane to Full Control Facility | 25 | Y |  |  |  |  | 530000 | 2019 | 520000 | 2019 | 85170000 | 2020 | 2018-07-10 08:18 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | Statewide | 56.4626 | 15.3304 | 7.5771 | 9.9615 | 1.8062 | 0 | 7.4009 | 14.3866
N; Committed | 11 | Cumberland Valley ADD | IP20160016 | 11-8003 | 2019-08-23 | A | IMPROVE US-421/KY-80 FROM KY-80 SOUTH TO KY-149 (LOCKARTS CREEK ROAD). (00CCN)(10CCR)(12CCR)(18CCR) | MINOR WIDENING(O) | Clay | 026-US-0421 -000 | 13.692 | 16.915 | 3.223 | Install Two-way Left Turn Lane | 28 | [5 empty] | 0 |  | 0 |  | 18000000 | 2020 | 2018-07-10 08:18 | The purpose of this project is to improve travel time, reliability, and reduce congestion on US 421. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 78.3791 | 7.0995 | 11.6588 | 12.2275 | 1.6588 | 8.673 | 0 | 7.0616 | 48 | 15 | 15
N; Committed | 11 | Cumberland Valley ADD | IP20160054 | 11-8856 | 2020-01-15 | A | IMPROVE GEOMETRICS ON THE S-CURVE FROM NORTHEAST OF KY-3135 (COLLEGE STREET) TO NORTHEAST OF PR-1006 (MULBERRY STREET).(14CCN)(18CCR) | RECONSTRUCTION(O) | Clay | 026-KY-0066 -000 | 32.9 | 33.217 | 0.317 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 380000 | 2019 | 2018-07-10 08:18 | This project is to improve the existing s-curve to improve geometrics on KY 66. | The following needs have been identified for this project: 1) Improve Roadway Safety | 11 | South | 19.5746 | 1.0142 | 3.8389 | 0.83531 | 3.981 | 5.1659 | 0 | 4.7393 | 20
N; Committed | 11 | Cumberland Valley ADD | IP20160140 | 11-147.10 | 2019-04-26 | A | ADDRESS SAFETY, CAPACITY, AND ACCESS MANAGEMENT ON KY-363 FROM KY-1006 TO KY-192. (06CCR)(2006BOPC).(10CCR)(14CCR) | MAJOR WIDENING(O) | Laurel | 063-KY-0363 -000 | 9.187 | 9.654 | 0.467 | Arterial to Partial Control | 23 | [5 empty] | 0 |  | 0 |  | 3000000 | 2018 | 2018-07-10 08:18 | The purpose of this project is to address safety, capacity and access management on KY 363 from KY 1006 to KY 192. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 57.1102 | 6.3223 | 12.2986 | 8.4419 | 3.3886 | 7.2038 | 0 | 4.455 | 42 | 15
N; Committed | 11 | Cumberland Valley ADD | IP20170076 | 11-11 |  | A | IMPROVE I-75 FROM KY 80 AT LONDON TO SOUTH OF THE KY-909 UNDERPASS. | MAJOR WIDENING(O) | Laurel | 063-I -0075 -000 | 41 | 48 | 7 | Add Lane to Full Control Facility | 25 | Y |  |  | 6000000 |  | 0 |  | 150000 |  | 249000000 | 2022 | 2018-07-10 08:18 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I 75 from KY 80 at London to south of the KY 909 underpass. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | Central Office | Statewide | 61.0639 | 16.1057 | 6.8722 | 9.185 | 1.8062 | 5.2643 | 7.9736 | 13.8569
N; Committed | 12 | Big Sandy ADD | IP20110162 | 12-195 | 2021-12-15 | A | SPOT IMPROVEMENTS FROM BRANHAM'S CREEK TO JOHN M. STUMBO SCHOOL.(12CCR)(16CCR) | SPOT IMPROVEMENTS(O) | Floyd | 036-KY-0979 -000 | 12.389 | 13.95 | 1.561 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 18820000 | 2022 | 2019-03-11 16:00 | Improve safety and reliability of this section of KY-979 by widening lanes and shoulders and improving sight distance. | This section of KY 979 is characterized by insufficient lane widths, due to heave coal haul activity; poor site distance and little to no recovery room for lane departure corrections. Further, there are steep dropoffs for drivers to contend with in case | 12 | East | 74.8234 | 6.3353 | 12.3952 | 11.5419 | 4.2216 | 0 | 3.503 | 6.8263 | 45 | 15 | 15
N; Committed | 12 | Big Sandy ADD | IP20150171 | 12-192 | 2022-07-15 | A | IMPROVE ALIGNMENT AND GEOMETRICS OF THE CURVE LOCATED JUST BEFORE THE JUNCTION OF KY-2031 AND KY-40 TO .1 MILES BEFORE GORDON HOLLOW ROAD, AND IMPROVE THE CULVERT/SAFETY DESIGN TO INCREASE MOTORIST AND PEDESTRIAN SAFETY. (12CCR) | RECONSTRUCTION(O) | Martin | 080-KY-0040 -000 | 18.2 | 18.4 | 0.2 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 1300000 | 2024 | 2019-03-07 14:50 | Address safety and reliability by improving the geometrics and alignment of the curve on KY-40 between KY-2031 and Gordon Hollow Road. | The following needs have been identified for this project: 1) Improve Roadway Safety. | 12 | East | 55.5778 | 7.988 | 6.9162 | 5.0749 | 4.521 | 8.8024 | 4.0419 | 3.2335 | 41 | 15
N; Committed | 12 | Big Sandy ADD | IP20150335 | 12-191 | 2020-07-15 | A | IMPROVE SAFETY AND ACCESS ON US-23 BETWEEN KY-80 AND KY-3384.(12CCR) | SAFETY(P) | Floyd | 036-US-0023 -000 | 12.775 | 13.775 | 1 | Access Consolidation | 25 | Y |  |  | 0 |  | 100000 | 2019 | 410000 | 2019 | 2410000 | 2021 | 2019-03-01 14:15 |  |  | 12 | East | 76.0569 | 9.4251 | 14.5509 | 10.8234 | 0.7485 | 0 | 4.8802 | 5.6287 | 46 | 15 | 15
N; Committed | 12 | Kentucky River ADD | IP20160112 | 12-199.10 |  | A | IMPROVE US-119 FROM NORTH OF KY-15 TO BRASS DRIVE (SOUTH).(16CCN)(18CCR) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 15.772 | 17.805 | 2.033 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 0 |  | 1370000 | 2021 | 1820000 | 2021 | 10060000 |  | 2019-02-27 10:41 |  |  | 12 | East | 89.4775 | 8.2275 | 14.7305 | 12.5075 | 1.0778 | 9.8204 | 4.491 | 8.6228 | 60 | 15 | 15
N; Committed | 12 | Kentucky River ADD | IP20160114 | 12-199.15 |  | A | IMPROVE US-119 FROM KY 2034/COUGAR DRIVE TO BRASS DRIVE (SOUTH).(16CCN)(SEE 12-199.10 FOR D, R, U)(18CCR) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 16.731 | 17.805 | 1.074 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | [8 empty] | 10060000 | 2021
N; Committed | 12 | Big Sandy ADD | IP20160154 | 12-301.20 | 2020-07-15 | A | IMPROVE THE MINNIE-HAROLD CONNECTOR FROM LITTLE MUD CREEK RD TO THE MOUTH OF TACKETT CREEK (ALT.3B SEC.2)(08CCN)(10CCR)(12CCR)(14CCR)(18CCR) | NEW ROUTE(O) | Floyd | 036-KY-0680 -000 | 5.026 | 10.467 | 5.441 | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 72080000 | 2021 | 2019-03-11 16:58 | To improve alignment, reduce accident, reduce travel time, increase capacity of roadway between Minnie and Harold. | Improve safety and reduce travel time. | 12 | East | 49.4731 | 6.1198 | 0 | 13.7425 | 3.1437 | 8.3234 | 3.1437 | 0 | 34 | 15
N; Committed | 12 | Big Sandy ADD | IP20160162 | 12-263.67 / 12-263.69 / 12-263.74 | 2017-12-08 | A | PIKEVILLE TO VA. STATE LINE; US 460/KY 80 AT BEAVER CREEK NEAR BEAVER BOTTOM (SECTION 7A-2), RAMP 2, GRADE, DRAIN AND SURFACING.(14CCR)(16CCR) | RELOCATION(O) | Pike | 098-US-0460 -000 | 0 | 25.325 | 25.325 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | [8 empty] | 308220000 | 2017 |  | Improve regional connectivity and mobility by relocating this segment of US-460. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity. | 12 | Statewide | 68.227 | 4.7577 | 17.2687 | 13.6123 | 9.5595 | 7.0485 | 1.1894 | 14.7909
N; Auth Tier 3/4 | 9 | Bluegrass ADD | IP20160223 | 7-310.30 | 2017-12-08 | A | PARIS-MAYSVILLE ROAD; RECONSTRUCT FROM MILLERSBURG TO KY-1455 AT CARLISLE (SECTION 3). (08CCR)(12CCR)(14CCR)(16CCR)(18CCN) | MAJOR WIDENING(O) | Nicholas | 091-US-0068 -000 | 5.771 | 5.964 | 0.193 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  |  |  | 0 |  | 0 |  | 0 | 2021 | 2018-11-16 13:50 | PARIS-MAYSVILLE ROAD; RECONSTRUCT FROM MILLERSBURG TO KY-1455 AT CARLISLE (SECTION 3). (08CCR)(12CCR)(14CCR)(16CCR) | PARIS-MAYSVILLE ROAD; RECONSTRUCT FROM MILLERSBURG TO KY-1455 AT CARLISLE (SECTION 3). (08CCR)(12CCR)(14CCR)(16CCR) | BLUEGRASS ADD | Statewide | 21.7911 | 1.9559 | 3.7004 | 0.52863 | 1.8062 | 7.0264 | 0.79295 | 5.9805
N; Auth Tier 3/4 | 11 | Cumberland Valley ADD | IP20180038 | 11-80000 |  | A | US25E TURN LANES- TURN LN @ THE PALLET STORE, L. TURN LN @ SAWMILL @ CNTY LINE, R. TURN LN @ DOLLAR GENERAL, L. TURN LN PAST BENNETT BR SBND, L. TURN LN @ WARREN LOOP DR, LEFT TURN LN @ SUE MNTN DR., L. TURN LANE @ SIERRA LN, R. LN. @ HIGGINS RD.(18CCN) | SAFETY(P) | Knox | 061-US-0025E -000 | 8.5 | 22.7 | 14.2 | Improve Intersection | 26 | Y |  |  | 30000 | 2019 |  |  |  |  | 0 | 2019 | 2018-07-10 08:18 | The purpose of this project is to address safety and access issues along US 25E, as well as to improve mobility, better control access, and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | General Assembly | South | 49.5413 | 6.9528 | 15 | 12.2583 | 0.4717 | 0 | 4.8585 | 10 | 50
N; Auth Tier 3/4 | 12 | Big Sandy ADD | IP20160151 | 12-8100 | 2018-10-26 | I | CURVE REVISION TO INCLUDE IMPROVED SIGHT DISTANCE AND A LEFT TURN LANE ON KY-122 AT THE KY-680 INTERSECTION IN MCDOWELL. (02CCN)(12CCR)(18CCN) | SAFETY(P) | Floyd | 036-KY-0122 -000 | 18.5 | 18.697 | 0.197 | Improve Intersection | 26 | [5 empty] | 0 |  | 0 |  | 0 |  | 2018-11-20 07:10 | Address safety and congestion issues on KY-122 at the Ky-680 intersection by improving the sight distance and adding a left turn lane. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity. | 12 | East | 44.5808 | 4.6108 | 6.4671 | 7.8144 | 3.8024 | 0 | 3.5329 | 3.3533 | 30 | 15
N | 1 | Purchase ADD | IP20060057 |  |  |  | Address bike/pedestrian travel, safety issues, traffic flow and movement along 28th Street from US 60 (Jackson St) to US60X ( Park Ave). See March, 2002 Paducah - McCracken County Transportation Plan. | Bike/Ped Facility | McCracken | 073-US-0045 -000 | 9.87 | 10.806 | 0.936 | Other Improvement Types | 0 | Y | 500000 |  | 1000000 |  | 1500000 |  | 2500000 |  | 6000000 |  | 2010-02-25 16:51 | The purpose of this project is to improve the mobility of vehicular, bicycle and pedestrian traffic along the 28th Street corridor. | The main issue w/ 28th St (US 45/60) is the weaving of traffic that currently occurs between several blocks of the route and some streets are misaligned. The vehicular weaving is caused in part by the lane assignments at some signalized intersections, and
N | 1 | Purchase ADD | IP20080023 |  |  |  | Improve safety at the intersection with KY464 in Mayfield. | Lighting | Graves | 042-KY-0121 -000 | 6.957 | 7 | 0.043 | Other Improvement Types | 0 |  | 0 |  | 50000 |  | 0 |  | 0 |  | 200000 |  | 2015-04-03 10:30 | The purpose of this project is to improve night time visibility. | This project is needed to add illumination lighting at the intersection with KY 121 Bypass and KY 464 in Mayfield to provide better night time visibility of vehicles crossing KY 121 from KY 464. ADT numbers are likely to increase as development along a f
N | 1 | Purchase ADD | IP20080026 |  |  |  | Address safety concerns with night time visibility issues at the intersection of KY 121 Bypass and KY 58 in Mayfield. | Lighting | Graves | 042-KY-0121 -000 | 7.61 | 7.625 | 0.015 | Other Improvement Types | 0 |  | 0 |  | 10000 |  | 0 |  | 0 |  | 200000 |  | 2017-04-10 11:59 | The purpose of this project is to provide better night time visibility. | This project is needed to add illumination lighting at the intersection with KY 121 Bypass and KY 58 in Mayfield to provide better night time visibility of vehicles crossing KY 121 from KY 58. | 1 | West | 13.1134 | 8.8866 | 0 | 0 | 0 | 0 | 4.2268 | 0 | 13
N | 1 | Purchase ADD | IP20080049 |  |  |  | Address safety concerns with night time visibility issues at US 68 / Purchase Parkway Interchange in Draffenville. | Lighting | Marshall | 079-I -0069 -000 | 46.694 | 47.232 | 0.538 | Other Improvement Types | 0 | Y | 0 |  | 75000 |  | 0 |  | 0 |  | 450000 |  | 2017-04-11 11:17 | Address safety concerns with night time visibility. | This project is needed to address night time visibility concerns and reduce night time safety issues. Past crash data indicates aproximately 33% of the crashes are occuring at night. | PURCHASE ADD | West | 20.7706 | 7.1065 | 0 | 8.1314 | 0.54983 | 0 | 4.9828 | 0 | 21
N | 1 | Purchase ADD | IP20150159 | 1-1140.01 |  | A | PE AND ENVIRONMENTAL FOR REPLACEMENT OF CAIRO BRIDGE AT OR BESIDE EXISTING LOCATION. (004B00021N)(SD)(18CCR) | AM-BRIDGE (P) | Ballard | 004-US-0051 -000 | 7.327 | 8.297 | 0.97 | Transportation Studies | 0 | Y |  |  | 0 | 2020 | 1000000 | 2023 | 100000 | 2023 | 99000000 | 2023 | 2018-07-10 08:18 | PE and Environmental for replacement of US 51 Ohio River Bridge between Wickliffe and Cairo, Il. | The US 51 Bridge, built in 1937, crosses the Ohio River with 2-10' lanes and 1' shoulders. Curb to curb span is 22.5' and has sufficiency rating of 24.2, which is considered low by federal sufficiency standards. The bridge is considered to be functionall | 1 | West | 19.9476 | 5.622 | 0 | 5.0129 | 4.5533 | 0 | 4.7595 | 0 | 20
N | 1 | Pennyrile ADD | IP20150471 |  |  |  | REPLACE BRIDGE ON US 60 OVER THE CUMBERLAND RIVER 0.27 MILE N OF KY 70 (SR 32.7) 070B00017N | Bridge Replacement | Livingston | 070-US-0060 -000 | 12.524 | 12.868 | 0.344 | Other Improvement Types | 0 |  | 0 |  | 1600000 |  | 500000 |  | 350000 |  | 15000000 |  | 2016-09-08 08:57
N | 1 | Pennyrile ADD | IP20160108 |  |  |  | Upgrade a structurally deficient bridge to meet load limits needed for KY 937. | Bridge Replacement | Livingston | 070-KY-0937 -000 | 1.53 | 1.85 | 0.32 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-31 09:12 |  | REPLACE EXISTING BRIDGE LOCATED ON KY 937 MP 0.872 JUST EAST OF US 60.
N | 2 | Clarksville-Oak Grove MPO | IP20070038 |  |  |  | Address safety issues by installing interchange lighting. | Lighting | Christian | 024-I -0024 -000 | 88.459 | 89.113 | 0.654 | Innovative Interchange | 40 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 665000 |  | 2018-11-09 09:42 | To address night time visibility issues by installing lighting at an existing interchange . | There is currently no lighting at the interchange of I 24 and KY 115. The interchange is rural and visibility is sometimes an issue. | Clarksville MPO | West | 20.488 | 6.3643 | 0 | 9.2784 | 0.75601 | 0 | 4.0893 | 0 | 20
N | 2 | Evansville-Henderson MPO | IP20070060 |  |  |  | Improve pedestrian safety and convenience. | Bike/Ped Facility | Henderson | 051-US-0041A -000 | 13.235 | 15.042 | 1.807 | Bike and Pedestrian Improvements | 13 | Y | 0 |  | 50000 |  | 1656000 |  | 750000 |  | 1000000 |  | 2018-12-13 15:45 | Improve pedestrian safety and mobility | Extend the sidewalk on the west side of US 41A from Hancock St to Sand Ln and continue on both sides of US 41A to US 60. Sidewalks are discontinuous and in disrepair.
N | 2 | Evansville-Henderson MPO | IP20070063 |  |  |  | IMPROVE PEDESTRIAN SAFETY AND CONVENIENCE. PART OF THIS PROJECT IS INCLUDED IN PROJECT 02 051 D0136 1.00 | Bike/Ped Facility | Henderson | 051-KY-0136 -000 | 19.548 | 21.05 | 1.502 | Bike and Pedestrian Improvements | 13 |  | 0 |  | 50000 |  | 150000 |  | 50000 |  | 1000000 |  | 2018-12-11 11:22 | Improve pedestrian safety and mobility | Add sidewalks from US 60 to Community Park to accommodate pedestrians trying to access the park.
N | 2 | Evansville-Henderson MPO | IP20080085 |  |  |  | Improve safety and level of service. | Bridge Replacement | Henderson | 051-US-0060 -000 | 18.575 | 20.575 | 2 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 600000 |  | 750000 |  | 23000000 |  | 2014-05-29 11:27 | ? | REPLACE BRIDGE ON US-60 OVER THE GREEN RIVER AT SPOTTSVILLE KY. Bridge is narrow and carries significant traffic including trucks. Bridge is aging and has been struck several times by watercraft on the Green River.
N | 2 | Evansville-Henderson MPO | IP20080086 |  |  |  | Improve pedestrian safety and convenience. | Bike/Ped Facility | Henderson | 051-KY-0351 -000 | 1.358 | 1.558 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 75000 |  | 100000 |  | 90000 |  | 450000 |  | 2010-02-25 16:51 | To improve safety. | There is a lot of pedestrian traffic in this area near the High School. Need to connect sidewalks on each side of US 41 overpass.
N | 2 | Pennyrile ADD | IP20120049 |  |  |  | Build Bike and pedestrian ficilities (sidewalks) along West US 62 from MP 3.644 to MP 5.310 in Princeton. | Bike/Ped Facility | Caldwell | 017-US-0062 -000 | 3.644 | 5.31 | 1.666 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 500000 |  | 500000 |  | 950000 |  | 2013-05-03 13:05 | Improve pedestrian safety along the US 62 commercial corridor. | This involves adding wide walks along US 62 from MP 3.644 to MP 5.31 to improve pedestrian safety on the US 62 corridor along a section of road that has been developed commercially in Princeton.
N | 3 | Barren River ADD | IP20110030 | 3-10010 |  | A | IMPROVE SAFETY AND BRIDGE CONDITION ON WHIPPORWILL CREEK BRIDGE NEAR KY-1151. BRIDGE ID 071B00025 (SD) | AM-BRIDGE (P) | Logan | 071-US-0079 -000 | 4.35 | 4.85 | 0.5 | Modernize Roadway-Rural | 26 | Y |  |  | 0 | 2019 |  |  |  |  | 1715000 | 2020 | 2019-02-20 15:33 | Improve safety and bridge condition. | This project is intended to correct deficiencies on a narrow bridge near KY 1151. There is an existing PIF in the area of this project (03 071 B0079 1.00), however this is a widening project located along the entire length of US 79 in Logan/Todd Counties. | BARREN RIVER ADD | West | 62.2766 | 4.055 | 12.3196 | 3.4278 | 3.4364 | 0 | 3.8488 | 5.189 | 32 | 15 | 15
N | 3 | Barren River ADD | IP20110032 |  |  |  | Improve safety and address horizontal geometric deficiencies at the narrow bridge on KY 187. | Bridge Replacement | Edmonson | 031-KY-0187 -000 | 2.15 | 2.25 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 250000 |  | 150000 |  | 750000 |  | 2019-03-05 14:03 | Improve safety. | KY 187 is a two lane highway with minimal shoulder width, and curves that are difficult to navigate given the lane and shoulder widths.
N | 3 | Barren River ADD | IP20160240 | 3-20010 / 3-2042.02 |  | A | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO.(SEE 3-2042.10) | RECONSTRUCTION(O) | Butler | 016-WN-9007 -000 | 20.426 | 37.143 | 16.717 | Full Control to Interstate | 10 | Y |  |  | 240000 | 2019 |  |  |  |  | 2400000 | 2019 | 2018-07-10 08:18 | Upgrade and modernize. | Upgrading and modernizing the roadway is needed to increase economic development throughout the region.
N | 3 | Barren River ADD | IP20160241 | 3-20009 / 3-2042.01 |  | A | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO.(SEE 3-2042.10) | RECONSTRUCTION(O) | Butler | 016-WN-9007 -000 | 20.246 | 37.143 | 16.897 | Full Control to Interstate | 10 | Y |  |  | 675000 | 2024 |  |  |  |  | 6750000 | 2019 | 2018-07-10 08:18 | Upgrade and modernize. | Upgrading and modernizing the roadway is needed to increase economic development throughout the region.
N | 3 | Barren River ADD | IP20160242 | 3-20008 / 3-2042 |  | A | UPGRADE THE NATCHER PARKWAY TO INTERSTATE STANDARDS IN ORDER TO ESTABLISH "I-565"SPUR ROUTE BETWEEN BOWLING GREEN AND OWENSBORO.(SEE 3-2042.10) | RECONSTRUCTION(O) | Butler | 016-WN-9007 -000 | 20.246 | 37.143 | 16.897 | Full Control to Interstate | 10 | Y |  |  | 540000 | 2022 |  |  |  |  | 5400000 | 2017 | 2018-07-10 08:18 | Upgrade and modernize. | Upgrading and modernizing the roadway is needed to increase economic development throughout the region.
N | 3 | Barren River ADD | IP20170004 | 3-8506.20 | 2018-05-25 | I | ADDRESS DEFICIENCIES OF BRIDGE AND APPROACHES OVER ROGERS CREEK AT MP 7.307. (DESIGN HANDLED UNDER 3-8506.00) 085B00010N (2014BOP)(SD)(18CCR) | AM-BRIDGE (P) | Metcalfe | 085-KY-0163 -000 | 6.999 | 7.615 | 0.616 | Modernize Roadway-Rural | 26 | [9 empty] | 3000000 | 2018 |  | Address bridge deficiencies. | This segment of KY 163 is a two lane facility with 9' lanes and 2' shoulders. The bridge crossing Rogers Creek has a 19.4' horizontal clearance. The narrow bridge creates difficult driving conditions for trucks and other large vehicles. Between 2004 and 2 | 3 | West | 23.0077 | 2.9347 | 4.6907 | 5.2448 | 1.9759 | 0 | 2.6976 | 5.4639 | 23
N | 3 | Barren River ADD | IP20190100 |  |  |  | Improve safety and mobility on KY 100 at the narrow bridge over Spring Creek. | Bridge Replacement | Monroe | 086-KY-0100 -000 | 1.72 | 1.77 | 0.05 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 75000 |  | 100000 |  | 600000 |  | 2019-03-07 15:44 | Improve safety and mobility. | The bridge width is less than 19 feet, which makes it nearly impassable if two trucks meet on the bridge at the same time.
N | 3 | Barren River ADD | IP20190102 |  |  |  | Improve safety and mobility on KY 100 at the narrow bridge over Indian Creek. | Bridge Replacement | Monroe | 086-KY-0100 -000 | 4 | 4.1 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 75000 |  | 100000 |  | 800000 |  | 2019-03-07 15:43 | Improve safety and mobility. | The bridge width is 19 feet, which makes it nearly impassable if two trucks meet on the bridge at the same time.
N | 3 | Barren River ADD | IP20190104 |  |  |  | Improve safety and mobility on KY 100 at the narrow bridge over East Fork Barren River. | Bridge Replacement | Monroe | 086-KY-0100 -000 | 13.5 | 13.6 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 100000 |  | 200000 |  | 1500000 |  | 2019-03-07 15:41 | Improve safety and mobility. | The bridge width is 19 feet, which makes it nearly impassable if two trucks meet on the bridge at the same time.
N | 4 | Lincoln Trail ADD | IP20070178 |  |  |  | CONSTRUCT BIKEWAY (STRIPING AND SIGNS) ALONG KY 3005 (RING ROAD) IN ELIZABETHTOWN | Bike/Ped Facility | Hardin | 047-KY-3005 -000 | 0 | 10.582 | 10.582 | Bike and Pedestrian Improvements | 13 |  | 200000 |  | 1000000 |  | 1500000 |  | 1000000 |  | 5000000 |  | 2019-01-08 08:38 | Bike/Ped connectivity | Ring Road (KY 3005) is a major circulation route in the city of Elizabethtown. Currently it connects with US 62 west of Elizabethtown, KY 1357, KY 1600, US 31W, and US 62 (4-7010.00) east of Elizabethtown. The next major extension will be from US 62 wes
N | 4 | Lake Cumberland ADD | IP20070199 |  |  |  | CONSTRUCT A BIKEWAY ALONG KY 55 AND KY 1061 FROM US 68 TO GREEN RIVER STATE PARK | Bike/Ped Facility | Taylor | 109-KY-0055 -000 | 6.546 | 10.293 | 3.747 | Bike and Pedestrian Improvements | 13 | Y | 50000 |  | 75000 |  | 50000 |  | 50000 |  | 400000 |  | 2019-01-03 15:50 | Address lack of bike facilities around Campbellsville to the Green River State Park | Due to the close proximity of Green River State Park to the City of Campbellsville, KY 55/KY 1061 is a favorite route for avid bicyclists. However, traffic volumes and geometric conditions of the roadways do not lend themselves to safe cycling. Local gove
N | 4 | Lake Cumberland ADD | IP20090018 |  |  |  | CONSTRUCT BIKE ROUTES ON KY 55, KY 210, AND US 68 IN TAYLOR COUNTY. | Bike/Ped Facility | Taylor | 109-US-0068 -000 | 0 | 13.531 | 13.531 | Bike and Pedestrian Improvements | 13 |  | 500000 |  | 1600000 |  | 1500000 |  | 1000000 |  | 8000000 |  | 2019-01-03 15:49 | Address the lack of bicycle facilities around the City of Campbellsville. | Due to the close proximity of Green River State Park to the City of Campbellsville, as well as the location of Campbellsville University, KY 55, KY 210, and US 68 are favorite routes for avid bicyclists. However, traffic volumes and geometric conditions
N | 5 | KIPDA ADD | IP20060243 |  |  |  | Improve safety and mobility for bicyclists and pedestrians along KY 53 from US 60 to Warriors Way in Shelbyville. | Bike/Ped Facility | Shelby | 106-KY-0053 -000 | 8.006 | 9.607 | 1.601 | Bike and Pedestrian Improvements | 13 |  | 85000 |  | 250000 |  | 250000 |  | 100000 |  | 2000000 |  | 2018-11-30 14:55 | The purpose of this project is to improve safety and access for all transportation modes with consideration of a bike/ped path on KY 53 from US 60 to Harrington Mill Road | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types.
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080204 |  |  |  | Construct bicycle and pedestrian facilities along KY 155 from KY 148 to US 31 E. | Bike/Ped Facility | Jefferson | 056-KY-0155 -000 | 4.276 | 16.541 | 12.265 | Other Improvement Types | 0 | Y | 0 |  | 25000 |  | 12000 |  | 5000 |  | 273000 |  | 2011-02-08 14:37 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 155 from KY 148 (MP 4.250) to US 31E (MP 16.541) runs from eastern to central Jefferson County. This segment has variety of uses and densities, ranging from currently low-density agricultural uses to high-density multi-family dwellings. Uses also vary
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080206 | 5-481 |  | A | KY 864 - WIDEN BEULAH CHURCH ROAD FROM 2 TO 3 LANES FROM I-265 TO CEDAR CREEK ROAD.(2010BOP) | MATCHED FED FUNDS(O) | Jefferson | 056-KY-0864 -000 | 1.818 | 3.445 | 1.627 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 2950000 | 2018 | 1975000 | 2019 | 8502811 |  | 2018-07-10 08:18 | Improve the access, safety and mobility of Beulah Church Road south of the Gene Snyder Freeway. | The Beulah Church Road (KY 864) corridor is a rapidly developing section of Louisville with increasing traffic demand. KY 864 is classified as an urban collector and has many access points. It carries traffic from growing residential suburbs to the Gene
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080220 | 5-536 |  | A | WIDEN KY 1931 (MANSLICK ROAD) FROM 2 TO 3 LANES FROM US 31W (DIXIE HWY) TO DOSS HIGH SCHOOL. 1.7 MILES (2014BOP) | MINOR WIDENING(O) | Jefferson | 056-KY-1931 -000 | 3.148 | 4.887 | 1.739 | Install Two-way Left Turn Lane | 28 |  |  |  | 1000000 |  | 3150000 | 2018 | 6000000 | 2019 | 6700000 |  | 2019-03-07 15:22 | The purpose of the project is to improve safety, local traffic operations, and mobility for all modes along KY 1931 (Manslick Road) from Dixie Highway (US 31W) to Doss High School. | The Critical Rate Factor (CRF) along this segment is greater than 1.0 and over half of the crashes throughout the corridor are rear end collisions, with the next highest type being angle crashes at 20%. This segment experiences congested traffic operation | 5 | North | 84.8615 | 7.4462 | 13.0615 | 12.0923 | 2.5692 | 9.2308 | 3.1385 | 7.3231 | 55 | 15 | 15
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080223 | 5-531 |  | A | IMPROVE THE SAFETY AND CONGESTION OF KY 1932 (CHENOWETH LANE) FROM US 60 (SHELBYVILLE ROAD) TO US 42 (BROWNSBORO ROAD) APPROXIMATELY 1.07 MILES (2014BOP). | MATCHED FED FUNDS(O) | Jefferson | 056-KY-1932 -000 | 5.523 | 6.59 | 1.067 | Modernize Roadway-Urban | 16 |  | 0 |  | 0 | 2018 | 750000 | 2018 | 1990000 |  | 1700000 |  | 2018-09-21 09:20 | The purpose of the Chenoweth Lane project - from the CSX railroad (just north of Shelbyville Road) to Brownsboro Road is to 1) Improve sight distance and safety for all users, 2) Improve drainage along the corridor and 3) Improve pedestrian safety and mob | The needs stem from a higher than average crash rate in the southern section, pedestrian strike history, sight distance obstructions, obstructions in the clear zones, inadequate drainage in the corridor, substandard shoulders, and narrow (east side) and i
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080241 | 5-479 |  | A | WIDEN HUBBARDS LANE FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM US 60 (SHELBYVILLE ROAD) TO KY 1447 (WESTPORT ROAD). ADD BIKE LANES TO HUBBARDS LANE FROM KRESGE WAY TO KY 1447. PROJECT LENGTH IS 0.6 MI.(BOPC2010) | RECONSTRUCTION(O) | Jefferson | 056-CR-1005B -000 | 0 | 0.614 | 0.614 | Install Two-way Left Turn Lane | 28 |  | 0 |  | 0 |  |  | 2018 |  | 2018 |  | 2019 | 2018-07-10 08:18 | The purpose of this project is to increase capacity and safety of Hubbards Lane between KY 1447 (Westport Road) to US 60 (Shelbyville Road) and to improve bicycle and pedestrian accessibility from KY 1447 (Westport Road) to Kresge Way/Bowling Boulevard. | There was a total of 603 collisions reported along Hubbards Lane from 12/1/03 to 12/1/13. The 2012 ADT along the north section of Hubbards Lane is 12,687 (STA. 173) whereas the 2012 ADT along the south section of Hubbards Lane is 9,409 (STA. B17). The add
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080245 | 5-441.01 | 2021-07-15 | A | RECONSTRUCT US 42 AND WIDEN FROM 2 LANES TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM JEFFERSON/OLDHAM COUNTY LINE TO RIDGEMOOR DRIVE. PROJECT WILL INCLUDE THE CONSIDERATION OF IMPROVEMENTS TO THE HAYFIELD WAY INTERSECTION. (2004BOPC) | RECONSTRUCTION(O) | Oldham | 093-US-0042 -000 | 0 | 0.942 | 0.942 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 0 |  | 0 |  | 5010000 | 2018 | 2019-03-08 14:05 | The purpose of the project is to improve traffic flow, minimize congestion, and address safety issues on US 42 between the Jefferson County/Oldham County line and Ridgemoor Drive. | Due to an increase in commuters to and from Louisville and the development along the project corridor, the traffic volumes are expected to double in the next 20 years. The accident data for the last 3 years shows that there are between 10 and 14 rear end | 5 | North | 63.4277 | 5.9508 | 10.9846 | 9.3231 | 2.5692 | 8.9846 | 3.4462 | 7.1692 | 48 | 15
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110075 | 5-404.01 |  | A | PHASE 3.EXTEND AND CONSTRUCT 2 LANE ROADWAY WITH CONTINUOUS CENTER-TURN LANE FROM KY 864 (BEULAH CHURCH RD) TO US 31E (BARDSTOWN RD) AT BARDSTOWN FALLS RD. PROJECT WILL INCORPORATE SIDEWALKS AND 10' PAVED SHOULDERS. | NEW ROUTE(O) | Jefferson | 056-PF-9999 - |  |  |  | Other Improvement Types | 0 |  |  |  | 0 |  | 3200000 | 2018 | 1500000 | 2018 | 16000000 | 2025 | 2018-07-10 08:18 | The purpose of this project is to increase access, mobility, and safety in a rapidly developing section of southeastern Louisville from KY 864 (Beulah Church Road) to US 31E (Bardstown Road) at Bardstown Falls Road. | This project is needed because there is a lack of connectivity from KY 864 (Beulah Church Road) to US 31E (Bardstown Road). Development is planned for this area and has occurred to the south, east and west of this segment. This segment is needed to provi | Louisville MPO | North | 33.6877 | 9.6185 | 6.9692 | 11.4692 | 1.1231 | 0 | 4.5077 | 0 | 34
N | 5 | KIPDA ADD | IP20110080 | 5-434 |  | A | CONSTRUCT A 4-LANE UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE. (LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY) (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). (14CCR) | SAFETY(P) | Oldham | 093-PF-9999 - |  |  |  | Grade Seperation of Highway/Railroad Crossing | 90 |  |  |  | 0 | 2018 | 0 |  | 0 |  | 10000000 | 2019 | 2018-07-10 08:18 | CONSTRUCT AN UNINTERRUPTED RAIL UNDERPASS WEST OF LAGRANGE.(LOCAL MATCH)(ALL WORK BY OLDHAM COUNTY)(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP).(14CCR) | The need of the project is to address concerns that the existing at-grade CSX Railroad crossing on Allen Lane near the northern tie in to KY146 may cause delays for local residents and emergency vehicles. Approximately 21 trains cross this location at A | 5 | North | 27.5769 | 6 | 3.5538 | 11.4692 | 2.5692 | 0 | 3.9846 | 0 | 28
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110084 | 5-518 |  | A | WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM RUCKRIEGEL PARKWAY TO MAPLE ROAD, AND WIDEN WATTERSON TRAIL FROM 2 TO 3 LANES FROM OLD TAYLORSVILLE ROAD TO RUCKRIEGEL PARKWAY. PROJECT TO INCLUDE STREETSCAPE ENHANCEMENTS TO IMPROVE THE CORRIDOR. | MINOR WIDENING(O) | Jefferson | 056-CS-1073H -000 | 0.352 | 0.694 | 0.342 | Bike and Pedestrian Improvements | 13 |  |  |  | 0 |  | 330000 | 2018 | 440000 | 2018 | 1580000 | 2019 | 2018-07-10 08:18 | Improve pedestrian mobility on Watterson Trail from Ruckriegel Parkway to Maple Road and from Old Taylorsville Road to Ruckriegel Parkway in Jeffersontown. | This project is needed because Watterson Trail from Ruckriegel Parkway to Maple Road to the southwest and Old Taylorsville Road to Ruckriegel Parkway to the northeast connect to downtown Jeffersontown and lack sidewalk connections or have existing facilit | Louisville MPO | North | 11.8062 | 5.36 | 0 | 3.8769 | 2.5692 | 0 | 0 | 0 | 12
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160187 |  |  |  | RESTRIPE & UPGRADE SIDEWALKS ALONG 4TH STREET FROM CHESTNUT ST TO BROADWAY IN LOUISVILLE (2014BOP). | Bike/Ped Facility | Jefferson | 056-CS-1001F -000 | 0.535 | 0.734 | 0.199 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-24 11:21 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160189 |  |  |  | IROQUOIS PARK MULTI USE PATH & REST STATIONS- REDUCE LANES TO 10 FT FOR VEHICULAR TRAFFIC & DESIGNATE A 10 FT LANE FOR BIKE/PED TRAFFIC & ADD 10 REST STATIONS ALONG RUNDILL RD. (2014BOP) | Bike/Ped Facility | Jefferson | 056-CS-1009F -000 | 0 | 3.301 | 3.301 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-24 11:51 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160191 |  |  |  | CONSTRUCTION OF AN EXTENSION OF THE WATTERSON TRAIL MULTI-USE PATH BETWEEN STONYBROOK DRIVE AND MULBERRY ROW WAY (PHASE II). (2014BOP) | Bike/Ped Facility | Jefferson | 056-CS-1004H -000 | 1.667 | 2.5 | 0.833 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-24 14:15 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160238 | 5-542 |  | A | INTERSECTION REALIGNMENT/RECONSTRUCTION AT KY 329 AND KY 329 BYPASS (2016BOP). | RECONSTRUCTION(O) | Oldham | 093-KY-0329B -000 | 0 | 0.2 | 0.2 | Improve Intersection | 26 |  |  |  | 0 | 2018 | 110000 | 2019 | 440000 | 2020 | 950000 |  | 2018-09-21 09:58 | The purpose of this project is to improve safety and the traffic flow of the KY 329/KY 329 Bypass intersection. | This project is needed because existing traffic volumes result in traffic congestion and intersection delays, crashes are notably high, and sight distances exist at the KY 329/ KY 329 Bypass intersection. The existing eastbound left turn movement operate
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170032 | 5-353 | 2021-12-15 | A | WIDEN ENGLISH STATION ROAD FROM 2 TO 3 LANES (3RD LANE WILL BE A CENTER TURN LANE) FROM AIKEN ROAD TO AVOCA ROAD.(FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP). | MINOR WIDENING(O) | Jefferson | 056-CR-1006C -000 | 0.457 | 1.232 | 0.775 | Install Two-way Left Turn Lane | 28 | [5 empty] | 1200000 |  | 450000 |  | 6410000 | 2020 | 2018-07-10 08:18 | The purpose of this project is to provide a wider roadway configuration to improve safety, increase capacity and elevate level of service. Project will improve the safety of the rail crossing and enhance bike and pedestrian network. | Due to the two lane configuration and the numerous developments and entrances along the roadway, traffic operations are adversely impacted by vehicles making left turns along this congested corridor. Sight distance in the sag near Chenoweth Run and the c | 5 | North | 71.7577 | 8.6769 | 10.1538 | 7.3269 | 2.5692 | 9.2 | 3.8308 | 0 | 42 | 15 | 15
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170033 |  |  |  | INSTALLATION OF SIDEWALKS TO FIX GAPS IN PEDESTRIAN NETWORK ON US 60 (SHELBYVILLE RD), KY 1747 (HURSTBOURNE PKWY), AND KY 22 (BROWNSBORO RD). (2014BOP) | Bike/Ped Facility | Jefferson | 056-US-0060 -000 | 7.966 | 8.241 | 0.275 | Other Improvement Types | 0 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 360000 |  | 2017-02-17 08:14 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
N | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170080 | 5-378.10 | 401769 | A | EXTEND AND RECONSTRUCT I-65 SB RAMP TO BROOK STREET AND FLOYD STREET. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | RECONSTRUCTION(O) | Jefferson | 056-I -0065 -471 | 0 | 0.248 | 0.248 | Interchange Safety Improvements | 35 | Y |  |  |  | 2018 |  |  | 1020000 | 2019 | 2110000 |  | 2018-07-10 08:18 | EXTEND AND RECONSTRUCT I-65 SB RAMP TO BROOK STREET AND FLOYD STREET. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) | The needs of this project are to improve the safety of the intersection of the I-65 ramp at Brook/Jefferson street, to improve the intersection geometry and operations, and to provide better accomdations for bicyclists and pedestrians. | Louisville MPO | North | 67.7538 | 9.2 | 14.0308 | 12.6 | 3.6308 | 0 | 4.8923 | 8.4 | 53 |  | 15
N | 5 | KIPDA ADD | IP20190084 | 5-544 | 2019-06-21 | A | INSTALLATION OF NEW SIDEWALKS AND REHABILITATION OF EXISTING SIDEWALKS TO FIX GAPS IN THE PEDESTRIAN NETWORK ALONG KY 44 FROM FRANK E. SIMON DRIVE (CITY PARK DRIVE) EAST TO KY 61 IN SHEPHERDSVILLE. KY 44 MILEPOINTS FROM 11.75 TO 12.25.(2016BOP) | BIKE/PED FACIL(O) | Bullitt | 015-KY-0044 -000 | 11.75 | 12.25 | 0.5 | [5 empty] | 0 |  | 0 | 2018 | 60000 | 2018 | 200000 | 2019 | 2018-07-10 08:18
N | 5 | KIPDA ADD | IP20190123 | 5-64 |  | A | ADDRESS DEFICIENCIES ON I-64 SHERMAN MINTON BRIDGE OVER THE OHIO RIVER. (JOINT PROJECT WITH INDIANA)(056B00279N)(BSBP) | AM-BRIDGE (P) | Jefferson | 056-I -0064 -000 | 0 | 0.316 | 0.316 | [6 empty] | 2019 |  |  |  |  | 20800000 | 2020 | 2018-07-10 08:18
N | 5 | KIPDA ADD | IP20190128 | 5-20016 |  | A | ADDRESS PAVEMENT CONDITION OF PCC PAVEMENT ON I-264 BOTH DIRECTION(S) FROM MILEPOINT 12.7 TO MILEPOINT 18.41 | AM-PAVEMENT (INT)(P) | Jefferson | 056-I -0264 -000 | 12.7 | 18.41 | 5.71 | [5 empty] | 1150000 | 2024 |  |  |  |  | 11500000 | 2024 | 2018-07-10 08:17
N | 5 | KIPDA ADD | IP20190129 | 5-136 | 401769 | A | CLEAN AND PAINT ALL STEEL BRIDGES AND STEEL BEARINGS ON THE GENE SNYDER FREEWAY(10CCR)(SD) | AM-BRG PAINTING(P) | Jefferson | 056-I -0265 -000 | 10.25 | 34.727 | 24.477 | [11 empty] | 3790000 | 2021
N | 6 | Northern Kentucky ADD | IP20080272 |  |  |  | Provide Walkway on north side of KY 18 thru I-75 Interchange | Bike/Ped Facility | Boone | 008-KY-0018 -000 | 14.7 | 15.3 | 0.6 | Other Improvement Types | 0 | Y | 0 |  | 1000000 |  | 150000 |  | 250000 |  | 6000000 |  | 2017-08-08 10:44 |  | The KY 18 over pass of I-71/75 provides a critical linkage between east and west Florence, Major destinations served by this link include Boone County high school, the City of Florence government center, downtown Florence, Florence Mall and Houston Road r
N | 6 | Northern Kentucky ADD | IP20080318 |  |  |  | RECONSTRUCTION\WIDENING FROM KNOX LILLARD RD TO 5TH STREET IN WARSAW. | Landslide Repair | Gallatin | 039-US-0042 -000 | 4.619 | 6.6 | 1.981 | Other Improvement Types | 0 |  | 0 |  | 2000000 |  | 1500000 |  | 1000000 |  | 16000000 |  | 2010-02-25 16:51 | Modernize Roadway on US-42 to Increase safety, ease of travel, and travel times due to major landslide area | is stretch of road is extremely prone to the hill slipping and effecting US-42, which creates multiple delays and road closure as well as repaving. Reconstruction may be cheaper in the long run for everyone. US-42 had billions of dollars investing in m | NORTHERN KENTUCKY ADD | North | 11.5654 | 2.9846 | 0 | 3.8885 | 2.3385 | 0 | 2.3538 | 0 | 12
N | 6 | Northern Kentucky ADD | IP20080356 | 6-1086 |  | A | ADDRESS DEFICIENCIES OF BRIDGE OVER LICKING RIVER ON WEST 4TH STREET (KY 8) IN COVINGTON/NEWPORT AT KENTON/CAMPBELL CO LN. (059B00037N) *CAMPBELL CO MPS ARE 0.0-0.19 | AM-BRIDGE (P) | Kenton | 059-KY-0008 -000 | 7.57 | 7.662 | 0.092 | Modernize Roadway-Rural | 26 | Y |  |  | 3900000 | 2021 | 2440000 | 2022 | 1170000 | 2022 | 32900000 | 2024 | 2018-09-24 10:47 |  | Improve safety, reduce congestion and improve multi-modal facilities for linking two communities via a functionally obsolete bridge. ADT in this area is 16,793 vpd on a max. of 3 (10') lanes with 0' shoulders. A composite rating as low as 49.5 indicat | Cincinnati/Northern Kentucky MPO | North | 27.5492 | 7.9569 | 3.0462 | 0.80769 | 2.5692 | 0 | 4.1692 | 9 | 28
N | 6 | Northern Kentucky ADD | IP20130019 |  |  |  | Improve safety and mobility along 19th St from Augustine St to Jefferson Ave. | ITS | Kenton | 059-CS-2171 -000 | 0.356 | 0.552 | 0.196 | Other Improvement Types | 0 |  | 0 |  | 50000 |  | 150000 |  | 50000 |  | 250000 |  | 2014-02-27 15:52 |  | Minimize travel delay and increase pedestrian safety. This is a MEDIUM priority recommendation in the KCTP 6/14. Conduct traffic study to examine vehicular peak hour traffic patterns and identify other needed improvements. Include an analysis of redirec
N | 6 | Northern Kentucky ADD | IP20150033 | 6-1087 |  | A | ADDRESS DEFICIENCIES OF BRIDGE OVER NS (CNO&TP)RR ON RICHARDSON ROAD (KY 842) 0.14 MI E OF US 25 NEAR INDEPENDENCE (008B00092N) | AM-BRIDGE (P) | Boone | 008-KY-0842 -000 | 0 | 0.283 | 0.283 | Other Improvement Types | 0 |  |  |  | 500000 | 2019 | 3000000 | 2020 | 1000000 | 2020 | 4000000 | 2022 | 2018-10-04 08:44 |  | The bridge over NS RR was closed in 2013, received repairs to re-open in 2014. However, bridge is still in need of replacement to provide safety and reliability. KY 842 provides east-west connectivity between Boone and Kenton Counties for people, goods
N | 6 | Northern Kentucky ADD | IP20150328 | 6-8105.01 / 6-8105.02 / 6-8105.03 / 6-8105.06 |  | A | TRANSPORTATION IMPROVMENTS TO AA-I-275; CONSTRUCT A NEW CONNECTOR RD FROM THE AA HWY (KY 9) TO THE END OF NEW CONSTRUCTION JUST SOUTH OF JOHN'S HILL RD (KY 2345). (SECTION 2) (2005HPP-KY166) (SEE 6-8105.00 FOR "KYD" COMPONENT) | NEW ROUTE(O) | Campbell | 019-KY-1998 -000 | 0 | 1.73 | 1.73 | Construct Road in New Location | 0 |  |  |  | 0 |  | 2500000 | 2025 | 1560000 | 2025 | 30700000 | 2017 | 2018-07-10 08:18 |  |  | 6 | North | 55.1446 | 2.4677 | 0 | 10.0615 | 4.2308 | 6.1538 | 2.2308 | 0 | 25 | 15 | 15
N | 6 | Northern Kentucky ADD | IP20150389 | 6-183 |  | A | STUDY AND REHABILITATE THE I-471 CORRIDOR, CAMPBELL COUNTY, KENTUCKY. (SEE ALSO 6-8104.00)(2005HPP-KY120) | RECONSTRUCTION(O) | Campbell | 019-I -0471 -000 | 0 | 5.016 | 5.016 | Transportation Studies | 0 | Y | [8 empty] | 1670000 | 2018
N | 6 | Northern Kentucky ADD | IP20160171 | 6-433 | 2019-01-25 | A | IMPROVE SAFETY ALONG KY 717 AT THE 90 DEGREE BEND NEAR THE CIN/NKY AIRPORT, 0.337 MI N OF KY 1017. (FUNDING SUBJECT TO FISCAL CONSTRAINT PENDING MPO TIP) (2014BOP) | SAFETY(P) | Boone | 008-KY-0717 -000 | 0.7 | 1 | 0.3 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2018 | 260000 | 2018 | 0 | 2018 | 2019-01-08 09:41
N | 6 | Northern Kentucky ADD | IP20160253 | 6-17.05 / 6-17.09 |  | A | KY 143 HPP EARMARK "ADDRESS DEFICIENCIES OF BRENT SPENCE BRIDGE, KENTON COUNTY, KENTUCKY". (2005HPP-KY143)(SEE 6-17.04 FOR ADDITIONAL 2005HPP FUNDING)(SD) | AM-BRIDGE (P) | Kenton | 059-I -0075 -000 | 191.277 | 191.777 | 0.5 | Modernize Roadway-Rural | 26 | Y |  |  |  |  | 6520000 |  | 0 |  | 10850000 | 2018 | 2018-09-24 10:43 |  |  | 6 | Statewide | 72.5803 | 19.1013 | 4.5815 | 11.63 | 8.2819 | 9.6256 | 10 | 9.36
N | 6 | Northern Kentucky ADD | IP20190181 | 6-8716 | 401769 | A | ADDRESS DEFICIENCIES OF BRIDGE ON NORTH END OF DELANEY ROAD 0.1 MILE NORTH OF THE JUNCTION WITH US 25. 041C00016N (12CCN) | AM-BRIDGE (P) | Grant | 041-CR-1142 -000 | 0 | 0.07 | 0.07 | Local Roadway Improvements | 3 |  |  |  | 0 |  | 600000 |  | 550000 |  | 12000000 | 2020 | 2019-02-15 11:38 | Provide connectivity between Delaney Road and US 25 by extending Delaney Road | Provide connectivity.
N | 8 | Lake Cumberland ADD | IP20040027 | 8-9010 |  | A | SAFETY PROJECT TO RECONSTRUCT KY 635 TO ELIMINATE AT GRADE RAILROAD CROSSING AND REPLACE WITH RAILROAD SEPARATION CROSSING AT SCIENCE HILL, KENTUCKY IN PULASKI COUNTY. (2016BOP) | SAFETY-RR SEPARATN(P) | Pulaski | 100-KY-0635 -000 | 6.9 | 8.186 | 1.286 | Improve Railroad Crossing | 55 |  |  |  | 0 |  | 1800000 | 2020 | 1300000 | 2020 | 6500000 | 2022 | 2018-07-10 08:18 | This project is needed because the geometrics along US 127 and KY 1552 near the intersection are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility 3.) Provide access | 8 | South | 48.4882 | 5.3365 | 13.5071 | 9.8104 | 4.8341 | 0 | 0 | 0 | 34 | 15
N | 8 | Lake Cumberland ADD | IP20180002 |  |  |  | Improve pedestrian safety and mobility on KY 439 (Greensburg Street) from intersection of KY 767 (Pelham Branch Road) to milepoint 1.67. | Bike/Ped Facility | Adair | 001-KY-0439 -000 | 0.838 | 1.073 | 0.235 | Other Improvement Types | 0 |  | 0 |  | 20000 | 2019 | 50000 | 2020 | 100000 | 2021 | 150000 | 2022 | 2018-11-27 15:59 | This project is needed because there is a lack of sidewalk between the intersection of KY 767 (Pelham Branch Road) to milepoint 1.67 on KY 439 resulting in pedestrians walking on the shoulder of the roadway. | The following needs have been identified for this project: 1) Improve pedestrian safety. 2) Improve access and mobility for pedestrians.
N | 9 | FIVCO ADD | IP20150129 |  |  |  | Install high-mast lighting at the intersection of I-64 and KY 67 (Industrial Parkway). | Lighting | Carter | 022-I -0064 -000 | 177.9 | 179 | 1.1 | Other Improvement Types | 0 | Y | 0 |  | 50000 |  | 0 |  | 0 |  | 1750000 |  | 2015-04-09 14:18
N | 9 | Buffalo Trace ADD | IP20150130 |  |  |  | Repair bridge on US 68(081B00067N) over Lawrence Creek. | Bridge Replacement | Mason | 081-US-0068 -000 | 16.8 | 17.2 | 0.4 | Other Improvement Types | 0 | Y | 0 |  | 550000 |  | 0 |  | 0 |  | 2000000 |  | 2016-09-13 14:51 | To prevent a hazardous issue from occurring. | This bridge is a very tall bridge on the approach to the Harsha Bridge over the Ohio River 1.3 miles away. Since construction, this structure has experienced movement of the superstructure relative to the substructure. During the past several years, the
N | 9 | FIVCO ADD | IP20150180 | 9-8506 | 2018-10-26 | I | REPLACEMENT OF TWO TRUSS BRIDGES ON KY 773 OVER THE LITTLE SANDY RIVER. (022B00074N)(022B00075N) | AM-BRIDGE (P) | Carter | 022-KY-0773 -000 | 1 | 1.3 | 0.3 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 560000 |  | 370000 |  | 0 | 2019 | 2019-01-23 07:48 |  |  | 9 | East | 20.7488 | 2.6228 | 3.6826 | 2.268 | 2.2754 | 0 | 0 | 9.9 | 21
N | 9 | Bluegrass ADD | IP20150472 |  |  |  | REPLACE BRIDGE ON KY 36 (2.966) OVER BRUSHY FORK (SD, SR = 49.6) 091B00018N | Bridge Replacement | Nicholas | 091-KY-0036 -000 | 2.9 | 3.2 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 750000 |  | 250000 |  | 500000 |  | 2100000 |  | 2015-07-21 13:40 | REPLACE BRIDGE ON KY 36 (2.966) OVER BRUSHY FORK (SD, SR = 49.6) 091B00018N | Bridge is not up to current geometric standards and the concrete structure is deteriorating.
N | 9 | Gateway ADD | IP20180048 |  |  |  | Construct pedestrian/bicycle/equestrian bridge over Cave Run Lake at KY 1274 to provide access to the Cave Run Lake Loop Trail. | Bike/Ped Facility | Rowan | 103-KY-1274 -000 | 0 | 0.1 | 0.1 | Bike and Pedestrian Improvements | 13 |  | 0 |  | 200000 |  | 0 |  | 0 |  | 2000000 |  | 2018-11-30 14:35 | The purpose of this project is to construct a bike/ped facility. | The following need has been identified for the project: bicycle/pedestrian/equestrian access to the Cave Run Loop Trail.
N | 10 | Bluegrass ADD | IP20080561 |  |  |  | IMPROVE SAFETY AND SUFFICIENCY RATING ON KY-52 BRIDGE OVER THE KENTUCKY RIVER AT IRVINE. BRIDGE # B00016 | Bridge Replacement | Estill | 033-KY-0052 -000 | 7.188 | 7.588 | 0.4 | Other Improvement Types | 0 |  | 100000 |  | 750000 |  | 5000000 |  | 250000 |  | 4600000 |  | 2010-02-25 16:51 | Improve safety and sufficiency rating on KY-52 bridge over the Kentucky River at Irvine BRIDGE # B00016 | Safety is a concern on the KY 52 bridge leading into Irvine as indicated by high Critical Rate Factor. Congestion is also present. Bridge Sufficiency Rating on bridge B00016 on KY 52 over the Kentucky River in Irvine is 30.7. Bridge is 26' wide contributi
N | 10 | Kentucky River ADD | IP20110012 |  |  |  | Replace bridge over Moores Fork and realign roadway. | Bridge Replacement | Owsley | 095-KY-0708 -000 | 0.3 | 0.5 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 200000 |  | 200000 |  | 750000 |  | 2013-08-12 09:09 |  | Eliminate a set of substandard curves crossing a bridge.
N | 10 | Bluegrass ADD | IP20110035 |  |  |  | Stabalize Slide and repair roadway at MP 4.00 on KY 52 in Estill County. | Landslide Repair | Estill | 033-KY-0052 -000 | 4 | 4.1 | 0.1 | Other Improvement Types | 0 |  | 5000 |  | 100000 |  | 0 |  | 100000 |  | 700000 |  | 2011-02-10 14:32 |  | Previous slide on KY 52 at MP 4.00 in Estill County has caused the need for slide stabilization and repairs to the roadway.
N | 10 | Bluegrass ADD | IP20110038 |  |  |  | Reconstruct segment of KY 3354 in Powell County out of break area due to mountain slide. | Landslide Repair | Powell | 099-KY-3354 -000 | 1 | 2 | 1 | Other Improvement Types | 0 |  | 5000 |  | 100000 |  | 50000 |  | 100000 |  | 500000 |  | 2011-02-10 14:38 | Reconstruct segment of KY 3354 in Powell County out of break area due to mountain slide. | Mountain slide at MP 1.00 to MP 2.00 has caused a break in the roadway on KY 3354 in Powell County.
N | 10 | Kentucky River ADD | IP20150110 |  |  |  | Repair embankment failure to correct a continous maintenance issue for highway and adjacent railroad. | Landslide Repair | Lee | 065-KY-0052 -000 | 22 | 22.7 | 0.7 | Maintenance Improvement | 10 |  | 0 |  | 1000000 |  | 150000 |  | 500000 |  | 4500000 |  | 2016-09-20 09:36
N | 10 | Kentucky River ADD | IP20150111 |  |  |  | Repair slide area to correct a continous maintenance issue. | Landslide Repair | Perry | 097-KY-1166 -000 | 2.9 | 3.1 | 0.2 | Maintenance Improvement | 10 |  | 0 |  | 530000 |  | 53000 |  | 53000 |  | 530000 |  | 2015-06-29 17:00
N | 10 | Kentucky River ADD | IP20150474 |  |  |  | To correct a continuous maintenance issue between Crawford Mt. and Smitty Dr. on KY 550. | Landslide Repair | Perry | 097-KY-0550 -000 | 1.07 | 1.304 | 0.234 | Maintenance Improvement | 10 |  | 0 |  | 650000 |  | 100000 |  | 75000 |  | 3500000 |  | 2016-06-17 11:24
N | 10 | Kentucky River ADD | IP20160119 |  |  |  | REPAIR SLIDE AREA TO CORRECT A CONTINUOUS MAINTENANCE ISSUE FROM MP 2.9 TO MP 3.1. (16CCN) | Landslide Repair | Perry | 097-KY-0476 -000 | 2.9 | 3.1 | 0.2 | Maintenance Improvement | 10 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-18 13:00
N | 11 | Kentucky River ADD | IP20100046 |  |  |  | Realign existing curve ending 0.060 miles West of KY 3427 and replace bridge over Cutshin Creek (0066B00033N SR=61.0). | Bridge Replacement | Leslie | 066-KY-0699 -000 | 1.9 | 2 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 380000 |  | 275000 |  | 75000 |  | 915495 |  | 2010-12-14 13:40 |  | The existing bridge is narrow for passing vehicles. The speed limit for this road is 55 mph and the existing curve at this location is rated for only 25 mph.
N | 11 | Cumberland Valley ADD | IP20130065 |  |  |  | Benching to address rock slides on I-75 from milepoint 0 to mile point 27 | Landslide Repair | Whitley | 118-I -0075 -000 | 0 | 27 | 27 | Maintenance Improvement | 10 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 8000000 |  | 2013-05-30 10:31 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. There is a need to stabilize and repair rock slides along this section of I-75 that have been a problem over the years. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
N | 11 | Cumberland Valley ADD | IP20150018 |  |  |  | Bridge replacement over Sand Gap (Bridge ID 055B00002 SR 59.4) | Bridge Replacement | Jackson | 055-US-0421 -000 | 16.91 | 16.912 | 0.002 | Modernize Roadway-Rural | 26 |  | 0 |  | 300000 |  | 286000 |  | 200000 |  | 500000 |  | 2015-07-06 10:31 | The purpose of this project is to replace the bridge over Sand Gap (Bridge ID 055B00002 SR 59.4) Currently tractor trailers and school buses cross over the bridge. However, there is difficulty in turning without hitting the bridge. It is recommended tha | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Improve Mobility
N | 11 | Cumberland Valley ADD | IP20150023 |  |  |  | Address safety concerns with road slides on the south end of KY 856 from US 25W to Wood Street. | Landslide Repair | Whitley | 118-KY-0856 -000 | 0 | 0.7 | 0.7 | Maintenance Improvement | 10 |  | 0 |  | 400000 |  | 75000 |  | 425000 |  | 2000000 |  | 2015-03-26 14:01 | This project is to address safety and road slides along KY-856. Guardrails are needed to be placed in various locations along the route. With an IRI over 130, the smoothness of the roadway is considered very rough. It has a low adequacy rating of 60. | The following needs have been identified for this project: 1) Improve Roadway Safety
N | 11 | Cumberland Valley ADD | IP20150061 |  |  |  | Rock fall mitigation on US 25E from Knox County/Bell County Line to KY 229 | Landslide Repair | Knox | 061-US-0025E -000 | 0 | 14.474 | 14.474 | Maintenance Improvement | 10 | Y | 0 |  | 500000 |  | 500000 |  | 500000 |  | 300000 |  | 2015-03-26 14:24 | This project is to provide mitigation of ongoing rockfalls along US 25E. | The following needs have been identified for this project: 1) Improve Roadway Safety
N | 11 | Cumberland Valley ADD | IP20150065 | 11-1105 |  | A | REHAB BRIDGE ON I-75 AT MILEPOINT 27.9 OVER LYNN CAMP CREEK (SR 34.1) (B00063R AND B00063L)(SD) | AM-BRIDGE (P) | Whitley | 118-I -0075 -000 | 27.8 | 27.943 | 0.143 | Other Improvement Types | 0 | Y | [8 empty] | 4000000 | 2018 | 2016-05-24 07:21 | The purpose of this project is to improve roadway safety, improve access, and reduce congestion on I-75 in Whitley County. This project is a part of an overall plan to widen I-75 from the Tennessee state line to Lexington. ADT in the project area continu | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
N | 11 | Cumberland Valley ADD | IP20150114 |  |  |  | Improve safety along US 119 with landslide repairs | Landslide Repair | Harlan | 048-US-0119 -000 | 10.05 | 10.25 | 0.2 | Maintenance Improvement | 10 | Y | 0 |  | 300000 |  | 50000 |  | 200000 |  | 550000 |  | 2015-03-26 14:32 | The purpose of this project is to improve safety along US 119 with landslide repairs | The following needs have been identified for this project: 1) Improve Roadway Safety
N | 11 | Cumberland Valley ADD | IP20150218 | 11-10018 | 2019-08-23 | A | ADDRESS DEFICIENCIES OF KENTUCKY AV BRIDGE OVER MARTINS FK CUMBERLAND RV. (048C00067N) | AM-BRIDGE (P) | Harlan | 048-CS-1041 -000 | 0.126 | 0.182 | 0.056 | Local Roadway Improvements | 3 |  |  |  | 90000 | 2019 | 10000 |  | 10000 |  | 1360000 | 2020 | 2018-10-08 08:37 | The purpose of this project is to address deficiencies of Kentucky Avenue bridge over Martins Fork Cumberland River | The following needs have been identified for this project: 1) Improve Roadway Safety 2) Improve Access 3) Increase Capacity 4) Improve Mobility
N | 11 | Cumberland Valley ADD | IP20160144 | 11-20023 / 11-8952 |  | A | ADDRESS PAVEMENT CONDITION ON KY-490 FROM MILEPOINT 0.00 TO MILEPOINT 6.14 | AM-PAVEMENT (PRI)(P) | Laurel | 063-KY-0490 -000 | 0 | 3.8 | 3.8 | Maintenance Improvement | 10 | [9 empty] | 1424000 | 2022 |  | The purpose of this project is to improve safety on KY 490 from US 25 to KY 1394 by repairing shoulder breakoffs and pavement settling, as well as resurfacing roadway. | The following needs have been identified for this project: 1) Improve Roadway Safety | CUMBERLAND VALLEY ADD | South | 32.5118 | 6.9194 | 10.8057 | 11.7299 | 3.0569 | 0 | 0 | 0 | 32
N | 12 | Big Sandy ADD | IP20080639 |  |  |  | CURVE IMPROVEMENT\LANDSLIDE CORRECTION NEAR WOLFE BRANCH | Landslide Repair | Floyd | 036-KY-1427 -000 | 1.8 | 2.1 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 40000 |  | 97000 |  | 32000 |  | 636000 |  | 2010-12-01 10:49 | Address safety and reliability of this section of KY-1427 by improving curve geometrics and sight distance at Wolfe Branch. | The purpose of this project is to correct a dangerous curve and landslide on KY 1427 at Wolfe Branch. KY 1427 has an ADT of 328. The geometry of this curve which includes the intersection of Wolfe Branch limits sight distance of approaching traffic to t
N | 12 | Big Sandy ADD | IP20100015 |  |  |  | Create new connector between KY 3051 and KY 321 at Auxier. | Bridge Replacement | Floyd | 036-KY-0003 -000 | 2.5 | 2.8 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 400000 |  | 400000 |  | 165000 |  | 2875000 |  | 2011-01-11 14:54 |  | There is no ADEQ Rating information available. The purpose of this project is to address the need for a safe crossing of the Levisa Fork to the community of Auxier from KY 321 and link to KY 3051. The growing community of Auxier, KY is now only accessed
N | 12 | Big Sandy ADD | IP20110155 |  |  |  | Eliminate rockfall hazards from KY 3051 north to KY 321/KY 3 intersection. | Landslide Repair | Floyd | 036-KY-0003 -000 | 2.177 | 2.672 | 0.495 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 500000 |  | 600000 |  | 3800000 |  | 2011-09-15 15:34 | Address safety and reliability issues along this section of KY-3 by correcting rockfall hazards. | This location suffers numerous rockfall incidents of varying severity, especially during heavy rains or freeze/thaw cycles.
N | 12 | Big Sandy ADD | IP20110156 |  |  |  | Eliminate rockfall hazards from KY 3 south approx. 1 mile. | Landslide Repair | Floyd | 036-KY-0321 -000 | 3.1 | 4.182 | 1.082 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 400000 |  | 400000 |  | 3400000 |  | 2011-09-15 16:08 | Address safety and reliability of this section of KY-321 by eliminating rockfall hazards. | This location suffers from numerous rockfall incidents of varying severity, especially during heavy rain or freeze/thaw cycles, often closing the roadway to traffic for days at a time.
N | 12 | Big Sandy ADD | IP20110157 |  |  |  | Mitigate or eliminate rockfalls from KY 3 to KY 2381/Johnson Co.line. | Landslide Repair | Floyd | 036-KY-0321 -000 | 4.182 | 5.076 | 0.894 | Maintenance Improvement | 10 |  | 0 |  | 750000 |  | 800000 |  | 1400000 |  | 16000000 |  | 2015-01-08 13:21 | Address safety and reliability on this section of KY-321 by eliminating rockfall hazards. | This location suffers numerous rockfall incidents or varying severity, especially during heavy rainfall or freeze/thaw cycles, often closing the roadway for days at a time.
N | 12 | Big Sandy ADD | IP20110161 |  |  |  | Eliminate rockfall hazard at various locations adjacent church and Martin intersections. | Landslide Repair | Floyd | 036-KY-0080 -000 | 8.725 | 9.489 | 0.764 | Maintenance Improvement | 10 | Y | 0 |  | 500000 |  | 800000 |  | 800000 |  | 4260000 |  | 2015-01-08 12:17 |  | This location suffers numerous rockfall incidents, of varying severity, especially during periods of heavr rainfall or freeze/thaw cycles. | 12 | East | 20.2126 | 5.7365 | 0 | 8.8473 | 0.8982 | 0 | 4.7305 | 0 | 20
N | 12 | Big Sandy ADD | IP20160082 |  |  |  | NEW BRIDGE OVER THE LEVISA FORK OF THE BIG SANDY RIVER NEAR THE EXISTING SUSPENSION BRIDGE. (14CCN) | Bridge Replacement | Pike | 098-CS-1215 -000 | 1.644 | 1.654 | 0.01 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-11 14:46
Legacy SYP | 1 | Pennyrile ADD | IP20120066 | 1-8901 |  | A | RECONSTRUCT INTERSECTION AT JUNCTION OF KY-93 AND KY-3305. (16CCN) | RECONSTRUCTION(O) | Lyon | 072-KY-0093 -000 | 15.115 | 15.415 | 0.3 | Improve Intersection | 26 | [9 empty] | 1560000 | 2017 |  | Improve safety and sight distance at intersection | KY 3305 (Riley Rd) and Gregory Rd intersection accesses KY 93 at the apex of a hill. The is not suficent line-of-sight distances for vehilces pulling out onto KY 93 from either KY 3395 or Gregory RD. | 1 | West | 25.8789 | 4.7835 | 12.9897 | 2.5387 | 0 | 0 | 0 | 5.567 | 26
Legacy SYP | 1 | Purchase ADD | IP20150132 | 1-121 | 767011 | A | MURRAY FIVE-POINTS INTERSECTION ROUNDABOUT. (12CCR)(16CCR) | RECONSTRUCTION(O) | Calloway | 018-KY-1327 -000 | 1.49 | 1.51 | 0.02 | Improve Intersection | 26 | [5 empty] | 2740000 | 2017 | 2130000 | 2017 | 3170000 | 2019 | 2017-05-19 09:25 | MURRAY FIVE-POINTS INTERSECTION ROUNDABOUT. (12CCR)(16CCR) | This is a "five point" intersection in Murray with KY 1327 (Chestnut Street ADT 12,760 & College Farm RD ADT 5130), KY 748 (16th St ADT 6030), KY 774 (Coldwater Water RD ADT 6270), and N 16th St (ADT approximately 8420). It is very congested during peak | 1 | West | 29.8711 | 8.3849 | 3.866 | 10.5928 | 0 | 0 | 3.866 | 3.1615 | 30
Legacy SYP | 1 | Purchase ADD | IP20150166 | 1-8502 |  | A | CITY OF MURRAY BUSINESS LOOP FROM GLENDALE TO INDUSTRIAL ROAD. (SEE 1-120 FOR D, R, & U FUNDING)(08CCN)(10CCR)(LET BY CITY) | NEW ROUTE(O) | Calloway | 018-PF-9999 - |  |  |  | Construct Road in New Location | 0 | [5 empty] | 0 |  | 0 |  | 3760000 | 2016 | 2017-05-19 12:02 | CITY OF MURRAY BUSINESS LOOP FROM US 641X (GLENDALE) TO KY 2075 (INDUSTRIAL ROAD). (SEE 1-120 FOR D, R, & U FUNDING)(08CCN)(10CCR)(LET BY CITY) | In 2004 the city of Murray received Federal funds to begin a business loop along the eastern edge of the city to improve access from the south and south west to the city industrial area. With the designated funds the city has completed the design of the r | 1 | West | 64.3849 | 8.0275 | 1.8041 | 11.2887 | 0.94502 | 8.7629 | 3.5567 | 0 | 34 | 15 | 15
Legacy SYP | 1 | Purchase ADD | IP20150168 | 1-8851 |  | A | CONSTRUCT A NEW IMPROVEMENT ALLOWING FOR AN OVERPASS FOR PEDESTRIANS CROSSING 16TH STREET GOING TO THE OTHER SIDE OF CAMPUS. MURRAY STATE AND THE CITY ARE IN AGREEMENT WITH THE NEED OF THE IMPROVEMENT. (14CCN) (16CCR) | SAFETY(P) | Calloway | 018-CS-1047 -000 | 1.17 | 1.687 | 0.517 | Other Improvement Types | 0 |  |  |  | 0 |  |  |  | 1500000 | 2017 | 7280000 | 2018 | 2017-05-19 12:52 | Improve the mobility and safety of pedestrians and bicyclists crossing 16th Street in Murray. | This two lane city street runs through the campus of Murray State University. Because of walking/biking university students, significant pedestrian/bike crossing demand exists on this street with an average annual daily traffic (AADT) of 9,033 (2017). | 1 | West | 14.5017 | 7.9038 | 0 | 6.5979 | 0 | 0 | 0 | 0 | 14
Legacy SYP | 1 | Purchase ADD | IP20150239 | 1-1115.10 / 1-1115.20 |  | A | RELOCATION AND MINOR WIDENING OF US-60 FROM CLARKS RIVER TO US-62 JCT.(10CCR)(14CCR)(LET W/ 1-1115.20)(16CCR) | RELOCATION(O) | McCracken | 073-US-0060 -000 | 18.65 | 20.1 | 1.45 | Modernize Roadway-Rural | 26 | Y |  |  | 500000 | 2016 | 8200000 | 2016 | 5700000 | 2016 | 19700000 | 2019 | 2017-05-19 11:23 | The purpose of this project is to improve network flow and access to new Tennessee River Bridge. | Due to the construction of a new four lane US 60 TN River Bridge, (which replaces the 2 lane bridge just upstream on the TN River)this realignment is needed to improve traffic flow and access to the new bridge. | 1 | West | 73.5052 | 9.1409 | 9.2268 | 10.7732 | 0.94502 | 0 | 4.7251 | 8.6942 | 44 | 15 | 15
Legacy SYP | 1 | Purchase ADD | IP20150267 | 1-310.50 |  | A | PADUCAH OUTER LOOP (PRIORITY SECTION 3); FROM US-62 (BLANDVILLE ROAD) TO US-60 (PADUCAH-WICKLIFFE ROAD). (GRADE & DRAIN AND INC. SURFACE) (2002BOPC) | NEW ROUTE(O) | McCracken | 073-KY-0998 -000 | 0 | 2.314 | 2.314 | Construct Road in New Location | 0 | [5 empty] | 5960000 | 2016 | 4750000 | 2016 | 27970000 | 2023 | 2017-05-19 11:09 | PADUCAH OUTER LOOP (PRIORITY SECTION 3); FROM US-62 (BLANDVILLE ROAD) TO US-60 (PADUCAH-WICKLIFFE ROAD). (GRADE & DRAIN AND INC. SURFACE) (2002BOPC) | PADUCAH OUTER LOOP (PRIORITY SECTION 3); FROM US-62 (BLANDVILLE ROAD) TO US-60 (PADUCAH-WICKLIFFE ROAD). (GRADE & DRAIN AND INC. SURFACE) (2002BOPC) | 1 | West | 33.6426 | 3.7457 | 6.8041 | 11.7526 | 4.9828 | 6.3574 | 0 | 0 | 34
Legacy SYP | 1 | Purchase ADD | IP20150286 | 1-1115.20 |  | A | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR)(LET W/ 1-1115.10)(16CCR) | RELOCATION(O) | McCracken | 073-US-0062 -000 | 12.881 | 13.651 | 0.77 | Modernize Roadway-Rural | 26 | Y |  |  | 500000 | 2016 | 4600000 | 2018 | 2600000 | 2019 | 8770000 | 2020 | 2017-05-19 11:25 | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR) | RELOCATION OF US-62 FROM US-60 DEPARTURE TO KY-1887 (PARK ROAD).(10CCR)(12CCR)
Legacy SYP | 1 | Purchase ADD | IP20160020 | 1-8953 |  | A | STUDY IMPROVEMENTS TO HALLOWAY LANDING ROAD (CR1232) (16CCN). | SAFETY(P) | Ballard | 004-CR-1232 -000 | 0 | 5.762 | 5.762 | Transportation Studies | 0 |  | 210000 | 2021 | [9 empty] | Study improvements to Halloway Landing Rd. | This road needs to be studied to determine what can be done to improve access to the wildlife management area. The issue is river flooding during winter-early spring washes out road creating the need to replace when waters recede. This effort is costly bu | 1 | West | 7.878 | 0 | 0 | 3.067 | 4.811 | 0 | 0 | 0 | 8
Legacy SYP | 1 | Purchase ADD | IP20160023 | 1-8952 |  | A | IMPROVE N 16TH STREET FROM KY 1327 (5 POINTS) TO KY 121. (16CCN) | SAFETY(P) | Calloway | 018-KY-0748 -000 | 0 | 0.307 | 0.307 | Modernize Roadway-Rural | 26 |  |  |  | 420000 | 2017 | 2210000 | 2018 | 2170000 | 2020 | 3380000 | 2022 | 2017-05-19 13:14 | IMPROVE N 16TH STREET FROM KY 1327 (5 POINTS) TO KY 121. (16CCN) | Narrow lanes and shoulders create congestion and capacity issues. Improvements would enhance access to Murray State University and decrease traffic demands on Chestnut Street. This route serves local travel in Murray and provides a north-south link throug | 1 | West | 54.7234 | 8.4605 | 6.9072 | 9.3557 | 0 | 0 | 0 | 0 | 25 | 15 | 15
Legacy SYP | 1 | Purchase ADD | IP20160036 | 1-234.10 |  | I | (I-69 CORRIDOR SIGNING) PURCHASE PARKWAY FROM EXIT 22 (KY80/US 45) AT MP 22 TO US 62 AT MP 52 AT CALVERT CITY TO MEET INTERSTATE STANDARDS. (I-69 CORRIDOR IMPROVEMENT)(2014BOP) | SAFETY(P) | Marshall | 079-I -0069 -010 | 34.487 | 50.547 | 16.06 | Full Control to Interstate | 10 | Y |  |  | 0 | 2015 |  |  |  |  | 0 | 2015 | 2015-03-25 | To change Purchase Parkway signs to I-69 signs. | Update parkway signs to interstate signs.
Legacy SYP | 1 | Purchase ADD | IP20160040 | 1-234.30 | 2016-09-30 | I | REPAIRS TO VARIOUS BRIDGES ALONG THE PURCHASE PARKWAY IN GRAVES AND MARSHALL COUNTIES. (I-69 CORRIDOR IMPROVEMENT)(042B00155L, 042B00155R, 079B00076L, 042B00167L, 042B00167R, 042B00168R, AND 079B00074R)(2014BOP) | SAFETY(P) | Marshall | 079-I -0069 -000 | 42.747 | 43.71 | 0.963 | Full Control to Interstate | 10 | Y | [8 empty] | 0 | 2016 |  | Put up I-69 signs to replace Purchase Parkway signs. | Update signs from parkway to interstate.
Legacy SYP | 1 | Purchase ADD | IP20160047 | 1-3016 | 2018-06-07 | I | CONSTRUCT ROADWAY IMPROVEMENTS & MULTI-USE PATH ON US 62 BETWEEN I-24 AND KENTUCKY DAM VILLAGE STATE RESORT PARK IN CALVERT CITY (2014BOP). | TRANSP ENHANCEMENT(P) | Marshall | 079-US-0062 -000 | 9.1 | 10.6 | 1.5 | Other Improvement Types | 0 |  |  |  | 0 |  |  |  | 0 | 2019 | 0 | 2018 | 2017-03-14 09:06 | The purpose of this project is to provide transportation infrastructure to facilitate tourism and economic development. | This route is the main access from the Purchase Parkway and I-24 to the KY Lake Recreation Area, KY Lock and Dam and provides access in conjunction with US 641 access to Barkley Lake and Barkley Lock and Dam. This route provides access to many different t
Legacy SYP | 1 | Purchase ADD | IP20160277 | 1-8002 | 2017-10-27 | I | WIDEN KY-348 TO 4 LANES BETWEEN PURCHASE PARKWAY AND US-641. (00CCN)(06CCR)(INCLUDES DESIGN FOR 1-8101.00)(RU-04DEOB)(12CCR)(16CCR) | MAJOR WIDENING(O) | Marshall | 079-KY-0348 -000 | 7.62 | 8.325 | 0.705 | 2 Lane to 4 Lane Divided - Rural | 36 | Y | [8 empty] | 0 |  | 2017-12-20 09:10 | Widen KY348 to 4 Lanes Between Purchase Parkway and US641. (00CCN)(06CCR)(Includes Design for 1-8101.00)(RU-04DEOB)(12CCR)(16CCR) | This project is needed to relieve congestion, improve traffic flow and access issues. | 1 | West | 76.9596 | 6.3024 | 13.5052 | 11.6881 | 1.9244 | 8.0412 | 0 | 5.4983 | 47 | 15 | 15
Legacy SYP | 2 | Pennyrile ADD | IP20060076 | 2-805 |  | I | NEW INTERCHANGE AT KY 107 SOUTH OF HOPKINSVILLE. KYTC SHALL CONSIDER DESIGN-BUILD OPPORTUNITY. (NO BUILD RECOMMENDATION PER PLANNING STUDY)(14CCR) | SCOPING STUDY DD (O) | Christian | 024-I -0024 -000 | 79.9 | 80.2 | 0.3 | Construct Road in New Location | 0 | Y |  |  | 1200000 | 2023 | 750000 | 2023 | 600000 | 2023 | 7040000 | 2017 | 2017-05-24 12:04 | Improve safety and access | A proposed new interchange would reduce the response times of emergency personnel to an incident on I24 in the area of KY 107. An abreviated IJS was recently completed on this proposed interchange. | PENNYRILE ADD | West | 26.079 | 8.5361 | 0 | 2.1649 | 0.54983 | 9.9656 | 4.8625 | 0 | 26
Legacy SYP | 2 | Green River ADD | IP20060109 | 2-231 | 767011 | A | RECONSTRUCT INTERSECTION AT KY 54 AND KY 2671. (12CCR) | SAFETY(P) | Ohio | 092-KY-0054 -000 | 3.939 | 4.039 | 0.1 | Improve Intersection | 26 |  |  |  | 0 |  | 210000 | 2016 | 170000 | 2016 | 1350000 | 2017 | 2017-05-18 12:33 | Address safety issues at the intersection of KY 54 and KY 2671. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 22.6718 | 4.1237 | 4.4845 | 5.4381 | 1.5808 | 0 | 2.6804 | 4.3643 | 23
Legacy SYP | 2 | Clarksville-Oak Grove MPO | IP20070034 | 2-8954 |  | A | IMPROVE AND WIDEN KY 115 FROM I-24 (MP 2.901) TO ANDERSON ROAD (MP 6.87).(16CCN) | SAFETY(P) | Christian | 024-KY-0115 -000 | 2.901 | 6.87 | 3.969 | Modernize Roadway-Rural | 26 |  |  |  | 1360000 | 2022 | 1300000 | 2023 | 2250000 | 2023 | 8750000 | 2023 | 2018-07-10 08:18 | To improve access, increase mobility and increase safety along this route. | This is an economic developmnet project. This is one phase of a larger project to widen KY 115 for better truck access from the Hopkinsville Industrial Park to I-24. The existing 2/9 lane width and 1.5 shoulders are not widen enough to accommodate the 1 | 2 | West | 53.4854 | 1.7113 | 11.5979 | 10.6572 | 1.9759 | 0 | 3.7457 | 8.7973 | 38 | 15
Legacy SYP | 2 | Pennyrile ADD | IP20080101 | 2-8501 | 767011 | A | US-62; THREE LANES FROM BOARD OF EDUCATION TO CITY PARK IN DAWSON SPRINGS. (08CCN)(10CCR)(12CCR)(16CCN) | MINOR WIDENING(O) | Hopkins | 054-US-0062 -000 | 0.829 | 1.35 | 0.521 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 0 | 2017 | 0 | 2017 | 1880000 | 2018 | 2017-05-18 10:24 | Improve safety and congestion | There is alot of congestion on this road with left turning vehicles adding to the congestion | 2 | West | 42.4072 | 7.8282 | 11.6495 | 8.1701 | 0.84192 | 8.9003 | 0 | 5.0172 | 42
Legacy SYP | 2 | Pennyrile ADD | IP20150177 | 2-8634 |  | A | WIDEN KY-70 (PRINCETON ROAD) FROM US-41 WESTERLY TO SEMINARY STREET. (10CCN) | MAJOR WIDENING(O) | Hopkins | 054-KY-0070 -000 | 18.412 | 18.653 | 0.241 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 2030000 | 2023 | 2110000 | 2023 | 3900000 | 2023 | 2017-05-18 12:06 | Improve traffic flow and safety, as well as pedestrian traffic across a railroad bridge on KY 70 | This section of KY 70 is a narrow 2-lane road with a narrow railroad bridge. There are no sidewalks on the RR Bridge and pedestrians have to walk in the traffic lanes when crossing the bridge. | 2 | West | 46.9184 | 9.5945 | 8.9691 | 9.5747 | 0.94502 | 9.3471 | 3.2646 | 5.2234 | 47
Legacy SYP | 2 | Owensboro MPO | IP20150216 | 2-8632 |  | A | CONSTRUCT A NEW SECTION OF KY-1554 FROM AUDUBON PARKWAY TO KY-56. (10CCN) | NEW ROUTE(O) | Daviess | 030-KY-1554 -000 | 0 | 0.648 | 0.648 | Construct Road in New Location | 0 |  |  |  | 0 |  | 340000 | 2023 | 130000 | 2023 | 870000 | 2023 | 2016-05-24 07:22 | This project has been deleted by the MPO. | This project has been deleted by the MPO.
Legacy SYP | 2 | Green River ADD | IP20150231 | 2-8705 | 767011 | A | ADDRESS LEFT TURN LANE ISSUES ON US-231 AT SOUTHERN ELEMENTARY SCHOOL, MP 5.15 TO 5.25. (12CCN) | SAFETY(P) | Ohio | 092-US-0231 -000 | 5.15 | 5.25 | 0.1 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 420000 | 2016 | 520000 | 2016 | 980000 | 2017 | 2017-05-18 12:26 | Address safety issues along US 231 near the Southern Elementary School. | The following need has been identified for this project: Improve Roadway Safety. | 2 | West | 19.0464 | 5.0172 | 3.0928 | 2.6031 | 1.5808 | 0 | 2.8007 | 3.9519 | 19
Legacy SYP | 2 | Pennyrile ADD | IP20150298 | 2-176 |  | A | RECONSTRUCT KY-85 FROM KY-70 EAST TO AIRPORT ROAD AT ANTON. (08CCR)(10CCR)(16CCR) | RECONSTRUCTION(O) | Hopkins | 054-KY-0085 -000 | 0 | 1.72 | 1.72 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 1260000 | 2016 | 1150000 | 2016 | 1090000 | 2017 | 2017-05-18 12:08 | Improve Safety | Improve Safety | PENNYRILE ADD | West | 37.0945 | 1.8625 | 10.1031 | 6.7268 | 2.3024 | 6.2199 | 3.1787 | 6.701 | 37
Legacy SYP | 2 | Owensboro MPO | IP20150313 | 2-8801 |  | A | ADDRESS SUBSTANDARD ROADWAY GEOMETRICS AND SAFETY CONCERNS ON KY 1456 FROM KY 54 TO HAYDEN ROAD. MP 2.778 TO 4.714 (SEE 2-8709.00)(14CCN)(16CCR) | SAFETY(P) | Daviess | 030-KY-1456 -000 | 2.778 | 4.714 | 1.936 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1580000 | 2016 | 1560000 | 2016 | 11700000 | 2018 | 2017-05-18 11:49 | The purpose of this project is to improve safety, reliability and mobility along KY 1456, better control access and reduce congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types | 2 | West | 61.8368 | 4.3368 | 7.2165 | 10.799 | 2.3024 | 0 | 0 | 7.1821 | 32 | 15 | 15
Legacy SYP | 2 | Pennyrile ADD | IP20150354 | 2-8804 |  | A | LOWER THE ROAD AT THE INTERSECTION OF MERLE TRAVIS HIGHWAY (KY 246) AND KY 176 SO THAT THE INTERSECTION IS ON THE SAME LEVEL AS 176 AND MERLE TRAVIS HIGHWAY. (14CCN)(16CCR) | RECONSTRUCTION(O) | Muhlenberg | 089-KY-0246 -000 | 0 | 0.04 | 0.04 | Improve Intersection | 26 |  |  |  | 300000 | 2017 | 140000 | 2018 | 190000 | 2019 | 1060000 | 2020 | 2017-05-18 12:22 | Improve safety and line of sight distances | Improve safety | PENNYRILE ADD | West | 19.5 | 2.3093 | 4.7423 | 7.4485 | 5 | 0 | 0 | 0 | 20
Legacy SYP | 2 | Green River ADD | IP20150369 | 2-143 / 2-143 |  | A | RECONSTRUCT US-41A BETWEEN PROVIDENCE AND DIXON (04CCN)(08CCR)(10CCR)(12CCR) | RECONSTRUCTION(O) | Webster | 117-US-0041A -000 | 1.324 | 10.01 | 8.686 | Other Improvement Types | 0 |  |  |  | 3400000 | 2016 | 10740000 | 2016 | 8860000 | 2016 | 69300000 | 2018 | 2016-05-24 07:22
Legacy SYP | 2 | Green River ADD | IP20150383 | 2-310.21 | 401769 | A | ADDRESS SAFETY, CONDITION AND SERVICE CONCERN FROM KY 109 TO WEST OF KY 360 TO ESTABLISH TRUCK NETWORK CONNECTION TO SHAWNEETOWN BRIDGE.(14CCR) (SAME AS ITEM NO. 2-310.20 IN 2014 SYP) | MINOR WIDENING(O) | Union | 113-KY-0056 -000 | 2.723 | 7.182 | 4.459 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 15080000 | 2017 | 2017-05-18 10:13 | Address safety and access issues along KY 56 from KY 109 to West of KY 360. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | 2 | West | 63.5052 | 2.543 | 6.0309 | 8.8144 | 4.2612 | 0 | 3.2302 | 8.6254 | 34 | 15 | 15
Legacy SYP | 2 | Green River ADD | IP20160021 | 2-197 | 401783 | A | IMPROVE CONNECTION BETWEEN US-60 AND CANNELTON BRIDGE APPROACH AT HAWESVILLE. (06CCR) (08CCR) (10CCR)(12CCR) | RELOCATION(O) | Hancock | 046-KY-0069 -000 | 13.08 | 13.568 | 0.488 | Construct Road in New Location | 0 | [5 empty] | 0 |  | 0 |  | 6660000 | 2017 | 2017-03-30 17:01 | To address safety and improve connectivity between US 60 and the Cannelton Bridge approach. | The following needs have been identified for this project: 1) Improve roadway safety; 2) Improve mobility and connectivity. | 2 | West | 60.323 | 7.1615 | 0 | 6.8557 | 4.8797 | 7.2165 | 4.2096 | 0 | 30 | 15 | 15
Legacy SYP | 2 | Green River ADD | IP20160284 | 2-8811 |  | A | CONSTRUCT A CONNECTOR ROAD INTO BLUEGRASS CROSSINGS INDUSTRIAL PARK TO IMPROVE ACCESS AND ELIMINATE SAFETY ISSUES. (14CCN) | NEW ROUTE(O) | Ohio | 092-CR-1193 -000 | 0 | 1.134 | 1.134 | Construct Road in New Location | 0 |  |  |  | 0 |  | 740000 | 2016 | 320000 | 2016 | 3380000 | 2017 | 2017-05-18 12:29 | Address safety and access issues along US 231 at the Bluegrass Crossings Industrial Park entrance. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Access along the route. | 2 | West | 12.7363 | 0 | 0 | 6.018 | 1.5636 | 5.1546 | 0 | 0 | 13
Legacy SYP | 2 | Pennyrile ADD | IP20180092 | 2-804.10 / 2-804.20 | 2016-02-05 | A | CENTER STREET/ISLAND FORD CONNECTOR ROAD IN MADISONVILLE FROM CENTER STREET NORTH TO CSX RAILROAD. (14CCN) | NEW ROUTE(O) | Hopkins | 054-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 | 2018 | 0 |  | 0 |  | 0 |  | 2016-10-10 13:15 | Reduce congestion on Main Street in Madisonville and improve traffic flow. | This new route will provide a new North/South Connector between Center Street (KY 70) and Island Ford Rd (KY 281), It will connect two major commercial areas in the City of Madisonville.
Legacy SYP | 3 | Barren River ADD | IP20060143 | 3-8819.10 |  | A | MAJOR WIDENING ON KY 90 (5 LANES WITH CURB, GUTTER, AND SIDEWALK) FROM SANDERS STREET TO ESTES ROAD IN CAVE CITY. (SECTION 1)(2016BOP) | MAJOR WIDENING(O) | Barren | 005-KY-0090 -000 | 0.16 | 1.4 | 1.24 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2016 | 4200000 | 2017 | 3640000 | 2017 | 6490000 | 2019 | 2017-03-31 11:39 | Improve safety and mobility. | Ky 90 between Sanders Street in Cave City and Estes Road has significant traffic and truck volumes. KY 90 provides a link between I65 at Cave City and the Louie B Nunn Parkway at Glasgow. It also provides a link between the Barren River Lake State Park at | 3 | West | 47.3591 | 6.3368 | 7.9897 | 11.4175 | 0.72165 | 9.244 | 4.6735 | 6.9759 | 47
Legacy SYP | 3 | Barren River ADD | IP20060174 | 3-112.10 |  | A | SUMMER SHADE BYPASS. (06CCR)(2006BOPC)(08CCR)(12CCR)(14CCR) | SPOT IMPROVEMENTS(O) | Metcalfe | 085-KY-0090 -000 | 0 | 3.283 | 3.283 | Modernize & Widen Roadway-Rural | 26 |  |  |  | 775000 |  | 2940000 | 2017 | 3330000 | 2018 | 16660000 | 2020 | 2017-03-16 08:20 | Improve safety and mobility. | KY 90 between Barren County Line and KY 640 in Summer Shade is a two lane facility with a number of horizontal curves. The traffic and truck volumes are significant, especially in this area. KY 90 provides access to Monroe, Cumberland, and Clinton Countie | 3 | West | 62.7655 | 5.3127 | 2.1649 | 8.4665 | 4.3814 | 8.8316 | 3.6082 | 0 | 33 | 15 | 15
Legacy SYP | 3 | Barren River ADD | IP20060176 | 3-8506 |  | A | IMPROVE KY 163 CORRIDOR FROM INTERSECTION WITH KY 90 TO US 68 EAST INCLUDING NEW ROUTE OF WEST EDMONTON BYPASS.(SEE 3-8506.20 & 3-8506.30 FOR CONSTRUCTION SECTIONS) (12CCR)(14CCR) | NEW ROUTE(O) | Metcalfe | 085-KY-0163 -000 | 3.223 | 10.695 | 7.472 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-11 10:59 | Improve safety and mobility. | KY163 between KY90 and the Edmonson City Limits is a two lane facility with 9' lane and 2' shoulders. There are numerous horizontal and vertical curves. The flashing beacon at this intersection provides evidence that a problem did once exist at that inter
Legacy SYP | 3 | Barren River ADD | IP20060183 | 3-8954 |  | A | RECONSTRUCT INTERSECTION OF KY 63 AND POPLAR LOG CHURCH ROAD. (16CCN) | RECONSTRUCTION(O) | Monroe | 086-KY-0063 -000 | 10.5 | 10.6 | 0.1 | Improve Intersection | 26 |  |  |  | 200000 | 2017 | 300000 | 2018 | 400000 | 2018 | 700000 | 2019 | 2016-05-24 07:20 | Improve safety. | KY63 in the area of the intersection with the Poplar Church Road is a two lane facility with 10' lanes and 2' shoulders. There are numerous vertical and horizontal curves on the road. There are no turning lanes on either road. The sight distance at the in | 3 | West | 10.5155 | 1.4777 | 1.701 | 0 | 3.488 | 0 | 0 | 3.8488 | 10
Legacy SYP | 3 | Bowling Green MPO | IP20060205 | 3-8951 |  | A | IMPROVE CAPACITY AND SAFETY ON SCOTTSVILLE ROAD BY WIDENING TO SIX LANES FROM KY 884 (3 SPRINGS RD) TO WILKINSON TRACE/ASHLEY CIRCLE. (16CCN) | MAJOR WIDENING(O) | Warren | 114-US-0231 -000 | 9.457 | 10.455 | 0.998 | Add Lane to Full Control Facility | 25 |  |  |  | 2000000 | 2017 | 9500000 | 2019 | 19900000 | 2019 | 30100000 | 2021 | 2016-05-24 07:21 | Reduce congestion and improve mobility. | US 231 between I-65 and US 231X/KY 880 is a five lane facility with 12' lanes and 10' shoulders. The center lane is designated as a left turn only lane. The route is a major commuter facility with the Greenwood Mall and numerous other traffic generators | Bowling Green MPO | West | 49.549 | 9.5533 | 6.5464 | 14.0335 | 0 | 9.5533 | 4.6048 | 5.2577 | 50
Legacy SYP | 3 | Barren River ADD | IP20080142 | 3-319 |  | A | IMPROVEMENTS TO KY 100: RECONSTRUCT KY 100 FROM KY 622 TO EAST OF SULPHUR FORK CREEK. (12CCR) | RECONSTRUCTION(O) | Simpson | 107-KY-0100 -000 | 16.343 | 19.123 | 2.78 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 2440000 | 2016 | 2250000 | 2016 | 12900000 | 2018 | 2017-03-22 14:24 | Improve safety and mobility. | KY 100 is a rural two lane facility with 9' lanes and 4' shoulders. Heavy vehicles make up a relatively large proportion of the traffic composition on this route, and there is also a significant amount of horse and buggy traffic due to the large number of | 3 | West | 70.7113 | 3.4777 | 9.5361 | 9.433 | 2.3024 | 5.4639 | 2.732 | 7.7663 | 41 | 15 | 15
Legacy SYP | 3 | Bowling Green MPO | IP20080150 | 3-8852 |  | A | RECONSTRUCT KY-884 FROM LONG ROAD TO THE NATCHER PARKWAY (MP 5.516 TO MP 7.438). (14CCN) (BRIDGE OVER NATCHER PKWY UNDER 3-8818). | MINOR WIDENING(O) | Warren | 114-KY-0884 -000 | 5.516 | 7.438 | 1.922 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 2370000 | 2017 | 3920000 | 2018 | 5950000 | 2019 | 2019-02-28 10:19 | Improve safety and mobility. | KY 884 between Long Road and the Natcher Parkway overpass is a narrow two lane facility with 9' lanes and 3' shoulders. KY 884 is developing rapidly with numerous large subdivisions emerging, as well as private residences and small commercial development | 3 | West | 48.604 | 5.8076 | 8.866 | 9.8582 | 2.3024 | 0 | 0 | 6.7698 | 34 | 15
Legacy SYP | 3 | Bowling Green MPO | IP20080752 | 3-8858 |  | A | EXTEND SHIVE LANE TO LOVERS LANE (KY 880) IN BOWLING GREEN. (14CCN)(16CCR) | NEW ROUTE(O) | Warren | 114-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 840000 | 2017 | 1740000 | 2018 | 1690000 | 2018 | 3350000 | 2018 | 2019-03-14 14:45 | Increase mobility. | Shive Lane is a two lane facility that is primarily a mix use of commercial, mulifamily residential, and assisted living. Shive Lane is used as a cut through to access KY 880 and US 231. Fruit of the Loom is located in the vicinity, creating high volumes | 3 | West | 22.3299 | 9.7526 | 0 | 3.9691 | 0.94502 | 7.6632 | 0 | 0 | 22
Legacy SYP | 3 | Bowling Green MPO | IP20110204 | 3-8853 |  | A | MINOR WIDENING (2 + 1 CONCEPT) FROM WARREN/SIMPSON COUNTY LINE TO BUCHANON PARK.(14CCN) | MINOR WIDENING(O) | Warren | 114-US-0031W -000 | 0 | 4.258 | 4.258 | Modernize & Widen Roadway-Rural | 26 |  |  |  | 0 |  | 1550000 | 2018 | 4470000 | 2019 | 13450000 | 2020 | 2019-03-13 10:07 | Reduce congestion and increase mobility. | Congestion and further development in the area have created the need for a minor widening project of this section. | 3 | West | 57.3883 | 7.4227 | 10.1546 | 10.5155 | 0.94502 | 0 | 4.5189 | 8.8316 | 42 | 15
Legacy SYP | 3 | Bowling Green MPO | IP20120083 | 3-8854 |  | A | MAJOR WIDENING/RECONSTRUCTION OF CEMETERY ROAD (KY-234) FROM FOUNTAIN TRACE TO ROGER PORTER ROAD (MP 7.878 TO MP 9.625).(14CCN)(16CCR) | MAJOR WIDENING(O) | Warren | 114-KY-0234 -000 | 7.878 | 9.553 | 1.675 | Modernize Roadway-Rural | 26 |  |  |  | 750000 | 2017 | 2000000 | 2018 | 2500000 | 2019 | 5500000 | 2020 | 2016-05-24 07:22 | Increase mobility. | Congestion and further development in the area have created the need for reconstruction of this section. | 3 | West | 57.9218 | 7.0241 | 9.1753 | 8.75 | 2.3024 | 6.6667 | 0 | 9.0034 | 43 | 15
Legacy SYP | 3 | Barren River ADD | IP20150365 | 3-7030 / 3-7030 / 3-7030.50 |  | A | RECONSTRUCT KY-259 FROM 0.42 MILE NORTH OF THE KY-70 INTERSECTION TO NORTH OF THE KYROCK ELEMENTARY SCHOOL (PRIORITY SECTION). (2004BOPC) | SPOT IMPROVEMENTS(O) | Edmonson | 031-KY-0259 -000 | 12.096 | 15.633 | 3.537 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 3480000 | 2016 | 1690000 | 2016 | 20440000 | 2018 | 2005-02-22 16:00 | Improve safety and mobility. | Reconstruction is needed to improve areas with safety concerns along the corridor. | 3 | West | 54.4656 | 6.0206 | 7.1134 | 10.1289 | 4.6907 | 0 | 3.1959 | 8.3162 | 40 |  | 15
Legacy SYP | 3 | Barren River ADD | IP20150375 | 3-8820 |  | A | MAJOR WIDENING OR 2+1 FROM STATE PARK ROAD TO NUNN PARKWAY. (14CCN) | MAJOR WIDENING(O) | Barren | 005-US-0031E -000 | 1.222 | 12.296 | 11.074 | Modernize Roadway-Rural | 26 |  |  |  | 3500000 | 2017 | [6 empty] | 2014-05-29 08:11 | Reduce congestion and increase mobility. | MAJOR WIDENING OR 2+1 FROM STATE PARK ROAD TO NUNN PARKWAY. (14CCN) | 3 | West | 55.262 | 7.2509 | 10.0515 | 14.4201 | 0.92784 | 8.4536 | 4.5017 | 9.6564 | 55
Legacy SYP | 3 | Barren River ADD | IP20160001 | 3-8902 |  | A | RECONSTRUCT 1.0 MILE EAST OF BRIDGE OVER BARREN RIVER LAKE TO CORRECT VERTICAL AND HORIZONTAL DEFICIENCIES.(16CCN) | RECONSTRUCTION(O) | Allen | 002-KY-0098 -000 | 10 | 10.1 | 0.1 | Modernize Roadway-Rural | 26 |  |  |  | 400000 | 2017 | 400000 | 2018 | 300000 | 2019 | 1300000 | 2020 | 2016-05-24 07:21 | Improve safety. | RECONSTRUCT 1.0 MILE EAST OF BRIDGE OVER BARREN RIVER LAKE TO CORRECT VERTICAL AND HORIZONTAL DEFICIENCIES. (16CCN) | 3 | West | 14.7388 | 1.8007 | 1.9588 | 0 | 1.9759 | 5.3952 | 0 | 3.6082 | 15
Legacy SYP | 3 | Barren River ADD | IP20160260 | 3-8953 |  | I | CONSTRUCT AN INDUSTRIAL ACCESS ROAD TO CONNECT TO KY 70 NEAR MP 5.9, INCLUDING A LEFT TURNING LANE ON KY 70. (INCLUDES 3-8906 AND 8907)(16CCN) | NEW ROUTE(O) | Barren | 005-PF-9999 - |  |  |  | Construct Road in New Location | 0 | [9 empty] | 0 | 2018 |  | Connectivity. | Economic development. | BARREN RIVER ADD | West | 11.6271 | 1.9794 | 0 | 1.0567 | 1.89 | 6.701 | 0 | 0 | 12
Legacy SYP | 3 | Bowling Green MPO | IP20170022 | 3-8707 |  | A | CONSTRUCT A NEW INTERCHANGE ON THE NATCHER PARKWAY AT ELROD ROAD IN BOWLING GREEN (MP 3.4 TO MP 4.0).(12CCN) | NEW INTERCHANGE(O) | Warren | 114-PF-9999 - |  |  |  | Innovative Interchange | 40 |  |  |  | 800000 | 2019 | 8810000 | 2021 | 8290000 | 2021 | 25290000 | 2022 | 2016-12-28 11:12 | Reduce congestion and increase mobility. | With the growing population of Bowling Green, especially in the Elrod area, a new interchange is needed on Natcher Parkway at Elrod Road to provide residents with a more efficient transportation system. | Bowling Green MPO | West | 70.4192 | 7.189 | 6.8557 | 13.5567 | 4.0893 | 0 | 0 | 8.7285 | 40 | 15 | 15
Legacy SYP | 3 | Barren River ADD | IP20170038 | 3-8819.20 |  | A | WIDEN KY 90 TO 2 + 1 ROADWAY FROM ESTES ROAD IN CAVE CITY TO THE GLASGOW OUTER LOOP (US68). (SECTION 2)(2016BOP) | MAJOR WIDENING(O) | Barren | 005-KY-0090 -000 | 1.4 | 8.754 | 7.354 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2016 | 1050000 | 2017 | 1040000 | 2017 | 2080000 | 2019 | 2017-03-31 12:08 | Reduce congestion and increase mobility. | Widening and optimization of the roadway with the 2+1 method would greatly increase mobility on this corridor. | BARREN RIVER ADD | West | 75.5851 | 7.9175 | 14.6392 | 14.0077 | 0 | 9.5189 | 4.5361 | 9.9656 | 61 |  | 15
Legacy SYP | 4 | Lake Cumberland ADD | IP20000010 | 4-158 |  | I | COLUMBIA TO GREENSBURG PRIORITY SECTION 1B; KY-61 FROM KY-487 AT GRESHAM, NW TO 5000' SE OF US-68 IN GREENSBURG, INCLUDING BRIDGE. (SEE ITEM #8-128.11) (2005HPP-KY125)(2005HPP-KY161). (2006BOPC)(10CCR)(12CCR) | RECONSTRUCTION(O) | Green | 044-KY-0061 -000 | 0 | 8.194 | 8.194 | Modernize Roadway-Rural | 26 | [5 empty] | 4940000 | 2014 | 1040000 | 2014 | 0 | 2016 | 2019-01-29 14:24 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 61 FROM THE ADAIR COUNTY LINE TO US 68 SOUTH OF GREENSBURG | KY 61 in Green County is a typical rural highway with 9’ lanes and minimal to no shoulders. Another problem is that there is currently no truck network roads in Green County. Industries in the county must either pay fines for trucking violations or locate
Legacy SYP | 4 | Lincoln Trail ADD | IP20070151 | 4-8901 |  | A | RECONSTRUCTION STUDY ON KY 86 FROM MP 15.957 TO MP 26.137 IN BRECKINRIDGE COUNTY & FROM MP 0.000 TO MP 16.145 IN HARDIN COUNTY. (16CCN) | SAFETY(P) | Breckinridge | 014-KY-0086 -000 | 15.957 | 18.712 | 2.755 | Modernize Roadway-Rural | 26 |  | 0 | [10 empty] | Address safety and geometric deficiencies along KY 86 where numerous accidents have occurred. | THE ROAD SEGMENT PROVIDES DIRECT LINKAGE BETWEEN THE CITY OF HARDINSBURG LOCATED IN BRECKINRIDGE COUNTY TO THE CITY OF ELIZABETHTOWN LOCATED IN HARDIN COUNTY. NARROW LANES AND SMALL SHOULDERS ARE PRESENT ALONG THIS ROAD. | LINCOLN TRAIL ADD | South | 50.1232 | 1.6872 | 0 | 7.6777 | 3.3175 | 0 | 0 | 7.4408 | 20 | 15 | 15
Legacy SYP | 4 | Lake Cumberland ADD | IP20100055 | 4-397.11 |  | A | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US68 BETWEEN T DAVIS RD (MP 6.425) AND THE TOP OF RUSSELL CREEK HILL (MP 9.985). (3-203.00 STUDY RECOMMENDATION #13) (DESIGN UNDER 4-397)(2016BOP) | RECONSTRUCTION(O) | Green | 044-US-0068 -000 | 0 | 9.682 | 9.682 | Modernize Roadway-Rural | 26 | [5 empty] | 1920000 |  | 1880000 |  | 8440000 |  | 2017-05-09 08:34 | ADDRESS SAFETY, GEOMETRIC DEFICIENCIES AND MAINTENANCE ISSUES ALONG US 68 FROM THE METCALFE COUNTY LINE (MP 0.000) TO 1600 FEET WEST OF SOUTH THURLOW ROAD (MP 9.682). | US 68 is currently geometrically deficient with many horizontal and vertical curves. There have been numerous accidents and several fatalities which is indicated by the CRF. The adequacy rating shows that almost 55% of the roadway segments within this sa | 4 | South | 26.9905 | 2.7488 | 4.4076 | 4.6209 | 2.7014 | 5.8294 | 0 | 6.6825 | 27
Legacy SYP | 4 | Lincoln Trail ADD | IP20150038 | 4-8308.10 |  | A | WIDEN US-150 FROM KY-49 TO NEAR KY-245/WAL-MART WIDENING. (06CCN) | MAJOR WIDENING(O) | Nelson | 090-US-0150 -000 | 0.44 | 1.697 | 1.257 | Major Widening-Rural Mutilane | 34 |  |  |  | 0 | 2016 | 2440000 | 2017 | 710000 | 2017 | 13160000 | 2019 | 2016-05-24 07:22 | ADDRESS SAFETY, MOBILITY AND GEOMETRIC ISSUES ALONG US 150 IN NELSON COUNTY FROM KY 49 (MP 0.440) TO KY 245 (MP 1.697). | This section of US 150 is the main route between downtown Bardstown and the Bluegrass Parkway along with My Old KY Home State Park and major shopping areas. This section of road has reached near capacity, has a lot of truck traffic, and along with having
Legacy SYP | 4 | Lincoln Trail ADD | IP20150042 | 4-396.30 |  | A | ADDRESS SAFETY, MOBILITY, AND GEOMETRIC ISSUES ALONG US 150 IN WASHINGTON COUNTY FROM 0.7 MILES EAST OF GRUNDY HOME ROAD (MP 2.500) TO 600' EAST OF THE CARTWRIGHT CREEK BRIDGE (MP4.311). SECTION 2 (2016BOP) | RECONSTRUCTION(O) | Washington | 115-US-0150 -000 | 2.5 | 6.557 | 4.057 | Modernize Roadway-Rural | 26 |  |  |  | 500000 |  | 900000 |  | 1000000 |  | 9000000 |  | 2017-01-06 | ADDRESS SAFETY, MOBILITY AND GEOMETRIC ISSUES ALONG US 150 IN WASHINGTON COUNTY FROM 0.7 MILES EAST OF GRUNDY HOME ROAD (MILEPOINT 2.500) TO US 150X (MP 6.557) AT THE OLD ST. CATHERINE'S COLLEGE. | US 150 is the primary roadway from the Bluegrass Parkway to the City of Springfield located in Washington County. Along this section of US 150 there are six substandard vertical curves indicating possible sight distance and speed differential issues. | LINCOLN TRAIL ADD | South | 45.7488 | 7.9526 | 9.3128 | 6.5403 | 1.327 | 8.1991 | 4.3128 | 8.1043 | 46
Legacy SYP | 4 | Elizabethtown-Radcliff MPO | IP20150149 | 4-20.01 |  | A | IMPROVE THE SAFETY AND INCREASE THE CAPACITY OF THE I-65/KY-222 INTERCHANGE BASED ON EXISTING AND FUTURE NEEDS OF THE AREA. (2006BOPC)(08CCR)(10CCR)(14CCR) | I-CHANGE RECONST(O) | Hardin | 047-I -0065 -000 | 85.313 | 86.064 | 0.751 | Innovative Interchange | 40 | [5 empty] | 0 |  | 700000 |  | 32760000 | 2022 | 2017-11-03 11:54 | IMPROVE THE SAFETY AND INCREASE THE CAPACITY OF THE I-65/KY-222 INTERCHANGE BASED ON EXISTING AND FUTURE NEEDS OF THE AREA. | There is a mega-industrial site at Glendale just west of the current interchange. If this site develops, the current interchange will not be able to provide adequate capacity for all of the trucks and employee traffic. There are currently numerous accid | 4 | South | 34.0284 | 9.763 | 4.763 | 9.6682 | 0.47393 | 0 | 5 | 4.3602 | 34
Legacy SYP | 4 | Lincoln Trail ADD | IP20150215 | 4-8851 |  | A | WIDEN TEMPLIN AVENUE BETWEEN CHAMBERS BLVD AND BEN IRVIN RD/KY 2737. (14CCN)(16CCR) | MINOR WIDENING(O) | Nelson | 090-KY-1430 -000 | 0.971 | 1.613 | 0.642 | Modernize Roadway-Rural | 26 |  |  |  | 650000 | 2016 | 2300000 | 2023 | 700000 | 2023 | 3100000 | 2023 | 2017-01-05 15:10 | Address congestion issues along KY 1430 (Templin Ave.) between Chambers Blvd. and KY 2737 (Ben Irvin Rd.) | KY 1430 is only 2 lanes with no shoulders and has increased in traffic due to new schools and a hospital being built on the west side of Bardstown. There is also another school being proposed along KY 1430 which will increase congestion. | LINCOLN TRAIL ADD | South | 24.6445 | 5.6398 | 6.6825 | 5.8294 | 2.2275 | 0 | 0 | 4.2654 | 25
Legacy SYP | 4 | Elizabethtown-Radcliff MPO | IP20150276 | 4-8703 |  | A | RECONSTRUCT KY 79 FROM KY 477 TO KY 428.(12CCN)(14CCR) | RECONSTRUCTION(O) | Meade | 082-KY-0079 -000 | 0 | 1.263 | 1.263 | Modernize Roadway-Rural | 26 |  | 1250000 |  | 0 | 2016 | 1000000 | 2017 | 2000000 | 2017 | 4000000 | 2019 | 2018-02-20 07:55 | Address safety, geometrics, and mobility along KY 79 from KY 477 in Breckinridge County to KY 428 in Meade County. | KY 79 is currently a narrow, 2 lane route with little to no shoulders. Many large trucks use this route to travel from US 60 in Breckinridge County to Brandenburg. | 4 | South | 30.1043 | 3.3744 | 7.1801 | 4.3365 | 2.6303 | 4.455 | 2.7251 | 5.4028 | 30
Legacy SYP | 4 | Elizabethtown-Radcliff MPO | IP20150339 | 4-198 |  | A | EXTEND RING ROAD FROM THE WESTERN KENTUCKY PARKWAY TO I-65. "2 LANE INITIAL/4 LANE ULTIMATE" (12CCR)(14CCR) | NEW ROUTE(O) | Hardin | 047-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 1100000 | 2016 | 19000000 | 2018 | 2019-02-13 08:14 | Improve east-west system connectivity between the radial routes and the interstate network on the south side of Elizabethtown | There is currently no route from I-65 to access the west side of Elizabethtown which is where the Industrial complex and sports park are. | 4 | South | 35.2358 | 9.128 | 2.4171 | 9.4727 | 0.75829 | 8.4834 | 4.9763 | 0 | 35
Legacy SYP | 4 | Lincoln Trail ADD | IP20150358 | 4-287.10 |  | A | BARDSTOWN-LOUISVILLE; WIDENING AND ACCESS MANAGEMENT IMPROVEMENTS ON US-31E BETWEEN NAZARETH DRIVE AND KY-509. (2004BOPC) | RELOCATION(O) | Nelson | 090-US-0031E -000 | 16.835 | 20.536 | 3.701 | Arterial to Partial Control | 23 |  |  |  | 1250000 | 2023 | 10000000 | 2016 | 3000000 | 2016 | 30000000 | 2018 | 2017-05-17 15:35 | Address safety and mobility along US 31E between KY 332 and KY 509 | US 31E is a 2-lane road with minimal shoulders and has had many accidents. Traffic volumes have increased and are projected to increase more as housing developments continue and motorists use this corridor as an alternative to I-65 to get to and from Loui | LINCOLN TRAIL ADD | South | 43.1552 | 7.782 | 8.9573 | 9.5438 | 1.2559 | 6.2085 | 2.8199 | 6.5877 | 43
Legacy SYP | 4 | Lake Cumberland ADD | IP20160012 | 4-8912 |  | A | SCOPING STUDY TO IMPROVE KY 210 FROM CAMPBELLSVILLE TO HODGENVILLE. ADD PASSING LANES AND ADDRESS GEOMETRIC DEFICIENCIES(SAME AS 4-8951.00) (16CCN) | MINOR WIDENING(O) | Taylor | 109-KY-0210 -000 | 0 | 14.148 | 14.148 | Modernize & Widen Roadway-Rural | 26 |  |  |  | 2000000 | 2017 | 2500000 | 2023 | 2500000 | 2023 | 25000000 | 2023 | 2017-05-17 15:02 | Address safety and travel time reliability along KY 210 from Hodgenville to Campbellsville | KY 210 is on the National Truck Network with over 16% truck traffic. There are numerous accidents throughout the corridor with several fatalities. Due to the traffic, there are not many opportunities to pass trucks. | 4 | South | 39.4988 | 4.5877 | 10.237 | 10.7879 | 0.87678 | 0 | 3.8152 | 9.1943 | 40
Legacy SYP | 4 | Lincoln Trail ADD | IP20160066 | 4-8903 |  | A | REALIGN S-CURVE AND CULVERT WIDENING. (16CCN) | SAFETY(P) | Breckinridge | 014-KY-0261 -000 | 12.3 | 12.6 | 0.3 | Modernize Roadway-Rural | 26 |  |  |  | 100000 | 2017 | 60000 | 2018 | 50000 | 2019 | 600000 | 2020 | 2016-05-24 07:21 | ADDRESS SAFETY AND GEOMETRIC DEFICIENCIES ALONG KY 261 AT THE S-CURVES JUST NORTH OF FIRST STREET. | There is an S-Curve along KY 261 where several accidents have occurred
Legacy SYP | 4 | Lincoln Trail ADD | IP20160073 | 4-8953 |  | A | PROVIDE A CONNECTION FROM EAST WHITE OAK STREET TO WEST CARROLL GIBSON BOULEVARD AT THE NEW JUDICIAL CENTER. (16CCN). | NEW ROUTE(O) | Grayson | 043-CS-1145 -000 | 0.036 | 0.172 | 0.136 | Local Roadway Improvements | 3 |  |  |  | 300000 | 2021 | [6 empty] | 2016-05-24 07:21 | PROVIDE A CONNECTION FROM EAST WHITE OAK STREET TO WEST CARROLL GIBSON BOULEVARD AT THE NEW JUDICIAL CENTER. | There is no connection between East White Oak Street to West Carroll Gibson Boulevard where the new judicial center is along with the new library and access to the new City park.
Legacy SYP | 4 | Lincoln Trail ADD | IP20160077 | 4-8307.20 |  | A | WIDEN KY-245 FROM FLAGET HOSPITAL (MP 7.722) THROUGH COUNTY LINE (MP12.261 NELSON/MP0.000 BULLITT) TO HAPPY HOLLOW RD (MP 4.425). | MAJOR WIDENING(O) | Nelson | 090-KY-0245 -000 | 7.722 | 12.261 | 4.539 | Modernize Roadway-Rural | 26 |  |  |  | 4000000 | 2017 | 10000000 | 2019 | 8000000 | 2019 | 45000000 | 2021 | 2017-05-18 08:55 | Address mobility and safety along KY 245 from Flaget Hospital in Nelson County to Happy Hollow Road in Bullitt County | KY 245 is only 2 lanes from Flaget Hospital to the I-65 interchange in Bullitt County. Traffic has dramatically increased through this area and is projected to continue increasing. This section of road is reaching capacity for a 2-lane road. | LINCOLN TRAIL ADD | South | 65.3436 | 8.9573 | 9.0284 | 11.6232 | 0 | 7.5355 | 4.763 | 8.436 | 50 | 15
Legacy SYP | 4 | Elizabethtown-Radcliff MPO | IP20160086 | 4-8919 |  | I | CONSTRUCT A ROUNDABOUT AT NORTHERN END OF MAIN STREET (CS 1004) IN BRANDENBURG. (16CCN) | RECONSTRUCTION(O) | Meade | 082-CS-1004 -000 | 0.04 | 0.05 | 0.01 | Innovative Intersection | 51 | [9 empty] | 0 | 2018 |  | Improve mobility for traffic going to the Ohio River and to see the Confederate memorial statue. | Currently Main St. dead ends at the Ohio River and Brandenburg has accepted the Confederate memorial statue to be placed near the river on Main Street which will draw more traffic.
Legacy SYP | 4 | Lincoln Trail ADD | IP20180046 | 4-8916.20 |  | A | HEARTLAND PARKWAY: IMPROVE MOBILITY FROM THE LEBANON BYPASS TO BOOKER ROAD (CR 1214) NEAR SPRINGFIELD. (CONSTRUCTION SEGMENT 2)(2018BOP) | RECONSTRUCTION(O) | Washington | 115-KY-0055 -000 | 0 | 4.551 | 4.551 | Modernize & Widen Roadway-Rural | 26 | Y |  |  |  |  | 50000 | 2019 | 350000 | 2019 | 4500000 | 2022 | 2018-07-26 | Address safety and mobility on KY 55 as part of the Heartland Parkway, from the Marion/Washington County line north to US 150X in Springfield. | KY 55 is part of the Heartland Parkway which is the corridor from the Bluegrass Parkway to the Cumberland Parkway. It is currently only 2 lanes in this area and passing lines of vehicles including trucks is common which creates a hazardous situation.
Legacy SYP | 5 | KIPDA ADD | IP20060244 | 5-396 |  | I | KY-44 CORRIDOR STUDY FROM TAYLORSVILLE TO MT. WASHINGTON. | SCOPING STUDY(O) | Spencer | 108-KY-0044 -000 | 0 | 7.451 | 7.451 | Modernize Roadway-Rural | 26 |  | 0 | [10 empty] | Address safety, substandard curves, and sight distance to upgrade the safety of the KY 44 roadway from Taylorsville to 2.0 miles east of the Mt. Washington Bypass. | The purpose of the project is to improve the safety of the road and to provide adequate transportation linkage between the Cities of Mt. Washington and Taylorsville. Improvements to the study corridor were considered because of crash concerns, less than s
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080189 | 5-8102 |  | I | IMPROVEMENTS TO I-65 FROM CRITTENDEN DRIVE TO ARTHUR STREET. (02CCN) | SPOT IMPROVEMENTS(O) | Jefferson | 056-I -0065 -000 | 132.6 | 133.6 | 1 | Innovative Interchange | 40 | Y |  |  | 0 | [7 empty] | 2005-12-08 14:52 | The purpose of this project is to establish ways to improve traffic flow, safety and access along I-65 from Crittenden Drive to St. Catherine Street. | Needs identified in the 5-8102 I-65 Planning Study include: 1. Poor Traffic Flow; 2. Too many ramps too close together; 3. Insufficient acceleration, deceleration, merging and weaving distances; 4. Safety problems, high incidences of crashes; 5. Inefficie | Louisville MPO | North | 44.1496 | 9.6862 | 6.6 | 13.3038 | 2.0615 | 0 | 4.9231 | 7.575 | 44
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080199 | 5-485 |  | A | RE-CURB US 60A (EASTERN PARKWAY) FROM KY 1631 (CRITTENDEN DRIVE) TO US 31E (BARDSTOWN ROAD). | PAVEMENT REHAB-PRI(P) | Jefferson | 056-US-0060A -000 | 3.57 | 6.831 | 3.261 | Modernize Roadway-Urban | 16 |  | 200000 | 2016 | 400000 | 2016 |  |  |  |  | 3800000 | 2017 | 2013-12-05 | The purpose of this project is to improve safety and mobility. | The average Critical Rate Factor (CRF) on US 60A from KY 1631 to US 31E was 3.76 for the years 2012 to 2016. Roadway deficiencies exist along the route. This segment connects I-65, KY 61, US 31E, , and the University of Louisville. Water run-off is causin
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080208 | 5-437 |  | I | WIDEN SOUTHSIDE DRIVE (KY-907) TO 5 LANES FROM NEW CUT ROAD TO NATIONAL TURNPIKE. | PE & ENVIRONMENTAL(O) | Jefferson | 056-KY-0907 -000 | 6.31 | 7.036 | 0.726 | Modernize Roadway-Urban | 16 |  |  |  | 0 | [7 empty] | 2011-08-02 09:22 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, 4) Mobility within designated freight corridors, and 5) Modal access and choice. | Existing and future traffic estimates show high traffic volumes creating congestion and reduced safety associated with the many entrances along the roadway. Adjacent roadways that have been improved to meet this traffic demand include New Cut Road (5 lane
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080218 | 5-8953 |  | A | IMPROVE THE HURSTBOURNE PARKWAY (KY 1747) AT SHELBYVILLE ROAD (US 60) INTERSECTION TO INCREASE CAPACITY, REDUCE DELAYS, AND IMPROVE SAFETY.(SEE 5-344.02) (16CCN) | SAFETY(P) | Jefferson | 056-KY-1747 -000 | 13.4 | 13.6 | 0.2 | Improve Intersection | 26 | Y |  |  | 0 | 2017 | 750000 | 2018 | 1040000 | 2019 | 2600000 | 2020 | 2017-03-09 14:19 | Reduce congestion and improve safety at the KY 1747/US 60 intersection. | This project is needed because development in this part of Jefferson County, and additional planned development is contributing to congestion issues at the KY 1747/US 60 intersection, especially at peak hour, where motorists may wait between two to three | 5 | North | 42.4031 | 8.48 | 13.3385 | 12.1846 | 0 | 0 | 4.0615 | 4.3385 | 42
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080248 | 5-371 |  | I | DESIGN STUDY FOR KY-22 IMPROVEMENTS FROM HERR LANE TO CRESTWOOD | SCOPING STUDY DD (O) | Oldham | 093-KY-0022 -000 | 0.021 | 3.262 | 3.241 | 2 Lane to 4 Lane Divided - Urban | 10 | [11 empty] | 2012-05-23 09:25 | The purpose of this project is to Improve safety and reduce congestion on KY 22 from Haunz Lane to KY 329. | This project is needed because the crash rate is high (particularly at the end of the project near KY 329), multiple roadway deficiencies exist, and projected growth results in inadequate capacity on KY 22 from Haunz Lane to KY 329. Roadway deficiencies
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20080254 | 5-5005 |  | I | CORRECT ROCKFALL HAZARD @ MP 1.8 TO MP 2.15(10CCR)(NOT REQUIRED) | ROCKFALL MITIGTN(P) | Oldham | 093-KY-1793 -000 | 1.8 | 2.141 | 0.341 | Maintenance Improvement | 10 | [5 empty] | 830000 | 2010 | 40000 | 2010 | 1580000 | 2011 | 2013-07-08 09:40 | The purpose of this project is to improve safety and access on KY 1793 from just southeast of Ridgeview Drive to KY 3222 (South Rose Island Road). | This project is needed to eliminate a potential rock fall hazard that exists on KY 1793 from just southeast of Ridgeview Drive to KY 3222 (South Rose Island Road) and there are concerns about a potential rock fall slide should this not be corrected. Ther
Legacy SYP | 5 | KIPDA ADD | IP20080265 | 5-147 |  | I | SCOPING STUDY FOR US-421 FROM I-71 TO BEDFORD. | SCOPING STUDY DP (O) | Trimble | 112-US-0421 -000 | 0 | 6.704 | 6.704 | Modernize Roadway-Rural | 26 |  | 0 | [10 empty] | Improve safety and address geometric deficiencies along US 421 from I-71 in Henry County to US 42 in Bedford (Trimble County). | The current roadway alignment has narrow lanes and shoulders. The most frequent crash type in the project area was a vehicle running off the road. Other issues with the existing route are the curves and grades that do not meet current guidelines or provid
Legacy SYP | 5 | KIPDA ADD | IP20080267 | 5-905 | 401769 | A | ADDRESS SAFETY ISSUES AND ACCESS AT THE INTERSECTION OF US-421/KY-1226 AT MP 11.5. (12CCR) | SAFETY(P) | Trimble | 112-US-0421 -000 | 11.278 | 11.678 | 0.4 | Improve Intersection | 26 |  |  |  | 0 |  | 650000 | 2016 | 520000 | 2016 | 950000 | 2017 | 2017-05-16 16:34 | Address safety issues and access at the intersection of US 421\KY 1226 from MP 11.27 to 11.67. | Currently, the angle of the intersection of US-421 and KY-1226 is approximately 63 degrees. Acute angle intersections increase the exposure time and tend to limit visibility of vehicles crossing the intersection. The existing intersection legs of KY-1226 | 5 | North | 39.8546 | 2.9662 | 11.0308 | 1.9962 | 2.2462 | 0 | 2.1846 | 4.4308 | 25 |  | 15
Legacy SYP | 5 | KIPDA ADD | IP20100047 | 5-147 |  | I | SCOPING STUDY FOR US-421 FROM I-71 TO BEDFORD. | SCOPING STUDY DP (O) | Trimble | 112-US-0421 -000 | 1 | 2.4 | 1.4 | Modernize Roadway-Rural | 26 |  | 0 | [10 empty] | The purpose of this project is to rebuild and elimate the major horizontal curve on US 421 in Trimble County. | This spot improvement project was identified as alternative 3B in the US 421 Alternative Study for Henry and Trimble Counties from I-71 to Bedford (SYP 05-147.00). The Critical Rate Factor indicates there is a significant safety issues located along the | KIPDA ADD | North | 29.0923 | 2.3077 | 8.3077 | 4.2462 | 4.8308 | 0 | 1.9538 | 7.4462 | 29
Legacy SYP | 5 | KIPDA ADD | IP20100048 | 5-8712 | 401769 | A | CONSTRUCT TURN LANES INTO TRIMBLE COUNTY HIGH SCHOOL. (12CCN) | SAFETY(P) | Trimble | 112-US-0421 -000 | 7.68 | 7.78 | 0.1 | Improve Intersection | 26 |  | 0 |  | 0 |  | 390000 | 2016 | 550000 | 2016 | 410000 | 2017 | 2017-05-16 16:35 | The purpose of this project is to add a turn lane and improve access at the Trimble County High School. | The Critical Rate Factor indicates that there are safey issues along US 421 in the vicinity of new Bedford Elementary School and Trimble County High School entrances near the KY 625 intersection. Based on intersection counts taken during late April and e | 5 | North | 21.1415 | 3.1569 | 5.9538 | 4.5692 | 1.5231 | 0 | 2.5538 | 3.3846 | 21
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110072 | 5-371 |  | I | DESIGN STUDY FOR KY-22 IMPROVEMENTS FROM HERR LANE TO CRESTWOOD | SCOPING STUDY DD (O) | Jefferson | 056-KY-0022 -000 | 6.05 | 6.725 | 0.675 | Install Two-way Left Turn Lane | 28 | [11 empty] | 2012-05-23 09:25 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | KY 22 from MP 4.42 to MP 6.517 is located in northeastern Jefferson County. Development is planned in this area, and to the east in Oldham County. Currently, existing land use is primarily residential and commercial. The continuing planned development al
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20110079 | 5-367 |  | A | CONSTRUCT NEW ROUTE FROM OLD HENRY INTERCHANGE AT I-265 TO CRESTWOOD BYPASS. (98CCR)(2004BOPP)(10CCN)(14CCR) | NEW ROUTE(O) | Oldham | 093-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 | 2016 | 0 | 2016 | 0 | 2017 | 2016-12-19 11:33 | The purpose of this project is to improve mobility and reduce congestion between the KY 3084 (Old Henry Road) interchange at I-265 (Gene Snyder Freeway) and KY 329B (KY 329 Bypass) in Crestwood. | This project is needed to improve mobility between the KY 3084 (Old Henry Road) interchange at I-265 (Gene Snyder Freeway) and KY 329B (KY 329 Bypass) in Crestwood. The existing two-lane KY 146 through PeWee Valley has poor roadway geometrics, numerous r
Legacy SYP | 5 | KIPDA ADD | IP20110225 | 5-8958 |  | A | WIDEN KY 55X FROM TWO TO FIVE LANES FROM US 60 (MP 0.0) NORTH TO KY 43 (MP 1.354).(16CCN) | RECONSTRUCTION(O) | Shelby | 106-KY-0055X -000 | 0 | 1.354 | 1.354 | Major Widening-Urban Streets | 25 |  |  |  | 1420000 | 2020 | 180000 | 2021 | 790000 | 2021 | 10720000 | 2022 | 2017-05-16 16:28 | WIDEN KY 55X FROM TWO TO FIVE LANES FROM US 60 (MP 0.0) NORTH TO KY 43 (MP 1.354. (16CCN) | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all user types. Higher than average reported crashes indicate potential safety concerns. Current congestion, along with high | KIPDA ADD | North | 15.8777 | 5.6123 | 0 | 6.45 | 0 | 0 | 3.8154 | 0 | 16
Legacy SYP | 5 | KIPDA ADD | IP20130011 | 5-8821 | 401769 | A | IMPROVE DRAINAGE AND INSTALL SIDEWALK ALONG KY 241 IN PLEASUREVILLE. (14CCN) | BIKE/PED FACIL(O) | Henry | 052-KY-0241 -000 | 0.094 | 1.147 | 1.053 | Bike and Pedestrian Improvements | 13 |  |  |  | 0 |  | 550000 | 2016 | 80000 | 2016 | 500000 | 2017 | 2017-05-16 12:52 | Improve drainage and pedestrian mobility on KY 241 from KY 1359 (Hillspring Road) to US 421 in Pleasureville. | This project is needed because existing sidewalks are not ADA compliant, drainage is insufficient, and their are gaps in the existing pedestrian network on KY 241 from KY 1359 (Hillspring Road) to US 421 in Pleasureville. | KIPDA ADD | North | 6.7462 | 1.0462 | 0 | 2.0077 | 3.6923 | 0 | 0 | 0 | 7
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150136 | 5-8102.20 |  | A | RECONSTRUCT RAMP FROM SB I-65 TO ARTHUR ST, RECONSTRUCT ARTHUR ST AND RAMP TO SB I-65 FROM ARTHUR ST AND REMOVE EXISTING RAMPS TO SB I-65 & OFF-RAMPS FROM SB I-65. (2004BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0065 -000 | 133.541 | 133.752 | 0.211 | Innovative Interchange | 40 | Y |  |  | 1450000 | 2023 | 310000 | 2023 | 250000 | 2023 | 15560000 | 2023 | 2016-05-24 07:22 | Improve traffic flow, safety, and access associated with the I-65/Arthur Street ramps. | This project is needed because the ramps at I-65/Arthur Street have insufficient acceleration, deceleration, merging and weaving distances leading to a high amount of crashes and confusion to motorists on I-65 in the vicinity of Arthur Street.
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150143 | 5-8102.40 |  | A | RECONSTRUCT RAMP FROM NB I-65 TO WARNOCK ST, FROM WARNOCK ST TO I-65 NB AND REMOVE RAMPS FROM NB I-65 TO EASTERN PARKWAY. (2004BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0065 -000 | 132.7 | 133.2 | 0.5 | Innovative Interchange | 40 | Y |  |  | 1060000 | 2023 | 4450000 | 2023 | 580000 | 2023 | 7420000 | 2023 | 2016-05-24 07:22 | Improve traffic flow, safety, and access associated with the I-65 ramps from US 60A (Eastern Parkway) to University Boulevard. | This project is needed because there is inadequate weaving distance between the on-ramp from Eastern Parkway to southbound I-65 and the exit ramp to Crittenden Drive, making entering, exiting, and weaving maneuvers difficult. The on-ramp from University
Legacy SYP | 5 | KIPDA ADD | IP20150150 | 5-8820 |  | A | REHABILITATION-OVERLAY AND WIDENING EXISTING KY-55 FROM KY-22 TO CURVE AT MP 2.210 NORTH OF EMINENCE. INCLUDES REPLACING EXISTING CURB AND GUTTER AND SIDEWALKS, AND RELOCATION OF IMPACT UTILITIES. (MP 1.408 TO 2.210)(14CCN) | MINOR WIDENING(O) | Henry | 052-KY-0055 -000 | 1.408 | 2.21 | 0.802 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1520000 | 2016 | 1250000 | 2017 | 2980000 | 2018 | 2017-05-16 12:43 | The purpose of the project is to improve safety and mobility of KY 55 from KY 22 to just north of Cobb Road (past the curve) in Eminence. | This project is needed because currently trucks that traverse the roadway have difficulty passing one another in opposite directions due to insufficient roadway width and there have been numerous accidents at the deficient horizontal curve on KY 55 from K | KIPDA ADD | North | 32.3 | 3.8154 | 9.4615 | 5.9769 | 4.5692 | 0 | 2.9385 | 5.5385 | 32
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150152 | 5-8001 |  | A | WIDEN BUECHEL BANK ROAD TO 3 LANES FROM GE APPLIANCE PARK TO BUECHEL BY-PASS (00CCN) (FUNDING MOVED FROM 5-8105 IN 2010 ENACTED HIGHWAY PLAN FOR R, U, AND C PHASES.)(12CCR) | MINOR WIDENING(O) | Jefferson | 056-CR-1007G -000 | 0 | 1.004 | 1.004 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 0 |  | 800000 | 2016 | 4500000 | 2017 | 2017-05-16 15:56 | Improve safety and capacity on Buechel Bank Road from GE Appliance Park to KY 2251 (Bardstown Road). | This project is needed because the capacity Of Buechel Bank Road from GE Appliance Park to KY 2251 (Bardstown Road) is inadequate which also creates potential safety hazards along this stretch of roadway. | Louisville MPO | North | 35.5385 | 7.1385 | 10.7538 | 6.9692 | 3.7538 | 6.9231 | 0 | 0 | 36
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150155 | 5-972 |  | A | US 42 SAFETY IMPROVEMENTS FROM HARRODS CREEK BRIDGE TO RIVER ROAD.(10CCR) | SAFETY-HAZARD ELIM(P) | Jefferson | 056-US-0042 -000 | 9.628 | 10.548 | 0.92 | Install Two-way Left Turn Lane | 28 |  |  |  | 600000 |  | 5790000 | 2016 | 3380000 | 2016 | 4160000 | 2018 | 2017-04-24 10:50 | Reduce traffic congestion and improve safety along US 42 from Harrods Creek Bridge to River Road. | This project is needed because of current traffic congestion combined with the projected future volumes on US 42 from Harrods Creek Bridge to River Road. The traffic congestion also leads to an increase in crashes. | Louisville MPO | North | 45.1169 | 8.1477 | 11.4923 | 10.8923 | 1.5231 | 0 | 4.5385 | 8.5231 | 45
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150163 | 5-8709 |  | A | NEW ROUTE FROM KY 480 TO KY 44 WITH SALT RIVER CROSSING.(12CCN)(14CCN) | NEW ROUTE(O) | Bullitt | 015-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 4250000 | 2023 | 3000000 | 2023 | 37500000 | 2023 | 2016-05-24 07:22 | The purpose of the project is to enhance mobility and safety within Bullitt County by providing a new connector route between KY 44 and KY 480. | The new 2.5-mile long connector would provide a new bridge over the Salt River, providing an improved connection between KY 44 and the industrial and residential areas along KY 480. Due to the rapid growth within the area (commercial and residential), the
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150164 | 5-8710 |  | A | NEW ROUTE NORTHWEST OF MT. WASHINGTON FROM US 31E TO KY 2706.(12CCN)(14CCN) | NEW ROUTE(O) | Bullitt | 015-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 |  | 500000 | 2023 | 500000 | 2023 | 2000000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to better facilitate traffic movement between eastern Jefferson and Bullitt Counties, as well as to reduce traffic congestion in downtown Mt. Washington. | The need of improved mobility in north Mt. Washington by providing an alternate route between KY 2706 (Wales Run) and US 31E (Bardstown Road) will serve to alleviate traffic congestion (due to future increased traffic volumes and current roadway condition
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150178 | 5-8102.30 |  | A | RECONSTRUCT RAMP FROM CRITTENDEN DRIVE TO NB I-65. (2004BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0065 -000 | 132.2 | 132.7 | 0.5 | Innovative Interchange | 40 | Y |  |  | 200000 | 2023 | 230000 | 2023 | 120000 | 2023 | 1390000 | 2023 | 2016-05-24 07:22 | Improve traffic flow, safety, and access associated with the ramp from Crittenden Drive to northbound I-65. | This project is needed because the existing ramp from Crittenden Drive to northbound I-65 has a curve just in advance of the merging lane that only allows for a speed of approximately 20 mph. The merging distance is short - roughly 300 feet. The curve a
Legacy SYP | 5 | KIPDA ADD | IP20150182 | 5-21.20 |  | A | COMPLETE RECONSTRUCTION OF THE I-265/I-64 INTERCHANGE: ELIMINATE REMAINING CLOVERLEAF RAMPS AND CONSTRUCT REMAINING FULLY DIRECTIONAL RAMPS. (2006BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0265 -000 | 23.3 | 26.5 | 3.2 | Innovative Interchange | 40 | Y |  |  | 3000000 | 2023 | 9390000 | 2023 | 8000000 | 2023 | 92520000 | 2023 | 2016-05-24 07:22 |  |  | 5 | North | 75.1992 | 9.8954 | 6.5077 | 13.8115 | 1.1231 | 0 | 4.5692 | 9.2923 | 45 | 15 | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150185 | 5-41.10 |  | A | SNYDER FREEWAY; RECONSTRUCT I-265/US-60 INTERCHANGE AS A SINGLE POINT URBAN INTERCHANGE AND CONSTRUCT NEEDED IMPROVEMENTS TO CONNECT WITH THE I-265/I-64 INTERCHANGE. (2006BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0265 -000 | 26.5 | 27.1 | 0.6 | Innovative Interchange | 40 | Y |  |  | 3250000 | 2023 | 4260000 | 2023 | 4260000 | 2023 | 52640000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to improve traffic operations and safety in the I-265 (Gene Snyder Freeway)/US 60 (Shelbyville Road) interchange area. | This project is needed because the capacity of the I-265 (Gene Snyder Freeway)/US 60 (Shelbyville Road) interchange is insufficient to meet current and future traffic demands, which results in congestion and potential safety concerns at this interchange. | Central Office | North | 34.2408 | 9.8523 | 3.4154 | 9.5423 | 1.1231 | 0 | 4.5846 | 5.7231 | 34
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150205 | 5-8102.10 |  | A | CONSTRUCT RAMPS CONNECTING NB AND SB I-65 TO THE CENTRAL AVENUE/CRITTENDEN DRIVE INTERSECTION. (2004BOPC) | NEW ROUTE(O) | Jefferson | 056-I -0065 -000 | 131.9 | 132.4 | 0.5 | Construct Road in New Location | 0 | Y |  |  | 1910000 | 2023 | 1350000 | 2023 | 220000 | 2023 | 19240000 | 2023 | 2016-05-24 07:22 | Improve traffic flow, safety, and access at I-65 from the Kentucky Fair and Exposition Center to KY 1631 (Crittenden Drive). | This project is needed because access to Crittenden Drive from northbound I-65 is currently limited and served by exiting at Eastern Parkway. This project would also provide direct access to Central Avenue and improve traffic flow and access to the Kentu
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150220 | 5-8102.50 |  | A | RECONSTRUCT RAMP FROM PRESTON ST TO NB I-65, CONSTRUCT ACCESS TO S JACKSON ST AND/OR S PRESTON ST, REMOVE RAMP FROM NB I-65 TO WOODBINE ST AND EVALUATE THE IMPACTS OF CLOSING THE MAGNOLIA ST RAMP TO SB I-65. (2004BOPC) | I-CHANGE RECONST(O) | Jefferson | 056-I -0065 -000 | 133.7 | 134.1 | 0.4 | Innovative Interchange | 40 | Y |  |  | 1650000 | 2023 | 4360000 | 2023 | 1230000 | 2023 | 15720000 | 2023 | 2016-05-24 07:22 | Improve traffic flow, safety, and access associated with the I-65 ramps at KY 61 (Preston Street), KY 61 (Jackson Street), Woodbine Street, and Magnolia Avenue. | This project is needed because the on-ramp from northbound KY 61 (Preston Street) is inadequate and provides little acceleration distance. KY 61 (Jackson Street) and Woodbine Street exits are immediately north of the on-ramp; all three ramps are too clos
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150228 | 5-8405 |  | A | INTERCHANGE AT MANSLICK ROAD (KY-1931) AND I-264. (08CCN)(10CCR)(12CCR)(14CCR)(16CCR) | NEW INTERCHANGE(O) | Jefferson | 056-PF-9999 - |  |  |  | Grade Separated to Interchange | 0 |  |  |  | 2600000 |  | 14430000 | 2019 | 330000 | 2020 | 6500000 | 2023 | 2017-04-07 10:34 | Provide a safe roadway to alleviate traffic congestion and improve connectivity to the interstate network on KY 1931 (Manslick Road) from US 31W (Dixie Highway) to KY 1865 (Taylor Boulevard). | This project is needed because of current and future traffic demands on US 31W (Dixie Highway) and KY 1865 (Taylor Boulevard) along with lack of interstate access on KY 1931 (Manslick Road). | Louisville MPO | North | 35.42 | 9.4277 | 0 | 6.8077 | 1.1231 | 9.5077 | 4.9538 | 3.6 | 35
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150246 | 5-347.56 |  | A | KY-44 SECTION 2 FROM PARKLAND TR/WINNING COLORS DRIVE EASTWARD TO KINGS CHURCH ROAD (KY 1319). (2008BOPC) | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 24.157 | 25.276 | 1.119 | Modernize Roadway-Rural | 26 |  |  |  | 1090000 | 2023 | 2320000 | 2023 | 830000 | 2023 | 5740000 | 2023 | 2017-05-16 12:03 | Improve capacity, relieve congestion, and improve safety along KY 44 from Parkland Trace/Winning Colors Drive to KY 1319 (Kings Church Road). | This project is needed because the vertical alignment provides inadequate sight distances, particularly at the intersections with East Sanders Lane and Kings Church Road on KY 44 from Parkland Trace/Winning Colors Drive to KY 1319 (Kings Church Road). Ex | Louisville MPO | North | 39.1923 | 5.9077 | 8.0308 | 4.9154 | 2.5692 | 8.0308 | 3.1846 | 6.5538 | 39
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150249 | 5-304.20 |  | A | RECONSTRUCT KY-22 TO 5-LANES FROM ABBOTT LANE TO PROPOSED KY-393 INTERSECTION AND CONTINUING WITH 3-LANES TO EXISTING KY-393. (2004BOPC) | MAJOR WIDENING(O) | Oldham | 093-KY-0022 -000 | 5.268 | 7.451 | 2.183 | Modernize Roadway-Urban | 16 |  |  |  | 910000 | 2016 | 3840000 | 2017 | 2540000 | 2017 | 10950000 | 2019 | 2016-05-24 07:22 | Reconstruct KY-22 with consideration of a 3 lane section with center turn lane from KY 2858 (Abbott Lane) to Centerfield Drive. MP 5.32 to MP 7.50 | The following needs have been identified for this project: 1) Improve Capacity, 2) Provide an improved highway that meets current safety design standards, 3) Enhance network connections, 4) Implement a long-term regional priority, 5) Serve recent and plan
Legacy SYP | 5 | KIPDA ADD | IP20150250 | 5-478.20 |  | A | IMPROVE DIXIE HIGHWAY BETWEEN ROCKFORD LANE (KY 2051) AND GREENWOOD ROAD (KY 1931) | SAFETY(P) | Jefferson | 056-US-0031W -000 | 11.65 | 13.837 | 2.187 | Access Consolidation | 25 | Y | [8 empty] | 7200000 | 2017 |  |  |  | Louisville MPO | Statewide | 78.2642 | 14.8546 | 19.7357 | 13.2654 | 7.4449 | 8.7225 | 1.8062 | 12.4349
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150255 | 5-347.50 |  | A | MT. WASHINGTON-TAYLORSVILLE RD; RECONSTRUCT KY 44 FROM MT. WASHINGTON BYPASS EAST 2.0 MILES (04CCN)(16CCR) | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 23.14 | 25.44 | 2.3 | Modernize Roadway-Urban | 16 | [5 empty] | 0 | 2016 | 0 | 2016 | 0 | 2020 | 2016-12-19 11:40 | The purpose of this project is to improve capacity, relieve congestion, and improve safety along KY 44 from US 31E/150 (Bardstown Road) to KY 1319 (Kings Church Road). | KY 44's intersection with US 31E has a current overall LOS of C and a projected 2033 overall LOS of F. Crash data reveals 252 crashes along the subject section of KY 44 over the last ten years, including 122 rear end collisions, 50 angle collisions and 42
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150273 | 5-8801 |  | A | WIDEN RANGELAND ROAD TO 3 LANES FOR 1.23 MILES. (14CCN) | MINOR WIDENING(O) | Jefferson | 056-CR-1015G -000 | 0 | 1.229 | 1.229 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 1250000 | 2016 | 1100000 | 2016 | 3500000 | 2017 | 2017-05-16 15:59 | Improve safety and capacity of Rangeland Road between KY 864 (Poplar Level Road) and KY 2052 (Shepherdsville Road). | This project is needed because existing Rangeland Road between KY 864 (Poplar Level Road) and KY 2052 (Shepherdsville Road) experiences high crash rates, high traffic volumes, and lacks multi-modal access. Rangleland Road experiences higher than average | Louisville MPO | North | 35.29 | 5.8708 | 12.6462 | 7.6038 | 2.3077 | 6.8615 | 0 | 0 | 35
Legacy SYP | 5 | Bluegrass ADD | IP20150283 | 5-97.50 |  | A | WIDEN US 60 FROM JUST EAST OF THE EXISTING BRIDGE OVER SOUTH BENSON CREEK (B97) TO JUST WEST OF VICKY WAY, WEST OF FRANKFORT, KY.(04CCN)(10CCR) | MAJOR WIDENING(O) | Franklin | 037-US-0060 -000 | 2.78 | 3.913 | 1.133 | 2 Lane to 4 Lane Divided - Rural | 36 | [5 empty] | 4880000 | 2017 | 2440000 | 2017 | 5630000 | 2018 | 2017-05-18 10:56 | The primary purpose for the proposed project is to relieve traffic congestion and improve operations. | On US 60 between the two-lane section just east of South Benson Creek and Vicky Way, located in Franklin County, just west of Frankfort, Kentucky, existing traffic volumes in the area are projected to nearly double by the year 2029, with a corresponding d | BLUEGRASS ADD | North | 50.2892 | 5.1508 | 8.5846 | 4.2923 | 2.1538 | 7.0769 | 0 | 8.0308 | 35 |  | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150290 | 5-443.10 / 5-8205.10 |  | A | IMPROVE AND WIDEN MT WASHINGTON ROAD FROM PRESTON HIGHWAY TO PENN RUN CREEK BRIDGE. (10CCN)(SAME AS 5-8611.00) | MINOR WIDENING(O) | Jefferson | 056-KY-2053 -000 | 0 | 1.501 | 1.501 | Install Two-way Left Turn Lane | 28 |  |  |  | 640000 | 2016 | 3990000 | 2017 | 7320000 | 2017 | 10300000 | 2019 | 2016-05-24 07:22 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150293 | 5-344.01 / 5-344.02 | 401769 | A | WIDEN SOUTHBOUND HURSTBOURNE LANE TO 3 LANES FROM LINN STATION RD (CS-1004H) TO EDEN AVE (CS-1660H). (06CCR)(03KYD)(2006BOPP)(SEE 5-344.02 FOR KYD C PHASE)(14CCR)(XCHNG UNDER 5-8953) | RECONSTRUCTION(O) | Jefferson | 056-KY-1747 -000 | 12.289 | 13.632 | 1.343 | Major Widening-Urban Streets | 25 | Y |  |  |  |  | 1260000 | 2017 | 3160000 | 2017 | 5390000 | 2018 | 2012-05-21 08:53 | Hurstbourne exists today as a highly congested corridor that serves as a commuter route as well as a regional shopping/entertainment destination. The purpose of this project is to reduce congestion and traffic conflict points. | The need for this project is demonstrated by the existing traffic congestion that has been quantified as Delay and Queue Length in the project traffic studies. Intersection queue lengths in excess of 800 feet and delays in excess of 60 seconds are commo | 5 | Statewide | 62.0005 | 11.6123 | 18.326 | 10.6222 | 0 | 7.3789 | 4.5815 | 9.4796
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150300 | 5-8803 | 2018-05-04 | I | SAFETY IMPROVEMENTS TO PALATKA ROAD (KY-1142) MP 0.0 TO MP 1.73. (14CCN) | SAFETY(P) | Jefferson | 056-KY-1142 -000 | 0 | 1.736 | 1.736 | Other Improvement Types | 0 |  |  |  | 0 | 2017 |  |  |  |  | 0 | 2016 | 2017-02-21 | The purpose of this project is to improve the safety of Palatka Rd. (KY1142) between St. Andrews Church Rd. (KY 1931) and Southside Dr. (KY 1020). | A study done on the 3rd Street Road/St. Andrews Church Road area recommended improvements from approximately MP 1.00 to MP 1.45 due to substandard roadway geometrics, restricted sight distances, and accident history. The following recommendations from the
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150305 | 5-150.40 |  | A | SECTION 4 - FROM ARMSTRONG LANE TO US 31EX. (2008BOPC) | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 21 | 22.8 | 1.8 | Modernize & Widen Roadway-Rural | 26 |  |  |  | 1140000 | 2023 | 11690000 | 2023 | 7850000 | 2023 | 15290000 | 2023 | 2017-05-16 12:28 | Reduce congestion and improve safety on KY 44 from Armstrong Lane to US 31EX in Mount Washington. | This project is needed because the capacity of KY does not adequately accommodate existing or future traffic volumes from Armstrong Lane to US 31EX in Mount Washington. In addition, the existing roadway exhibits a higher than average crash rate due to th | 5 | North | 69.6531 | 9.4338 | 10.5692 | 11.6192 | 2.5692 | 9.3846 | 4.1538 | 6.9231 | 55 | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150309 | 5-247.20 |  | A | WIDEN BLUE LICK ROAD FROM BULLITT COUNTY LINE NORTH TO THE SNYDER FREEWAY (LOU T.I.P.)(SEE 5-8010.00 AND 5-8907.00)(08CCR)(10CCR) | MAJOR WIDENING(O) | Jefferson | 056-KY-1450 -000 | 0 | 1.873 | 1.873 | Install Two-way Left Turn Lane | 28 |  |  |  | 0 |  | 11850000 | 2023 | 9970000 | 2023 | 13000000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, and 3) Air quality. | Blue Lick Road (KY 1450) from Bullitt County line north to the Snyder Freeway is currently a two lane road with narrow driving lanes, no shoulders, and steep roadside ditches. The crash rate in the project area is approximately double the statewide averag
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150310 | 5-478.30 |  | A | IMPROVE DIXIE HIGHWAY BETWEEN GREENWOOD ROAD (KY 1931) AND STONESTREET ROAD (CR 1003). (14CCN) | SAFETY(P) | Jefferson | 056-US-0031W -000 | 9.749 | 11.65 | 1.901 | Access Consolidation | 25 | Y |  |  |  |  | 400000 | 2017 | 1100000 | 2017 | 5800000 | 2017 | 2017-05-18 | Improve safety by reducing the number of vehicular and pedestrian injuries, and improve mobility by reducing the travel times for both vehicular and transit users. | The CFR for this section of roadway exceeded 1.0 for the years 2012 to 2016 including 5 fatal crashes. Existing sidewalks are discontinuous and in disrepair and not ADA Compliant. Intersections are often far apart resulting in unsafe mid-block crossings. | 5 | North | 64.3262 | 8.1415 | 14.8154 | 12.6923 | 1.5231 | 0 | 2.6769 | 9.4769 | 49 |  | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150318 | 5-150.02 |  | A | SECTION -1 FROM I-65 TO CHIMNEY ROCK DRIVE.(06CCN) | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 13.1 | 15.1 | 2 | Major Widening-Urban Streets | 25 |  |  |  | 2170000 | 2023 | 7280000 | 2023 | 9410000 | 2023 | 16610000 | 2023 | 2017-05-16 12:33 | The purpose of this project is to reduce congestion, improve safety and provide for better emergency vehicle access. This project would provide improved connectivity between the cities of Mt. Washington and Shepherdsville. | From the approved design executive summary (DES) completed in 2012 for the 2030 No-Build Analysis this segment has a Critical Rate Factor (CRF) of 1.9, a volume to capacity ratio (V/C) of 1.83 and level of service (LOS) of F. Pedestrian facilities curren | 5 | North | 83.2438 | 8.4554 | 10.7077 | 11.5731 | 2.5692 | 9.0462 | 3.8769 | 7.0154 | 53 | 15 | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150319 | 5-373 |  | A | RECONSTRUCT AND WIDEN WATTERSON TRAIL FROM PLANTSIDE DRIVE TO BLANKENBAKER ROAD. (98CCR) | RECONSTRUCTION(O) | Jefferson | 056-KY-1819 -000 | 10.795 | 12.811 | 2.016 | Install Two-way Left Turn Lane | 28 | [7 empty] | 2870000 | 2023 | 12410000 | 2023 | 2017-05-17 12:09 | Improve safety and mobility. | This section of Watterson Trail has many vertical curves that do not meet minimum sight distance criteria for the design speed of the road. Improvements to the horizontal alignment also need to be made, especially at the north end of the project where a | Louisville MPO | North | 49.3108 | 6.9415 | 10.6154 | 9.6462 | 3.8 | 7.6615 | 2.9846 | 7.6615 | 49
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150324 | 5-304.10 |  | A | RECONSTRUCT KY-22 FROM KY-329 TO ABBOTT LANE. (2004BOPC)(08CCR)(10CCR)(12CCR) | MAJOR WIDENING(O) | Oldham | 093-KY-0146 -000 | 2.018 | 2.36 | 0.342 | Modernize Roadway-Urban | 16 | [5 empty] | 2560000 | 2017 | 2540000 | 2017 | 12340000 | 2019 | 2014-05-29 08:12 | Reconstruct KY-22/KY146 with consideration of a 3 lane section with center turn lane from Pryor Avenue to KY-329 Bypass. KY-146 MP 2.018 to MP 2.360 and KY-22 MP 3.250 to MP 3.929. | The following needs have been identified for this project: 1) Improve Capacity, 2) Provide an improved highway that meets current safety design standards, 3) Enhance network connections, 4) Implement a long-term regional priority, 5) Serve recent and plan
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150374 | 5-150.01 |  | A | RECONSTRUCT KY-44 FROM I-65 TO MT. WASHINGTON. (06CCN) | RECONSTRUCTION(O) | Bullitt | 015-KY-0044 -000 | 13.1 | 23.25 | 10.15 | Modernize Roadway-Urban | 16 |  |  |  | 0 |  | 27800000 | 2023 | 33300000 | 2023 | 58800000 | 2023 | 2016-05-24 07:22 | The purpose of the KY 44 Widening Project is to reduce congestion, improve safety and provide for better emergency vehicle access. This project would provide improved connectivity between the cities of Mt. Washington and Shepherdsville. | There are six schools located along this section of KY 44. The current population is approximately 76,000 persons and is expected to reach nearly 114,000 by 2030. There are an estimated 409 access points located along the study portion of the corridor. Re
Legacy SYP | 5 | KIPDA ADD | IP20150424 | 5-475 |  | A | WIDEN I-64 TO SIX LANES FROM KY 53 IN SHELBYVILLE TO KY 1790 UNDERPASS. | SAFETY(P) | Shelby | 106-I -0064 -000 | 35.163 | 38.122 | 2.959 | Add Lane to Full Control Facility | 25 | Y |  |  | 2500000 | 2019 | 1300000 | 2023 | 500000 | 2023 | 29530000 | 2023 | 2016-05-24 07:22 | The purpose of the project is to meet existing and future capacity needs and transportation demands, and address the safety issues along I-64. | I-64 has roadway deficiencies and poor traffic operational characteristics, bridge crossings, and less than desirable shoulders. Traffic projections illustrate continued growth in traffic volumes. | 5 | Statewide | 59.9385 | 13.5859 | 7.2247 | 7.6156 | 1.8062 | 7.8634 | 7.6652 | 14.1775
Legacy SYP | 5 | KIPDA ADD | IP20150426 | 5-8300.10 |  | A | MAJOR RECONSTRUCTION OF KY-146 BETWEEN NEW CASTLE AT US-421 AND PENDLETON AT KY-153. SEGMENT 2:LOST CREEK (1/2 MILE EAST OF SAFETY KLEEN ENTRANCE) TO MAIN STREET (US 421/KY 55). MILE POINT 6.8 TO MILE POINT 9.8.(12CCN)(14CCR) | RECONSTRUCTION(O) | Henry | 052-KY-0146 -000 | 6.8 | 9.8 | 3 | Modernize Roadway-Rural | 26 | [5 empty] | 1900000 | 2017 | 0 |  | 10950000 | 2017 | 2017-05-16 12:47 | Improve safety with maintaining the efficiency of KY 146 from KY 153 near the I-71 interchange to US 421 at New Castle. Segment 2: Lost Creek (1/2 mile east of Safety Kleen entrance) to Main Street (US 421/KY 55). | This project is needed due to a steep grade at the western end of the project ("Pendleton Hill"), and improperly banked curve at "Baxter Curve" near Dawkins Lane, poor sight distance at the KY 1606 intersection, several blind entrances to local roads and | 5 | North | 47.33 | 2.2031 | 6.7846 | 5.2038 | 3.0308 | 7.1692 | 0 | 7.9385 | 32 |  | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20150467 | 5-5013 |  | I | LANDSLIDE REPAIR ON WESTPORT ROAD (KY-524) FROM JCT. US-42 WEST, NORTH 1.0 MILE. (2002BOPC)(NOT REQUIRED). | LANDSLIDE REPAIR(P) | Oldham | 093-KY-0524 -000 | 0 | 1 | 1 | Maintenance Improvement | 10 | [5 empty] | 0 |  | 0 |  | 0 |  | 2011-03-15 14:20 | The purpose of this project is to improve safety and reliability of KY 524 (Westport Road) from US 42 to 1/4 miles south of Smith Lane. | This project is needed because there has been an ongoing landslide issue on KY 524 (Westport) from US 42 to 1/4 miles south of Smith Lane. Maintenance addresses the problem each year with band-aid approaches including driving pilings, adding new rip rap, | 5 | North | 7.5215 | 0.43692 | 0 | 2.4692 | 4.6154 | 0 | 0 | 0 | 8
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160079 | 5-8403 | 401769 | A | INSTALL SOUND BARRIER ON BOTH SIDES OF KY-841 AT WATSONVILLE ROAD. (08CCN)(12CCR) | ENVIRO MITIGATION(P) | Jefferson | 056-KY-0841 -000 | 3.55 | 3.85 | 0.3 | Other Improvement Types | 0 | Y | [8 empty] | 2170000 | 2016 | 2010-04-12 12:48 | The purpose of this project is to reduce noise impacts along KY 841 to adjacent proper owners. | Public concern regarding freeway noise.
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160080 | 5-122 | 767011 | I | MAJOR REVISION OF THE INTERSECTION LOCATED AT THE OUTER LOOP, FEGENBUSH LANE, AND BEULAH CHURCH ROAD. TURN LANE TO BE COMPLETED BY TRANSPORTATION CABINET PER AGREEMENT. (04CCN)(08CCR)(10CCR)(12CCR) | SAFETY(P) | Jefferson | 056-KY-1065 -000 | 9.944 | 10.009 | 0.065 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 2016 | 2018-12-11 08:02 | The primary purpose of the project is to relieve the vehicle delay and improve safety while considering the possible residential, commercial, environmental, and historical impacts of any solution. | Currently KY 1065 (Outer Loop), Fegenbush Lane, Beulah Church Road, and Watterson Trail (CR-1005H) converge within 900' of each other. The junction is controlled by two signalized intersections. Both are plagued by excessive vehicle delay during the mor | 5 | North | 48.0246 | 5.7169 | 7.3385 | 8.2615 | 4.3231 | 0 | 3.6 | 3.7846 | 33 | 15
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160175 | 5-478.70 | 2017-09-29 | I | ADDRESS CONGESTION, SAFETY, AND FUNCTIONALITY OF THE DIXIE HIGHWAY CORRIDOR (FEDERAL TIGER PROJECT) (2016BOP) | SAFETY(P) | Jefferson | 056-US-0031W -000 | 4 | 20 | 16 | Other Improvement Types | 0 | Y |  |  | 0 | 2016 |  |  |  |  | 0 | 2017 | 2019-02-26 07:19 | The purpose of this project is to improve: 1) Safety, 2) Traffic flow on roadways during peak travel hours, 3) Air quality, and 4) Modal access and choice. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access and Increase Capacity for all vehicle types.
Legacy SYP | 5 | KIPDA ADD | IP20160184 | 5-8905 |  | A | EXTEND THE LEFT TURN LANE ON HURSTBOURNE LANE AT INTERSECTION WITH SIX MILE LANE. (16CCN) | SAFETY(P) | Jefferson | 056-KY-1747 -000 | 9.483 | 9.583 | 0.1 | Improve Intersection | 26 | Y |  |  | 90000 | 2017 |  |  |  |  | 130000 | 2017 | 2017-05-16 15:33 | Improve safety. | Crash reduction. | 5 | North | 37.4323 | 7.9323 | 15 | 6.3923 | 0 | 0 | 4.1385 | 3.9692 | 37
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160188 | 5-3703 |  | A | CONSTRUCTION OF A NEW BICYCLE PARKING & INTERMODAL TRANSIT STATION AT THE NW CORNER OF W. JEFFERSON STREET AND S. 4TH STREET (2010BOPC). | CONGESTION MITIGTN(O) | Jefferson | 056-CS-1002A -000 | 0.273 | 0.3 | 0.027 | Bike and Pedestrian Improvements | 13 | [9 empty] | 1353920 | 2014 |  | The purpose of this project is to improve safety, air quality, and intermodal access at the corner of W. Jefferson Street (CS1002A) and S 4th Street (CS-1001F ). | Improve access and increase capacity for bicycle, pedestrian, and transit modes.
Legacy SYP | 5 | Bluegrass ADD | IP20160195 | 5-600 | 2017-12-08 | I | ENHANCEMENT OF US 60 (EAST MAIN STREET) FROM MARTIN LUTHER KING BLVD TO SCHENKEL LANE IN FRANKFORT. (PEDESTRIAN BRIDGE UNDER ITEM NO. 5-8714) (08CCR)(12CCR) | RECONSTRUCTION(O) | Franklin | 037-US-0060 -000 | 9.338 | 10.148 | 0.81 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2019-02-12 10:21 | The purpose of the project is to enhance the safety and operation of the existing US 60/Douglas St./Langford Ave. intersection. | The needs of the project are primarily to better align the approach roads to improve vehicular operation and safety of the intersection; to add left turn lanes on US 60 so that left-turning traffic can safely maneuver and allow thru-traffic to continue un | BLUEGRASS ADD | North | 41.8515 | 5.2246 | 13.9846 | 11.4115 | 0 | 0 | 3.1692 | 8.0615 | 42
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160220 | 5-8956 |  | A | PROVIDE A RELIABLE CONNECTION AND IMPROVE SAFETY ALONG KY 44 FROM MP 9.2 TO MP 10.3, INCLUDING RAISING THE ROADWAY, WIDENING AND REPLACING BRIDGE 015B00020N. (16CCN) | SAFETY(P) | Bullitt | 015-KY-0044 -000 | 9.2 | 10.3 | 1.1 | Modernize Roadway-Urban | 16 |  |  |  | 800000 | 2020 | 1710000 | 2021 | 590000 | 2021 | 5000000 | 2022 | 2016-05-24 07:21 | PROVIDE A RELIABLE CONNECTION AND IMPROVE SAFETY ALONG KY 44 FROM MP 9.2 TO MP 10.3, INCLUDING RAISING THE ROADWAY, WIDENING AND IMPROVING OR REPLACING BRIDGE 015B00020N. (16CCN) | KY 44 is a two lane minor arterial road that is prone to flooding between MP 9.20 and 10.30 in the vicinity of Bridge ID 015B00020N creating system reliability issues between Shepherdsville and Fort Knox. There are also deficient roadway geometrics not m
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160226 | 5-444 |  | I | ACCESS MANAGEMENT AND INTERSECTION/SIGNAL IMPROVEMENTS TO PROVIDE CONGESTION RELIEF ON KY-53 FROM DOWNTOWN LAGRANGE TO I-71. (2004BOPC) | CONGESTION MITIGTN(O) | Oldham | 093-KY-0053 -000 | 6.434 | 6.667 | 0.233 | Modernize Roadway-Urban | 16 | Y |  |  | 265000 | 2014 | 750000 | 2019 | 320000 | 2019 | 1190000 | 2014 | 2017-12-22 11:53 | ACCESS MANAGEMENT AND INTERSECTION/SIGNAL IMPROVEMENTS TO PROVIDE CONGESTION RELIEF ON KY-53 FROM DOWNTOWN LAGRANGE TO I-71. (2004BOPC) | Oldham County Planning and Zoning has identified the need for an access management and enhancement plan for KY53 is typical for many older commercial corridors, with numerous small retailers and older community shopping centers. This corridor is characte | 5 | North | 45.0592 | 5.7785 | 14.4462 | 12.8192 | 2.5692 | 0 | 3.8462 | 5.6 | 45
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20160227 | 5-234 | 401769 | A | KY-393 RECONSTRUCT FROM 140FEET SOUTH OF RAILROAD CROSSING (CSX) EXTENDING NORTHWEST TOWARDS KY 146 ENDING AT STATION 12+00 (DESIGN UNDER 5-230.00). (CONSTRUCTION SEQ.#2) | MAJOR WIDENING(O) | Oldham | 093-KY-0393 -000 | 5.13 | 5.177 | 0.047 | Grade Seperation of Highway/Railroad Crossing | 90 |  |  |  | 0 | [5 empty] | 12470000 | 2016 | 2017-05-16 16:16 | The primary purpose of the proposed project is to improve traffic flow and correct safety deficiencies through reconstruction and realignment of the existing facility, including construction of an underpass to replace the at-grade crossing of the CSX Rail | The project will correct identified traffic problems associated with existing design deficiencies, sight distance, grades and curves, train/automobile conflicts, school complex ingress and egress, emergency service demands, travel safety, travel time, and | 5 | North | 52.1438 | 3.5015 | 10.1077 | 5.9654 | 2.5692 | 0 | 0 | 0 | 22 | 15 | 15
Legacy SYP | 5 | Bluegrass ADD | IP20160231 | 5-8902 |  | A | IMPROVE DRAINAGE ALONG SLICKWAY BRANCH BY EXPANDING WATER SHED BASIN AT JIM BEAM DISTRIBUTION CENTER ON US 421S TO IMPROVE DRAINAGE ISSUES ON COUNTRY LANE. (16CCN) | RECONSTRUCTION(O) | Franklin | 037-US-0421 -000 | 1.778 | 2.349 | 0.571 | Maintenance Improvement | 10 | [9 empty] | 2100000 | 2018 |  | The purpose of this project is to reduce flooding and enhance safety. | Project will reduce flooding associated with previous road construction and enhance the safety and reliability of the current roadway network including US 421S and Country Lane. | BLUEGRASS ADD | North | 14.2062 | 5.5138 | 0 | 3.8308 | 1.5231 | 0 | 3.3385 | 0 | 14
Legacy SYP | 5 | KIPDA ADD | IP20160239 | 5-8851 | 2017-11-17 | I | IMPROVE DRAINAGE ON KY-362 (ASH AVENUE) IN PEWEE VALLEY. (14CCN)(16CCR) | DRAINAGE IMPROVE(P) | Oldham | 093-KY-0362 -000 | 2.1 | 2.4 | 0.3 | Maintenance Improvement | 10 |  |  |  | 0 |  | 0 | 2023 | 0 | 2023 | 0 | 2016 | 2019-02-14 10:19 |  |  | 5 | North | 6.6169 | 1.2554 | 0 | 1.4538 | 3.9077 | 0 | 0 | 0 | 7
Legacy SYP | 5 | KIPDA ADD | IP20170029 | 5-8959 |  | A | NEW NORTH-SOUTH ROUTE BETWEEN US 60 AND BENSON PIKE WEST OF AND PARALLEL TO ROCKET LANE (KY 1871).(16CCN) | NEW ROUTE(O) | Shelby | 106-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 770000 | 2022 | 770000 | 2023 | 100000 | 2023 | 2475000 | 2023 | 2018-07-10 08:18 | NEW NORTH-SOUTH ROUTE BETWEEN US 60 AND BENSON PIKE WEST OF AND PARALLEL TO ROCKET LANE (KY 1871).(16CCN) | The purpose of this project is to provide better freight and commercial access to KY 1871, KY 1779 and CR 1002 (Benson Pike) for vehicles traveling to Guist Creek Lake recreation area and the new commercial developments along Benson Pike. This project is | KIPDA ADD | North | 21.7054 | 3.44 | 5.7692 | 4.7885 | 1.5231 | 6.1846 | 0 | 0 | 22
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170030 | 5-478.01 | 2017-05-26 | I | PEDESTRIAN ACCESS/SAFETY IMPROVEMENT (PART OF LOUISVILLE METRO FEDERAL TIGER GRANT PROJECT COMMITMENT) AND ACCESS CONTROL ON US-31W (DIXIE HIGHWAY) FROM HEATON ROAD MP 14.488 NORTHWARD TO HERBERT AVENUE MP 14.969. (2016BOP)(MOA W/ LVILLE METRO) | SAFETY(P) | Jefferson | 056-US-0031W -000 | 14.488 | 14.969 | 0.481 | Access Consolidation | 25 | Y | [8 empty] | 0 | 2017 |  | The purpose of this project is to improve traffic operations and pedestrian safety along US 31 W (Dixie Highway), including the 1-264 interchange. | The need of this project is to provide appropriate access control measures along US 31 W and to provide connected pedestrian facilities through the 1-264 interchange to improve safety within the proposed project limits.
Legacy SYP | 5 | Louisville-Southern Indiana (KIPDA) MPO | IP20170072 | 5-512 |  | I | EXTENSION OF RIVER ROAD, LOUISVILLE. (2006KYD) | NEW ROUTE(O) | Jefferson | 056-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 | [7 empty] | 2009-01-07 08:44 | Extend and reconfigure River Road as a complete street to create a safer corridor from end to end and reconnect West Louisville to Downtown | Extending River Road westward from its current terminus at 7th Street will provide connections from the East End and downtown to the Portland and Russell neighborhoods and to the future Waterfront Park Phase IV. Reconfiguring the existing portions of Rive | Louisville MPO | North | 25.7546 | 6.9046 | 0 | 8.3423 | 3.1231 | 7.3846 | 0 | 0 | 26
Legacy SYP | 5 | KIPDA ADD | IP20190079 | 5-371.16 |  | A | INTERSECTION IMPROVEMENT ON OLD KY-22 AT HERR LANE AND THE ENTRANCE TO BALLARD HIGH SCHOOL. (06CCR)(2004BOPC)(12CCR) | SAFETY(P) | Jefferson | 056-KY-0022 -000 | 0.42 | 0.8 | 0.38 | [5 empty] | 0 |  | 1370000 | 2016 | 0 |  | 1830000 | 2017 | 2016-05-24 07:22
Legacy SYP | 5 | KIPDA ADD | IP20190124 | 5-63 |  | A | I-64 BRIDGE (SHERMAN MINTON) OVER OHIO RIVER @ LOUISVILLE (B279); JOINT PROJECT WITH INDIANA TO PERFORM IN-DEPTH INSPECTION. (056B00279N) | BRIDGE INSPECTION(P) | Jefferson | 056-I -0064 -000 | 0 | 0.316 | 0.316 | [11 empty] | 160000 | 2016
Legacy SYP | 5 | KIPDA ADD | IP20190125 | 5-15 |  | I | CLEAN AND PAINT ALL STEEL BRIDGES AND STEEL BEARINGS ON THE WATTERSON EXPRESSWAY. (SEE ITEMS 5-15.10, 5-15.20, AND 5-15.30 FOR PHASED CONSTRUCTION) | BRIDGE PAINTING(P) | Jefferson | 056-I -0264 -000 | 0 | 22.282 | 22.282 | [5 empty] | 0 | [5 empty] | 0 |  | 2009-11-09 14:43
Legacy SYP | 5 | KIPDA ADD | IP20190126 | 5-15.20 | 2015-11-30 | I | PHASE 2: CLEAN AND PAINT STEEL BRIDGES AND STEEL BEARINGS ON THE WATTERSON EXPRESSWAY. (PHASE 2) (2008BOPC)(12CCR) | BRIDGE PAINTING(P) | Jefferson | 056-I -0264 -000 | 0 | 22.282 | 22.282 | [11 empty] | 0
Legacy SYP | 5 | KIPDA ADD | IP20190127 | 5-15.30 | 2015-11-30 | I | PHASE 3: CLEAN AND PAINT STEEL BRIDGES AND STEEL BEARINGS ON THE WATTERSON EXPRESSWAY. (2008BOPC)(12CCR) | BRIDGE PAINTING(P) | Jefferson | 056-I -0264 -000 | 0 | 22.282 | 22.282 | [11 empty] | 0
Legacy SYP | 5 | KIPDA ADD | IP20190130 | 5-807 | 2021-01-15 | A | CONSTRUCT TURN LANE ON KY 146 (LAGRANGE ROAD) AT MILEPOINT 6.5 INTO THE LINAK DEVELOPMENT IN JEFFERSON COUNTY. (2016BOP) | CONTINGNCY ACCOUNT(O) | Jefferson | 056-KY-0146 -000 | 6.4 | 6.6 | 0.2 | [5 empty] | 0 | 2017 | 0 | 2017 | 0 | 2017 | 0 | 2017 | 2018-02-23 10:54
Legacy SYP | 5 | KIPDA ADD | IP20190134 | 5-8502 |  | A | WIDEN KY-1020, NATIONAL TURNPIKE, FROM FAIRDALE ROAD TO SOUTH PARK ROAD. MP .615 TO MP 2.669. (08CCN) | MAJOR WIDENING(O) | Jefferson | 056-KY-1020 -000 | 0.615 | 2.669 | 2.054 | [5 empty] | 1350000 | 2016 | [6 empty] | 2016-05-24 07:22
Legacy SYP | 5 | KIPDA ADD | IP20190138 | 5-8205.20 |  | A | IMPROVE AND WIDEN MT. WASHINGTON ROAD FROM PENN RUN CREEK BRIDGE TO CEDAR CREEK ROAD. (10CCN)(SAME AS 5-8612.00) | MINOR WIDENING(O) | Jefferson | 056-KY-2053 -000 | 1.501 | 2.688 | 1.187 | [5 empty] | 400000 | 2022 | 1500000 | 2022 | 1300000 | 2022 | 8200000 | 2022 | 2016-11-01 08:24
Legacy SYP | 6 | Buffalo Trace ADD | IP20080287 | 6-8311 | 2018-01-26 | I | RECONSTRUCT KY-1159 FROM BROOKSVILLE TO KY-9/AA HIGHWAY. (06CCN) (10CCR)(12CCR) (16CCR) | RECONSTRUCTION(O) | Bracken | 012-KY-1159 -000 | 0.85 | 4.355 | 3.505 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-02-21 13:24 | To improve safety. | Project has been studied by HNTB in March 2002. The critical rate factor is higher than 1 therefore, brings our attention to the route. According to the study of 2002, there were a high percentage of injury accidents compared to total of accidents. Ther | 6 | North | 65.0462 | 2.0615 | 6.9231 | 7.4308 | 4.1385 | 6.3692 | 0 | 8.1231 | 35 | 15 | 15
Legacy SYP | 6 | Cincinnati-Northern Kentucky MPO | IP20080290 | 6-8104 |  | I | CONSTRUCT NEW I-471 SOUTHBOUND OFF-RAMP AT KY-8 (SEE ALSO 6-183.00). (02CCN)(06CCN) | NEW ROUTE(O) | Campbell | 019-I -0471 -000 | 4.649 | 4.749 | 0.1 | Other Improvement Types | 0 | Y |  |  | 2600000 |  | 3610000 | 2016 | 690000 | 2023 | 25760000 | 2023 | 2017-05-18 11:42 | TBD | ADT on this exit ramp 9106 vpd on a maximum of one lane. This is project is included in the OKI 2030 Regional Transportation Plan, 2008 Update's Needs List. | 6 | North | 25.3415 | 9.8031 | 0 | 9.4154 | 1.3231 | 0 | 4.8 | 0 | 25
Legacy SYP | 6 | Northern Kentucky ADD | IP20080325 | 6-112.10 |  | I | CONSTRUCT AN INTERCHANGE ON I-75 AT SHERMAN. (06CCN)(08CCN)(10CCN) | NEW INTERCHANGE(O) | Grant | 041-I -0075 -000 | 161.974 | 162.074 | 0.1 | Construct Road in New Location | 0 | Y |  |  | 4680000 | 2016 | 6080000 | 2017 | 2340000 | 2017 | 37960000 | 2019 | 2017-05-22 07:30 | Construct an interchange on I-75 at Sherman Rd. | Giving KY-1994 an interchange with I-75, would open up the northern portion of grant county, while alleviating truck traffic on US-25. | NORTHERN KENTUCKY ADD | North | 26.0692 | 5.8769 | 2.8154 | 1.7308 | 1 | 9.9692 | 4.6769 | 0 | 26
Legacy SYP | 6 | Northern Kentucky ADD | IP20080385 | 6-8508.10 |  | I | RELOCATE KY22 FROM THE INTERSECTION OF FRYER ROAD AND KY 330 TO US27 (ALIGNMENT H FROM 1988 STUDY) | DESIGN ENGINEERING(O) | Pendleton | 096-KY-0022 -000 | 8.704 | 10.365 | 1.661 | Modernize Roadway-Rural | 26 |  |  |  | 2860000 | 2023 | 9270000 | 2023 | 1690000 | 2023 | 53540000 | 2023 | 2017-05-17 13:56 | Improve safety, mobilty and connectivity and address geometric deficiencies along KY 22 from Turner Ridge Road to US 27. | The KY-22 corridor is going to be the focus of our regional efforts. KY22 links Pendleton, Grant and Owen Counties. Since I-74 is not going to be constructed at present, we feel there is a need to connect the three counties, mainly to give Pendleton and | 6 | North | 19.4946 | 0.77538 | 2.4923 | 3.5192 | 4.9231 | 0 | 0 | 7.7846 | 20
Legacy SYP | 6 | Buffalo Trace ADD | IP20110118 | 6-8901 |  | I | IMPROVE SAFETY ALONG KY 2228 FROM KY 9 TO KY 8. (16CCN) | SAFETY(P) | Bracken | 012-KY-2228 -000 | 0 | 0.287 | 0.287 | Modernize Roadway-Rural | 26 |  |  |  | 80000 | 2017 | 60000 | 2018 | 60000 | 2019 | 570000 | 2020 | 2017-05-17 10:06 | To improve safety and mobility | KY 2228 provides a connector between KY 8 and KY 9 in Bracken County. This connector handles a lot of freight and needs improvements. Traffic turning NB from KY 2228 to EB KY 8 have poor sight distance and frequently crashing into the guardrail that pro | 6 | North | 14.5292 | 1.0215 | 4.8462 | 1.3385 | 2.5231 | 0 | 0 | 4.8 | 14
Legacy SYP | 6 | Buffalo Trace ADD | IP20150014 | 6-8902 |  | I | ADD TURN LANES ON KY 9 AT KY 875 MT. ZION ROAD. (16CCN) | RECONSTRUCTION(O) | Bracken | 012-KY-0009 -000 | 7.5 | 8 | 0.5 | Improve Intersection | 26 | Y |  |  | 520000 | 2017 | 280000 | 2018 | 280000 | 2019 | 3380000 | 2020 | 2017-05-17 09:47 | To improve safety and mobility. | Currently there are no turn lanes from the AA Hwy to KY 875. There is a company on the south side of the AA Hwy that generates a lot of truck traffic. A left turn lane on AA Hwy WB to KY 875 and a right turn lane on AA Hwy EB to KY 875 is needed. | BUFFALO TRACE ADD | North | 17.7315 | 3.2431 | 3.4615 | 1.2577 | 1 | 0 | 3.5692 | 5.2 | 18
Legacy SYP | 6 | Northern Kentucky ADD | IP20150017 | 6-8909 |  | I | IMPROVE SAFETY, CONGESTION, AND PEDESTRIAN AND FREIGHT MOBILITY ON US 42 IN WARSAW FROM DAVIS DRIVE TO 0.4 MILES EAST OF DORMAN DRIVE. MP 7.281-7.8. (16CCN) | SAFETY(P) | Gallatin | 039-US-0042 -000 | 7.281 | 8.066 | 0.785 | Improve Intersection | 26 |  |  |  | 1040000 | 2017 | 1110000 | 2018 | 820000 | 2018 | 7880000 | 2020 | 2017-05-17 11:12 | Improve safety and mobility on US 42 in Warsaw. Improve traffic flow and pedestrian facilities near Gallatin County Schools. | Traffic congestion on US 42 in front of Gallatin County High and Middle Schools needs to be improved. Sidewalks on both sides of the road need to be provided for students walking to and from school. Assume curb and gutter with 5' wide sidealk, two 12' l | 6 | North | 22.9985 | 2.5908 | 5.4923 | 4.1769 | 2.1538 | 0 | 2.1538 | 6.4308 | 23
Legacy SYP | 6 | Northern Kentucky ADD | IP20150133 | 6-8851 |  | A | INCREASE SAFETY & OPERATIONS AT THE INTERSECTION OF KY 842 (RICHARDSON RD.) AND US 25 (DIXIE HIGHWAY) FROM JUST W OF US 25 TO BOONE CO. LINE AND INCLUDES MULTI-MODES; (14CCN) | SAFETY(P) | Boone | 008-KY-0842 -000 | 0 | 0.34 | 0.34 | Improve Intersection | 26 |  |  |  | 840000 | 2016 | 4640000 | 2017 |  |  | 3650000 | 2018 | 2017-05-17 10:48 |  | The existing intersection at US 25 is offset with the west leg of KY 842, causing poor operations. Further, there are topographical issues that cause sight distance problems. KY 842 may require realignment at US 25. Realignment impacts the Wiseway bu | 6 | North | 33.4838 | 7.7723 | 6.6923 | 4.95 | 2.9692 | 0 | 2.6 | 8.5 | 34
Legacy SYP | 6 | Northern Kentucky ADD | IP20150138 | 6-8000.20 |  | I | I-275/KY-212 INTERCHANGE AND KY-20 RECONSTRUCTION NEAR GREATER CINCINNATI AIRPORT. (2004BOPC)(KYTC SHARE @ 46.6%) | I-CHANGE RECONST(O) | Boone | 008-I -0275 -000 | 3.793 | 4.287 | 0.494 | Innovative Interchange | 40 | Y |  |  | 6240000 | 2022 | 14590000 | 2022 | 4680000 | 2022 | 44290000 | 2022 | 2017-05-22 11:41 |  |  | Cincinnati/Northern Kentucky MPO | North | 30.9738 | 8.7508 | 3.3231 | 7.0385 | 1.1231 | 0 | 4.6462 | 6.0923 | 31
Legacy SYP | 6 | Cincinnati-Northern Kentucky MPO | IP20150144 | 6-407 | 401769 | I | KY 9 EXTENSION, CAMPBELL COUNTY. (2006KYD). (KYD FUNDING MOVED FROM 6-8101.02) | SAFETY(P) | Campbell | 019-KY-0009 -000 | 21.734 | 22.005 | 0.271 | Improve Railroad Crossing | 55 |  |  |  | 0 |  | 100000 | 2016 | 0 |  | 2170000 | 2016 | 2016-05-24 07:22 | TBD | TBD | Cincinnati/Northern Kentucky MPO | North | 21.8408 | 2.4677 | 12.3692 | 4.3731 | 0 | 0 | 2.6308 | 0 | 22
Legacy SYP | 6 | Buffalo Trace ADD | IP20150174 | 6-8712 |  | I | IMPROVE SAFETY BY RECONSTRUCTING THE CURVE ON KY 165 FROM MP 7.0 TO MP 7.2.(12CCN)(14CCN)(16CCR) | SAFETY(P) | Robertson | 101-KY-0165 -000 | 7 | 7.2 | 0.2 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 210000 | 2016 | 60000 | 2016 | 1630000 | 2017 | 2017-05-17 14:17 | The purpose of this project is to reconstruct a curve of KY 165 at mile point 7.00 to 7.20 to improve safety | This will be a curve correction project only. There have been several accidents since construction was finished on KY 165 into Mt. Olivet | BUFFALO TRACE ADD | North | 9.3046 | 0.50462 | 2.3538 | 0 | 2.4769 | 0 | 0 | 3.9692 | 9
Legacy SYP | 6 | Northern Kentucky ADD | IP20150268 | 6-8702 |  | A | WIDEN KY 22 FROM INTERSECTION WITH KY 845 TO THE OWEN/GRANT COUNTY LINE.(12CCN)(14CCR)(16CCR) | MAJOR WIDENING(O) | Owen | 094-KY-0022 -000 | 16.057 | 18.56 | 2.503 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 275000 | 2017 | 200000 | 2018 | 3200000 | 2019 | 2018-10-23 12:13 | Bring geometric deficiencies up to modern standards to Improve connectivity and mobility in the NKY ADD region by Widening KY 22 from 0.4 north of KY 845 to the Owen/Grant County line. (12CCN)(14CCR) | Increase safety, ease of travel, and travel times on KY-22 (Grant, Owen, Pendleton) Reference Section A3 May 2004 Programming Study. | 6 | North | 59.8854 | 0.99692 | 5.6769 | 3.6577 | 4.9077 | 5.8769 | 0 | 8.7692 | 30 | 15 | 15
Legacy SYP | 6 | Buffalo Trace ADD | IP20150277 | 6-8713 |  | I | IMPROVE SAFETY BEGINNING AT ORCHARD AVENUE TO THE INTERSECTION AT KY 616. (12CCN)(14CCN)(16CCR) | SAFETY(P) | Robertson | 101-US-0062 -000 | 10.834 | 12.102 | 1.268 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1320000 | 2017 | 2860000 | 2018 | 12980000 | 2019 | 2017-05-17 14:15 | This project addresses the goals of the most efficient and safe movement of people and goods through the BTADD region | This section needs realigned with wider lanes and shoulders. | BUFFALO TRACE ADD | North | 17.7531 | 1.3415 | 2.6308 | 1.2115 | 4.6 | 0 | 1.9692 | 6 | 18
Legacy SYP | 6 | Northern Kentucky ADD | IP20150326 | 6-8101.25 | 2017-07-28 | I | RECONSTRUCT KY 9 ALONG A NEW ROUTE FROM NORTH OF 10TH STREET TO 5TH STREET. (2014BOP) | NEW ROUTE(O) | Campbell | 019-CS-1134 -000 | 0.153 | 0.653 | 0.5 | Construct Road in New Location | 0 | [9 empty] | 0 |  |  |  |  | 6 | North | 16.3554 | 2.3938 | 0 | 8.0538 | 0 | 5.9077 | 0 | 0 | 16
Legacy SYP | 6 | Bluegrass ADD | IP20150341 | 6-8300 |  | I | CONSTRUCT WEST US-27 CYNTHIANA BYPASS: SECTION THREE FROM US-27 NORTH TO US 62 EAST. (06CCN) | BYPASS(O) | Harrison | 049-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 2080000 |  | 2900000 | 2023 | 570000 | 2023 | 18250000 | 2023 | 2017-05-22 08:13 | Provide connectivity and reduce travel times. | Extending W US 27 to KY 392 will provide access from US 27 N and US 27 W to US 62 and KY 392 without traffic moving through Cynthiana. | BLUEGRASS ADD | North | 31.5662 | 6.8738 | 4.0154 | 6.1846 | 3.2308 | 8.8308 | 2.4308 | 0 | 32
Legacy SYP | 6 | Northern Kentucky ADD | IP20150421 | 6-411 | 2017-10-27 | I | ROADWAY IMPROVEMENTS TO KY-36 FROM US-25 AT WILLIAMSTOWN TO APPROXIMATELY 1 MILE EAST OF HEEKIN CLARKS ROAD.(12CCR)(14CCR) | SAFETY(P) | Grant | 041-KY-0036 -000 | 13.7 | 14.761 | 1.061 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 | 2016 | 1010000 | 2016 | 0 | 2017 | 2019-02-26 07:38 | Modernize Roadway to KY 36 from I-75 at Williamstown to approximately 1 mile west of Heekin Clarks Road by bringing deficiencies up to modern standards. | Improve mobility on KY 36 in Grant County. | 6 | North | 22.5746 | 1.1015 | 10.2 | 3.4269 | 1.3538 | 0 | 0 | 6.4923 | 23
Legacy SYP | 6 | Northern Kentucky ADD | IP20150423 | 6-158 | 2016-11-18 | I | RECONSTRUCT KY-536 TO A 5-LANE URBAN SECTION FROM 1500' WEST OF US-42 TO I-75 (MP 10.3 TO MP 13.24). (DOES NOT INCLUDE INTERCHANGE RECONSTRUCTION) (00CCR) (10CCR)(12CCR)(14CCR)(16CCR) NOTE: BORROWED SNK FUNDS USED FOR THE C PHASE TO BE REPAIDED TO OKI. | RECONSTRUCTION(O) | Boone | 008-KY-0536 -000 | 10.3 | 13.24 | 2.94 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 0 | 2017 | 2018-12-11 09:47
Legacy SYP | 6 | Northern Kentucky ADD | IP20150445 | 6-352 |  | I | EXTEND PROPOSED POND CREEK ROAD FROM US-27 TO AA HIGHWAY VIA PORTION OF KY 10/KY 1997 CORRIDOR (NEW KY-536)(04CCN)(12CCR)(14CCR) | NEW ROUTE(O) | Campbell | 019-KY-0547 -000 | 0 | 2 | 2 | Construct Road in New Location | 0 |  |  |  | 2600000 |  | 11000000 | 2021 | 8000000 | 2022 | 37010000 | 2022 | 2017-05-19 08:31 |  |  | Cincinnati/Northern Kentucky MPO | North | 23.3215 | 1.6369 | 2.7231 | 8.7923 | 4.3538 | 5.8154 | 0 | 0 | 23
Legacy SYP | 6 | Buffalo Trace ADD | IP20150446 | 6-8309 |  | I | SPOT IMPROVEMENTS FROM THE CITY OF BROOKSVILLE SOUTH TO POWERSVILLE. (06CCN) (10CCR) (16CCR) | RECONSTRUCTION(O) | Bracken | 012-KY-0010 -000 | 10.38 | 13.959 | 3.579 | Modernize Roadway-Rural | 26 |  |  |  | 3120000 | 2016 | 5790000 | 2016 | 2820000 | 2019 | 24340000 | 2020 | 2017-05-17 09:53 | To improve mobility | Spot improvements from the city of Brooksville south to Powersville | BUFFALO TRACE ADD | North | 33.7562 | 1.2985 | 6 | 7.9038 | 4.2462 | 6.3077 | 0 | 8 | 34
Legacy SYP | 6 | Northern Kentucky ADD | IP20160091 | 6-202 | 401769 | A | RECONSTRUCT US-42 ALONG THE OHIO RIVER TO CORRECT LANDSLIDE PROBLEMS BETWEEN MARKLAND DAM AND CRAIGS CREEK.(U-04DEOB)(10CCR)(14CCR) | LANDSLIDE REPAIR(P) | Gallatin | 039-US-0042 -000 | 3.325 | 4.636 | 1.311 | Maintenance Improvement | 10 | [9 empty] | 17310000 | 2016 | 2015-09-29 15:49 | RECONSTRUCT US-42 ALONG THE OHIO RIVER TO CORRECT LANDSLIDE PROBLEMS BETWEEN MARKLAND DAM AND CRAIGS CREEK.(U-04DEOB)(10CCR)(14CCR) | US-42 ALONG THE OHIO RIVER EXPERIENCES MAJOR LANDSLIDE ISSUES WHICH AFFECTS THIS HEAVILY TRAVELED CAR AND TRUCK ROUTE | 6 | North | 11.9308 | 2.9846 | 0 | 3.5769 | 3.0154 | 0 | 2.3538 | 0 | 12
Legacy SYP | 6 | Bluegrass ADD | IP20160159 | 6-8710 | 2017-07-28 | I | REPLACE UNION ROBINSON ROAD BRIDGE.(12CCN) | BRIDGE REPLACEMENT(P) | Harrison | 049-CR-1062 -000 | 3.884 | 3.902 | 0.018 | Other Improvement Types | 0 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2017-08-14 11:58 | Replace bridge. | Structure has been designated structurally deficient. | 6 | North | 4.0554 | 0.024615 | 0 | 0 | 4.0308 | 0 | 0 | 0 | 4
Legacy SYP | 7 | Lexington MPO | IP20000055 | 7-430 |  | A | ACCESS MANAGEMENT ON NICHOLASVILLE ROAD BETWEEN NICHOLASVILLE AND MAN-O-WAR BLVD. (14CCR) | SAFETY(P) | Jessamine | 057-US-0027 -000 | 10.87 | 15.278 | 4.408 | Access Consolidation | 25 | Y |  |  | 0 |  | 7670500 | 2017 | 1350000 | 2017 | 30970000 | 2017 | 2017-10-24 07:41 |  | Heavy auto and truck traffic volumes impacts the pavement quality in specific sections. The combination of trucks and cars create backups near major intersections, and the trucks slow start up from a red light reduces the V/SF ratio. AM and PM Peak hour t | Lexington MPO | North | 78.8862 | 8.9477 | 13.6615 | 12 | 0 | 0 | 4.6154 | 9.6615 | 49 | 15 | 15
Legacy SYP | 7 | Lexington MPO | IP20070219 | 7-8906 |  | A | RECONSTRUCT KY 169 FROM US 68 TO 0.54 MILES NORTH OF CLEAR CREEK RD (MP 14.448 TO MP 19.00). (16CCN) | RECONSTRUCTION(O) | Jessamine | 057-KY-0169 -000 | 14.448 | 19 | 4.552 | Modernize Roadway-Rural | 26 |  |  |  | 2750000 | 2017 | 4410000 | 2018 | 4330000 | 2019 | 21650000 | 2020 | 2017-05-18 09:54 | Improve roadway typical section and eliminate hazards along KY 169 from US 68 to 0.54mi N of Clear Creek Rd. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility, 3) Reduce Congestion. | Lexington MPO | North | 41.3646 | 2.4492 | 9.0923 | 10.0846 | 4.4154 | 6 | 0 | 9.3231 | 41
Legacy SYP | 7 | Bluegrass ADD | IP20080398 | 5-806 |  | A | RECONSTRUCT KY 151 FROM US 127 AT LAWRENCEBURG TO I-64 IN FRANKLIN COUNTY. | RECONSTRUCTION(O) | Anderson | 003-KY-0151 -000 | 0 | 4.587 | 4.587 | Modernize Roadway-Rural | 26 |  | 0 | 2017 | 1750000 | 2017 | 5000000 | 2018 | 5000000 | 2020 | 20000000 | 2022 | 2016-05-24 07:21 | The purpose of this project is to: 1) Improve Roadway Safety. | Improve safety on KY 151 between the intersections with US 127 in Anderson County and I-64 in Franklin County. | BLUEGRASS ADD | North | 43.0062 | 3.6677 | 8.1692 | 8.5385 | 4.0615 | 6.8308 | 3.1231 | 8.6154 | 43
Legacy SYP | 7 | Gateway ADD | IP20080463 | 7-250.01 |  | A | RECONSTRUCTION OF US 460 FROM KY 599 AT JEFFERSONVILLE TO KY 713 AT MEANS. (00CCR)(2004BOPC) | RECONSTRUCTION(O) | Montgomery | 087-US-0460 -000 | 19.6 | 22.067 | 2.467 | Modernize Roadway-Rural | 26 |  |  |  | 2980000 | 2023 | 29040000 | 2023 | 4290000 | 2023 | 33300000 | 2023 | 2017-05-17 09:29 | The purpose of this project is to improve: safety and sight-distance. | The following needs have been identified for this project: 1) Improve Roadway Safety, and 2) Improve Sight-Distance from Rocky Branch onto US 460. | GATEWAY ADD | North | 38.7962 | 3.9077 | 5.1692 | 7.4423 | 4.1538 | 6.5538 | 2.1231 | 9.4462 | 39
Legacy SYP | 7 | Gateway ADD | IP20150067 | 7-8953 |  | A | RECONSTRUCT US 60 FOR SAFETY IMPROVEMENTS FROM 500 FEET WEST OF SEWELL SHOP ROAD (MP 17.032) IN CLARK COUNTY TO 500 FEET WEST OF BENTBROOK (MP 2.007) IN MONTGOMERY COUNTY.(16CCN) | RECONSTRUCTION(O) | Montgomery | 087-US-0060 -000 | 0 | 2.007 | 2.007 | Modernize Roadway-Rural | 26 |  |  |  | 1560000 | 2022 | 2500000 | 2023 | 2500000 | 2023 | 8250000 | 2023 | 2018-07-10 08:18 | The purpose of this project is to improve safety and congestion. | The following needs have been identified for this project: 1) Improve Roadway Safety; and 2) Improve Roadway Congestion. | 7 | North | 31.2938 | 4.3631 | 7.2923 | 4.1308 | 2.1538 | 6.5846 | 0 | 6.7692 | 31
Legacy SYP | 7 | Bluegrass ADD | IP20150179 | 7-416 |  | A | IMPROVE SAFETY ON US 68 AT KY 127 INTERSECTION IN HARRODSBURG. (12CCR)(14CCR)(16CCR) | SAFETY(P) | Mercer | 084-US-0068 -000 | 6.752 | 6.852 | 0.1 | Improve Intersection | 26 |  |  |  | 500000 | 2016 | 1050000 | 2017 | 1040000 | 2017 | 1090000 | 2018 | 2017-05-17 14:24 | Improve safety on US 68 at US 127 intersection in Harrodsburg. | The following needs have been identified on this project: 1) Improve Safety. | BLUEGRASS ADD | North | 30.3892 | 7.3969 | 9.3231 | 5.1923 | 0 | 0 | 4.2923 | 4.1846 | 30
Legacy SYP | 7 | Bluegrass ADD | IP20150188 | 7-417 |  | A | IMPROVE SYSTEM MOBILITY ALONG MOBERLY ROAD FROM KY 390 TO KY 1989 IN NORTHWEST HARRODSBURG. (12CCR) | SPOT IMPROVEMENTS(O) | Mercer | 084-CS-1237 -000 | 0 | 0.341 | 0.341 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 211876 | 2016 | 2850000 | 2016 | 1313617 | 2017 | 2017-05-19 08:58 | Improve mobility along Moberly Rd. from KY 390 to KY 1989 in Northwest Harrodsburg. | The following needs have been identified on this project: 1) Improve Roadway Mobility, 2) Improve Safety. | 7 | North | 46.2777 | 3.7354 | 8.0769 | 4.4654 | 0 | 0 | 0 | 0 | 16 | 15 | 15
Legacy SYP | 7 | Bluegrass ADD | IP20150219 | 7-8707 |  | A | EXTEND FIFTH STREET IN MILLERSBURG TO THE MILLERSBURG BYPASS.(12CCN) (16CCR) | NEW ROUTE(O) | Bourbon | 009-CS-2016 -000 | 0 | 0.07 | 0.07 | Construct Road in New Location | 0 |  |  |  | 160000 | 2016 | 350000 | 2017 | 120000 | 2017 | 1060000 | 2017 | 2017-05-17 15:33 | Improve mobility to the Millersburg Bypass from Fifth St. in Millersburg. | The following needs have been identified on this project: 1) Improve Mobility and Roadway Access. | 7 | North | 11.3323 | 0.024615 | 0 | 1.9385 | 3.9846 | 5.3846 | 0 | 0 | 11
Legacy SYP | 7 | Bluegrass ADD | IP20150225 | 7-916 |  | A | ADDRESS SAFETY AND CONGESTION AT THE INTERSECTION OF US 27 AND KY 1939 IN PARIS | SAFETY(P) | Bourbon | 009-US-0027 -000 | 6.573 | 6.673 | 0.1 | Improve Intersection | 26 | Y |  |  | 250000 | 2023 | 390000 | 2023 | 370000 | 2023 | 610000 | 2023 | 2017-05-17 14:46 | Reduce congestion and improve safety at the intersection of US 27 and KY 1939 in Paris. | The following needs have been identified on this project: 1) Reduce Congestion, 2) Improve Safety. | 7 | North | 32.4015 | 4.6708 | 12.1385 | 8.1923 | 0 | 0 | 3.6462 | 3.7538 | 32
Legacy SYP | 7 | Bluegrass ADD | IP20150237 | 7-345 |  | A | NORTHWEST VERSAILLES MOBILITY CORRIDOR. (06CCR)(10CCN)(12CCN) | NEW ROUTE(O) | Woodford | 120-US-0062 -000 | 1.5 | 7.048 | 5.548 | Construct Road in New Location | 0 |  | 0 |  | 2000000 | 2014 | 2600000 | 2016 | 10060000 | 2016 | 16440000 | 2017 | 2017-05-17 11:59 | Improve mobility and reduce congestion at NW Versailles mobility corridor. | The following needs have been identified on this project: 1) Improve Mobility, 2) Reduce Congestion. | BLUEGRASS ADD | North | 28.4731 | 2.9538 | 3.2769 | 11.6885 | 4.0923 | 6.4615 | 0 | 0 | 28
Legacy SYP | 7 | Lexington MPO | IP20150247 | 7-415 |  | A | IMPROVE ROADWAY TYPICAL SECTION AND PAVEMENT ON KY 2335 (WARE RD) FROM KY 57 (BRIAR HILL RD) TO NORTHERN ENTRANCE TO LEXINGTON BLUEGRASS ARMY DEPOT. (NOTE: DISTRICT IS ANTICIPATING EXPANSION OF LOCKHEED MARTIN FACILITY AT BLUEGRASS STATION)(12CCR)(16CCR) | SAFETY(P) | Fayette | 034-KY-2335 -000 | 0 | 2.1 | 2.1 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2016 | 4000000 | 2017 | 1000000 | 2017 | 5570000 | 2018 | 2017-05-17 14:14 | Modernize roadway on KY 2335 (WARE RD) FROM KY 57 (BRIAR HILL RD) TO NORTHERN ENTRANCE TO LEXINGTON BLUEGRASS ARMY DEPOT. (NOTE: DISTRICT IS ANTICIPATING EXPANSION OF LOCKHEED MARTIN FACILITY AT BLUEGRASS STATION)(12CCR) | The following needs have been identified on this project: 1) Modernize Roadway. | 7 | North | 16.8696 | 0.49846 | 3.1385 | 2.4577 | 4.4 | 0 | 0 | 6.375 | 17
Legacy SYP | 7 | Bluegrass ADD | IP20150270 | 7-8506.01 |  | A | RECONSTRUCT I-64/MOUNTAIN PARKWAY INTERCHANGE TO ADD NEW RAMPS TO AND FROM THE EAST.(12CCR)(14CCR)(16CCR) | MAJOR WIDENING(O) | Clark | 025-I -0064 -000 | 95.1 | 97.675 | 2.575 | Innovative Interchange | 40 | Y | 0 |  | 0 |  | 1890000 | 2018 | 940000 | 2018 | 12440000 | 2019 | 2017-05-22 13:42 | Improve mobility on I-64/Mountain Pkwy. interchange. | The following needs have been identified for this project: 1) Improve Roadway Mobility. | BLUEGRASS ADD | Statewide | 53.9131 | 13.1806 | 9.3392 | 8.2434 | 1.8062 | 0 | 9.6476 | 11.6961
Legacy SYP | 7 | Bluegrass ADD | IP20150279 | 7-8306 | 401769 | A | WIDEN/IMPROVE SHOULDERS ON KY-620. (06CCN) (08CCR) | MAJOR WIDENING(O) | Scott | 105-KY-0620 -000 | 11.26 | 12.63 | 1.37 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 620000 | 2023 | 450000 | 2023 | 2810000 | 2016 | 2017-05-17 14:52 | Improve safety and mobility on KY-620 between US 25 and approximately MP 12.65. | The following needs have been identified on this project: 1) Improve Safety, 2) Improve Mobility. | BLUEGRASS ADD | North | 14.8162 | 0.41231 | 3.3692 | 1.0962 | 4.5846 | 5.3538 | 0 | 0 | 15
Legacy SYP | 7 | Gateway ADD | IP20150295 | 7-8818 |  | A | WIDEN EXISTING BYPASS FROM 2 LANES TO 4 LANES FROM US 460 TO US 60. IMPROVE CAPACITY AND SAFETY IMPROVEMENTS ALONG KY-713 INTERSECTION. ADD TURNING LANES WHERE APPROPRIATE. INCLUDE MULTI-USE TRAILWAY ALONG ROUTE. (14CCN) | MAJOR WIDENING(O) | Montgomery | 087-KY-0686 -000 | 3.506 | 6.333 | 2.827 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 840000 | 2016 | 100000 | 2023 | 200000 | 2023 | 8000000 | 2023 | 2018-07-10 08:18 | The purpose of this project is to: widen the roadway, improve safety, improve capacity, and include multi-use trailway. | The following needs have been identified for this project: 1) Improve Roadway Safety at KY713 Intersection; 2) Widen Existing Roadway from 2 Lanes to 4 Lanes; 3) Add Turning Lanes Where Appropriate; 4) Include Multi-Use Trailway Along Route; and 5) Impro | GATEWAY ADD | North | 45.3723 | 3.7723 | 13.8462 | 9.3231 | 0 | 7.8769 | 2.8 | 7.7538 | 45
Legacy SYP | 7 | Bluegrass ADD | IP20150308 | 7-8302 |  | A | WIDEN KY-89 WINCHESTER-IRVINE ROAD: SECTION EIGHT FROM MILEPOST 12.45 TO MILEPOST 14.32. (06CCN)(12CCR)(16CCR) | MAJOR WIDENING(O) | Clark | 025-KY-0089 -000 | 12.45 | 14.32 | 1.87 | Modernize Roadway-Rural | 26 | [5 empty] | 1960000 | 2016 | 2230000 | 2016 | 5120000 | 2018 | 2017-05-17 14:48 | Improve mobility on KY-89, Winchester-Irvine Rd. from 0.2 miles East of Veterans Memorial Pkwy (MP 12.45) to MP 14.32. | The following needs have been identified for this project: 1) Improve Roadway Mobility. | BLUEGRASS ADD | North | 35.2577 | 2.4308 | 7.9846 | 4.95 | 2.4154 | 6.0923 | 2.3077 | 9.0769 | 35
Legacy SYP | 7 | Bluegrass ADD | IP20150336 | 7-196.20 |  | A | CONSTRUCT WEST LANCASTER BYPASS. (2006BOPC) | RELOCATION(O) | Garrard | 040-US-0027 -000 | 0 | 1 | 1 | Construct Road in New Location | 0 | Y |  |  |  |  | 12850000 | 2023 | 8330000 | 2023 | 31640000 | 2023 | 2019-03-04 08:09 | Improve mobility in Lancaster. | The following needs have been identified on this project: 1) Improve Mobility. | BLUEGRASS ADD | North | 23.3554 | 5.9323 | 0 | 3.0692 | 1.4615 | 9.3538 | 3.5385 | 0 | 23
Legacy SYP | 7 | Lexington MPO | IP20150343 | 7-8404 |  | A | CONSTRUCT A NEW 4 LANE CONNECTOR BETWEEN US-27 AND I-75. (08CCN)(12CCR)(16CCR) | NEW ROUTE(O) | Jessamine | 057-KY-0169 -000 | 0 | 10.458 | 10.458 | Construct Road in New Location | 0 |  | 0 |  | 15000000 | 2017 | 15000000 | 2019 | 15000000 | 2020 | 99999999 | 2023 | 2018-07-10 08:18 | Improve mobility and connectivity between US-27 and I-75. | The following needs have been identified on this project: 1) Improve Mobility, 2) Reduce Congestion. | 7 | North | 28.0562 | 1.8215 | 2.7692 | 13.0962 | 4.6462 | 5.7231 | 0 | 0 | 28
Legacy SYP | 7 | Lexington MPO | IP20150344 | 7-87.30 |  | A | EAST NICHOLASVILLE BYPASS SECTION IB FROM 125 FEET NORTH OF KY 169 TO END OF PROJECT AT TIE-IN TO WEST BYPASS. THIS INCLUDES THE INTERCHANGE AT US 27 NORTH OF NICHOLASVILLE. (14CCR) | NEW ROUTE(O) | Jessamine | 057-US-0027X -000 | 2.4 | 3.8 | 1.4 | Construct Road in New Location | 0 | [9 empty] | 38000000 | 2017 |  | Improve mobility and safety on East Nicholasville Bypass section IB from approximately 125 ft. N. of KY 169 to end of project at tie-in to W. Bypass, including the interchange at US-27 N. of Nicholasville. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Safety. | 7 | North | 66.72 | 7.0277 | 2.8615 | 13.2462 | 0 | 9.5077 | 4.0769 | 0 | 37 | 15 | 15
Legacy SYP | 7 | Gateway ADD | IP20150353 | 7-8817 |  | A | WIDEN EXISTING PAVEMENT AND IMPROVE VERTICAL AND HORIZONTAL CURVES FROM BOTTOM OF HILL TO US 460 IN JEFFERSONVILLE. ADD FULL-WIDTH SHOULDERS TO IMPROVE SAFETY. (14CCN) | MAJOR WIDENING(O) | Montgomery | 087-KY-0213 -000 | 0 | 2.894 | 2.894 | Modernize Roadway-Rural | 26 |  |  |  | 1000000 | 2016 | 2500000 | 2023 | 3000000 | 2023 | 6000000 | 2023 | 2018-07-10 08:18 | The purpose of this project is to: improve safety, improve geometrics, and widen the exiting pavement. | The following needs have been identified for this project: 1) Improve Roadway Safety; 2) Improve Vertical and Horizontal Curves; and 3) Add Full-Width Shoulders. | 7 | North | 38.1431 | 1.7969 | 10.3385 | 8.1462 | 2.4462 | 5.8462 | 0 | 9.5692 | 38
Legacy SYP | 7 | Gateway ADD | IP20150404 | 7-8819 |  | A | WIDEN TO SIX LANES FROM MP 107.5 TO MP 113.7. (14CCN) | MAJOR WIDENING(O) | Montgomery | 087-I -0064 -000 | 107.5 | 113.7 | 6.2 | Add Lane to Full Control Facility | 25 | Y |  |  | 4000000 | 2016 | 250000 | 2023 | 500000 | 2023 | 69750000 | 2023 | 2018-07-10 08:18 | The purpose of this project is to improve capacity and congestion. | The following needs have been identified for this project: 1) improve capacity; 2) improve congestion; 3) heavy freight traffic and project traffic volumes are projected to double over the next 20 years; and 4) the only major east-west interstate connect | 7 | Statewide | 51.2854 | 10.1498 | 6.5198 | 9.3007 | 1.8062 | 2.1586 | 8.6784 | 12.6719
Legacy SYP | 7 | Lexington MPO | IP20150433 | 7-122.10 |  | A | RECONSTRUCT/WIDEN US-25 FROM SPURR ROAD SOUTH OF I-75 TO 1400 FEET SOUTH OF IRONWORKS ROAD. (06CCN)(08CCR)(10CCR)(12CCR)(16CCR) | MAJOR WIDENING(O) | Fayette | 034-US-0025 -000 | 18.264 | 21.415 | 3.151 | 2 Lane to 4 Lane Divided - Rural | 36 | [5 empty] | 14790000 | 2016 | 4120000 | 2016 | 21680000 | 2018 | 2017-05-17 09:11 | Improve mobility and safety, reduce congestion and improve roadway geometrics on US-25 from Spurr Rd. South of I-75 to approximately 1400 ft. South of Ironworks Rd. | The following needs have been identified on this project: 1) Improve Mobility, 2) Improve Safety, 3) Reduce Congestion, 4) Improve Roadway Geometrics. | 7 | North | 84.9669 | 9.3477 | 11.8615 | 9.45 | 1.5231 | 9.5077 | 3.5538 | 9.7231 | 55 | 15 | 15
Legacy SYP | 7 | Bluegrass ADD | IP20160228 | 7-8904 |  | A | RECONSTRUCT KY 33 FROM 100 FEET NORTH OF KY 1267 TO 100 FEET NORTH OF KY 169. (MP 3.04 TO MP 10.65) (16CCN) | RECONSTRUCTION(O) | Woodford | 120-KY-0033 -000 | 3.04 | 10.65 | 7.61 | Modernize Roadway-Rural | 26 |  |  |  | 3000000 | 2018 | 9160000 | 2019 | 6930000 | 2020 | 26330000 | 2021 | 2017-05-18 09:50 | Improve safety and mobility on KY 33 from approximately 100 ft. North of KY 1267 to 100 ft. North of KY 169. | The following needs have been identified for this project: 1) Improve Safety, 2) Improve Mobility. | BLUEGRASS ADD | North | 40.7262 | 1.2185 | 8.6769 | 10.7538 | 4.5385 | 5.6 | 0 | 9.9385 | 41
Legacy SYP | 7 | Lexington MPO | IP20160267 | 7-8901 |  | A | EXTEND CITATION BLVD. (16CCN) | NEW ROUTE(O) | Fayette | 034-KY-1878 -010 | 0.399 | 3.739 | 3.34 | Construct Road in New Location | 0 |  |  |  | 840000 | 2017 | 2320000 | 2018 | 1130000 | 2019 | 5850000 | 2020 | 2017-05-17 15:54 | Improve mobility on Citation Blvd. to Russell Cave Rd. | The following needs have been identified on this project: 1) Improve Mobility. | Lexington MPO | North | 19.0662 | 3.7969 | 0 | 5.4692 | 1.5231 | 8.2769 | 0 | 0 | 19
Legacy SYP | 7 | Bluegrass ADD | IP20160268 | 7-8903 |  | A | STUDY IMPROVEMENTS TO TRAFFIC FLOW ISSUES IN DOWNTOWN VERSAILLES. (16CCN) | SCOPING STUDY DD (O) | Woodford | 120-US-0060 -000 | 7.562 | 10.151 | 2.589 | Transportation Studies | 0 | Y |  |  | 110000 | 2017 | [6 empty] | 2017-05-18 09:47 | STUDY IMPROVEMENTS TO TRAFFIC FLOW ISSUES IN DOWNTOWN VERSAILLES. | The following needs have been identified for this project: 1) Improve Mobility, 2) Reduce Congestion. | 7 | North | 26.0692 | 6.4615 | 0 | 11.8385 | 3.4923 | 0 | 4.2769 | 0 | 26
Legacy SYP | 7 | Bluegrass ADD | IP20170063 | 7-8908 |  | A | EXTEND FALLING SPRINGS BLVD FROM TYRONE PIKE (US-62) TO CLIFTON ROAD (KY-1964). (16CCN) | NEW ROUTE(O) | Woodford | 120-US-0062 -000 | 5.318 | 6.594 | 1.276 | Construct Road in New Location | 0 |  |  |  | 940000 | 2019 | 3190000 | 2020 | 4790000 | 2021 | 8830000 | 2022 | 2017-05-18 10:35 | Improve mobility on Falling Springs Blvd. from Tyrone Pike (US-62) to Clifton Rd. (KY-1964). | The following needs have been identified on this project: 1) Improve Mobility. | 7 | North | 26.1508 | 2.9046 | 2.9538 | 7.3385 | 3.8769 | 6.8 | 2.2769 | 0 | 26
Legacy SYP | 7 | Bluegrass ADD | IP20190153 | 7-8632 |  | A | DESIGN ENGINEERING FOR 7TH STREET RELOCATION. (10CCN) | DESIGN ENGINEERING(O) | Clark | 025-CS-1225 -000 | 0 | 0.161 | 0.161 | 2 Lane to 4 Lane Divided - Rural | 36 |  |  |  | 0 |  | 320000 | 2023 | 780000 | 2023 | 2810000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to: - Improve Safety - Improve Mobility - Improve Connectivity to KY-627/I-64 | Truck routes from two facilities in Winchester currently cut through residential neighborhoods to reach KY-627, an I-64 connector. This truck traffic damages residential roadways as well as creates an unsafe area for children and pedestrians in the neighb
Legacy SYP | 8 | Lake Cumberland ADD | IP20150146 | 8-8705 |  | A | REALIGN KY 501 TO INTERSECT KY 70 EAST OF EXISTING LOCATION AND CORRECT VERTICAL ALIGNMENT OF KY 70 NEAR EXISTING INTERSECTION.(12CCN) | RECONSTRUCTION(O) | Casey | 023-KY-0501 -000 | 11 | 11.18 | 0.18 | Realign Intersection | 26 |  |  |  | 520000 | 2016 | 80000 | 2018 | 250000 | 2018 | 900000 | 2019 | 2016-05-24 07:22 | This project is needed because the geometrics at the intersection of KY 501 and KY 70 are inadequate and causes safety issues. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 6.3791 | 0.45498 | 2.1327 | 0 | 3.7915 | 0 | 0 | 0 | 6
Legacy SYP | 8 | Lake Cumberland ADD | IP20150181 | 8-8702 |  | A | CORRECT VERTICAL ALIGNMENT ON US 127 AND KY 1552 NEAR INTERSECTION.(12CCN) | RECONSTRUCTION(O) | Casey | 023-US-0127 -000 | 18.746 | 19.046 | 0.3 | Realign Intersection | 26 | Y |  |  | 780000 | 2016 | 530000 | 2018 | 260000 | 2018 | 750000 | 2023 | 2018-07-10 08:18 | This project is needed because the geometrics along US 127 and KY 1552 near the intersection is inadequate and causes safety issues. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 41.5545 | 5.4882 | 6.2559 | 5.6161 | 1.9668 | 0 | 3.5308 | 3.6967 | 27 | 15
Legacy SYP | 8 | Bluegrass ADD | IP20150200 | 7-196.10 |  | A | RECONSTRUCT US 27 FROM US 150 BYPASS IN LINCOLN COUNTY TO WEST LANCASTER BYPASS IN GARRARD COUNTY. (2006BOPC) | RELOCATION(O) | Lincoln | 069-US-0027 -000 | 0 | 0.444 | 0.444 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  |  |  | 20670000 | 2023 | 7730000 | 2023 | 38600000 | 2023 | 2019-03-04 08:12 | RECONSTRUCT US 27 FROM US 150 BYPASS IN LINCOLN COUNTY TO WEST LANCASTER BYPASS IN GARRARD COUNTY. (2006BOPC) | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and Increase Capacity for all vehicle types. | BLUEGRASS ADD | North | 25.1423 | 3.3846 | 2.6769 | 1.5577 | 1.4308 | 8.3385 | 2.4 | 5.3538 | 25
Legacy SYP | 8 | Lake Cumberland ADD | IP20150202 | 8-121 |  | A | HORIZONTAL AND VERTICAL REALIGNMENT OF KY-196 AT WHITE OAK CREEK FROM 1.0 MILE E OF WARNER ROAD TO 0.3 MILE W OF SIEVERS ROAD.(10CCR)(14CCR) | SAFETY(P) | Pulaski | 100-KY-0196 -000 | 7.7 | 8.2 | 0.5 | Modernize Roadway-Rural | 26 | [5 empty] | 70000 | 2016 | 180000 | 2016 | 1410000 | 2017 | 2016-05-24 07:22 | This project is needed because the geometrics along KY 196 at White Oak Creek from 1.0 Mile E of Warner Road to 0.3 Mile W of Sievers Road are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 40.2334 | 1.2701 | 14.218 | 6.4514 | 3.2938 | 0 | 0 | 0 | 25 | 15
Legacy SYP | 8 | Lake Cumberland ADD | IP20150214 | 8-8701 |  | A | NEW ALIGNMENT FROM MP 16.8 TO MP 17.4 (12CCN) | RECONSTRUCTION(O) | Casey | 023-KY-0070 -000 | 16.8 | 17.4 | 0.6 | Modernize Roadway-Rural | 26 |  |  |  | 780000 | 2016 | 480000 | 2018 | 500000 | 2018 | 3500000 | 2023 | 2018-07-10 08:18 | This project is needed because the geometrics along US 127 and KY 1552 near the intersection are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | 8 | South | 24.8855 | 1.1374 | 6.8246 | 1.5995 | 4.455 | 4.9289 | 0 | 5.94 | 25
Legacy SYP | 8 | Lake Cumberland ADD | IP20150254 | 8-164 |  | A | RECONSTRUCT CURVE ON US-127 AT DUNNVILLE. (02CCR)(04CCR) (10CCR)(12CCR) | RECONSTRUCTION(O) | Casey | 023-US-0127 -000 | 1.9 | 4.2 | 2.3 | Modernize Roadway-Rural | 26 | Y |  |  |  |  | 1540000 | 2023 | 850000 | 2023 | 7610000 | 2023 | 2016-05-24 07:22 | This project is needed because the geometrics along US 127 at Dunnville is inadequate and causes safety issues. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | 8 | South | 70.2536 | 4.7204 | 7.8199 | 7.5711 | 3.1991 | 6.8246 | 3.6256 | 6.4929 | 40 | 15 | 15
Legacy SYP | 8 | Lake Cumberland ADD | IP20150264 | 8-394 |  | A | RAISE GRADE TO PREVENT FLOODING FROM 0.5 MI EAST OF VALLEY VIEW DRIVE TO 0.7 MI W OF KY 1258. (12CCR)(14CCR) | RECONSTRUCTION(O) | Wayne | 116-KY-0092 -000 | 10.62 | 13.1 | 2.48 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1660000 | 2016 | 2170000 | 2016 | 9000000 | 2018 | 2016-05-24 07:22 | This project is needed because the geometrics along KY 92 between 0.5 miles east of Valley View Drive and 0.7 miles west of KY 1258 are inadequate and causes safety issues and reduced mobility on this stretch of highway. | The following needs have been identified for this project: 1.) Improve roadway safety 2.) Improve mobility | LAKE CUMBERLAND ADD | South | 31.7938 | 2.3033 | 6.6114 | 7.4289 | 3.128 | 6.1137 | 0 | 6.2085 | 32
Legacy SYP | 8 | Lake Cumberland ADD | IP20150373 | 8-59.50 / 8-59.52 / 8-59.60 / 8-59.61 |  | A | SOMERSET NORTHERN BYPASS (HAL ROGERS PKWY) SECTION 4; "GRADE AND DRAIN" FROM EAST OF THE KY-39 I-CHNG, E TO KY-80 EAST OF SOMERSET (INCLUDES I-CHNG AT KY-80). (CONST SEQ 4) (2002BOP)(05KYD) | NEW ROUTE(O) | Pulaski | 100-KY-0080 -000 | 18 | 27.6 | 9.6 | Construct Road in New Location | 0 | Y | [8 empty] | 126910000 | 2023 | 2016-05-24 07:22 |  |  | 8 | Statewide | 22.6068 | 6.2907 | 0 | 9.2676 | 1.8062 | 0 | 5.2423 | 0
Legacy SYP | 8 | Lake Cumberland ADD | IP20150388 | 8-8600 |  | A | RELOCATE US 127 FROM KY 90 TO EXISTING US-127 NORTH OF KY-90 APPROX. 0.18 MILES EAST OF THE INTERSECTION OF AARON RIDGE ROAD. (10CCN)(12CCR) | RELOCATION(O) | Clinton | 027-US-0127 -000 | 11.049 | 16.135 | 5.086 | Construct Road in New Location | 0 | Y |  |  | 3120000 | 2023 | 5520000 | 2023 | 3250000 | 2023 | 39670000 | 2023 | 2016-05-24 07:22 | This project is needed because the capacity of KY 90 to Existing US 127 North of KY 90 approximately 0.18 miles East of the intersection of Aaron Ridge Road is inadequate to meet current and future traffic volumes, resulting in congestion, safety issues a | The following needs have been identified for this project: 1.) Improve capacity and reduce congestion 2.) Improve roadway safety 3.) Improve mobility | 8 | South | 35.1825 | 1.3555 | 0 | 7.2867 | 4.2417 | 4.6445 | 2.654 | 0 | 20 | 15
Legacy SYP | 8 | Cumberland Valley ADD | IP20150397 | 8-5009 |  | A | LANDSLIDE REPAIR ON KY-1329 FROM LOWER RIVER ROAD NEAR THE LAUREL COUNTY LINE, NORTHEAST TO JCT. US-25. (2002BOPC) | LANDSLIDE REPAIR(P) | Rockcastle | 102-KY-1329 -000 | 0 | 5.599 | 5.599 | Maintenance Improvement | 10 | [5 empty] | 60000 | 2014 | 60000 | 2014 | 870000 | 2015 | 2014-05-29 08:11 | The purpose of this project is to improve landslide repair. | The following needs have been identified for this project: 1) Improve Roadway Safety | 8 | South | 5.6327 | 0.12322 | 0 | 1.0308 | 4.4787 | 0 | 0 | 0 | 6
Legacy SYP | 8 | Lake Cumberland ADD | IP20150428 | 8-146 |  | A | SCOPING STUDY FOR EASTERN COLUMBIA BYPASS. | SCOPING STUDY(O) | Adair | 001-KY-0055X -000 | 0 | 3.025 | 3.025 | Transportation Studies | 0 |  | 210000 | 2023 | [9 empty] | The project is needed to determine if there is adequate need for an eastern portion of the Columbia Bypass. | The following needs have been identified for this project: 1.) Determine if adequate need is there for the eastern portion of the Columbia bypass. 2.) Determine path of eastern portion of the Columbia bypass. | LAKE CUMBERLAND ADD | South | 19.4941 | 8.1137 | 0 | 3.9633 | 3.2464 | 0 | 4.1706 | 0 | 20
Legacy SYP | 8 | Lake Cumberland ADD | IP20160203 | 8-8901 / 8-8902 / 8-8903 |  | A | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS ROCKCASTLE RIVER BRIDGE AND APPROACHES. (SEGMENT 3)(16CCN) | RECONSTRUCTION(O) | Pulaski | 100-KY-0080 -000 | 21.175 | 39.571 | 18.396 | Arterial to Full Control | 36 | Y |  |  | 39500000 | 2017 | 45000000 | 2018 | 46800000 | 2019 | 199800000 | 2020 | 2016-05-24 07:21 |  |  | 8 | Statewide | 55.933 | 6.1322 | 7.7533 | 10.9526 | 1.8062 | 9.0308 | 5.5507 | 14.7072
Legacy SYP | 9 | Buffalo Trace ADD | IP20080547 | 9-8808 |  | A | RECONSTRUCT INTERSECTION AT KY-9 AND KY-2523. (14CCN) | RECONSTRUCTION(O) | Lewis | 068-KY-0009 -000 | 12.709 | 12.789 | 0.08 | Improve Intersection | 26 | Y | 0 |  | 0 |  | 210000 | 2016 | 130000 | 2016 | 1040000 | 2017 | 2017-04-26 11:08 | To improve safety and mobility | This project is along the very busy AA (KY9) highway in Lewis County which has a high volume of trucks. The intersection of KY 2523 (Maintenance Drive) with the AA provides access to 3 schools (Middle/High/& Tech School), all high school athletic facilit | BUFFALO TRACE ADD | East | 21.2066 | 7.5689 | 4.7605 | 1.5719 | 0.41916 | 0 | 4.3713 | 2.515 | 21
Legacy SYP | 9 | Buffalo Trace ADD | IP20080553 | 9-8907 |  | A | WIDEN KY 9/AA HIGHWAY TO 4 LANES FROM KY 435 TO KY 2370 IN BRACKEN CO. (16CCN) | MAJOR WIDENING(O) | Mason | 081-KY-0009 -000 | 17.343 | 19.541 | 2.198 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 4160000 | 2017 | 3650000 | 2018 | 5850000 | 2019 | 56940000 | 2020 | 2017-04-28 08:22 | To improve mobility. | Existing KY 9 will not provide adequate capacity for projected design year 2025 traffic volumes, the number of vehicle crashes at intersections is relatively high, existing roadway geometry restricts sight distance in numerous locations and speed dif | BUFFALO TRACE ADD | East | 55.1737 | 8.4671 | 4.4012 | 5.6587 | 0.41916 | 8.6826 | 4.2216 | 8.3234 | 40 |  | 15
Legacy SYP | 9 | Buffalo Trace ADD | IP20110024 | 9-8909 |  | A | IMPROVE SAFETY BY ADDING LEFT AND RIGHT TURN LANES FOR EXIT ALONG KY 11. (16CCN) | SAFETY(P) | Mason | 081-KY-0011 -000 | 1.4 | 2.2 | 0.8 | Improve Intersection | 26 |  |  |  | 550000 | 2017 | 560000 | 2018 | 440000 | 2019 | 4680000 | 2020 | 2017-04-28 08:58 | To improve safety and mobility. | The intersection of KY 11 and KY 597 has been a location of several rear end collisions and daily near misses as vehicles traveling south on KY 11 stop in the lane to make the left turn and cars will pass on the shoulder which is confined with gurardrail. | 9 | East | 35.6512 | 8.024 | 11.0479 | 7.2081 | 0 | 0 | 4.1617 | 5.2096 | 36
Legacy SYP | 9 | Buffalo Trace ADD | IP20110100 | 9-8901 |  | A | CONSTRUCT LEFT TURN LANES ON KY 11 AT ROSS DRIVE, TAYLOR MILL AND THE INDUSTRIAL PARK ROAD. (16CCN) | SAFETY(P) | Fleming | 035-KY-0011 -000 | 13.038 | 13.6 | 0.562 | Improve Intersection | 26 |  |  |  | 250000 | 2017 | 450000 | 2018 | 380000 | 2019 | 850000 | 2020 | 2017-04-26 10:42 | To improve safety | Minimize congestion, reduce delays and potential rear end collisions, increase efficiency by constructing a 14' wide TWLTL and right turn lanes to the approach roads. Stripe the shoulders for right turn lanes into the businesses. Utilize a curb and gu | 9 | East | 38.7695 | 8.515 | 13.024 | 8.0389 | 0 | 0 | 4.2814 | 4.9102 | 39
Legacy SYP | 9 | Buffalo Trace ADD | IP20150145 | 9-8809 |  | A | ADDITION OF AN INTERCHANGE ON HEATHER FRENCH HENRY SOUTHERN LOOP (US 62 AND US 68). (14CCN)(16CCR) | NEW INTERCHANGE(O) | Mason | 081-US-0068 -000 | 11.75 | 11.9 | 0.15 | Grade Separated to Interchange | 0 | Y |  |  | 750000 | 2018 | 750000 | 2019 | 500000 | 2019 | 750000 | 2020 | 2017-05-31 10:57 | To improve safety and mobility | With the interchange emergency vehicles would have a straight shot to the hospital allowing for less travel time and intersection disruptions. | BUFFALO TRACE ADD | East | 22.7425 | 2.0838 | 3.0539 | 4.2216 | 0.41916 | 6.7066 | 3.3832 | 2.8743 | 23
Legacy SYP | 9 | Gateway ADD | IP20150203 | 9-193 |  | A | RECONSTRUCT KY-111 IN THE VICINITY OF THE "S-CURVE" EAST OF OWINGSVILLE.(14CCR) | RECONSTRUCTION(O) | Bath | 006-KY-0111 -000 | 1 | 1.5 | 0.5 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1580000 | 2016 | 1040000 | 2016 | 3640000 | 2018 | 2017-04-26 08:03 |  |  | GATEWAY ADD | East | 38.3159 | 1.4371 | 2.9641 | 1.9985 | 4.7605 | 6.3473 | 0 | 5.8084 | 23 |  | 15
Legacy SYP | 9 | Gateway ADD | IP20150223 | 9-8404 |  | A | RECONSTRUCT CURVE AT .8 MILE SOUTH OF KY-36. (08CCN)(12CCR) | RECONSTRUCTION(O) | Bath | 006-KY-0965 -000 | 7.147 | 7.247 | 0.1 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 154000 |  | 0 | 2016 | 1460000 | 2016 | 2018-03-20 13:05 |  |  | 9 | East | 23.2485 | 3.5329 | 5.2994 | 4.3563 | 2.9341 | 7.1257 | 0 | 0 | 23
Legacy SYP | 9 | Buffalo Trace ADD | IP20150405 | 9-8815 |  | A | UPGRADE, WIDEN, AND PROVIDE SPOT IMPROVEMENTS ON KY-165 TO IMPROVE SAFETY FROM KY-32 TO US-68. (14CCN) | MINOR WIDENING(O) | Fleming | 035-KY-0165 -000 | 0 | 6.243 | 6.243 | Modernize Roadway-Rural | 26 |  |  |  | 900000 | 2017 | 280000 | 2017 | 280000 | 2018 | 5850000 | 2019 | 2017-04-26 10:50 | To improve safety and mobility. | UPGRADE, WIDEN, AND PROVIDE SPOT IMPROVEMENTS ON KY-165 TO IMPROVE SAFETY FROM KY-32 TO US-68. | BUFFALO TRACE ADD | East | 37.753 | 2.491 | 11.8563 | 12.0584 | 2.485 | 0 | 0 | 8.8623 | 38
Legacy SYP | 9 | Buffalo Trace ADD | IP20150410 | 9-8817 |  | A | CORRECT GEOMETRIC AND WIDTH DEFICIENCIES BEGINNING AT SLEEPY RUN BRIDGE EXTENDING TO 0.5 MILES SOUTH OF LEWIS COUNTY LINE TO IMPROVE OPERATIONAL EFFICIENCY, SIGHT DISTANCE RESTRICTIONS AND OVERALL FLOW OF TRAFFIC. (14CCN) | DESIGN ENGINEERING(O) | Fleming | 035-KY-0057 -000 | 2.108 | 8.812 | 6.704 | Modernize Roadway-Rural | 26 |  |  |  | 2000000 | 2016 | 5500000 | 2023 | 4400000 | 2023 | 50000000 | 2023 | 2018-07-10 08:18 | To improve safety and mobility. | IMPROVE OPERATIONAL EFFICIENCY, SIGHT DISTANCE RESTRICTIONS AND OVERALL FLOW OF TRAFFIC. | 9 | East | 62.2051 | 3.5449 | 5.0299 | 8.6901 | 1.8862 | 0 | 3.2335 | 9.8204 | 32 | 15 | 15
Legacy SYP | 9 | Gateway ADD | IP20150436 | 9-301.10 |  | A | NEW ROUTE FROM US-60/KY-32 EAST OF MOREHEAD TO I-64 INCLUDING A NEW INTERCHANGE. (98CCN)(08CCR)(14CCR) | NEW ROUTE(O) | Rowan | 103-KY-0032 -000 | 5.4 | 8.4 | 3 | Construct Road in New Location | 0 |  |  |  | 3120000 | 2016 | 9730000 | 2018 | 3510000 | 2018 | 50620000 |  | 2017-04-28 09:13 |  |  | GATEWAY ADD | East | 42.0359 | 9.8802 | 2.7844 | 14.8204 | 0 | 9.8802 | 4.6707 | 0 | 42
Legacy SYP | 9 | FIVCO ADD | IP20160105 | 9-8312.10 |  | A | SAFETY IMPROVEMENTS TO KY-773 AT KY-7: ADD LEFT-TURN LANE AND IMPROVE SIGHT DISTANCE ON KY-7. (06CCN)(2006BOPC)(08CCR)(10CCR)(12CCR) | SAFETY(P) | Carter | 022-KY-0773 -000 | 0 | 0.1 | 0.1 | Improve Intersection | 26 |  |  |  | 0 |  | 60000 | 2016 | 60000 | 2016 | 550000 | 2017 | 2017-04-26 10:25 |  |  | 9 | East | 29.1946 | 2.6228 | 11.1377 | 10.6437 | 4.7904 | 0 | 0 | 0 | 29
Legacy SYP | 9 | Buffalo Trace ADD | IP20160181 | 9-8903 |  | A | SAFETY IMPROVEMENTS AND PAVEMENT REHAB EAST OF FLEMINGSBURG BYPASS TO KY 156. (16CCN) | SAFETY(P) | Fleming | 035-KY-0032 -000 | 10.165 | 10.615 | 0.45 | Modernize Roadway-Rural | 26 |  |  |  | 0 | 2018 | 1660000 | 2019 | 1630000 | 2020 | 12580000 | 2021 | 2017-04-26 10:46 | To improve safety and mobility | SAFETY IMPROVEMENTS AND PAVEMENT REHAB EAST OF FLEMINGSBURG BYPASS TO KY 156 | BUFFALO TRACE ADD | East | 79.8922 | 7.7365 | 13.2036 | 14.012 | 1.0479 | 0 | 3.9521 | 9.9401 | 50 | 15 | 15
Legacy SYP | 9 | Buffalo Trace ADD | IP20160183 | 9-8908 |  | A | WIDEN THE AA HIGHWAY TO 4 LANES FROM KY 1449 TO KY 11. (16CCN) | MAJOR WIDENING(O) | Mason | 081-KY-0009 -000 | 3.781 | 7.56 | 3.779 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 2600000 | 2017 | 1860000 | 2018 | 3940000 | 2019 | 30370000 | 2020 | 2017-04-28 08:26 | Increase capacity, safety and decrease conflict points from KY 1449 to KY 11. | Widen to 4 lanes to increase safety for motorist on the AA highway and increase operational efficiency | BUFFALO TRACE ADD | East | 70.4566 | 8.5629 | 13.1138 | 10.756 | 0.41916 | 9.0419 | 4.6407 | 8.9222 | 56 |  | 15
Legacy SYP | 10 | Kentucky River ADD | IP20060274 | 10-8851 | 2017-07-28 | I | MINOR WIDENING & RESURFACING OF KY 451 FROM MP 11.3 TO MP 11.65. (14CCN) | MINOR WIDENING(O) | Perry | 097-KY-0451 -000 | 11.3 | 11.65 | 0.35 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-03-12 11:24 |  | This segment runs along the river throughout this 1.900 mile segment. The pavement is in rough condition with potholes, cracking, and clips. There are a coupld of RR Crossings. The segment is a heavily congested residential area. | 10 | East | 18.4117 | 1.4132 | 9.0719 | 5.5913 | 2.3353 | 0 | 0 | 0 | 18
Legacy SYP | 10 | Kentucky River ADD | IP20060282 | 10-8803 | 2017-07-28 | I | RECONSTRUCTION OF KY-715 & KY-2016 INTERSECTION MP 2.548 - MP 2.748. (14CCN) | RECONSTRUCTION(O) | Wolfe | 119-KY-0715 -000 | 0 | 5.765 | 5.765 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-08-07 13:34 | Reconstruction of KY 715 from KY 11 to KY 15. | To replace an existing regional corridor with numerous safety issues and roadway deficiencies. | 10 | East | 7 | 2.5988 | 0 | 2.3353 | 2.0659 | 0 | 0 | 0 | 7
Legacy SYP | 10 | Kentucky River ADD | IP20110119 | 10-162 | 2017-07-28 | I | RECONSTRUCT TO CURRENT STANDARDS THE CURVE FROM THE KY 15 OVERPASS TO 2700 EAST OF KY 15 OVERPASS. (12CCR)(16CCR) | RECONSTRUCTION(O) | Wolfe | 119-KY-9000 -000 | 38 | 38.6 | 0.6 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 0 |  | 0 |  | 0 | 2017 | 2017-08-28 11:29 | The project consists of a 55 mph curve that has a high CRF. The project will increase safety and reduce crashes. | Improve Safety and geometrics of curve along a high speed facility. | 10 | Statewide | 47.1904 | 2.5903 | 11.7181 | 3.3866 | 9.0308 | 7.467 | 4.2291 | 8.7686
Legacy SYP | 10 | Kentucky River ADD | IP20120019 | 10-366 |  | A | RECONSTRUCTION OF KY 11 IN OWSLEY COUNTY BEGINNING AT THE CLAY COUNTY LINE AND EXTENDING 1 MILE NORTH ALONG KY 11 (MP 0 TO MP 1.0). (2014BOP) | RECONSTRUCTION(O) | Owsley | 095-KY-0011 -000 | 0 | 1 | 1 | Construct Road in New Location | 0 |  | 0 |  | 0 |  | 750000 |  | 200000 |  | 15000000 |  | 2015-08-19 15:44 | Reconstruction of one mile of KY 11 beginning at the Clay County line. | To correct roadway structural problems due to the location adjacent to the KY River. Improve connectivity between Clay and Owsley Counties. | KENTUCKY RIVER ADD | East | 26.7919 | 0.34731 | 3.1437 | 5.8159 | 3.9521 | 5.7485 | 0 | 7.7844 | 27
Legacy SYP | 10 | Kentucky River ADD | IP20150206 | 10-8852 | 2017-05-26 | I | CONSTRUCT SIDEWALKS, CURB AND GUTTER ON KY 52 FROM DOWNTOWN BEATTYVILLE TOWARD IRVINE. (14CCN)(AR/W)(16CCR) | SAFETY(P) | Lee | 065-KY-0052 -000 | 11.78 | 12.26 | 0.48 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 0 | 2016 | 2019-01-22 09:56 |  |  | 10 | East | 26.9296 | 1.4132 | 10.8683 | 6.8937 | 1.5269 | 0 | 0 | 6.2275 | 27
Legacy SYP | 10 | Kentucky River ADD | IP20150359 | 10-292.40 |  | A | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM 0.5 MILE SOUTH OF KY-587 TO 0.65 MILE NORTH OF KY-52 IN BEATTYVILLE AND CONSTRUCT BRIDGE OVER KENTUCKY RIVER. | RECONSTRUCTION(O) | Lee | 065-KY-0011 -000 | 1.082 | 4.798 | 3.716 | Modernize Roadway-Rural | 26 | [5 empty] | 11310000 | 2023 | 1560000 | 2023 | 36000000 | 2023 | 2016-05-24 07:22 | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM 0.5 MILE SOUTH OF KY-587 TO 0.65 MILE NORTH OF KY-52 IN BEATTYVILLE AND CONSTRUCT BRIDGE OVER KENTUCKY RIVER. | I-75 TO MOUNTAIN PARKWAY; RECONSTRUCT KY-11 FROM 0.5 MILE SOUTH OF KY-587 TO 0.65 MILE NORTH OF KY-52 IN BEATTYVILLE AND CONSTRUCT BRIDGE OVER KENTUCKY RIVER.
Legacy SYP | 10 | Kentucky River ADD | IP20150364 | 10-8102 |  | A | HILL AND CURVE CORRECTION ON KY-191 BETWEEN HAZEL GREEN AND KY-205. (02CCN)(08CCR)(10CCR) | SAFETY(P) | Wolfe | 119-KY-0191 -000 | 10.256 | 14.298 | 4.042 | Maintenance Improvement | 10 |  |  |  | 0 |  | 320000 | 2016 | 810000 | 2016 | 2040000 | 2017 | 2017-02-21 12:12 | HILL AND CURVE CORRECTION ON KY-191 BETWEEN HAZEL GREEN AND KY-205. (02CCN)(08CCR)(10CCR) | HILL AND CURVE CORRECTION ON KY-191 BETWEEN HAZEL GREEN AND KY-205. (02CCN)(08CCR)(10CCR) | KENTUCKY RIVER ADD | East | 29.274 | 3.0539 | 0 | 8.1961 | 3.024 | 0 | 0 | 0 | 14 | 15
Legacy SYP | 10 | Big Sandy ADD | IP20150392 | 10-169 |  | A | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM US 460 TO THE MAGOFFIN/FLOYD COUNTY LINE. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | MAJOR WIDENING(O) | Magoffin | 077-KY-0114 -000 | 0 | 5.026 | 5.026 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 3000000 | 2017 | 8570000 | 2018 | 2500000 | 2019 | 98000000 | 2021 | 2016-10-20 12:42 |  |  | BIG SANDY ADD | Statewide | 41.2613 | 3.1894 | 5.815 | 5.5011 | 6.1674 | 7.511 | 0.57269 | 12.5046
Legacy SYP | 10 | Gateway ADD | IP20150422 | 10-8402 |  | A | RECONSTRUCT KY-7 FROM MILE POST 2.7 TO MILE POST 5.6 (JUNCTION 519 TO SOUTH SIDE OF WRIGLEY HILL). (08CCN)(12CCR) | RECONSTRUCTION(O) | Morgan | 088-KY-0007 -000 | 2.667 | 5.592 | 2.925 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 2440000 | 2016 | 1630000 | 2016 | 13960000 | 2018 | 2017-05-10 09:06 | The purpose of this project is to: reconstruct the roadway and modernize the roadway. | The following needs have been identified for this project: 1) Reconstruct the Roadway; and 2) Modernize the Roadway. | GATEWAY ADD | East | 47.1018 | 5.2455 | 8.982 | 8.982 | 3.9521 | 7.6048 | 3.2934 | 9.0419 | 47
Legacy SYP | 10 | Kentucky River ADD | IP20150439 | 10-269.20 |  | A | RECONSTRUCTION OF KY 15 FROM BONNYMAN TO NEAR KY 28. (14CCN) | MAJOR WIDENING(O) | Perry | 097-KY-0015 -000 | 16.9 | 21.2 | 4.3 | Modernize Roadway-Rural | 26 | Y |  |  | 1510000 | 2020 | 3040000 | 2020 | 2050000 | 2020 | 60000000 | 2020 | 2015-08-19 15:55 | RECONSTRUCTION OF KY 15 FROM BONNYMAN TO NEAR KY 28. (14CCN) | RECONSTRUCTION OF KY 15 FROM BONNYMAN TO NEAR KY 28. (14CCN)
Legacy SYP | 10 | Bluegrass ADD | IP20190101 | 10-163.10 | 2020-01-15 | A | IMPROVE SAFETY AND UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 213 FROM KY 11 TO KY 615, INCLUDES BRIDGE OVER RED RIVER. (PRIORITY SECTION 1)(R & U FUNDING SEE 10-163.00)(2018BOP) | SAFETY(P) | Powell | 099-KY-0213 -000 | 7.6 | 9.3 | 1.7 | Install Two-way Left Turn Lane | 28 | [5 empty] | 0 | 2018 | 0 | 2019 | 8320000 | 2020 | 2019-03-06 13:13 | IMPROVE SAFETY AND UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 213 FROM KY 11 TO KY 615, INCLUDES BRIDGE OVER RED RIVER. | IMPROVE SAFETY AND UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 213 FROM KY 11 TO KY 615, INCLUDES BRIDGE OVER RED RIVER.
Legacy SYP | 10 | Bluegrass ADD | IP20190103 | 10-163.20 |  | A | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 213 FROM KY 615 TO BOTTOM OF MOUNTAIN. (PRIORITY SECTION 2)(2018BOP) | SAFETY(P) | Powell | 099-KY-0213 -000 | 9.3 | 11.2 | 1.9 | Modernize & Widen Roadway-Rural | 26 | [5 empty] | 3310000 | 2025 | 1630000 | 2025 | 6820000 | 2025 | 2019-03-06 13:25 | IMPROVE SAFETY, UPGRADE GEOMETRICS, AND ADDRESS CAPACITY ISSUES FOR KY 213 FROM KY 11 TO BOTTOM OF MOUNTAIN. | KY 213 has narrow lanes with little to no shoulders. Part of the Stanton to US 460 corridor.
Legacy SYP | 11 | Cumberland Valley ADD | IP20000081 | 11-8001 | 2017-12-08 | I | RECONSTRUCT KY-2432 FROM SECOND STREET IN EAST MANCHESTER NORTH TO THE LEFT FORK OF COAL HOLLOW ROAD (MP 2.10) (00CCN)(06CCR)(08CCR)(10CCR) | RECONSTRUCTION(O) | Clay | 026-KY-2432 -000 | 0.351 | 1.58 | 1.229 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 0 | 2016 | 2018-04-06 10:04 | The purpose of this project is to improve this section of KY 2432 by enhancing safety, upgrade surface conditions, and expand capacity. Currently the roadway has narrow lanes with little to no shoulders with infrequent curves. In addition, while the roa | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 32.1908 | 3.327 | 5.3318 | 5.0296 | 4.3839 | 5.1185 | 0 | 9 | 32
Legacy SYP | 11 | Cumberland Valley ADD | IP20080596 | 11-364 |  | A | CORRECT STANDARDIZED ROADWAY GEOMETRICS AND ADDRESS SAFETY ISSUES FROM SOUTH OF ENGINE BRANCH ROUTE TO US 421 (MP 7.2 TO MP 8.9). | RECONSTRUCTION(O) | Clay | 026-KY-0011 -000 | 7.2 | 8.8 | 1.6 | Modernize Roadway-Rural | 26 |  |  |  | 500000 | 2019 | 2000000 | 2021 | 600000 | 2021 | 7000000 | 2023 | 2016-05-24 07:21 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on KY 11. | This project is part of an overall plan to improve KY 11 from Barbourville (Knox County) to Manchester (Clay County) and was identified in a 1999 corridor feasibility study (see segment 7). Operational efficiency along the corridor is diminished as a res | 11 | South | 33.5545 | 1.3744 | 10.5924 | 6.1848 | 2.1801 | 5.4976 | 0 | 7.7251 | 34
Legacy SYP | 11 | Cumberland Valley ADD | IP20110171 | 11-8906 |  | A | ADDRESS HORIZONTAL ALIGNMENT AND SAFETY ISSUES ON US 119 NEAR HARLAN/BELL COUNTY LINE. (16CCN) | SAFETY(P) | Harlan | 048-US-0119 -000 | 0 | 1.2 | 1.2 | Modernize Roadway-Rural | 26 | Y |  |  | 840000 | 2019 | 390000 | 2019 | 110000 | 2019 | 17420000 | 2019 | 2017-05-19 08:19 | The purpose of this project is to improve the congestion, freight movement, and safety for US-119 near the Harlan/Bell County Line. This segment of US-119 is a two lane rural road that provides access directly to Pine Mountain State Park. The 2012 US 11 | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 25.5687 | 5.2133 | 4.9052 | 3.6967 | 1.7062 | 0 | 3.3175 | 6.7299 | 26
Legacy SYP | 11 | Cumberland Valley ADD | IP20130062 | 11-8857 |  | A | IMPROVE SAFETY NEAR INTERSECTION OF US 25E AND KY 3439 BY PROVIDING SIDEWALKS TO AN AREA FREQUENTED BY PEDESTRIANS. (MP 0.0-MP 0.9)(14CCN) | SAFETY(P) | Knox | 061-KY-3439 -000 | 0 | 0.897 | 0.897 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 1050000 | 2016 | 2080000 | 2016 | 4330000 | 2017 | 2015-10-08 16:30 | The purpose of this project is to address the intersection safety & congestion issues, widening, and adding sidewalks for heavy pedestrian traffic to KY 3439 from US 25E to Bradley Martin Road in Barbourville. Wal-Mart Store's entrance is close to the re | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 21.2441 | 7.1564 | 5.4028 | 7.0024 | 1.6825 | 0 | 0 | 0 | 21
Legacy SYP | 11 | Kentucky River ADD | IP20150173 | 11-8708 |  | A | WIDEN KY 118 TO PROVIDE LEFT AND RIGHT TURN LANES ONTO DENTON ROAD.(12CCN)(14CCR) | MINOR WIDENING(O) | Leslie | 066-KY-0118 -000 | 2 | 2.2 | 0.2 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 1420000 | 2017 | 2015-10-08 16:11 |  |  | 11 | South | 11.6209 | 2.7583 | 2.2749 | 0 | 0 | 0 | 3.0332 | 3.5545 | 12
Legacy SYP | 11 | Cumberland Valley ADD | IP20150187 | 11-8514.10 | 767011 | A | WIDEN 5TH STREET FROM MEYER BAKER RD TO THE KY-192 BYPASS (10CCN)(2006KYD) | MAJOR WIDENING(O) | Laurel | 063-KY-1006 -000 | 5.3 | 5.8 | 0.5 | 2 Lane to 4 Lane Divided - Urban | 10 | [5 empty] | 0 |  | 0 |  | 2250000 | 2023 | 2017-01-03 12:54 | The purpose of this project is to address congestion, improve access, and improve mobility on KY 1006 from Meyer-Baker Road to KY 192. This route is a major route into downtown London, with businesses, restaurants, college, medical facilities, and church | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 33.814 | 4.8152 | 5.545 | 10.3258 | 1.327 | 7.3934 | 0 | 4.4076 | 34
Legacy SYP | 11 | Cumberland Valley ADD | IP20150221 | 11-8852 |  | A | PROVIDE LEFT AND RIGHT TURN LANES FOR KY 354 WHILE LOWERING THE EXISTING VERTICAL GRADE TO IMPROVE ALIGNMENT WITH KY 30. (14CCN) | SAFETY(P) | Laurel | 063-KY-0354 -000 | 0.9 | 1.106 | 0.206 | Improve Intersection | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 600000 | 2016 | 2016-05-24 07:22 | The purpose of this project is to address safety and access issues on KY 354 while lowering the existing vertical grade to improve alignment with KY 30. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | 11 | South | 31.8874 | 8.4929 | 13.3649 | 2.8258 | 3.6967 | 0 | 0 | 3.5071 | 32
Legacy SYP | 11 | Cumberland Valley ADD | IP20150238 | 11-8703 |  | A | PROVIDE A PASSING BAY ON US 119 FROM MP 1.2 TO MP 2.2 IN HARLAN COUNTY.(12CCN)(14CCR)(16CCR) | MINOR WIDENING(O) | Harlan | 048-US-0119 -000 | 1.2 | 3 | 1.8 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 500000 | 2016 | 500000 | 2016 | 3000000 | 2019 | 2016-09-23 14:12 |  |  | 11 | South | 29.0225 | 5.2133 | 8.8863 | 3.9988 | 1.3033 | 0 | 3.3175 | 6.3033 | 29
Legacy SYP | 11 | Cumberland Valley ADD | IP20150248 | 11-113.20 |  | A | RECONSTRUCT US-421 FROM SAND LICK ROAD TO CONGLETON HOLLOW SPUR ROAD. (2006BOPC) | RECONSTRUCTION(O) | Jackson | 055-US-0421 -000 | 16.891 | 18.993 | 2.102 | Modernize Roadway-Rural | 26 |  |  |  | 1080000 | 2023 | 1510000 | 2023 | 650000 | 2023 | 13680000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to reconstruct US 421 from Sand Lick Road to Congleton Hollow Spur Road. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 38.6481 | 4.673 | 7.6066 | 5.705 | 4.6445 | 6.5403 | 2.7014 | 6.7773 | 39
Legacy SYP | 11 | Cumberland Valley ADD | IP20150260 | 11-113.30 |  | A | RECONSTRUCT US-421 FROM CONGLETON HOLLOW SPUR ROAD TO 0.12 MILE SOUTH JCT. KY 3446. (2006BOPC) | RECONSTRUCTION(O) | Jackson | 055-US-0421 -000 | 18.993 | 21.421 | 2.428 | Modernize Roadway-Rural | 26 | [5 empty] | 1390000 | 2023 | 610000 | 2023 | 12660000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to reconstruct US 421 from Congleton Hollow Spur Road to South Tree Tower Road. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 44.0794 | 4.7014 | 9.9526 | 7.7666 | 4.763 | 6.6351 | 2.7725 | 7.4882 | 44
Legacy SYP | 11 | Cumberland Valley ADD | IP20150288 | 11-8702 |  | A | PROVIDE PASSING OPPORTUNITIES ON US 119 IN THE VICINITY OF MP 4.5 IN BELL COUNTY. (12CCN)(14CCR)(16CCR) | MINOR WIDENING(O) | Bell | 007-US-0119 -000 | 3.7 | 5.2 | 1.5 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 1000000 | 2017 | 520000 | 2018 | 4480000 | 2019 | 2016-12-09 14:19 | Provide a safe and secure highway system on existing corridors to reduce fatalities and injuries in the region. Improve local, regional, global connectivity, and access. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) IMprove Access and Increase Capacity for all vehicle types. | 11 | South | 45.6564 | 6.8531 | 7.5355 | 4.5853 | 0.47393 | 0 | 3.673 | 7.5355 | 31 |  | 15
Legacy SYP | 11 | Cumberland Valley ADD | IP20150325 | 11-113.40 |  | A | RECONSTRUCT US-421 FROM 0.12 MILE SOUTH JCT. KY 3446 TO CLOVER BOTTOM CREEK ROAD. (2006BOPC) | RECONSTRUCTION(O) | Jackson | 055-US-0421 -000 | 21.421 | 23.541 | 2.12 | Modernize Roadway-Rural | 26 |  |  |  | 1060000 | 2023 | 1330000 | 2023 | 580000 | 2023 | 12060000 | 2023 | 2016-05-24 07:22 | The purpose of this project is to reconstruct US 421 from South Tree Tower Road to Clover Bottom Creek Road (2006BOPC) | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 74.8709 | 4.7109 | 10.0948 | 7.34 | 4.7393 | 6.5877 | 2.8673 | 8.5308 | 45 | 15 | 15
Legacy SYP | 11 | Cumberland Valley ADD | IP20150331 | 11-273 / 11-8632 |  | A | CONSTRUCT A NEW ENTRANCE TO THE GREEN PARK FROM US-421 TO END NEAR CEMETERY. (10CCN)(12CCR) | SAFETY(P) | Clay | 026-US-0421 -000 | 0 | 1 | 1 | Construct Road in New Location | 0 |  |  |  | 0 | [5 empty] | 3150000 | 2022 | 2012-05-21 08:53 | The purpose of this project is to improve safety, travel time, reliability, and reduce congestion on US 421. | The following needs have been identified for this project: 1) Improve Roadway Safety 2) Improve Access 3) Increase Capacity 4) Improve Mobility 5) Reduce Congestion
Legacy SYP | 11 | Cumberland Valley ADD | IP20150347 | 11-8851 |  | A | PROVIDE FRONTAGE ROADS ON BOTH SIDES OF KY 80 JUST WEST OF I-75 EXIT 41 (MP 9.9 TO MP 10.9) MAY INCLUDE RELOCATING EXISTING SIGNAL TO PROVIDE FOR ADEQUATE TURN LANE STORAGE AND IMPROVE CAPACITY.(14CCN) | RECONSTRUCTION(O) | Laurel | 063-KY-0080 -000 | 9.9 | 10.9 | 1 | Construct Road in New Location | 0 | Y |  |  | 0 |  | 0 |  | 0 |  | 3330000 | 2017 | 2017-05-18 13:45 | Provide frontage roads on both sides of KY 80, just west of I 75 exit 41 (MP 9.9 to MP 10.9). May include relocating existing turn signal to provide adequate turn lane storage and improve capacity. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | 11 | South | 52.6528 | 8.891 | 0 | 14.1647 | 0 | 9.6682 | 4.9289 | 0 | 38 | 15
Legacy SYP | 11 | Cumberland Valley ADD | IP20150361 | 11-269 / 11-269.10 | 401769 | A | HARLAN-VIRGINIA STATE LINE; RESCOPE US-421 FROM BARN BRANCH TO VIRGINIA STATE LINE.(08CCR)(10CCR)(16CCR) | MAJOR WIDENING(O) | Harlan | 048-US-0421 -000 | 0 | 3.832 | 3.832 | Construct Road in New Location | 0 |  |  |  | 100000 | 2017 |  |  |  |  | 77480000 | 2018 | 2017-01-03 12:51 | The purpose of this project is to reconstruct US 421 from Barn Branch Road in Harlan County to Virginia State Line. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 55.5486 | 2.8531 | 2.5592 | 10.6813 | 4.5735 | 4.8815 | 0 | 0 | 26 | 15 | 15
Legacy SYP | 11 | Cumberland Valley ADD | IP20160043 | 11-8907 |  | A | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: EASTERN APPROACH TO THE ROCKCASTLE RIVER BRIDGE TO I-75 (SEGMENT 4) (16CCN) | RECONSTRUCTION(O) | Laurel | 063-US-0025 -000 | 12.119 | 13.621 | 1.502 | Arterial to Full Control | 36 |  |  |  | 1000000 | 2016 | 40000000 | 2019 | 20400000 | 2020 | 99000000 | 2021 | 2016-05-24 07:21 | The purpose of this project is to upgrade Hal Rogers Parkway (KY 80) from Somerset to Hazard to interstate standards. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 54.1848 | 6.3886 | 11.4455 | 14.7156 | 3.6256 | 8.2938 | 0 | 9.7156 | 54
Legacy SYP | 11 | Cumberland Valley ADD | IP20160049 | 11-953 | 2016-09-30 | I | REPLACE TURNDOWN AND OTHER DEFICIENT END TREATMENTS ON US 119 FROM US 25E TO THE BELL/HARLAN COUNTY LINE. (2014BOP) | SAFETY-HAZARD ELIM(P) | Bell | 007-US-0119 -000 | 0 | 15.88 | 15.88 | Modernize Roadway-Rural | 26 | Y | [8 empty] | 0 | 2016 |  | Address safety issues on US 119 from US 25 E to the Bell/Harlan County Line | Replace turndown and other deficient end treatments on US 119 from US 25E to the Bell/Harlan County Line. (2014BOP)
Legacy SYP | 11 | Cumberland Valley ADD | IP20160050 | 11-8903 |  | A | IMPROVE SAFETY ALONG KY 221 WHILE PROVIDING SAFER TURNING LANES FOR SCHOOL TRAFFIC. (16CCN) | SAFETY(P) | Bell | 007-KY-0221 -000 | 0 | 5.366 | 5.366 | Improve Intersection | 26 |  |  |  | 200000 | 2017 | 200000 | 2018 | 75000 | 2019 | 625000 | 2020 | 2016-05-24 07:21 | Address safety issues along KY 221 to reduce fatalities and injuries in the region. | Improve safety along KY 221 while providing safer turning lanes for school traffic.
Legacy SYP | 11 | Cumberland Valley ADD | IP20160051 | 11-8902 |  | A | RECONSTRUCT KY 1534 AND YELLOW CREEK ALONG THE EASTSIDE OF ROADWAY FROM MP 1.3 TO MP 3.5 TO IMPROVE SAFETY. (16CCN) | RECONSTRUCTION(O) | Bell | 007-KY-1534 -000 | 1.3 | 3.5 | 2.2 | Modernize Roadway-Rural | 26 |  |  |  | 250000 | 2017 | 300000 | 2018 | 250000 | 2019 | 2250000 | 2020 | 2016-05-24 07:21 | Address horizontal alignment and safety issues on KY 1534 and Yellow Creek | The following needs have been identified for this project: 1) Improve Roadway Safety and 2) Improve mobility and capacity.
Legacy SYP | 11 | Cumberland Valley ADD | IP20160053 | 11-8957 |  | A | RECONSTRUCT AND IMPROVE EXISTING ALIGNMENTS, WITH SHOULDERS, OF BARBOURVILLE - MANCHESTER ROAD (KY 11) FROM THE KNOX-CLAY COUNTY LINE (MP 0.0) TO US 421 IN CLAY COUNTY (MP 8.891). (16CCN) | RECONSTRUCTION(O) | Clay | 026-KY-0011 -000 | 0 | 8.891 | 8.891 | Transportation Studies | 0 |  |  |  | 3000000 | 2021 | [6 empty] | 2016-05-24 07:21 | The purpose of this project is to reconstruct and improve existing alignments, with shoulders, of KY 11 from Knox/Clay County line to US 421 in Clay County. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion
Legacy SYP | 11 | Cumberland Valley ADD | IP20160059 | 11-8713 | 401769 | A | RAISE KY-459 ABOVE FLOOD PLAIN FROM MP 3 TO MP 5, INCLUDING RAISING THE BULL RUN CREEK BRIDGE (INCLUDES 11-8712).(12CCN) | SAFETY(P) | Knox | 061-KY-0459 -000 | 3 | 5 | 2 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 4290000 | 2016 | 2017-05-19 14:06 | The purpose of this project is to raise KY 459 above the flood plain, as well as raising the Bull Run Creek Bridge. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access | 11 | South | 13.8538 | 0.38863 | 2.9147 | 1.3507 | 4.5498 | 0 | 0 | 4.65 | 14
Legacy SYP | 11 | Cumberland Valley ADD | IP20160060 | 11-8955 |  | A | IMPROVE KY 3041 FROM MP 1.5 TO MP 2.0 TO INCREASE SAFETY AND PROVIDE ACCESS TO THUNDER GAP HORSE RACING TRACK. (16CCN) | SAFETY(P) | Knox | 061-KY-3041 -000 | 1.5 | 2 | 0.5 | Realign Intersection | 26 | Y |  |  | 200000 | 2017 | 200000 | 2017 | 100000 | 2017 | 500000 | 2017 | 2016-05-24 07:21 | The purpose of this project is to improve KY 3041 to increase safety and provide access to Thunder Gap Horse Racing Track. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 31.0806 | 5.6777 | 12.3697 | 4.6919 | 0 | 0 | 3.2227 | 5.1185 | 31
Legacy SYP | 11 | Cumberland Valley ADD | IP20160063 | 11-8901 |  | A | RECONSTRUCT TO CORRECT SAFETY ISSUES AND IMPROVE STABILIZATION OF ROADWAY ON KY 188 AND YELLOW CREEK ON THE SOUTHSIDE OF ROADWAY. (16CCN) | RECONSTRUCTION(O) | Bell | 007-KY-0188 -000 | 0 | 2.55 | 2.55 | Maintenance Improvement | 10 |  |  |  | 250000 | 2017 | 200000 | 2018 | 350000 | 2019 | 2500000 | 2020 | 2016-05-24 07:21 | Address safety and access issues along KY 188 | The following needs have been identified for this project: 1) Improve roadway safety and 2) Improve access
Legacy SYP | 11 | Kentucky River ADD | IP20160106 | 11-5010 |  | A | LANDSLIDE REPAIR ON US-421 FROM 0.2 MILE SOUTH JCT. KY-406 AT STINNETT NORTH 1.0 MILE. (2002BOPC) (10CCR)(ADDITIONAL FUNDS FROM ITEM NO. 11-8707 R,U,C) | LANDSLIDE REPAIR(P) | Leslie | 066-US-0421 -000 | 15 | 16 | 1 | Maintenance Improvement | 10 |  |  |  | 0 |  | 2970000 | 2012 | 630000 | 2012 | 8440000 | 2013 | 2015-10-08 13:10 |  |  | 11 | South | 14.6149 | 5.2133 | 0 | 2.3637 | 4.2891 | 0 | 2.7488 | 0 | 15
Legacy SYP | 11 | Cumberland Valley ADD | IP20160152 | 11-8908 |  | A | UPGRADE ROUTE FROM SOMERSET TO HAZARD TO INTERSTATE STANDARDS: LONDON BYPASS, I-75 TO THE HAL ROGERS PARKWAY (SEGMENT 5). (16CCN) | RECONSTRUCTION(O) | Laurel | 063-US-0025 -000 | 12.119 | 13.621 | 1.502 | Arterial to Full Control | 36 |  |  |  | 1000000 | 2017 | 25000000 | 2019 | 18500000 | 2020 | 99000000 | 2021 | 2016-05-24 07:21 | The purpose of this project is to upgrade Hal Rogers Parkway (KY 80) from Somerset to Hazard to interstate standards. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 54.5403 | 6.3886 | 11.8009 | 14.7156 | 3.6256 | 8.2938 | 0 | 9.7156 | 54
Legacy SYP | 11 | Cumberland Valley ADD | IP20170011 | 11-184.11 |  | I | RECONSTRUCT KY-92 FROM 500 FT WEST OF THE WHITLEY/MCCREARY COUNTY LINE TO 1200 FT EAST OF OLD JELLICO CREEK ROAD. (SECTION 1) (ADDITIONAL FUNDING FOR 11-184.10) | PREFINANCD CONVRSN(O) | Whitley | 118-KY-0092 -000 | 0 | 4.172 | 4.172 | Construct Road in New Location | 0 | [9 empty] | 0 | 2021 |  | THE PURPOSE OF THIS PROJECT IS TO RECONSTRUCT KY-92 FROM 500 FT WEST OF THE WHITLEY/MCCREARY COUNTY LINE TO 1200 FT EAST OF OLD JELLICO CREEK ROAD. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Access, 3) Increase Capacity, 4) Improve Mobility, 5) Reduce Congestion | CUMBERLAND VALLEY ADD | South | 54.7453 | 3.3649 | 0 | 10.2192 | 2.891 | 5.7346 | 2.5355 | 0 | 25 | 15 | 15
Legacy SYP | 11 | Cumberland Valley ADD | IP20180076 | 11-5005 |  | A | CORRECT ROCKFALL HAZARD @ MP 23.5 TO 24.1(10CCR) | ROCKFALL MITIGTN(P) | Clay | 026-KY-0066 -000 | 23.5 | 24.1 | 0.6 | Local Roadway Improvements | 3 | [5 empty] | 130000 | 2014 | 40000 | 2014 | 3990000 | 2015 | 2014-05-29 08:11 | The purpose of this project is to improve safety and stability of the road along KY 66. | The following needs have been identified for this project: 1) Improve Roadway Safety
Legacy SYP | 11 | Cumberland Valley ADD | IP20180078 | 11-217 |  | A | RECONSTRUCT KY-66 FROM 500' S OF NCL PINEVILLE TO KY-221 | RECONSTRUCTION(O) | Bell | 007-KY-0066 -000 | 0.289 | 1 | 0.711 | Modernize Roadway-Urban | 16 | [5 empty] | 2220000 | 2016 | 830000 | 2016 | 7980000 | 2018 | 2016-05-24 07:22 | Address Flooding, safety and access issues on KY 66 from the bridge over Straight Creek to MP 1.00. | Reconstruct KY-66 from the bridge over Straight Creek to MP 1.00.
Legacy SYP | 12 | Big Sandy ADD | IP20080653 | 12-5008 | 767011 | A | CORRECT ROCKFALL HAZARD @ MP 1.80 TO 3.05. (04CCR)(10CCR)(12CCR) | ROCKFALL MITIGTN(P) | Johnson | 058-KY-0321 -000 | 1.8 | 3.05 | 1.25 | Maintenance Improvement | 10 |  |  |  | 0 |  | 0 |  | 0 |  | 12770000 | 2016 | 2017-09-01 13:48 | Address safety and reliability by mitigating rockfall hazards on this section of KY-321. | This segment of KY 321 (old US 23) was constructed in 1960. There are several high-wall rock cuts that consist of geological layers of shale, coal, brown and gray sandstone. The shale is under the layers of brown and gray sandstone. The highwall cuts ar | 12 | East | 31.9117 | 6.2754 | 0 | 6.9835 | 0 | 0 | 3.6527 | 0 | 17 |  | 15
Legacy SYP | 12 | Big Sandy ADD | IP20080658 | 12-8903 |  | A | IMPROVE SAFETY AND GEOMETRICS FROM KY 321 RAMP TO PAINTSVILLE, AT THE BROADWAY INTERSECTION. (16CCN) | SAFETY(P) | Johnson | 058-KY-1428 -000 | 0.805 | 2.897 | 2.092 | Modernize Roadway-Rural | 26 |  |  |  | 1500000 | 2018 | 8000000 | 2019 | 1500000 | 2020 | 15000000 | 2021 | 2016-05-24 07:21 | Address safety and connectivity issues by improving lane width and roadway geometrics on this segment of KY-1428 from the KY-321 ramp to the Broadway intersection. | The purpose of this project is to address various issues on a segment of KY 1428 from the KY 321 ramp to the Broadway intersection in Paintsville, a length of 2.1 miles. KY 1428 is a primary route linking the communities of Hager Hill, West Van Lear, and | 12 | East | 55.4072 | 5.018 | 9.1617 | 11.8563 | 2.9641 | 0 | 3.6826 | 7.7246 | 40 |  | 15
Legacy SYP | 12 | Kentucky River ADD | IP20080675 | 12-311.80 |  | A | RECONSTRUCTION OF US-119 FROM 0.15 MILE WEST OF KY-806 TO KY-932. 2012BOP | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 7.526 | 8.967 | 1.441 | Modernize Roadway-Rural | 26 | Y |  |  | 0 |  | 2500000 | 2018 | 300000 | 2019 | 34000000 | 2020 | 2014-05-29 08:12 |  | This section of US 119 connects Cumberland to Whitesburg and has a significant amount of traffic including truck traffic. Currently four sections of US 119 from the Harlan County line are either completed, under construction, or approved for construction | 12 | East | 59.7051 | 3.7246 | 7.2754 | 11.3398 | 5 | 7.4251 | 3.4132 | 6.5269 | 45 |  | 15
Legacy SYP | 12 | Kentucky River ADD | IP20080679 | 12-8702 | 401769 | A | IMPROVE THE EXISTING ROADWAY TO MEET CURRENT STANDARDS AND IMPROVE CONGESTION INTO AND OUT OF JENKINS BETWEEN MP 8.741 AND MP 9.247.(12CCN) | CONGESTION MITIGTN(O) | Letcher | 067-KY-0805 -000 | 8.741 | 9.247 | 0.506 | Modernize Roadway-Rural | 26 |  |  |  | 0 |  | 0 |  | 0 |  | 6060000 | 2016 | 2016-05-24 07:22 |  | To improve the existing roadway segment by eliminating the deficient horizontal curves, no shoulder, and with poor superelevation between Jenkins and the interchange of KY 805 with US 23. This is the primary connector for Jenkins to US 23. | 12 | East | 19.4716 | 2.982 | 3.3234 | 1.9087 | 3.7425 | 0 | 3.0838 | 4.4311 | 20
Legacy SYP | 12 | Big Sandy ADD | IP20080703 | 12-281 | 767011 | A | CURVE REVISION AND PASSING LANES ON KY-194 NEAR DESKINS BRANCH (08CCR)(12CCR) | SAFETY(P) | Pike | 098-KY-0194 -000 | 21.3 | 22 | 0.7 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 8870000 | 2016 | 2017-05-19 14:02 | Address safety and increase capacity on this segment of KY-194 by improving geometrics and adding a passing lane near Deskins Branch. | This portion of road has narrow lanes, virtually no shoulders, and very steep curves (3 horz. alignment). This project was documented in a District Memo dated 2\21\96 and is Location #3. | 12 | East | 46.2949 | 6.4072 | 4.8503 | 5.3668 | 4.6108 | 0 | 3.7725 | 6.2874 | 31 | 15
Legacy SYP | 12 | Big Sandy ADD | IP20080712 | 12-8905 |  | A | IMPROVE CONNECTIVITY BETWEEN KY 881 AND US 119. (16CCN) | RECONSTRUCTION(O) | Pike | 098-KY-0881 -000 | 0.481 | 2.081 | 1.6 | Construct Road in New Location | 0 |  |  |  | 1750000 | 2018 | 1530000 | 2019 | 1500000 | 2020 | 21500000 | 2021 | 2016-05-24 07:21 | Address mobility and regional connectivity by relocating this segment to improve connectivity to improve connectivity between KY 881 AND US 119. | The following needs have been identified for this project: 1) Improve mobility and capacity.
Legacy SYP | 12 | FIVCO ADD | IP20150233 | 12-3 |  | A | CONSTRUCT A NEW ROADWAY TO CONNECT BETWEEN KY 3215 TO KY 1185 AT YATESVILLE LAKE. (12CCR)(14CCR) | NEW ROUTE(O) | Lawrence | 064-PF-9999 - |  |  |  | Construct Road in New Location | 0 |  |  |  | 0 |  | 0 |  | 610000 | 2016 | 22390000 | 2019 | 2017-05-19 12:19 |  |  | 12 | East | 12.6557 | 0.095808 | 0 | 2.1108 | 4.8204 | 5.6287 | 0 | 0 | 13
Legacy SYP | 12 | Big Sandy ADD | IP20150282 | 12-298.30 | 2019-08-23 | A | KY-199 SPOT IMPROVEMENT (PRIORITY 2); IMPROVE INTERSECTION WITH KY-1056 AND RELOCATE PORTIONS OF KY-199 ALONG OLD NORFOLK SOUTHERN RAILROAD BED @ MCANDREWS. (2002BOPC) (08CCR)(10CCR) | RECONSTRUCTION(O) | Pike | 098-KY-0199 -000 | 7.9 | 9.3 | 1.4 | Modernize Roadway-Rural | 26 | [5 empty] | 0 |  | 0 |  | 4000000 | 2016 | 2018-02-08 11:48
Legacy SYP | 12 | Big Sandy ADD | IP20150292 | 12-154.10 / 12-154.11 / 12-154.16 / 12-154.17 / 12-154.21 | 401769 | A | INEZ TO WARFIELD (SECTION 2-2): FROM BOOTH FORK TO KY-2031 [STA. 298+00 TO STA. 382+00 (ENGLISH)](16CCR) | RELOCATION(O) | Martin | 080-KY-0040 -000 | 16 | 18 | 2 | 2 Lane to 4 Lane Divided - Rural | 36 | [5 empty] | 0 |  | 6160000 | 2018 | 136680000 | 2019 | 2012-12-17 13:34 | Improve KY 40 and reduce travel time between Inez and State Line at Warfield. | Increase safety, reduce travel time and increase capacity of roadway. | 12 | East | 49.9326 | 8.982 | 6.8263 | 10.1722 | 3.9222 | 8.7425 | 3.982 | 7.3054 | 50
Legacy SYP | 12 | Big Sandy ADD | IP20150294 | 12-8704 |  | A | IMPROVEMENTS TO CASSIDY BLVD. AND THOMPSON RD TO ADDRESS SAFETY CONCERNS AND CONGESTION ISSUES.(12CCN)(14CCR)(16CCR) | RECONSTRUCTION(O) | Pike | 098-CS-1215 -000 | 0 | 1.654 | 1.654 | Local Roadway Improvements | 3 |  |  |  | 0 |  | 1240000 | 2016 | 1240000 | 2016 | 5410000 | 2017 | 2017-05-19 14:18 | Improve access and reduce congestion by reconstructing Thompson Road and restoring access to US-23 | The following need has been identified for this project: Improve access, improve capacity, and reduce congestion. | BIG SANDY ADD | East | 14.111 | 4.515 | 0 | 4.8278 | 0.92814 | 0 | 0 | 3.84 | 14
Legacy SYP | 12 | Big Sandy ADD | IP20150301 | 12-1.40 |  | A | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM NEELEY BRANCH ROAD TO COUNTY ROAD 1386 AT PRESTONSBURG ELEMENTARY SCHOOL. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | MAJOR WIDENING(O) | Floyd | 036-PF-9999 - |  |  |  | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 1800000 | 2018 | 2780000 | 2019 | 600000 | 2019 | 39670000 | 2022 | 2016-05-24 07:22 |  |  | 12 | Statewide | 50.7112 | 8.6167 | 10.4846 | 3.2214 | 7.9736 | 6.1894 | 1.4978 | 12.7277
Legacy SYP | 12 | Big Sandy ADD | IP20150355 | 12-298.40 | 2019-08-23 | A | KY-199 SPOT IMPROVEMENT; RELOCATE PORTIONS OF KY-199 ALONG OLD NORFOLK SOUTHERN RAILROAD BED @ STONE. (2002BOPC)(08CCR) | RECONSTRUCTION(O) | Pike | 098-KY-0199 -000 | 9.5 | 10.5 | 1 | Modernize Roadway-Rural | 26 | [9 empty] | 5020000 | 2016 | 2018-02-08 11:48 |  |  | BIG SANDY ADD | East | 60.6856 | 4.8623 | 12.1257 | 9.5659 | 3.2036 | 8.1437 | 0 | 7.7844 | 46 | 15
Legacy SYP | 12 | Big Sandy ADD | IP20150362 | 12-1.30 |  | A | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM THE HEAD OF LEFT FORK OF ABBOTT CREEK TO NEELEY BRANCH ROAD. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | MAJOR WIDENING(O) | Floyd | 036-PF-9999 - |  |  |  | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 3200000 | 2019 | 6290000 | 2020 | 1300000 | 2020 | 41210000 | 2022 | 2016-05-24 07:22 |  |  | 12 | Statewide | 48.217 | 4.511 | 11.1894 | 4.8899 | 6.1233 | 6.674 | 0.48458 | 14.3448
Legacy SYP | 12 | Big Sandy ADD | IP20150443 | 12-1.20 |  | A | MOUNTAIN PARKWAY CORRIDOR: EXTEND THE FOUR LANE MOUNTAIN PARKWAY FROM THE MAGOFFIN/FLOYD COUNTY LINE TO THE HEAD OF LEFT FORK OF ABBOTT CREEK. (SEE 12-1.01 FOR PE & ENV)(14CCR)(16CCR) | MAJOR WIDENING(O) | Floyd | 036-PF-9999 - |  |  |  | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 2900000 | 2020 | 6020000 | 2021 | 1200000 | 2021 | 60370000 | 2022 | 2016-05-24 07:22 |  |  | 12 | Statewide | 42.7583 | 3.4537 | 6.696 | 4.13 | 8.2379 | 5.6388 | 0.39648 | 14.2054
Legacy SYP | 12 | Kentucky River ADD | IP20160081 | 12-199.31 |  | A | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM EXISTING 4-LANE AT KY-1862 TO PAST JUST NORTH OF THE MAYKING MALL.(16CCN) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 17.805 | 18.692 | 0.887 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 0 | 2018 | 1350000 | 2019 | 1010000 | 2019 | 2440000 | 2021 | 2019-02-27 15:18
Legacy SYP | 12 | Kentucky River ADD | IP20160088 | 12-199.32 |  | A | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM NORTH OF MAYKING MALL TO JUST SOUTH OF THE TRUCK PASSING LANES AND KY-3406.(16CCN) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 19.191 | 20.256 | 1.065 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 600000 | 2020 | 750000 | 2022 | 450000 | 2022 | 0 |  | 2016-12-19
Legacy SYP | 12 | Kentucky River ADD | IP20160089 | 12-199.33 |  | A | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM KY-3406 AND THE BEGINNING OF THE NORTHBOUND TRUCK PASSING LANES TO JUST NORTH OF KY-805. (16CCN) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 20.256 | 21.54 | 1.284 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 1300000 | 2020 | 1150000 | 2022 | 1450000 | 2022 | 0 |  | 2016-12-19
Legacy SYP | 12 | Big Sandy ADD | IP20160156 | 12-154.10 |  | A | INEZ TO WARFIELD (PRIORITY SECTION II): FROM LITTLE BLACK LOG TO KY-292. [STA. 190+00 TO STA. 427+00 (ENGLISH)] (2002BOP) | RELOCATION(O) | Martin | 080-KY-0040 -000 | 1.632 | 10.18 | 8.548 | 2 Lane to 4 Lane Divided - Rural | 36 | [7 empty] | 4160000 | 2019 |  |  | 2012-12-17 13:34 | Address regional connectivity and mobility by relocating this segment of KY-40 | The following needs have been identified for this project: 1) Improve Roadway Safety, 2)Improve Mobility and Capacity.
Legacy SYP | 12 | Big Sandy ADD | IP20160157 | 12-154.11 | 401769 | A | INEZ TO WARFIELD (SECTION 2-1): FROM LITTLE BLACKLOG TO BOOTH FORK. [STA. 190+00 TO STA. 298+00 (ENGLISH)] (2002BOP)(12CCR)(AR/W)(16CCR) | RELOCATION(O) | Martin | 080-KY-0040 -000 | 1.632 | 10.18 | 8.548 | 2 Lane to 4 Lane Divided - Rural | 36 | [5 empty] | 0 |  | 2000000 | 2018 | 41430000 | 2019 | 2017-09-26 15:16 | Improve regional connectivity and increase capacity by relocating this segment of KY-40. | The following needs have been identified for this project: 1) Improve Roadway Safety, 2) Improve Mobility and Capacity. | 12 | East | 71.1033 | 6.3353 | 12.9341 | 14.7979 | 3.5329 | 8.503 | 0 | 10 | 56 |  | 15
Legacy SYP | 12 | Kentucky River ADD | IP20160165 | 12-8200 | 401769 | A | NEW CONSTRUCTION OF ONE MILE STRETCH OF KY-1231 BEGINNING AT BRIDGE AFTER LEAVING KY-550. (04CCN)(06CCR)(08CCR)(10CCR)(12CCR) | RESURFACING(P) | Knott | 060-KY-1231 -000 | 6.982 | 7.982 | 1 | Construct Road in New Location | 0 | [5 empty] | 0 |  | 0 |  | 4870000 | 2016 | 2017-09-01 13:59 | Address safety concerns along KY 1231, increase capacity and mobility by correcting deficient curves and reducing travel time. | Improve safety, increase capacity. | 12 | East | 13.232 | 0.93413 | 0 | 2.8967 | 3.1737 | 6.2275 | 0 | 0 | 13
Legacy SYP | 12 | Big Sandy ADD | IP20160166 | 12-9002 |  | A | PERFORM LOW COST SAFETY IMPROVEMENTS ON KY 632 FROM KY 194 (MP 0.00) TO 0.037 MI EAST OF BLACKBERRY FRK (CR-1576) AT (MP 7.00) IN PIKE COUNTY. (2016BOP) | SAFETY-HAZARD ELIM(P) | Pike | 098-KY-0632 -000 | 0 | 7 | 7 | Other Improvement Types | 0 |  |  |  | 0 |  | 0 | 2019 |  |  |  |  | 2019-02-19 13:03 | Improve roadway safety, reliability, and mobility of KY-632 by making spot improvements from the KY-194 intersection to MP 7.0. | The following needs have been identified for this project: 1) Improve Roadway Safety.
Legacy SYP | 12 | Kentucky River ADD | IP20160244 | 12-8804 | 2017-12-21 | I | CONGESTION/SAFETY IMPROVEMENT AT THE JUNCTION OF MAIN STREET AND EAST MAIN IN DOWNTOWN WHITESBURG. (14CCN)(16CCR) | SAFETY(P) | Letcher | 067-KY-0015X -000 | 1.6 | 1.7 | 0.1 | Improve Intersection | 26 |  |  |  | 0 |  | 150000 | 2016 | 200000 | 2016 | 0 |  | 2018-01-02 10:32
Legacy SYP | 12 | Kentucky River ADD | IP20160245 | 12-8909 |  | A | UPGRADE KY-160 (ROXANA-VAN ROAD) WITH SHOULDER/BREAK REPAIRS, CULVERT EXTENSIONS, AND DRAINAGE UPGRADES. (16CCN) | RECONSTRUCTION(O) | Letcher | 067-KY-0160 -000 | 0 | 21.843 | 21.843 | Modernize Roadway-Rural | 26 | [5 empty] | 50000 | 2019 | 100000 | 2019 | 3150000 | 2020 | 2016-05-24 07:21 | Widen roadway and shoulders, repair roadway breaks, improve drainage and improve roadway geometry. | Improve safety, increase capacity and improve roadway drainage. | 12 | East | 50.1512 | 1.7006 | 14.4611 | 13.8099 | 3.8323 | 6.4671 | 0 | 9.8802 | 50
Legacy SYP | 12 | Kentucky River ADD | IP20160246 | 12-8910 |  | A | CURVE CORRECTION AT MP 17.7 ALONG KY 160 NEAR INTERSECTION WITH KY 588. (16CCN) | RECONSTRUCTION(O) | Letcher | 067-KY-0160 -000 | 17.5 | 17.9 | 0.4 | Modernize Roadway-Rural | 26 |  |  |  | 300000 | 2019 | 100000 | 2020 | 100000 | 2020 | 5000000 | 2021 | 2016-05-24 07:21 | CURVE CORRECTION AT MP 17.7 ALONG KY 160 NEAR INTERSECTION WITH KY 588. (16CCN) | CURVE CORRECTION AT MP 17.7 ALONG KY 160 NEAR INTERSECTION WITH KY 588. (16CCN) | KENTUCKY RIVER ADD | East | 20.2695 | 1.9162 | 2.515 | 0.8982 | 4.2814 | 6.7665 | 0 | 3.8922 | 20
Legacy SYP | 12 | Kentucky River ADD | IP20160250 | 12-199.34 |  | A | RECONSTRUCT US-119 BY WIDENING TO 4-LANES FROM NORTH OF KY-805 TO THE EXISTING 4-LANE.(16CCN) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 21.402 | 26.689 | 5.287 | 2 Lane to 4 Lane Divided - Rural | 36 | Y |  |  | 1000000 | 2020 | 750000 | 2022 | 750000 | 2022 | 0 |  | 2016-12-19
Legacy SYP | 12 | Kentucky River ADD | IP20160251 | 12-199.50 |  | A | RECONSTRUCT US-119 BY WIDENING TO 4-LANES ALONG A NEW ALIGNMENT (ORANGE) THROUGH THE GATEWAY INDUSTRIAL PARK TO US-23, INCLUDING US-23 FLYOVER RAMP.(16CCN) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 23.889 | 26.495 | 2.606 | Construct Road in New Location | 0 | Y |  |  | 0 | 2017 | 2860000 | 2018 | 1150000 | 2018 | 18340000 | 2023 | 2019-02-27 15:22 | To improve the roadway geometrics and increase the safety by providing a continuous turning movement for trucks. Increase the access to the industrial site for larger vehicles. | Improve roadway safety, increase capacity, and improve access. | 12 | East | 30.8608 | 5.509 | 0 | 10.8009 | 0.95808 | 9.4012 | 4.1916 | 0 | 31
Legacy SYP | 12 | Kentucky River ADD | IP20160252 | 12-199.51 |  | A | RECONSTRUCT US-119 BY WIDENING TO 4-LANES ALONG A NEW ALIGNMENT (ORANGE) THROUGH THE GATEWAY INDUSTRIAL PARK TO US-23.(16CCN)(R & U UNDER 12-199.50) | RECONSTRUCTION(O) | Letcher | 067-US-0119 -000 | 23.889 | 26.495 | 2.606 | Construct Road in New Location | 0 | Y | [8 empty] | 31500000 | 2020
Legacy SYP | 12 | Big Sandy ADD | IP20160266 | 12-8906 |  | A | IMPROVE CONNECTIVITY BETWEEN KY 292 AND US 119/US 52 MINGO. (16CCN) | RECONSTRUCTION(O) | Pike | 098-KY-0292 -000 | 12.5 | 12.7 | 0.2 | Construct Road in New Location | 0 |  |  |  | 450000 | 2018 | 60000 | 2019 | 110000 | 2020 | 3090000 | 2021 | 2017-05-19 14:11 |  |  | BIG SANDY ADD | East | 29.2425 | 7.8204 | 0 | 7.8593 | 4.1018 | 9.4611 | 0 | 0 | 29
Legacy SYP | 12 | Big Sandy ADD | IP20170010 | 12-8805 |  | I | EXTEND THE INDUSTRIAL PARK ACCESS ROAD ON CR-1268.(14CCN)(16CCN) | NEW ROUTE(O) | Pike | 098-CR-1268 -000 | 0 | 0.46 | 0.46 | Construct Road in New Location | 0 | [9 empty] | 0 | 2017 |  | Improve mobility and facilitate economic development by extending the access road to the industrial park on CR-1268. | The following needs have been identified for this project: 1) Improve Capacity | BIG SANDY ADD | East | 9.5793 | 0.035928 | 0 | 0.11228 | 3.6228 | 5.8084 | 0 | 0 | 10
? | 1 | Pennyrile ADD | IP20050001 |  |  |  | Address safety and traffic circulation issues from MP 1.53 to MP 1.85 on KY 937 in front of South Livingston Elementary School. |  | Livingston | 070-KY-0937 -000 | 1.53 | 1.85 | 0.32 | Modernize Roadway-Rural | 26 |  | 0 |  | 150000 |  | 100000 |  | 250000 |  | 1500000 |  | 2017-04-10 10:44 | Improve school buss access, traffic flow and safety | There is poor traffic flow and substandard geometrics for school business and other vehicles accessing South Livingston Elementray School off KY 937. There is traffic congestion due to school bussess blocking traffic while waiting for on-coming traffic t | PENNYRILE ADD | West | 17.0954 | 3.8007 | 2.732 | 1.5593 | 3.2646 | 0 | 0 | 5.7388 | 17
? | 1 | Pennyrile ADD | IP20060053 |  |  |  | Widen KY 453 from just north of the rock quarry entrance (MP 7.13) to just south of the quarry entrance (MP 6.83) |  | Livingston | 070-KY-0453 -000 | 6.83 | 7.13 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 150000 |  | 100000 |  | 200000 |  | 1500000 |  | 2015-01-15 13:21 | Improve safety and geometrics | There are sight distance safety issues from traffic coming south on KY 453 to the quarry access road intersection. Also, gravel trucks cause congestion by slowing down other traffic on KY 453. When the trucks leave the quarry, it takes time for them to
? | 2 | Pennyrile ADD | IP20060078 |  |  |  | CONVERT WALNUT & CAMPBELL TO ONE-WAY COUPLET FROM 4TH TO 21ST ST IN HOPKINSVILLE (INCLUDES NEW BRIDGE OVER RR) |  | Christian | 024-US-0041A -000 | 14.49 | 15.29 | 0.8 | Other Improvement Types | 0 | Y | 0 |  | 1000000 |  | 1300000 |  | 500000 |  | 3400000 |  | 2010-02-25 16:51 |  | Traffic congestion is a problem on these two routes.
? | 2 | Pennyrile ADD | IP20070021 |  |  |  | Construct left turn lane into Eagle Cove neighborhood from US 68 BP. |  | Christian | 024-US-0068 -000 | 9.56 | 9.66 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 50000 |  | 0 |  | 0 |  | 250000 |  | 2010-02-25 16:51 |  | This is a traffic flow issue
? | 2 | Pennyrile ADD | IP20070044 |  |  |  | COUNTRY CLUB LANE - RECONSTRUCT AND ADD TURN LANES AT SUNSET CIRCLE IN HOPKINSVILLE from MP 1.4 to MP 1.5. |  | Christian | 024-KY-0380 -000 | 1.4 | 1.5 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 750000 |  | 300000 |  | 600000 |  | 2010-02-25 16:51 |  | Vehicles traving on KY 380 block traffic while trying to make left turns onto Sunset Circle.
? | 2 | Pennyrile ADD | IP20070047 |  |  |  | COX MILL RD - RECONSTRUCT AND ADD TURN LANES AT GARY LANE IN HOPKINSVILLE |  | Christian | 024-KY-0695 -000 | 9.695 | 9.795 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 250000 |  | 500000 |  | 800000 |  | 1200000 |  | 2010-02-25 16:51 |  | Left rurning vehicles block traffic
? | 2 | Pennyrile ADD | IP20180027 |  |  |  | US 41A NEW TURNING LANE NORTHBOUND AT EXISTING MEDIAN CROSSOVER NEAR MILEPOST 11.4. CITY TO CONSTRUCT AND BE REIMBURSED. |  | Christian | 024-US-0041A -000 | 11.3 | 11.4 | 0.1 | Improve Intersection | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2018-04-26 18:02 |  |  | General Assembly | West | 22.0989 | 9.1301 | 0 | 1.4897 | 0.83904 | 0 | 5 | 5.64 | 22
? | 2 | Pennyrile ADD | IP20180041 |  |  |  | US 41A NEW TURNING LANE NORTHBOUND AT EXISTING MEDIAN CROSSOVER NEAR MILEPOST 11.4. CITY TO CONSTRUCT AND BE REIMBURSED. |  | Christian | 024-US-0041A -000 | 11.3 | 11.4 | 0.1 |  |  | Y
? | 2 | Green River ADD | IP20190169 |  |  |  | Reconstruct KY 812/Airline Rd from Atkinson St (CS-1014) to KY 2084 to improve safety and level of service. |  | Henderson | 051-KY-0812 -000 | 7.395 | 7.935 | 0.54
? | 2 | Green River ADD | IP20190170 |  |  |  | Reconstruct KY 136/Madison St from Atkinson St (CS-1014) to the bridge over North Fork Canoe Creek to improve safety and level of service. |  | Henderson | 051-KY-0136 -000 | 20.74 | 21.236 | 0.496
? | 2 | Green River ADD | IP20190171 |  |  |  | Reconstruct North McKinley St (CS-1239) from Garfield (CS-1133) to Priest St (CS-1292) to improve safety and level of service. |  | Henderson | 051-CS-1239 -000 | 0 | 0.209 | 0.209
? | 2 | Green River ADD | IP20190172 |  |  |  | Reconstruct South McKinley St (CS-1044) from Washington (CS-1368) to Garfield (CS-1133) to improve safety and level of service. |  | Henderson | 051-CS-1044 -000 | 0 | 0.154 | 0.154
? | 4 | Lake Cumberland ADD | IP20060238 |  |  |  | EXTEND KY 289 SOUTH FROM US 68 TO HOTCHKISS STREET IN CAMPBELLSVILLE. |  | Taylor | 109-KY-0289 -000 | 0 | 0.2 | 0.2 | Construct Road in New Location | 0 |  | 0 |  | 250000 |  | 250000 |  | 200000 |  | 900000 |  | 2015-01-14 13:35 | Improve connection from US 68 to southern portions of Campbellsville to address congestion and safety. | Campbellsville has limited connectivity from US 68 (BROADWAY) to the southern portions of the city. These incomplete connections result in traffic congestion and safety concerns at certain intersections. This project is to extend S. Lebanon Avenue to S.C
? | 4 | Lincoln Trail ADD | IP20180025 |  |  |  | Add center turn lane along US 68 from entrance to TG Kentucky to the previous widening and along KY 2154/Corporate Drive from the intersection with US 68 to just north of the entrance to Fuel Total Systems and improve the intersection of US 68/KY 2154. |  | Marion | 078-US-0068 -000 | 12.2 | 12.8 | 0.6
? | 5 | KIPDA ADD | IP20190088 |  |  |  | Improve capacity, relieve congestion, and improve safety along KY 44 from the Spencer County Line to Oak Tree Way (PS-1200). MP 0.00 to MP 7.542. |  | Spencer | 108-KY-0044 -000 | 0 | 7.542 | 7.542
? | 5 | KIPDA ADD | IP20190091 |  |  |  | Improve safety and reduce congestion on KY 146 (LaGrange Road) from KY-393 to Button Lane (CS-1169). Project will evaluate widening from 2 to 4 travel lanes and consider other lower impact alternatives. Design will also consider accommodations for bicyc |  | Oldham | 093-KY-0146 -000 | 7.41 | 9.58 | 2.17
? | 5 | KIPDA ADD | IP20190092 |  |  |  | Improve safety on KY 155 near the entrance to Spencer Christian Church. MP 0.20 to MP 0.40. |  | Spencer | 108-KY-0155 -000 | 0.2 | 0.4 | 0.2
? | 5 | KIPDA ADD | IP20190093 |  |  |  | Improve safety at the intersection of KY 155 and Goebel Road/Hochstrasser Road. MP 0.65 to MP 0.85. |  | Spencer | 108-KY-0155 -000 | 0.65 | 0.85 | 0.2
? | 5 | KIPDA ADD | IP20190144 |  |  |  | Address safety issues and geometric issues along KY 636 from KY 248 to Shelby County Line. MP 0.000 to MP 3.608 |  | Spencer | 108-KY-0636 -000 | 0 | 3.608 | 3.608
? | 5 | KIPDA ADD | IP20190145 |  |  |  | Address safety issues and geometric issues along KY 1060 from KY 44 to KY 1169. MP 0.00 to MP 1.70 |  | Spencer | 108-KY-1060 -000 | 0 | 1.7 | 1.7
? | 5 | KIPDA ADD | IP20190175 |  |  |  | BRIDGE PAINTING OF I-64 RIVERSIDE EXPRESSWAY BRIDGES. (056B00298N,056B00299N,056B00300N,056B00301N,056B00302N, 056B00285N,056B00292N,056B00293N,056B00142N) 5-10016.00 |  | Jefferson | 056-I -0064 -000 | 2.59 | 4.995 | 2.405
? | 5 | KIPDA ADD | IP20190179 |  |  |  | ADDRESS DEFICIENCIES OF BRIDGE OVER NORTHERN DITCH ON GRADE LANE (CR 1001G) 0.34 MI S OF KY 1747 (FERN VALLEY ROAD) (056C00064N) SYP 5-1077.00 |  | Jefferson | 056-CR-1001G -000 | 2.48 | 2.5 | 0.02
? | 6 | Northern Kentucky ADD | IP20170060 |  |  |  | Construct a 66" storm overflow through/around the Newport Floodwall. |  | Campbell | 019-KY-0008 -000 | 0.05 | 0.15 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 100000 |  | 100000 |  | 50000 |  | 1500000 |  | 2017-03-17 14:12 |  | Supports multiple redevelopment efforts for surrounding area. Re-alignment for KY 9 currently in construction; part of a multi-phase construction project. Large mixed use development (Corporex) to the north. Potential bridge replacement project for KY
? | 6 | Northern Kentucky ADD | IP20190002 |  |  |  | Improve safety, mobility, address geometric deficiencies, and drainage along KY 237 (Gunpowder Rd.) from KY 536 (Mt. Zion Rd.) to US 42. |  | Boone | 008-KY-0237 -000 | 0 | 1.588 | 1.588
? | 6 | Northern Kentucky ADD | IP20190003 |  |  |  | Improve existing grade separated railroad crossing over KY 467 to correct geometric deficiencies and raise road out of flood plain. |  | Gallatin | 039-KY-0467 -000 | 3.3 | 3.7 | 0.4
? | 6 | Buffalo Trace ADD | IP20190008 |  |  |  | Improve safety along KY 9 at Iller Road. |  | Bracken | 012-KY-0009 -000 | 19.75 | 19.85 | 0.1 | [14 empty] | Improve safety along KY 9 at Iller Road. | KY 9 is a high speed highway (operation speeds are 70 mph at times). Vehicles turning onto Iller from SB KY 9 are at risk of a rear end crash because the speeds are so high and sight-distance is not optimal.
? | 6 | Northern Kentucky ADD | IP20190010 |  |  |  | Address safety and geometric deficiencies along KY 1829 (Richardson Rd) from KY 1303 (Turkeyfoot Rd) to KY 3035 (Old Madison Pike) and KY 1486 from KY 3035 to KY 17 Connector Rd. |  | Kenton | 059-KY-1829 -000 | 1.024 | 4.387 | 3.363
? | 6 | Northern Kentucky ADD | IP20190011 |  |  |  | Address safety and geometric deficiencies along KY 1501 (Hands Pike) from Edwin Drive to KY 16. |  | Kenton | 059-KY-1501 -000 | 2 | 2.4 | 0.4
? | 6 | Northern Kentucky ADD | IP20190012 |  |  |  | Address safety and geometric deficiencies along KY 1501 (Hands Pike) from Otter to Edwin drives. |  | Kenton | 059-KY-1501 -000 | 1.5 | 2 | 0.5
? | 6 | Northern Kentucky ADD | IP20190013 |  |  |  | Address safety and geometric deficiencies along KY 1501 (Hands Pike) from Crystal Lake to Otter drives. |  | Kenton | 059-KY-1501 -000 | 1 | 1.5 | 0.5
? | 6 | Northern Kentucky ADD | IP20190014 |  |  |  | Improve safety and traffic mobility at the intersection of US 25 and KY 491 (Gardnersville Road) and railroad at-grade crossing. |  | Grant | 041-KY-0491 -000 | 3.98 | 5 | 1.02
? | 6 | Northern Kentucky ADD | IP20190015 |  |  |  | Replace Bridge over Kentucky River on US 42 in Prestonville/Carrollton 0.13 MI E of KY 55 (021B00043N) |  | Carroll | 021-US-0042 -000 | 5.697 | 5.947 | 0.25
? | 6 | Northern Kentucky ADD | IP20190016 |  |  |  | Improve safety & mobility, and address geometric deficiencies along KY 2924 (Tollgate Rd) from US 27 to KY 915. |  | Campbell | 019-KY-2924 -000 | 0 | 2.757 | 2.757
? | 6 | Buffalo Trace ADD | IP20190017 |  |  |  | Improvement to the intersection of KY 19 and KY 539 at Milford. |  | Bracken | 012-KY-0019 -000 | 1.9 | 2.4 | 0.5 | [14 empty] | Improvement to the intersection of KY 19 and KY 539 at Milford. | KY 539 is an offset intersection in Milford with the west leg approaching KY 19 will sharp curves. Sight distance is poor.
? | 6 | Cincinnati-Northern Kentucky MPO | IP20190018 |  |  |  | Reconstruction of KY 14 from Stephenson Mill Rd to I-75. |  | Boone | 008-KY-0014 -000 | 5.35 | 8.114 | 2.764 | [14 empty] | TBD | TBD
? | 6 | Cincinnati-Northern Kentucky MPO | IP20190019 |  |  |  | Improve safety & mobility, and address geometric deficiencies along US 25 (Dixie Hwy.) between KY 16 and KY 338 (Richwood Rd.) |  | Boone | 008-US-0025 -000 | 2.264 | 4.859 | 2.595 | 2 Lane to 4 Lane Divided - Rural | 36 |  | 0 |  | 5000000 |  | 2500000 |  | 30000000 |  | 39000000 |  | 2019-01-26 15:11 | Improve safety & mobility, and address geometric deficiencies along US 25 (Dixie Hwy.) between KY 16 and KY 338 (Richwood Rd.) | ADT in the area reaches a maximum of 8,052 vpd on two, 10'-12' lanes with 1' shoulders. A composite rating of 48.6 indicates that nearly 78% of the statewide urban minor arterials are rated better. An IRI as high as 156 is contributing to a condition in
? | 6 | Northern Kentucky ADD | IP20190065 |  |  |  | I-75 / KY 236 DCD (IMR part of 6-79) |  | Kenton | 059-I -0075 -000 | 183.1 | 184.1 | 1
? | 7 | Lexington MPO | IP20000033 |  |  |  | Corridor scoping study on US 60 from US 25 (Main St) to KY 4 (New Circle Rd). |  | Fayette | 034-US-0060 -000 | 8.551 | 10.091 | 1.54 | Transportation Studies | 0 | Y | 1000000 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2015-06-29 14:15 | Address congestion and improve safety via Corridor scoping study on US 60 from US 25 (Main St) to KY 4 (New Circle Rd). | The V/SF figures during the AM and PM Peak Hours creates congestions that lead to unsafe manuevers by drivers.
? | 7 | Lexington MPO | IP20000034 |  |  |  | >>>From MPO: WINCHESTER RD - MAJOR WIDENING FROM MIDLAND AVE TO NEW CIRCLE ROAD (KY 4) IN LEXINGTON -- MTP 2035 PROJECT DESCRIPTION: UPL RANK #29 - ACCESS MANAGEMENT, OPERATIONAL AND MULTIMODAL IMPROVEMENTS. COST $0.77 MIL. >>>From KYTC: Operational & |  | Fayette | 034-US-0060 -000 | 8.551 | 9.934 | 1.383 | Other Improvement Types | 0 | Y | 0 |  | 350000 |  | 500000 |  | 500000 |  | 1400000 |  | 2013-10-31 17:01 | Improve mobility, address congestion and improve safety via roadway modernization | The roadway segment's CRF is above the threshold and indicates a high collision/accident area.
? | 7 | Lexington MPO | IP20000037 |  |  |  | South Broadway (US 68): from US 25 (Main St.) to Mason Headley Rd. in Lexington - Access Management; operational improvements, and multimodal improvements. |  | Fayette | 034-US-0068 -000 | 5.095 | 5.639 | 0.544 | Access Consolidation | 25 | Y | 0 |  | 600000 |  | 500000 |  | 1500000 |  | 1100000 |  | 2017-05-19 09:47 | Improve mobility on South Broadway (US 68): from US 25 (Main St.) to Mason Headley Rd. in Lexington - Access Management; operational improvements, and multimodal improvements. | The following needs have been identified on this project: 1) Improve Mobility. | 7 | North | 50.6485 | 8.4369 | 14.9077 | 13.8577 | 2.1231 | 0 | 3.3538 | 7.9692 | 51
? | 7 | Lexington MPO | IP20000044 |  |  |  | Improve capacity & multimodal access on KY 1974 (Tates Creek Rd) from Armstrong Mill Rd to Malabu Dr. Revise to match the Lexington Area MPO 2040 Metropolitan Transportation Plan. |  | Fayette | 034-KY-1974 -000 | 8.84 | 9.455 | 0.615 | Modernize Roadway-Rural | 26 | Y | 500000 |  | 1300000 |  | 1400000 |  | 1400000 |  | 4500000 |  | 2017-06-14 16:43 | Improve capacity & multimodal access on KY 1974 (Tates Creek Rd) from Armstrong Mill Rd to Malabu Dr. | The following needs have been identified on this project: 1) Improve Capacity, 2) Improve Access. | Lexington MPO | North | 41.3415 | 7.3108 | 14.1231 | 13.1077 | 0 | 0 | 0 | 6.8 | 41
? | 7 | Lexington MPO | IP20080429 |  |  |  | New Circle Rd. (KY 4): from Boardwalk to North Limestone Street - Improve safety and PM Peak hour traffic flows. volumes, numerous accidents, and reduced LOS delays. A designated truck network, the AM peak hour truck traffic contributes delay problems al |  | Fayette | 034-KY-0004 -000 | 10.015 | 10.356 | 0.341 | Other Improvement Types | 0 | Y | 0 |  | 1500000 |  | 7490000 |  | 1200000 |  | 23185000 |  | 2010-10-28 11:53 |  | Adequacy ratings data for the proposed New Circle Road (KY 4 shows an increase in overall traffic volumes, collisions, An average CRF rating of approximately 1.002. non-recurring congestion incidents during traffic contribute to reduced LOS represented by
? | 7 | Lexington MPO | IP20130099 |  |  |  | Access Management improvements on US 27 (Nicholasville Rd) at KY 4 (New Circle Rd) interchange. |  | Fayette | 034-US-0027 -000 | 2.1 | 2.6 | 0.5 | Innovative Interchange | 40 | Y | 0 |  | 200000 |  | 100000 |  | 100000 |  | 1200000 |  | 2013-08-12 11:12 | Address Congestion, Improve Safety, and Improve mobility options via Access Management improvements on US 27 (Nicholasville Rd) at KY 4 (New Circle Rd) interchange. | Address Congestion, Improve safety, improve mobility
? | 7 | Lexington MPO | IP20140060 |  |  |  | To relieve traffic congestion at the New Circle Road and Tates Creek Road interchange. |  | Fayette | 034-KY-1974 -000 | 7.751 | 9.455 | 1.704 |  |  | Y
? | 8 | Lake Cumberland ADD | IP20070231 |  |  |  | CONSTRUCT SIDEWALK ON THE SOUTH SIDE OF KY 70 FROM KY 1247 TO US 27 IN EUBANK |  | Pulaski | 100-KY-0070 -000 | 2.705 | 3.55 | 0.845 | Other Improvement Types | 0 |  | 0 |  | 125000 |  | 75000 |  | 225000 |  | 650000 |  | 2013-05-13 08:50 |  | KY 70 is narrow two lane roadway with 9' - 10' driving lanes and 3' shoulders. This segment is located within the city limits of Eubank and is used by children to walk to and from the Eubank Grade School, and to the city park. This roadway carries 1,490
? | 8 | Lake Cumberland ADD | IP20130069 |  |  |  | Spot improvements to reduce congestion and provisions for pedestrian facilities by Pulaski County High School. |  | Pulaski | 100-KY-1575 -000 | 0.89 | 1.151 | 0.261 | Modernize Roadway-Rural | 26 |  | 0 |  | 230000 |  | 275000 |  | 570000 |  | 530000 |  | 2013-07-01 14:20 |  | During school start and ending hours and school events, excessive congestion resulting in travel delay occurs on this route.
? | 8 | Lake Cumberland ADD | IP20180035 |  |  |  | WIDEN KY 1275 TO FOUR LANES WITH FOUR FOOT SHOULDERS AND FIVE FOOT SIDEWALKS FROM KY 90 TO BELL LANE |  | Wayne | 116-KY-1275 -000 | 4 | 4.479 | 0.479 | Other Improvement Types | 0 |  | 0 |  | 490000 | 2019 | 200000 | 2020 | 500000 | 2020 | 3000000 | 2021 | 2018-11-27 15:58 | WIDEN KY 1275 TO FOUR LANES WITH FOUR FOOT SHOULDERS AND FIVE FOOT SIDEWALKS FROM KY 90 TO BELL LANE | The following needs have been identified for this project: 1) Improve Roadway Safety. 2) Improve Access and increase Capacity for all vehicle types. | General Assembly | South | 8.5908 | 3.5377 | 0 | 3.0955 | 1.9575 | 0 | 0 | 0 | 9
? | 9 | FIVCO ADD | IP20080529 |  |  |  | Improve geometric configuration of the KY 9/KY 1959 intersection to decrease rear end crashes on KY 9 at the intersection with KY 1959 (KY 9 MP 1.078) Add right turn lane on KY 9 NB, Utilize the existing shoulder. |  | Carter | 022-KY-0009 -000 | 0.978 | 1.078 | 0.1 | Other Improvement Types | 0 | Y | 0 |  | 10000 |  | 0 |  | 0 |  | 100000 |  | 2010-02-25 16:51 |  | KY9 is a route heavily traveled by large trucks. Located just 1 mile east of the KY9 & KY1959 intersections are 3 very large, highly used truck stops which generate tremendous truck traffic for this segment of KY9. KY1959 is a rural crossroad that provi
? | 9 | Huntington-Ashland-Ironton MPO | IP20080546 |  |  |  | Improve operational efficiency on KY-2541 at the junction with US-23 in Greenup to relieve traffic congestion and aid traffic turning onto US-23. |  | Greenup | 045-KY-2541 -000 | 0 | 0.164 | 0.164 | Improve Intersection | 26 |  | 0 |  | 100000 |  | 300000 |  | 150000 |  | 500000 |  | 2013-06-12 11:37 | Improve operational efficiency on KY-2541 at the junction with US-23 in Greenup to relieve traffic congestion and aid traffic turning onto US-23. | Traffic congestion at the intersection of KY-2541 and US-23 is a major problem mainly due to an entrance/exit for McDonalds on KY-2541 being located so close to US-23 (approximately 100 feet). Traffic entering and/or exiting McDonalds' parking lot causes | Huntington/KYOVA MPO | East | 28.1886 | 8.3234 | 7.4551 | 3.997 | 4.1617 | 0 | 0 | 4.2515 | 28
? | 9 | FIVCO ADD | IP20110067 |  |  |  | KY 504 is a winding curvy road with several approach roads that have sight distance issues and safety concerns. This project is located near mp 1.6 to 2.6 with KY 549 instersecting at mp 2.1 along KY 504. Reconstruct the intersection, improve sight di |  | Elliott | 032-KY-0504 -000 | 1.6 | 2.6 | 1 | Other Improvement Types | 0 |  | 0 |  | 650000 |  | 450000 |  | 450000 |  | 5000000 |  | 2013-06-12 10:04 |  | The intersection of KY 504 and KY 649 poses significant safety concerns. As the photos reveal, KY 549 intersects at a 15° angle which causes motorists turning West on KY 504 to go across the road and utilize a widened area off the shoulder. Horizontal,
? | 9 | FIVCO ADD | IP20110068 |  |  |  | Reconstruct the Intersection of KY 504 and KY 1555. The intersection of KY 504 and KY 1555 (mp 6.763) needs to be realigned. This section of KY 504 has a sharp curve and KY 1555 approach is on a steep vertical curve. Impove vertical, horizontal defi |  | Elliott | 032-KY-0504 -000 | 6 | 7.2 | 1.2 | Other Improvement Types | 0 |  | 0 |  | 350000 |  | 125000 |  | 100000 |  | 825000 |  | 2013-06-12 10:20 |  | Reconstruct the Intersection of KY 504 and KY 1555(mp 6.763). This section of KY 504 has a sharp curve and KY 1555 approach is on a steep vertical curve. There is not any sight distance when turning onto KY 504 from KY 1555 which poses significant safet
? | 9 | FIVCO ADD | IP20110213 |  |  |  | Improve width and shoulder deficiencies between rock cuts to allow shoulders to catch falling rock from rolling into driving paths. |  | Carter | 022-US-0060 -000 | 7.646 | 8.106 | 0.46 | Maintenance Improvement | 10 |  | 0 |  | 450000 |  | 150000 |  | 75000 |  | 3500000 |  | 2011-11-21 14:41 |  |  | 9 | East | 10.5539 | 6.2874 | 0 | 3.4581 | 0.80838 | 0 | 0 | 0 | 11
? | 9 | FIVCO ADD | IP20110214 |  |  |  | Improve width and shoulder deficiencies between rock cuts to allow shoulders to catch falling rock from rolling into driving paths. |  | Carter | 022-US-0060 -000 | 6.75 | 6.9 | 0.15 | Modernize Roadway-Rural | 26 |  | 0 |  | 600000 |  | 100000 |  | 75000 |  | 1500000 |  | 2017-05-01 13:51 |  |  | 9 | East | 20.1647 | 6.2874 | 5.2096 | 3.7275 | 0.80838 | 0 | 0 | 4.1317 | 20
? | 9 | FIVCO ADD | IP20110215 |  |  |  | Reconstruct intersection of KY 3296 to allow better sight distance and safer exit/entrance onto US60. |  | Carter | 022-US-0060 -000 | 0 | 0.4 | 0.4 | Other Improvement Types | 0 |  | 0 |  | 500000 |  | 350000 |  | 100000 |  | 750000 |  | 2013-06-05 13:20
? | 9 | FIVCO ADD | IP20110216 |  |  |  | Increase the length of the I64 EB on-ramp to accommodate large volumes of merging traffic leaving Grayson. |  | Carter | 022-I -0064 -000 | 171.855 | 172.855 | 1 | Other Improvement Types | 0 | Y | 0 |  | 500000 |  | 100000 |  | 100000 |  | 2000000 |  | 2011-11-21 14:40
? | 9 | FIVCO ADD | IP20150227 |  |  |  | SAFETY IMPROVEMENTS AT THE EAST CARTER HIGH SCHOOL. (06CCN)(08CCR)(12CCR) |  | Carter | 022-KY-0001 -000 | 9.824 | 10.242 | 0.418 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 870000 |  | 570000 |  | 2080000 |  | 2017-03-09 09:47
? | 9 | FIVCO ADD | IP20150232 |  |  |  | SAFETY IMPROVEMENTS TO KY-773 FROM KY-7 TO KY-1. (06CCN)(08CCR) |  | Carter | 022-KY-0773 -000 | 0 | 0.1 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 1250000 |  | 120000 |  | 110000 |  | 0 |  | 2017-03-17 09:48
? | 9 | FIVCO ADD | IP20150390 |  |  |  | KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO KY-7 NEAR NEWFOUNDLAND. (06CCR) (08CCR) |  | Elliott | 032-KY-0032 -000 | 0 | 8.656 | 8.656 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 3310000 |  | 3250000 |  | 20250000 |  | 2017-03-14 15:49
? | 9 | FIVCO ADD | IP20150391 |  |  |  | RECONSTRUCT KY-32 FROM KY-504 NEAR ELLIOTTVILLE TO 0.408 MI WEST OF STEGALL COLD SPRING ROAD IN ELLIOTT COUNTY. PRIORITY SECTION 2 (10CCR) |  | Elliott | 032-KY-0032 -000 | 16.619 | 18.047 | 1.428 | Modernize Roadway-Rural | 26 |  | 0 |  | 3250000 |  | 11700000 |  | 6000000 |  | 57000000 |  | 2017-03-16 14:21
? | 9 | FIVCO ADD | IP20150441 |  |  |  | SAFETY IMPROVEMENTS TO KY-773 FROM KY-7 TO KY-1. (06CCN)(08CCR) |  | Carter | 022-KY-0773 -000 | 0.1 | 3.505 | 3.405 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 120000 |  | 110000 |  | 0 |  | 2017-03-17 09:51
? | 9 | FIVCO ADD | IP20160290 |  |  |  | The KY 1/KY 1947 intersection operates at LOS D in the PM peak hour (worst case) with 47.3 seconds/ vehicle of overall delay. However, the through/right (eastbound/southbound) movement operates at LOS F (96 seconds/vehicle delay). This project would prov |  | Carter | 022-KY-1947 -000 | 3.25 | 3.398 | 0.148 | Improve Intersection | 26 |  | 0 |  | 50000 |  | 75000 |  | 75000 |  | 238000 |  | 2017-05-01 14:09 |  | The KY 1/KY 1947 intersection operates at LOS D in the PM peak hour (worst case) with 47.3 seconds/ vehicle of overall delay. However, the through/right (eastbound/southbound) movement operates at LOS F (96 seconds/vehicle delay). In addition, the interse | 9 | East | 36.6976 | 8.2994 | 14.6407 | 9.6557 | 1.2874 | 0 | 0 | 2.8144 | 37
? | 9 | FIVCO ADD | IP20160293 |  |  |  | KY 3297 carries approximately 3,080 vpd near East Carter Middle School. According to school officials and other stakeholders, KY 3297 becomes congested when long queues form as motorists wait to turn into the East Carter Middle School parking lot. These l |  | Carter | 022-KY-3297 -000 | 0.325 | 0.45 | 0.125 | Improve Intersection | 26 |  | 0 |  | 35000 |  | 0 |  | 50000 |  | 150000 |  | 2017-05-01 14:10 |  | KY 3297 carries approximately 3,080 vpd near East Carter Middle School. According to school officials and other stakeholders, KY 3297 becomes congested when long queues form as motorists wait to turn into the East Carter Middle School parking lot. These l | 9 | East | 14.9401 | 3.5928 | 8.6228 | 1.0778 | 1.6467 | 0 | 0 | 0 | 15
? | 9 | FIVCO ADD | IP20170021 |  |  |  | KY 649 (Stark Ridge Road) intersects KY 504 at a very steep grade. This results in a potential safety issue for vehicles attempting to stop at the intersection, especially in the winter time during slick road conditions. This project would be to provide |  | Elliott | 032-KY-0649 -000 | 8.2 | 8.778 | 0.578 | Improve Intersection | 26 |  | 0 |  | 250000 |  | 100000 |  | 250000 |  | 1500000 |  | 2017-02-15 14:31 |  |  | FIVCO ADD | East | 7.0494 | 0.15569 | 2.4251 | 0.15719 | 4.3114 | 0 | 0 | 0 | 7
? | 9 | FIVCO ADD | IP20180001 |  |  |  | Develop a formal planning study to determine purpose and need of a new route that would serve as a "Carole Malone Blvd. Bypass" in the City of Grayson, Carter County, KY. Traffic congestion continues to increase along Carole Malone Blvd. (KY 1 and KY 7). |  | Carter | 022-KY-0001 -000 | 10.646 | 12.009 | 1.363
? | 9 | Huntington-Ashland-Ironton MPO | IP20190112 |  |  |  | KY 757 curve correction near Caldwell park. |  | Boyd | 010-KY-0757 -000 | 5.3 | 5.7 | 0.4 | Modernize & Widen Roadway-Rural | 26 |  | 0 |  | 400000 | 2021 | 100000 | 2022 | 100000 | 2022 | 2500000 | 2022 | 2019-03-15 08:55 | Spot improvement including curve correction and intersection improvement. | According to local resident Robert Rigsby, there have been several near misses at this location due to poor geometrics and sight distance.
? | 10 | Kentucky River ADD | IP20110017 |  |  |  | Improvements to KY 451 from Jess Fields Ln to Buster Dr/Morris Dr. |  | Perry | 097-KY-0451 -000 | 9.087 | 9.387 | 0.3 | Modernize Roadway-Rural | 26 |  | 5000 |  | 200000 |  | 500000 |  | 250000 |  | 750000 |  | 2011-02-01 08:55 |  | This project is needed due to safety issues and substandard roadway features.
? | 10 | Kentucky River ADD | IP20110020 |  |  |  | Improve safety and drainage deficiencies along a KY 476 from 0.087 miles North of Ajax Hollow to Jakes Branch Volunteer Fire Department. |  | Perry | 097-KY-0476 -000 | 3.5 | 3.75 | 0.25 | Modernize Roadway-Rural | 26 |  | 0 |  | 257500 |  | 265000 |  | 265000 |  | 1378000 |  | 2016-11-02 11:53 |  | This project is needed due to safety issues and substandard roadway drainage features.
? | 12 | Big Sandy ADD | IP20080628 |  |  |  | To improve traffic flow and increase the safety of commuters on this section of KY 3 |  | Floyd | 036-KY-0003 -000 | 1.245 | 2.177 | 0.932 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 1000000 |  | 1100000 |  | 1725000 |  | 2010-02-25 16:51 | Improve connectivity to US-23 and reduce congestion along this portion of KY-3. | The pupose of this project is to address congestion and improve access between Highlands Regional Medical Center and KY 3051. This section of KY 3 has an ADT of 9109 and an adequacy rating of 81.45, and is the only access to HRMC, which is a major hospi
? | 12 | Big Sandy ADD | IP20080640 |  |  |  | Minimize Flooding by raising KY 1427 above periods of high water for a distance of 1000 FT (State Road Fork). |  | Floyd | 036-KY-1427 -000 | 3.137 | 3.337 | 0.2 | Other Improvement Types | 0 |  | 0 |  | 100000 |  | 250000 |  | 110000 |  | 670000 |  | 2015-01-08 13:13 | Address safety and reliability on this section of KY-1427 by raising the roadway above high water. | KY 1427 in Floyd County is a narrow (16 ft.) road with 1-2 foot shoulders. No ADEQ Rating information is available. The area recommended for spot improvement is parallel and directly adjacent to Abbott Creek. During periods of heavy rains, the road is bl
? | 12 | Big Sandy ADD | IP20080645 |  |  |  | Improve low roadway condition from just past John Bays Branch Road to Railroad Circle.. |  | Floyd | 036-KY-3051 -000 | 0.812 | 1.023 | 0.211 | Other Improvement Types | 0 |  | 0 |  | 300000 |  | 100000 |  | 150000 |  | 1400000 |  | 2010-02-25 16:51 | Address safety and reliability by elevating this section of KY-3051 above high water. | Flooding occurs between John Bays Branch and Railroad Circle at Auxier blocking the only way into and out of this area.
? | 12 | Big Sandy ADD | IP20080704 |  |  |  | Make safety spot improvements at this high crash location. Priority 8 of 8 of recommended spot improvement in referenced study. Spot 5, Section 2. |  | Pike | 098-KY-0194 -000 | 24.2 | 25.1 | 0.9 | Other Improvement Types | 0 |  | 0 |  | 700000 |  | 850000 |  | 650000 |  | 9035500 |  | 2016-10-31 16:14 | Address safety and reliability of this segment of KY-194 by improving roadway geometrics, increasing sight distance, and increasing lane and shoulder width. | Spot 5—(MP 24.0 to MP 25.0). This spot improvement is approximately 0.97 mile in length and is also a high crash location (many occurred wet weather) with shoulder failure. Rock walls and mine portals are located in the corridor. This improvement requires
? | 12 | Big Sandy ADD | IP20080706 |  |  |  | This project addresses the substandard alignment and pavement condition, and safety and sight distance issues, created by the old railroad crossing at the junction of KY 194 and KY 2059. |  | Pike | 098-KY-0194 -000 | 64.2 | 64.5 | 0.3 | Other Improvement Types | 0 |  | 0 |  | 200000 |  | 300000 |  | 220000 |  | 1700000 |  | 2010-02-25 16:51 | Address safety and reliability of this segment of KY-194 by improving sight distance and revising at-grade railroad crossing. | Though not shown on the data, this is a heavy coal haul route. This segment of KY 194, a vital access route to the proposed I-66 corridor, passes through a previous at-grade railroad crossing that was created with substandard alignment and a sudden change
? | 12 | Big Sandy ADD | IP20150135 |  |  |  | NEW BRIDGE OVER THE LEVISA FORK OF THE BIG SANDY RIVER NEAR THE EXISTING SUSPENSION BRIDGE. (14CCN) |  | Pike | 098-CS-1215 -000 | 1.644 | 1.654 | 0.01 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5410000 |  | 2016-10-31 11:18
? | 12 | Big Sandy ADD | IP20150229 |  |  |  | FEDERAL HIGHWAY FUNDS DEDICATED TO RECONSTRUCT STONE COAL ROAD IN JOHNSON COUNTY. ("KYD" FUNDS NOT AVAILABLE FOR ADDITIONAL AMOUNT NEEDED TO COVER COST) |  | Johnson | 058-KY-0172 -000 | 9.132 | 9.232 | 0.1 | Other Improvement Types | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 670000 |  | 2016-10-31 15:28
? | 12 | FIVCO ADD | IP20160148 |  |  |  | SPOT IMPROVEMENTS ON SPANKEM BRANCH ROAD (CR 1044).(16CCN) |  | Lawrence | 064-CR-1044 -000 | 0 | 8.41 | 8.41 | Local Roadway Improvements | 3 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-10-19 11:19 |  |  | General Assembly | East | 22.4438 | 8.0355 | 0 | 9.0533 | 2.8698 | 0 | 0 | 2.4852 | 22
? | 12 | Big Sandy ADD | IP20160265 |  |  |  | MOUNTAIN PARKWAY EXPANSION FROM PRESTONSBURG TO WEST VIRGINIA LINE. (16CCN) |  | Floyd | 036-US-0023 -000 | 15.379 | 21.986 | 6.607 | Modernize Roadway-Rural | 26 | Y | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 2016-11-03 12:23
Committed Projects:
Those projects that were in the Recommended Highway Plan and have either R, U, or C programmed in the biennium (2018-2020) of the Enacted Plan or only C programmed in 2021-2024 of the Enacted Plan (and no other phase in the Plan); and have consistent scope with what was proposed in 2018 (i.e., costs are within 5% and any R programmed in the biennium is on schedule for funding authorization within the biennium).
Potential Committed:
These projects require coordination with KYTC to determine if they are committed or must be sponsored. You may sponsor to ensure, but, if scope is consistent with what was proposed in 2018, the project is committed.

## Sponsor_Committed Group Desc
Group | include in Committed $ | Sponsor | # | Description
Auth Tier 3/4 |  | N | 4 | Projects with authorized phases in Tier 3/ 4. (If C is authorized sponsorship is not needed ) Tier 3 & 4 projects are projects either new to the Enacted plan or moved from the Appendix in the Recommended plan to the Enacted plan.
Auth Tier 3/4 |  | Y | 7 | Projects with authorized phases in Tier 3/ 4. Tier 3 & 4 projects are projects either new to the Enacted plan or moved from the Appendix in the Recommended plan to the Enacted plan.
C Avail Letting Set | C | N | 47 | C $ Available and scheduled to let within the biennium
C Avail Not Scheduled | C | N | 17 | C $ Available, but C is not yet scheduled
Future C Letting Set | C | N | 19 | Committed with letting scheduled
Inquiry Needed | PC | ? | 4 | Need to work with Districts on schedule and scope. Sponsor.
Let/Awarded |  | N | 49 | Let projects - no need to sponsor
Mega |  | N | 3 | Mega projects do not need to sponsor
Potential Committed | PC | Y | 42 | Sponsor to ensure, but will automatically be included if the scope is consistent with 2018. Project should be nearing R/W authorization by the end of 2019 to ensure appropriate scope is captured.
Sponsor |  | Y | 89 | These are projects either new to the enacted plan or moved from the Appendix in the Recommended plan to the Enacted plan.
Tier 3/4 |  | Y | 175 | Tier 3 & 4 projects are projects either new to the Enacted plan or moved from the Appendix in the Recommended plan to the Enacted plan.
* Note 9-144 is authorized, but is well over the cost, so it may need to be sponsored to adjust scope.
This includes all projects in the Enacted Plan with funding type of NH, STP, SPP, or BR2 (BRAC).
Committed Projects (Sponsorship Not Required):
Committed projects are those that:
1. were in the Recommended Highway Plan (body, not the appendix); and
2. have either R, U, or C programmed in the biennium (2018-2020) of the Enacted Plan or only C programmed in 2021-2024 of the Enacted Plan (and no other phase in the Plan); and
3. have consistent scope with what was proposed in 2018 (i.e., costs are within 5% and any R programmed in the biennium is on schedule for funding authorization within the biennium).
Potentially Committed :
These projects require coordination with KYTC to determine if they are committed or must be sponsored. You may sponsor to ensure, but, if scope is consistent with what was proposed in 2018, the project is committed.