## Sheet1
SHIFT Kentucky Ahead
Strategic Highway Investment Formula for Tomorrow
Draft Timeline ***Revision Date: 3/22/18***
| 2019 | Action | Acting Party | Description
Sponsorship | 1/2 - 3/15 | Projects Sponsored | ADD, MPO, HDO | ADDs and MPOs prepare new and/or update existing CHAFs as needed in their respective areas in order to sponsor projects in the CHAF program.
Data Verification | 3/18 - 3/29 | Review Sponsored Project List | Central Office, HDO, ADD, MPO | Review project list, discuss projects with districts, ADDS and MPOS, review projects for duplications and families
| 3/18 - 4/5 | Update project list groupings based upon comments | Central Office, HDO, ADD, MPO | Projects may need to be grouped together or separated after review.
| 4/8 -5/22 | Travel Time and Economic modeling | Central Office | Travel Time modeling and Economic modeling for projects
| 4/8 - 5/17 | Update Project Costs / Schedule Yr. | HDO | Update project costs and schedules. This information will be included in final data verification review.
| 4/8 - 5/17 | QA/QC CHAF Inormation | ADD, MPO, HDO | Review /correct location, description or other information identified by C.O. planning screening.
| 4/29 - 5/17 | Data Verification | Central Office | Confirm SHIFT scoring data is correct on sponsored CHAFs
ADD, MPO, HDO
| 4/29 - 5/17 | Investigate Data Issues | Central Office | Investigate issues with data flagged in Data Verification
| 2018-05-07 | Submit Draft District / Local (ADD/MPO) Priorities Plan | ADD, MPO, HDO | Draft prioritization plans should include what criteria will be used to select priority projects as well as involvement and feedback opportunities concerning the public.
| 5/27 - 5/31 | Final Data Verification | Central Office | Central Office will send out data for sponsored projects.
|  |  | ADD, MPO, HDO | Review data for projects and sign off before scoring begins
Statewide Prioritization | 6/3 - 6/7 | Statewide Scoring | Central Office | Planning will produce a Statewide list of scored projects on the NH System.
| 6/10 - 6/14 | District Meetings on Statewide Projects | Central Office and HDO | Districts meet with Central Office to discuss schedules, federal eligibility for statewide projects, and projected available funding.
| 6/10 - 6/18 | Statewide Project Identification | Central Office | Projects of statewide significance identified based on facility type and improvement impact. Statewide projects will be generated from this list to be included in Recommended Highway Plan.
Regional Prioritization | 6/19 - 6/21 | Regional Scoring | Central Office | Planning will produce regional lists, including projects on the NH System not selected through the Statewide Prioritization selection process, score regional projects, and distribute project list.
| 6/24 - 8/14 | Priority Point Allocation & submittal | ADD, MPO, HDO | ADD's, MPO's, and HDO's determine which 25% of projects within their area's Regional List will be selected to receive priority points.
| 2018-08-14 | Finalize Regional Scores | Central Office | Scores are finalized
Regional Project Selection | 8/15 - 8/21 | Prep for Regional Summits | HDO | District personnel prepare for Regional Summits – Planning to assist
| 2018-08-21 | Submit Final District / Local (ADD/MPO) Priorities Plan | ADD, MPO, HDO | Final prioritization plans should include what criteria was used to select priority projects as well as involvement and feedback opportunities concerning the public.
| 8/22 - 8/30 | Regional Summits | HDO | District personnel conduct Regional Summits at Central Office. Prepare proposed project selection list and schedule. Identify list of additional projects if more funding is available. – Planning to assist
| 9/3 - 9/5 | Partnering Conference | ADD, MPO, HDO | ACEC-KY/FHWA/KYTC Partnering Conference (tenative)
| 9/9 -9/13 | Finalize and Submit Selected Projects | Central Office | Central Office will summarize a list of identified additional projects from Regional and Statewide lists that could be completed if additional funding were obtained.
| 10/23 - 10/27 | Regional Presentations | HDO | Regions will each discuss their proposal with Cabinet Leadership, funding conflicts will be discussed and resolved.
| 10/30 - 11/10 | Regional Project Selection | Central Office | Cabinet Leadership will use regional projects listing based upon projected schedules and available funding for project phases to be identified in Recommended Highway Plan.
Draft Plan | 9/16 - 10/11/ | Adjust Statewide and Regional lists | Central Office | Adjust Statewide and Regional lists, as needed.
| 10/14 - 11/15 | KYTC Develops Draft Plan | Central Office | The Draft Recommended Highway Plan is a combination of statewide list and regional lists. It will also include system preservation and preventative maintenance projects.
| 11/18 - 12/27 | KYTC Delivers Draft Plan to the Governor | Central Office | Submit Draft Plan to Governor.